## Curva
Activity ID | Resource Name | Resource Type | Spreadsheet Field | 25-Sep-22 | 02-Oct-22 | 09-Oct-22 | 16-Oct-22 | 23-Oct-22 | 30-Oct-22 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 04-Dec-22 | 11-Dec-22 | 18-Dec-22 | 25-Dec-22 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 05-Feb-23 | 12-Feb-23 | 19-Feb-23 | 26-Feb-23 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 02-Apr-23 | 09-Apr-23 | 16-Apr-23 | 23-Apr-23 | 30-Apr-23 | 07-May-23 | 14-May-23 | 21-May-23 | 28-May-23 | 2023-06-04 | 2023-06-11 | 2023-06-18 | 2023-06-25 | 2023-07-02 | 2023-07-09 | 2023-07-16 | 2023-07-23 | 2023-07-30 | 06-Aug-23 | 13-Aug-23 | 20-Aug-23 | 27-Aug-23 | 03-Sep-23 | 10-Sep-23 | 17-Sep-23 | 24-Sep-23 | 01-Oct-23 | 08-Oct-23 | 15-Oct-23 | 22-Oct-23 | 29-Oct-23 | 2023-11-05 | 2023-11-12 | 2023-11-19 | 2023-11-26 | 03-Dec-23 | 10-Dec-23 | 17-Dec-23 | 24-Dec-23 | 31-Dec-23 | 2024-01-07 | 2024-01-14 | 2024-01-21 | 2024-01-28 | 04-Feb-24 | 11-Feb-24 | 18-Feb-24 | 25-Feb-24 | 2024-03-03 | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-31 | 07-Apr-24 | 14-Apr-24 | 21-Apr-24 | 28-Apr-24 | 05-May-24 | 12-May-24 | 19-May-24 | 26-May-24 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-23 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-21 | 2024-07-28 | 04-Aug-24 | 11-Aug-24 | 18-Aug-24 | 25-Aug-24 | 01-Sep-24 | 08-Sep-24 | 15-Sep-24 | 22-Sep-24 | 29-Sep-24 | 06-Oct-24 | 13-Oct-24 | 20-Oct-24 | 27-Oct-24 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 01-Dec-24 | 08-Dec-24 | 15-Dec-24 | 22-Dec-24 | 29-Dec-24 | 2025-01-05 | 2025-01-12 | 2025-01-19 | 2025-01-26 | 02-Feb-25 | 09-Feb-25 | 16-Feb-25 | 23-Feb-25
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [76 empty] | 20m³ | 99m³ | 99m³ | 79m³
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [76 empty] | 20m³ | 99m³ | 99m³ | 79m³
CPI0817-CWP-024 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [85 empty] | 2m³
CPI0817-CWP-024 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CPI0817-CWP-024 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [85 empty] | 2m³
MEM0817-CWP-025 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [86 empty] | 1m³
MEM0817-CWP-025 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
MEM0817-CWP-025 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [86 empty] | 1m³
CEC0820-CWP-054 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [76 empty] | 13m³ | 35m³ | 31m³
CEC0820-CWP-054 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CEC0820-CWP-054 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [76 empty] | 13m³ | 35m³ | 31m³
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [59 empty] | 37m³ | 179m³ | 179m³ | 179m³ | 179m³ | 149m³ |  | 179m³ | 171m³
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [59 empty] | 37m³ | 179m³ | 179m³ | 179m³ | 179m³ | 149m³ |  | 179m³ | 171m³
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [79 empty] | 0m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 0m³
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [79 empty] | 0m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³ | 0m³
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [72 empty] | 0m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [72 empty] | 0m³ | 1m³ | 1m³ | 1m³ | 1m³ | 1m³
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [60 empty] | 10m³ | 10m³ | 10m³ | 10m³ | 10m³ | 10m³ | 10m³ | 2m³
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [60 empty] | 10m³ | 10m³ | 10m³ | 10m³ | 10m³ | 10m³ | 10m³ | 2m³
MEM0827-CWP-315 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [91 empty] | 1m³
MEM0827-CWP-315 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
MEM0827-CWP-315 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [91 empty] | 1m³
CPI0827-CWP-314 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [89 empty] | 2m³
CPI0827-CWP-314 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CPI0827-CWP-314 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [89 empty] | 2m³
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [59 empty] | 3m³ | 3m³ | 3m³ | 3m³ | 3m³ | 3m³ | 3m³ | 3m³ | 2m³
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [59 empty] | 3m³ | 3m³ | 3m³ | 3m³ | 3m³ | 3m³ | 3m³ | 3m³ | 2m³
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [59 empty] | 0m³ | 2m³ | 2m³ | 1m³
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [59 empty] | 0m³ | 2m³ | 2m³ | 1m³
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | [62 empty] | 0m³ | 2m³ | 2m³ |  | 2m³ | 2m³ | 2m³
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Actual Units
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | [62 empty] | 0m³ | 2m³ | 2m³ |  | 2m³ | 2m³ | 2m³
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | [62 empty] | 13m³ | 13m³ |  |  | 10m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 10m³
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Actual Units
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | [62 empty] | 13m³ | 13m³ |  |  | 10m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 13m³ | 10m³
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | [56 empty] | 2m³ | 7m³ | 7m³ | 6m³
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Actual Units
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | [56 empty] | 2m³ | 7m³ | 7m³ | 6m³
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | [67 empty] | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 25m³
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Actual Units
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | [67 empty] | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 41m³ | 25m³
CDC0823-CWP-262 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units
CDC0823-CWP-262 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Actual Units
CDC0823-CWP-262 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units
CDC0827-CWP-351 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units
CDC0827-CWP-351 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Actual Units
CDC0827-CWP-351 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | [56 empty] | 0m³ | 2m³ | 2m³ | 1m³
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Actual Units
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | [56 empty] | 0m³ | 2m³ | 2m³ | 1m³
ELU0817-CWP-050 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
ELU0817-CWP-050 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
ELU0817-CWP-050 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SSD0817-CWP-028 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SSD0817-CWP-028 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SSD0817-CWP-028 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0817-CWP-029 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SES0817-CWP-029 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0817-CWP-029 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0817-CWP-040 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SES0817-CWP-040 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0817-CWP-040 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0817-CWP-041 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SES0817-CWP-041 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0817-CWP-041 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
MEM0817-CWP-043 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
MEM0817-CWP-043 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MEM0817-CWP-043 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
MEM0817-CWP-047 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
MEM0817-CWP-047 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MEM0817-CWP-047 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0817-CWP-049 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SES0817-CWP-049 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0817-CWP-049 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [84 empty] | 3t | 7t | 7t | 7t | 7t | 7t | 7t | 7t | 7t | 7t | 4t
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [84 empty] | 3t | 7t | 7t | 7t | 7t | 7t | 7t | 7t | 7t | 7t | 4t
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [71 empty] | 10t | 25t | 25t | 26t | 30t | 30t | 4t
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [71 empty] | 10t | 25t | 25t | 26t | 30t | 30t | 4t
MCD0822-CWP-103 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [93 empty] | 15t | 17t | 16t
MCD0822-CWP-103 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MCD0822-CWP-103 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [93 empty] | 15t | 17t | 16t
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [80 empty] | 2t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 1t
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [80 empty] | 2t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 1t
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [63 empty] | 4t | 14t |  | 17t | 17t | 17t | 17t | 5t
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [63 empty] | 4t | 14t |  | 17t | 17t | 17t | 17t | 5t
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [83 empty] | 5t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 1t
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [83 empty] | 5t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 1t
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [89 empty] | 5t | 10t | 10t | 10t | 10t | 5t
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [89 empty] | 5t | 10t | 10t | 10t | 10t | 5t
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [58 empty] | 4t | 17t | 17t | 17t | 17t | 17t | 14t |  | 17t
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [58 empty] | 4t | 17t | 17t | 17t | 17t | 17t | 14t |  | 17t
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [64 empty] | 9t |  | 22t | 22t | 22t | 22t | 13t
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [64 empty] | 9t |  | 22t | 22t | 22t | 22t | 13t
MEM0823-CWP-258 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
MEM0823-CWP-258 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MEM0823-CWP-258 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [61 empty] | 0t | 1t | 1t |  |  | 1t | 1t | 1t | 1t | 1t | 1t | 1t
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [61 empty] | 0t | 1t | 1t |  |  | 1t | 1t | 1t | 1t | 1t | 1t | 1t
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [77 empty] | 13t | 69t | 46t | 58t | 58t | 25t
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [77 empty] | 13t | 69t | 46t | 58t | 58t | 25t
MCD0824-CWP-278 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [97 empty] | 1t | 2t | 1t
MCD0824-CWP-278 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MCD0824-CWP-278 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [97 empty] | 1t | 2t | 1t
MCD0824-CWP-279 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [95 empty] | 1t | 2t | 0t
MCD0824-CWP-279 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MCD0824-CWP-279 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [95 empty] | 1t | 2t | 0t
ELU0827-CWP-340 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
ELU0827-CWP-340 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
ELU0827-CWP-340 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0827-CWP-318 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SES0827-CWP-318 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0827-CWP-318 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0827-CWP-319 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SES0827-CWP-319 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0827-CWP-319 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0827-CWP-330 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SES0827-CWP-330 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0827-CWP-330 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0827-CWP-331 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SES0827-CWP-331 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0827-CWP-331 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0827-CWP-339 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
SES0827-CWP-339 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0827-CWP-339 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
MEM0827-CWP-333 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
MEM0827-CWP-333 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MEM0827-CWP-333 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
MEM0827-CWP-337 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units
MEM0827-CWP-337 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MEM0827-CWP-337 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units
SES0827-CWP-452 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [71 empty] | 4t | 19t | 9t
SES0827-CWP-452 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0827-CWP-452 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [71 empty] | 4t | 19t | 9t
SES0827-CWP-307 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [78 empty] | 2t | 9t | 4t
SES0827-CWP-307 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0827-CWP-307 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [78 empty] | 2t | 9t | 4t
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [68 empty] | 7t | 13t | 13t | 9t
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [68 empty] | 7t | 13t | 13t | 9t
MCD0822-CWP-540 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [70 empty] | 23t | 58t | 0t
MCD0822-CWP-540 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MCD0822-CWP-540 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [70 empty] | 23t | 58t | 0t
MCD0822-CWP-541 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [72 empty] | 57t | 24t
MCD0822-CWP-541 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
MCD0822-CWP-541 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [72 empty] | 57t | 24t
SES0822-CWP-542 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [79 empty] | 9t | 21t
SES0822-CWP-542 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-542 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [79 empty] | 9t | 21t
SES0822-CWP-543 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [80 empty] | 20t | 10t
SES0822-CWP-543 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-543 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [80 empty] | 20t | 10t
SES0822-CWP-544 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [81 empty] | 30t
SES0822-CWP-544 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-544 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [81 empty] | 30t
SES0822-CWP-545 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [74 empty] | 30t
SES0822-CWP-545 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-545 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [74 empty] | 30t
SES0822-CWP-546 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [72 empty] | 10t | 2t
SES0822-CWP-546 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-546 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [72 empty] | 10t | 2t
SES0822-CWP-547 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [73 empty] | 12t
SES0822-CWP-547 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-547 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [73 empty] | 12t
SES0822-CWP-548 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [73 empty] | 9t | 3t
SES0822-CWP-548 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-548 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [73 empty] | 9t | 3t
SES0822-CWP-549 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | [72 empty] | 12t
SES0822-CWP-549 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Actual Units
SES0822-CWP-549 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | [72 empty] | 12t
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [71 empty] | 188m | 196m | 196m | 73m
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [71 empty] | 188m | 196m | 196m | 73m
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [53 empty] | 11m | 14m | 14m | 14m | 14m | 14m | 14m | 8m
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [53 empty] | 11m | 14m | 14m | 14m | 14m | 14m | 14m | 8m
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [65 empty] | 41m | 96m | 96m | 55m
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [65 empty] | 41m | 96m | 96m | 55m
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [83 empty] | 318m | 363m | 363m | 363m | 363m | 45m
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [83 empty] | 318m | 363m | 363m | 363m | 363m | 45m
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [82 empty] | 155m | 404m | 404m | 404m | 404m | 404m | 404m | 404m | 404m | 404m | 249m
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [82 empty] | 155m | 404m | 404m | 404m | 404m | 404m | 404m | 404m | 404m | 404m | 249m
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [79 empty] | 63m | 300m | 300m | 300m | 38m
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [79 empty] | 63m | 300m | 300m | 300m | 38m
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [82 empty] | 46m | 121m | 121m | 115m
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [82 empty] | 46m | 121m | 121m | 115m
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [85 empty] | 27m | 545m | 545m | 545m | 154m
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [85 empty] | 27m | 545m | 545m | 545m | 154m
TTU0822-CWP-190 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
TTU0822-CWP-190 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-190 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
TTU0822-CWP-211 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
TTU0822-CWP-211 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-211 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [82 empty] | 28m | 126m | 126m | 22m
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [82 empty] | 28m | 126m | 126m | 22m
TTU0822-CWP-216 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
TTU0822-CWP-216 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-216 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
MEM0822-CWP-221 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
MEM0822-CWP-221 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
MEM0822-CWP-221 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
MEM0822-CWP-222 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
MEM0822-CWP-222 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
MEM0822-CWP-222 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
MEM0822-CWP-223 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
MEM0822-CWP-223 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
MEM0822-CWP-223 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
TTU0822-CWP-227 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
TTU0822-CWP-227 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-227 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
TTU0822-CWP-232 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
TTU0822-CWP-232 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-232 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
TTU0822-CWP-236 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
TTU0822-CWP-236 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-236 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
TTU0822-CWP-239 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
TTU0822-CWP-239 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0822-CWP-239 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
TTU0823-CWP-505 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [74 empty] | 83m | 117m
TTU0823-CWP-505 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0823-CWP-505 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [74 empty] | 83m | 117m
TTU0826-CWP-283 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
TTU0826-CWP-283 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0826-CWP-283 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [82 empty] | 32m | 84m | 84m | 84m | 84m | 84m | 84m | 52m
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [82 empty] | 32m | 84m | 84m | 84m | 84m | 84m | 84m | 52m
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [76 empty] | 124m | 124m | 124m | 124m | 124m
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [76 empty] | 124m | 124m | 124m | 124m | 124m
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | [82 empty] | 15m | 66m | 66m | 66m | 66m | 51m
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | [82 empty] | 15m | 66m | 66m | 66m | 66m | 51m
TTU0623-CWP-412 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units
TTU0623-CWP-412 | TUBULACAO EM METROS - PIPING IN METERS | Material | Actual Units
TTU0623-CWP-412 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 195m | 488m | 488m | 488m | 488m | 488m | 293m
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | Actual Units
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 195m | 488m | 488m | 488m | 488m | 488m | 293m
ECB0821-CWP-082 | CABLAGEM - WIRING | Material | Budgeted Units | [85 empty] | 2901m | 24m
ECB0821-CWP-082 | CABLAGEM - WIRING | Material | Actual Units
ECB0821-CWP-082 | CABLAGEM - WIRING | Material | At Completion Units | [85 empty] | 2901m | 24m
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Budgeted Units | [53 empty] | 16m | 20m | 20m | 20m | 20m | 20m | 20m | 12m
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Actual Units
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | At Completion Units | [53 empty] | 16m | 20m | 20m | 20m | 20m | 20m | 20m | 12m
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | Budgeted Units | [89 empty] | 609m | 975m | 975m | 975m | 366m
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | Actual Units
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | At Completion Units | [89 empty] | 609m | 975m | 975m | 975m | 366m
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | [88 empty] | 2775m | 6529m | 6529m | 6529m | 6529m | 6529m | 6529m | 6529m | 3754m
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Actual Units
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | [88 empty] | 2775m | 6529m | 6529m | 6529m | 6529m | 6529m | 6529m | 6529m | 3754m
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 390m | 975m | 975m | 585m
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | Actual Units
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 390m | 975m | 975m | 585m
ECB0822-CWP-198 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-198 | CABLAGEM - WIRING | Material | Actual Units
ECB0822-CWP-198 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 488m | 1219m | 1219m | 731m
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | Actual Units
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 488m | 1219m | 1219m | 731m
ECB0822-CWP-214 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-214 | CABLAGEM - WIRING | Material | Actual Units
ECB0822-CWP-214 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-219 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-219 | CABLAGEM - WIRING | Material | Actual Units
ECB0822-CWP-219 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-226 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-226 | CABLAGEM - WIRING | Material | Actual Units
ECB0822-CWP-226 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-251 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-251 | CABLAGEM - WIRING | Material | Actual Units
ECB0822-CWP-251 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-252 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 488m | 1219m | 1219m
ECB0822-CWP-252 | CABLAGEM - WIRING | Material | Actual Units
ECB0822-CWP-252 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 488m | 1219m | 1219m
EEE0826-CWP-300 | CABLAGEM - WIRING | Material | Budgeted Units | [93 empty] | 43m | 50m | 7m
EEE0826-CWP-300 | CABLAGEM - WIRING | Material | Actual Units
EEE0826-CWP-300 | CABLAGEM - WIRING | Material | At Completion Units | [93 empty] | 43m | 50m | 7m
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | Budgeted Units | [86 empty] | 603m | 731m | 731m | 731m | 128m
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | Actual Units
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | At Completion Units | [86 empty] | 603m | 731m | 731m | 731m | 128m
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 760m | 1900m | 1900m | 1140m
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | Actual Units
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 760m | 1900m | 1900m | 1140m
ECB1214-CWP-526 | CABLAGEM - WIRING | Material | Budgeted Units | [90 empty] | 527m
ECB1214-CWP-526 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-526 | CABLAGEM - WIRING | Material | At Completion Units | [90 empty] | 527m
ECB1214-CWP-527 | CABLAGEM - WIRING | Material | Budgeted Units | [91 empty] | 527m
ECB1214-CWP-527 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-527 | CABLAGEM - WIRING | Material | At Completion Units | [91 empty] | 527m
ECB1214-CWP-528 | CABLAGEM - WIRING | Material | Budgeted Units | [92 empty] | 527m
ECB1214-CWP-528 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-528 | CABLAGEM - WIRING | Material | At Completion Units | [92 empty] | 527m
ECB1214-CWP-529 | CABLAGEM - WIRING | Material | Budgeted Units | [93 empty] | 527m
ECB1214-CWP-529 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-529 | CABLAGEM - WIRING | Material | At Completion Units | [93 empty] | 527m
ECB1214-CWP-530 | CABLAGEM - WIRING | Material | Budgeted Units | [94 empty] | 527m
ECB1214-CWP-530 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-530 | CABLAGEM - WIRING | Material | At Completion Units | [94 empty] | 527m
ECB1214-CWP-531 | CABLAGEM - WIRING | Material | Budgeted Units | [94 empty] | 527m
ECB1214-CWP-531 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-531 | CABLAGEM - WIRING | Material | At Completion Units | [94 empty] | 527m
ECB1214-CWP-532 | CABLAGEM - WIRING | Material | Budgeted Units | [95 empty] | 527m
ECB1214-CWP-532 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-532 | CABLAGEM - WIRING | Material | At Completion Units | [95 empty] | 527m
ECB1214-CWP-533 | CABLAGEM - WIRING | Material | Budgeted Units | [95 empty] | 527m
ECB1214-CWP-533 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-533 | CABLAGEM - WIRING | Material | At Completion Units | [95 empty] | 527m
ECB1214-CWP-534 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 527m
ECB1214-CWP-534 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-534 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 527m
ECB1214-CWP-535 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 527m
ECB1214-CWP-535 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-535 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 527m
ECB1214-CWP-536 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 527m
ECB1214-CWP-536 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-536 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 527m
ECB1214-CWP-537 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 527m
ECB1214-CWP-537 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-537 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 527m
ECB1214-CWP-538 | CABLAGEM - WIRING | Material | Budgeted Units | [88 empty] | 527m
ECB1214-CWP-538 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-538 | CABLAGEM - WIRING | Material | At Completion Units | [88 empty] | 527m
ECB1214-CWP-539 | CABLAGEM - WIRING | Material | Budgeted Units | [89 empty] | 527m
ECB1214-CWP-539 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-539 | CABLAGEM - WIRING | Material | At Completion Units | [89 empty] | 527m
ECB0817-CWP-550 | CABLAGEM - WIRING | Material | Budgeted Units | [85 empty] | 130m | 195m
ECB0817-CWP-550 | CABLAGEM - WIRING | Material | Actual Units
ECB0817-CWP-550 | CABLAGEM - WIRING | Material | At Completion Units | [85 empty] | 130m | 195m
ECB0817-CWP-551 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 130m | 195m
ECB0817-CWP-551 | CABLAGEM - WIRING | Material | Actual Units
ECB0817-CWP-551 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 130m | 195m
ECB0817-CWP-552 | CABLAGEM - WIRING | Material | Budgeted Units | [96 empty] | 65m | 261m
ECB0817-CWP-552 | CABLAGEM - WIRING | Material | Actual Units
ECB0817-CWP-552 | CABLAGEM - WIRING | Material | At Completion Units | [96 empty] | 65m | 261m
ECB0821-CWP-553 | CABLAGEM - WIRING | Material | Budgeted Units | [90 empty] | 1463m
ECB0821-CWP-553 | CABLAGEM - WIRING | Material | Actual Units
ECB0821-CWP-553 | CABLAGEM - WIRING | Material | At Completion Units | [90 empty] | 1463m
ECB0821-CWP-554 | CABLAGEM - WIRING | Material | Budgeted Units | [89 empty] | 975m | 488m
ECB0821-CWP-554 | CABLAGEM - WIRING | Material | Actual Units
ECB0821-CWP-554 | CABLAGEM - WIRING | Material | At Completion Units | [89 empty] | 975m | 488m
ECB0823-CWP-555 | CABLAGEM - WIRING | Material | Budgeted Units | [86 empty] | 975m
ECB0823-CWP-555 | CABLAGEM - WIRING | Material | Actual Units
ECB0823-CWP-555 | CABLAGEM - WIRING | Material | At Completion Units | [86 empty] | 975m
ECB0823-CWP-556 | CABLAGEM - WIRING | Material | Budgeted Units | [85 empty] | 731m | 244m
ECB0823-CWP-556 | CABLAGEM - WIRING | Material | Actual Units
ECB0823-CWP-556 | CABLAGEM - WIRING | Material | At Completion Units | [85 empty] | 731m | 244m
ECB0823-CWP-557 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 488m | 488m
ECB0823-CWP-557 | CABLAGEM - WIRING | Material | Actual Units
ECB0823-CWP-557 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 488m | 488m
ECB0824-CWP-558 | CABLAGEM - WIRING | Material | Budgeted Units | [86 empty] | 975m
ECB0824-CWP-558 | CABLAGEM - WIRING | Material | Actual Units
ECB0824-CWP-558 | CABLAGEM - WIRING | Material | At Completion Units | [86 empty] | 975m
ECB0824-CWP-559 | CABLAGEM - WIRING | Material | Budgeted Units | [85 empty] | 731m | 244m
ECB0824-CWP-559 | CABLAGEM - WIRING | Material | Actual Units
ECB0824-CWP-559 | CABLAGEM - WIRING | Material | At Completion Units | [85 empty] | 731m | 244m
ECB0824-CWP-560 | CABLAGEM - WIRING | Material | Budgeted Units | [84 empty] | 488m | 488m
ECB0824-CWP-560 | CABLAGEM - WIRING | Material | Actual Units
ECB0824-CWP-560 | CABLAGEM - WIRING | Material | At Completion Units | [84 empty] | 488m | 488m
ECB0826-CWP-561 | CABLAGEM - WIRING | Material | Budgeted Units | [96 empty] | 762m | 213m
ECB0826-CWP-561 | CABLAGEM - WIRING | Material | Actual Units
ECB0826-CWP-561 | CABLAGEM - WIRING | Material | At Completion Units | [96 empty] | 762m | 213m
ECB0826-CWP-562 | CABLAGEM - WIRING | Material | Budgeted Units | [95 empty] | 518m | 457m
ECB0826-CWP-562 | CABLAGEM - WIRING | Material | Actual Units
ECB0826-CWP-562 | CABLAGEM - WIRING | Material | At Completion Units | [95 empty] | 518m | 457m
ECB0826-CWP-563 | CABLAGEM - WIRING | Material | Budgeted Units | [94 empty] | 274m | 701m
ECB0826-CWP-563 | CABLAGEM - WIRING | Material | Actual Units
ECB0826-CWP-563 | CABLAGEM - WIRING | Material | At Completion Units | [94 empty] | 274m | 701m
ECB0827-CWP-564 | CABLAGEM - WIRING | Material | Budgeted Units | [94 empty] | 488m | 488m
ECB0827-CWP-564 | CABLAGEM - WIRING | Material | Actual Units
ECB0827-CWP-564 | CABLAGEM - WIRING | Material | At Completion Units | [94 empty] | 488m | 488m
ECB0827-CWP-565 | CABLAGEM - WIRING | Material | Budgeted Units | [94 empty] | 975m
ECB0827-CWP-565 | CABLAGEM - WIRING | Material | Actual Units
ECB0827-CWP-565 | CABLAGEM - WIRING | Material | At Completion Units | [94 empty] | 975m
ECB0827-CWP-566 | CABLAGEM - WIRING | Material | Budgeted Units | [94 empty] | 975m
ECB0827-CWP-566 | CABLAGEM - WIRING | Material | Actual Units
ECB0827-CWP-566 | CABLAGEM - WIRING | Material | At Completion Units | [94 empty] | 975m
ECB1048-CWP-567 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 100m
ECB1048-CWP-567 | CABLAGEM - WIRING | Material | Actual Units
ECB1048-CWP-567 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 100m
ECB1048-CWP-568 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 100m
ECB1048-CWP-568 | CABLAGEM - WIRING | Material | Actual Units
ECB1048-CWP-568 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 100m
ECB1048-CWP-569 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 100m
ECB1048-CWP-569 | CABLAGEM - WIRING | Material | Actual Units
ECB1048-CWP-569 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 100m
ECB1049-CWP-570 | CABLAGEM - WIRING | Material | Budgeted Units | [91 empty] | 13m | 88m
ECB1049-CWP-570 | CABLAGEM - WIRING | Material | Actual Units
ECB1049-CWP-570 | CABLAGEM - WIRING | Material | At Completion Units | [91 empty] | 13m | 88m
ECB1049-CWP-571 | CABLAGEM - WIRING | Material | Budgeted Units | [91 empty] | 100m
ECB1049-CWP-571 | CABLAGEM - WIRING | Material | Actual Units
ECB1049-CWP-571 | CABLAGEM - WIRING | Material | At Completion Units | [91 empty] | 100m
ECB1049-CWP-572 | CABLAGEM - WIRING | Material | Budgeted Units | [91 empty] | 100m
ECB1049-CWP-572 | CABLAGEM - WIRING | Material | Actual Units
ECB1049-CWP-572 | CABLAGEM - WIRING | Material | At Completion Units | [91 empty] | 100m
ECB1062-CWP-573 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 324m | 971m
ECB1062-CWP-573 | CABLAGEM - WIRING | Material | Actual Units
ECB1062-CWP-573 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 324m | 971m
ECB1062-CWP-574 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 1295m
ECB1062-CWP-574 | CABLAGEM - WIRING | Material | Actual Units
ECB1062-CWP-574 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 1295m
ECB1062-CWP-575 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 1295m
ECB1062-CWP-575 | CABLAGEM - WIRING | Material | Actual Units
ECB1062-CWP-575 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 1295m
ECB1214-CWP-576 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 88m | 439m
ECB1214-CWP-576 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-576 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 88m | 439m
ECB1214-CWP-577 | CABLAGEM - WIRING | Material | Budgeted Units | [87 empty] | 88m | 439m
ECB1214-CWP-577 | CABLAGEM - WIRING | Material | Actual Units
ECB1214-CWP-577 | CABLAGEM - WIRING | Material | At Completion Units | [87 empty] | 88m | 439m
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [86 empty] | 0un | 0un | 0un | 0un
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [86 empty] | 0un | 0un | 0un | 0un
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [81 empty] | 0un | 1un | 1un | 1un
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [81 empty] | 0un | 1un | 1un | 1un
JIL0817-CWP-051 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [99 empty] | 10un
JIL0817-CWP-051 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0817-CWP-051 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [99 empty] | 10un
JIL0800-CWP-058 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [86 empty] | 7un | 34un | 27un
JIL0800-CWP-058 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0800-CWP-058 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [86 empty] | 7un | 34un | 27un
JIL0820-CWP-418 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [86 empty] | 3un | 6un | 3un
JIL0820-CWP-418 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0820-CWP-418 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [86 empty] | 3un | 6un | 3un
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [90 empty] | 0un | 1un | 1un | 1un | 1un | 1un | 0un
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [90 empty] | 0un | 1un | 1un | 1un | 1un | 1un | 0un
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [77 empty] | 0un | 0un | 0un | 0un | 0un
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [77 empty] | 0un | 0un | 0un | 0un | 0un
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [90 empty] | 0un | 1un | 1un | 1un | 0un
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [90 empty] | 0un | 1un | 1un | 1un | 0un
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [92 empty] | 1un | 2un | 2un | 2un | 0un
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [92 empty] | 1un | 2un | 2un | 2un | 0un
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [77 empty] | 0un | 0un | 0un | 0un | 0un
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [77 empty] | 0un | 0un | 0un | 0un | 0un
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [94 empty] | 59un | 68un | 68un | 68un | 68un | 31un
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [94 empty] | 59un | 68un | 68un | 68un | 68un | 31un
EEE0822-CWP-158 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [86 empty] | 0un | 1un | 1un
EEE0822-CWP-158 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
EEE0822-CWP-158 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [86 empty] | 0un | 1un | 1un
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [83 empty] | 4un | 5un | 5un | 5un | 5un | 1un
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [83 empty] | 4un | 5un | 5un | 5un | 5un | 1un
JIL0822-CWP-164 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [77 empty] | 15un | 15un
JIL0822-CWP-164 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-164 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [77 empty] | 15un | 15un
JIL0822-CWP-165 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [93 empty] | 20un | 20un | 20un
JIL0822-CWP-165 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-165 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [93 empty] | 20un | 20un | 20un
JIL0822-CWP-166 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [86 empty] | 104un | 244un | 140un
JIL0822-CWP-166 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-166 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [86 empty] | 104un | 244un | 140un
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [92 empty] | 2un | 4un | 4un | 4un | 2un
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [92 empty] | 2un | 4un | 4un | 4un | 2un
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [93 empty] | 1un | 3un | 3un | 2un
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [93 empty] | 1un | 3un | 3un | 2un
JIL0822-CWP-199 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [55 empty] | 154un | 256un | 205un
JIL0822-CWP-199 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-199 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [55 empty] | 154un | 256un | 205un
JIL0822-CWP-206 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units
JIL0822-CWP-206 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-206 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units
JIL0822-CWP-213 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [85 empty] | 2un | 2un | 1un
JIL0822-CWP-213 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-213 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [85 empty] | 2un | 2un | 1un
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [57 empty] | 6un | 28un | 28un | 6un
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [57 empty] | 6un | 28un | 28un | 6un
JIL0822-CWP-224 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [55 empty] | 45un | 75un | 60un
JIL0822-CWP-224 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-224 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [55 empty] | 45un | 75un | 60un
JIL0822-CWP-228 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [85 empty] | 6un | 7un | 4un
JIL0822-CWP-228 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-228 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [85 empty] | 6un | 7un | 4un
JIL0822-CWP-233 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [85 empty] | 11un | 13un | 8un
JIL0822-CWP-233 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-233 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [85 empty] | 11un | 13un | 8un
JIL0822-CWP-237 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units
JIL0822-CWP-237 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-237 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units
JIL0822-CWP-240 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units
JIL0822-CWP-240 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0822-CWP-240 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [92 empty] | 0un | 1un | 1un | 1un | 1un | 0un
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [92 empty] | 0un | 1un | 1un | 1un | 1un | 0un
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [92 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [92 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [94 empty] | 0un | 0un | 0un | 0un | 0un
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [94 empty] | 0un | 0un | 0un | 0un | 0un
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [90 empty] | 0un | 1un | 1un | 1un | 0un
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [90 empty] | 0un | 1un | 1un | 1un | 0un
JIL0827-CWP-341 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [98 empty] | 10un
JIL0827-CWP-341 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0827-CWP-341 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [98 empty] | 10un
JIL0827-CWP-363 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [86 empty] | 2un | 5un | 3un
JIL0827-CWP-363 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0827-CWP-363 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [86 empty] | 2un | 5un | 3un
JPA0827-CWP-451 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [92 empty] | 1un | 2un | 1un
JPA0827-CWP-451 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JPA0827-CWP-451 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [92 empty] | 1un | 2un | 1un
EEE0827-CWP-345 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [71 empty] | 7un | 7un
EEE0827-CWP-345 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
EEE0827-CWP-345 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [71 empty] | 7un | 7un
EEE0827-CWP-457 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [83 empty] | 2un | 2un | 0un
EEE0827-CWP-457 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
EEE0827-CWP-457 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [83 empty] | 2un | 2un | 0un
JIL0827-CWP-349 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [73 empty] | 7un
JIL0827-CWP-349 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0827-CWP-349 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [73 empty] | 7un
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [91 empty] | 18un | 80un | 80un | 80un | 62un
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [91 empty] | 18un | 80un | 80un | 80un | 62un
JIL0827-CWP-365 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [86 empty] | 30un
JIL0827-CWP-365 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0827-CWP-365 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [86 empty] | 30un
EEE1062-CWP-460 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [86 empty] | 1un | 1un
EEE1062-CWP-460 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
EEE1062-CWP-460 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [86 empty] | 1un | 1un
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [83 empty] | 1un | 2un | 2un | 2un
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [83 empty] | 1un | 2un | 2un | 2un
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [70 empty] | 0un | 2un | 2un | 2un | 2un | 2un | 2un | 2un | 2un | 2un
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [70 empty] | 0un | 2un | 2un | 2un | 2un | 2un | 2un | 2un | 2un | 2un
MEM0823-CWP-248 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [71 empty] | 7un
MEM0823-CWP-248 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
MEM0823-CWP-248 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [71 empty] | 7un
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [86 empty] | 5un | 10un | 10un | 4un
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [86 empty] | 5un | 10un | 10un | 4un
RIN1110-CWP-387 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units
RIN1110-CWP-387 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
RIN1110-CWP-387 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [90 empty] | 0un | 1un | 1un | 0un
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [90 empty] | 0un | 1un | 1un | 0un
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [91 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [91 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un
JIL0622-CWP-004 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | [91 empty] | 0un | 1un | 0un
JIL0622-CWP-004 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Actual Units
JIL0622-CWP-004 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | [91 empty] | 0un | 1un | 0un
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [80 empty] | 46m | 1833m | 1833m | 1788m
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [80 empty] | 46m | 1833m | 1833m | 1788m
EEL0817-CWP-048 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units
EEL0817-CWP-048 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EEL0817-CWP-048 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units
EBD0800-CWP-056 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units
EBD0800-CWP-056 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0800-CWP-056 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units
EBD0821-CWP-081 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units
EBD0821-CWP-081 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0821-CWP-081 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units
EEE0821-CWP-089 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [83 empty] | 40m | 60m | 21m
EEE0821-CWP-089 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EEE0821-CWP-089 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [83 empty] | 40m | 60m | 21m
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [78 empty] | 21m | 19m | 24m | 24m | 24m | 8m
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [78 empty] | 21m | 19m | 24m | 24m | 24m | 8m
EBD0822-CWP-157 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units
EBD0822-CWP-157 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0822-CWP-157 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [80 empty] | 50m | 2000m | 2000m | 1950m
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [80 empty] | 50m | 2000m | 2000m | 1950m
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [80 empty] | 2m | 83m | 83m | 81m
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [80 empty] | 2m | 83m | 83m | 81m
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [80 empty] | 1m | 42m | 42m | 16m
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [80 empty] | 1m | 42m | 42m | 16m
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [57 empty] | 3m | 13m | 13m | 3m
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [57 empty] | 3m | 13m | 13m | 3m
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [80 empty] | 1m | 42m | 42m | 41m
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [80 empty] | 1m | 42m | 42m | 41m
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [80 empty] | 1m | 25m | 25m | 24m
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [80 empty] | 1m | 25m | 25m | 24m
EBD0826-CWP-282 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units
EBD0826-CWP-282 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0826-CWP-282 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units
EEL0827-CWP-338 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units
EEL0827-CWP-338 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EEL0827-CWP-338 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [83 empty] | 2m | 2m | 2m | 2m | 2m | 2m
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [83 empty] | 2m | 2m | 2m | 2m | 2m | 2m
EBD1062-CWP-459 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [80 empty] | 69m | 251m
EBD1062-CWP-459 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD1062-CWP-459 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [80 empty] | 69m | 251m
EBD1214-CWP-395 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units
EBD1214-CWP-395 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD1214-CWP-395 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [84 empty] | 103m | 117m | 117m | 14m
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [84 empty] | 103m | 117m | 117m | 14m
EBD0600-CWP-589 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [88 empty] | 492m | 738m
EBD0600-CWP-589 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EBD0600-CWP-589 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [88 empty] | 492m | 738m
EEE0800-CWP-416 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [77 empty] | 0un | 0un | 0un
EEE0800-CWP-416 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EEE0800-CWP-416 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [77 empty] | 0un | 0un | 0un
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [71 empty] | 14un | 34un | 34un | 34un | 34un | 34un | 34un | 34un | 34un | 20un
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [71 empty] | 14un | 34un | 34un | 34un | 34un | 34un | 34un | 34un | 34un | 20un
EEE0822-CWP-162 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [96 empty] | 9un | 21un | 12un
EEE0822-CWP-162 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EEE0822-CWP-162 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [96 empty] | 9un | 21un | 12un
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [92 empty] | 0un | 1un | 1un | 1un | 1un
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [92 empty] | 0un | 1un | 1un | 1un | 1un
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [77 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [77 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [80 empty] | 0un | 5un | 5un | 2un
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [80 empty] | 0un | 5un | 5un | 2un
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [83 empty] | 1un | 5un | 5un | 4un
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [83 empty] | 1un | 5un | 5un | 4un
ELU0600-CWP-007 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | [87 empty] | 10un | 16un
ELU0600-CWP-007 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Actual Units
ELU0600-CWP-007 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | [87 empty] | 10un | 16un
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [81 empty] | 1un | 1un | 1un | 1un
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [81 empty] | 1un | 1un | 1un | 1un
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [86 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [86 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [84 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [84 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [86 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [86 empty] | 1un | 40un | 40un | 39un
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [85 empty] | 9un | 40un | 40un | 7un
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [85 empty] | 9un | 40un | 40un | 7un
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [85 empty] | 9un | 40un | 40un | 7un
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [85 empty] | 9un | 40un | 40un | 7un
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [85 empty] | 9un | 40un | 40un | 7un
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [85 empty] | 9un | 40un | 40un | 7un
EEE0820-CWP-141 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [87 empty] | 33un | 40un | 23un
EEE0820-CWP-141 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE0820-CWP-141 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [87 empty] | 33un | 40un | 23un
EEE0820-CWP-142 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [89 empty] | 17un | 40un | 39un
EEE0820-CWP-142 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE0820-CWP-142 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [89 empty] | 17un | 40un | 39un
EEE0820-CWP-143 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [88 empty] | 25un | 40un | 31un
EEE0820-CWP-143 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE0820-CWP-143 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [88 empty] | 25un | 40un | 31un
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [84 empty] | 1un | 40un | 40un | 39un
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [84 empty] | 1un | 40un | 40un | 39un
EEE1049-CWP-471 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [81 empty] | 2un | 5un | 3un
EEE1049-CWP-471 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1049-CWP-471 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [81 empty] | 2un | 5un | 3un
EEE1048-CWP-472 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [73 empty] | 22un | 17un
EEE1048-CWP-472 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1048-CWP-472 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [73 empty] | 22un | 17un
EEE1048-CWP-473 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [84 empty] | 2un | 2un | 2un
EEE1048-CWP-473 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1048-CWP-473 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [84 empty] | 2un | 2un | 2un
EEE1049-CWP-376 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [81 empty] | 2un | 5un | 3un
EEE1049-CWP-376 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1049-CWP-376 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [81 empty] | 2un | 5un | 3un
EEE1049-CWP-377 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [83 empty] | 8un | 19un | 11un
EEE1049-CWP-377 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1049-CWP-377 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [83 empty] | 8un | 19un | 11un
EEE1049-CWP-378 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [89 empty] | 0un | 1un | 0un
EEE1049-CWP-378 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1049-CWP-378 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [89 empty] | 0un | 1un | 0un
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [92 empty] | 6un | 6un | 6un | 3un
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [92 empty] | 6un | 6un | 6un | 3un
EEE1062-CWP-383 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [79 empty] | 0un | 1un | 0un
EEE1062-CWP-383 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1062-CWP-383 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [79 empty] | 0un | 1un | 0un
EEE1062-CWP-384 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [81 empty] | 2un | 6un | 4un
EEE1062-CWP-384 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1062-CWP-384 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [81 empty] | 2un | 6un | 4un
EEE1062-CWP-386 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [86 empty] | 0un | 1un
EEE1062-CWP-386 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1062-CWP-386 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [86 empty] | 0un | 1un
EEE1062-CWP-381 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | [68 empty] | 0un | 1un | 1un
EEE1062-CWP-381 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Actual Units
EEE1062-CWP-381 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | [68 empty] | 0un | 1un | 1un
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Actual Units
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Actual Units
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Actual Units
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 12 | 12 | 12 | 12 | 12 | 12
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | Actual Units
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 12 | 12 | 12 | 12 | 12 | 12
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 2 | 2 | 2 | 2 | 2 | 2
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | Actual Units
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 2 | 2 | 2 | 2 | 2 | 2
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 24 | 24 | 24 | 24 | 24 | 24
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | Actual Units
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 24 | 24 | 24 | 24 | 24 | 24
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Actual Units
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Actual Units
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Actual Units
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | Budgeted Units | [61 empty] | 9 | 40 | 40 | 40 | 31
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | Actual Units
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | At Completion Units | [61 empty] | 9 | 40 | 40 | 40 | 31
MCD0827-CWP-342 | CALDEIRARIA (t) | Material | Budgeted Units | [76 empty] | 78 | 46
MCD0827-CWP-342 | CALDEIRARIA (t) | Material | Actual Units
MCD0827-CWP-342 | CALDEIRARIA (t) | Material | At Completion Units | [76 empty] | 78 | 46
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | Budgeted Units | [85 empty] | 0 | 3 | 3 | 3 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | Actual Units
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | At Completion Units | [85 empty] | 0 | 3 | 3 | 3 | 1
MEM0817-CWP-034 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [83 empty] | 1t
MEM0817-CWP-034 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0817-CWP-034 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [83 empty] | 1t
MEM0817-CWP-045 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [93 empty] | 1t | 0t
MEM0817-CWP-045 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0817-CWP-045 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [93 empty] | 1t | 0t
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [61 empty] | 1t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [61 empty] | 1t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t | 3t
MEM0821-CWP-421 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [84 empty] | 1t | 10t | 3t
MEM0821-CWP-421 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-421 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [84 empty] | 1t | 10t | 3t
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [88 empty] | 2t | 2t | 2t | 2t
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [88 empty] | 2t | 2t | 2t | 2t
MEM0821-CWP-083 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [86 empty] | 7t | 18t | 0t
MEM0821-CWP-083 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-083 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [86 empty] | 7t | 18t | 0t
MEM0821-CWP-084 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [83 empty] | 33t | 51t
MEM0821-CWP-084 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-084 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [83 empty] | 33t | 51t
MEM0821-CWP-087 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [85 empty] | 21t | 4t
MEM0821-CWP-087 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-087 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [85 empty] | 21t | 4t
TTU0821-CWP-420 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [84 empty] | 0t | 0t | 0t
TTU0821-CWP-420 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
TTU0821-CWP-420 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [84 empty] | 0t | 0t | 0t
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [88 empty] | 20t | 21t | 21t | 21t | 6t
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [88 empty] | 20t | 21t | 21t | 21t | 6t
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [77 empty] | 10t | 10t | 10t | 10t | 2t
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [77 empty] | 10t | 10t | 10t | 10t | 2t
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [88 empty] | 35t | 36t | 36t | 0t
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [88 empty] | 35t | 36t | 36t | 0t
MEM0821-CWP-080 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
MEM0821-CWP-080 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-080 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
TTU0821-CWP-419 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 0t | 1t
TTU0821-CWP-419 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
TTU0821-CWP-419 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 0t | 1t
MEM0822-CWP-168 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [77 empty] | 1t | 1t | 1t
MEM0822-CWP-168 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-168 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [77 empty] | 1t | 1t | 1t
MEM0822-CWP-169 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [80 empty] | 2t | 10t | 7t
MEM0822-CWP-169 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-169 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [80 empty] | 2t | 10t | 7t
MEM0822-CWP-170 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [84 empty] | 7t | 7t
MEM0822-CWP-170 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-170 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [84 empty] | 7t | 7t
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [81 empty] | 0t | 0t | 0t | 0t
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [81 empty] | 0t | 0t | 0t | 0t
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [71 empty] | 1t | 1t | 1t | 1t
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [71 empty] | 1t | 1t | 1t | 1t
SES0822-CWP-101 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
SES0822-CWP-101 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
SES0822-CWP-101 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [85 empty] | 0t | 0t | 0t | 0t | 0t | 0t
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [85 empty] | 0t | 0t | 0t | 0t | 0t | 0t
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [96 empty] | 2t | 6t | 6t | 3t
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [96 empty] | 2t | 6t | 6t | 3t
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [80 empty] | 1t | 1t | 1t | 1t | 0t
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [80 empty] | 1t | 1t | 1t | 1t | 0t
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [70 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [70 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [63 empty] | 2t | 4t |  | 4t | 4t | 4t | 4t | 4t | 4t | 3t
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [63 empty] | 2t | 4t |  | 4t | 4t | 4t | 4t | 4t | 4t | 3t
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [72 empty] | 2t | 4t | 5t | 5t | 5t | 5t | 5t | 3t
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [72 empty] | 2t | 4t | 5t | 5t | 5t | 5t | 5t | 3t
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [70 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [70 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [63 empty] | 2t | 4t |  | 4t | 4t | 4t | 4t | 4t | 4t | 3t
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [63 empty] | 2t | 4t |  | 4t | 4t | 4t | 4t | 4t | 4t | 3t
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [72 empty] | 2t | 4t | 4t | 5t | 5t | 5t | 5t | 3t
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [72 empty] | 2t | 4t | 4t | 5t | 5t | 5t | 5t | 3t
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [70 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [70 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [63 empty] | 2t | 3t |  | 4t | 4t | 4t | 4t | 4t | 4t | 3t
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [63 empty] | 2t | 3t |  | 4t | 4t | 4t | 4t | 4t | 4t | 3t
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 1t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [72 empty] | 2t | 4t | 5t | 5t | 5t | 5t | 5t | 3t
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [72 empty] | 2t | 4t | 5t | 5t | 5t | 5t | 5t | 3t
MEM0822-CWP-191 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
MEM0822-CWP-191 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-191 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
MEM0822-CWP-192 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
MEM0822-CWP-192 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-192 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
MEM0822-CWP-193 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
MEM0822-CWP-193 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-193 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
MEM0822-CWP-194 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
MEM0822-CWP-194 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-194 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
MEM0822-CWP-195 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
MEM0822-CWP-195 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-195 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
MEM0822-CWP-196 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
MEM0822-CWP-196 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-196 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
TTU0822-CWP-201 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
TTU0822-CWP-201 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
TTU0822-CWP-201 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
TTU0822-CWP-202 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
TTU0822-CWP-202 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
TTU0822-CWP-202 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
TTU0822-CWP-210 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [90 empty] | 0t | 1t | 0t
TTU0822-CWP-210 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
TTU0822-CWP-210 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [90 empty] | 0t | 1t | 0t
MEM0822-CWP-220 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [55 empty] | 7t | 12t | 2t
MEM0822-CWP-220 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0822-CWP-220 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [55 empty] | 7t | 12t | 2t
MCD0822-CWP-231 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
MCD0822-CWP-231 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MCD0822-CWP-231 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
MCD0822-CWP-235 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units
MCD0822-CWP-235 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MCD0822-CWP-235 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [88 empty] | 0t | 0t | 0t | 0t | 0t
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [88 empty] | 0t | 0t | 0t | 0t | 0t
MEM0823-CWP-439 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [87 empty] | 0t | 1t | 0t
MEM0823-CWP-439 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0823-CWP-439 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [87 empty] | 0t | 1t | 0t
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 0t | 1t | 1t | 1t | 1t | 1t | 0t
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 0t | 1t | 1t | 1t | 1t | 1t | 0t
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [88 empty] | 3t | 17t | 17t | 17t | 17t | 17t | 17t | 17t | 17t | 17t | 14t
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [88 empty] | 3t | 17t | 17t | 17t | 17t | 17t | 17t | 17t | 17t | 17t | 14t
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [88 empty] | 0t | 0t | 0t | 0t | 0t
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [88 empty] | 0t | 0t | 0t | 0t | 0t
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [97 empty] | 2t | 2t | 2t | 0t
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [97 empty] | 2t | 2t | 2t | 0t
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [91 empty] | 2t | 2t | 2t | 0t
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [91 empty] | 2t | 2t | 2t | 0t
MEM0824-CWP-272 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [97 empty] | 1t | 0t
MEM0824-CWP-272 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0824-CWP-272 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [97 empty] | 1t | 0t
MEM0824-CWP-273 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [91 empty] | 1t | 0t
MEM0824-CWP-273 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0824-CWP-273 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [91 empty] | 1t | 0t
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [97 empty] | 3t | 5t | 5t | 5t | 2t
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [97 empty] | 3t | 5t | 5t | 5t | 2t
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [86 empty] | 0t | 0t | 0t | 0t
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [86 empty] | 0t | 0t | 0t | 0t
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [95 empty] | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [95 empty] | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [80 empty] | 0t | 1t | 1t | 1t | 1t
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [80 empty] | 0t | 1t | 1t | 1t | 1t
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [93 empty] | 0t | 0t | 0t | 0t | 0t | 0t | 0t
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [93 empty] | 0t | 0t | 0t | 0t | 0t | 0t | 0t
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [71 empty] | 0t | 1t | 1t | 1t | 0t
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [71 empty] | 0t | 1t | 1t | 1t | 0t
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [80 empty] | 0t | 1t | 1t | 1t | 1t | 1t | 1t
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [80 empty] | 0t | 1t | 1t | 1t | 1t | 1t | 1t
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [58 empty] | 1t | 3t | 3t | 1t
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [58 empty] | 1t | 3t | 3t | 1t
MEM0827-CWP-321 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [84 empty] | 16t
MEM0827-CWP-321 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-321 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [84 empty] | 16t
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [65 empty] | 6t | 6t | 6t | 6t
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [65 empty] | 6t | 6t | 6t | 6t
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [63 empty] | 35t | 35t | 35t | 35t
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [63 empty] | 35t | 35t | 35t | 35t
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [80 empty] | 0t | 4t | 4t | 4t | 4t
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [80 empty] | 0t | 4t | 4t | 4t | 4t
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [73 empty] | 0t | 0t | 0t | 0t
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [73 empty] | 0t | 0t | 0t | 0t
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [71 empty] | 1t | 1t | 1t | 0t
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [71 empty] | 1t | 1t | 1t | 0t
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [85 empty] | 0t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [85 empty] | 0t | 2t | 2t | 2t | 2t | 2t | 2t | 1t
MEM0827-CWP-348 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [83 empty] | 0t | 1t | 0t
MEM0827-CWP-348 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-348 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [83 empty] | 0t | 1t | 0t
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [71 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [71 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [65 empty] | 1t | 2t | 2t | 2t | 2t | 0t
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [65 empty] | 1t | 2t | 2t | 2t | 2t | 0t
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [85 empty] | 0t | 0t | 0t | 0t | 0t | 0t
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [85 empty] | 0t | 0t | 0t | 0t | 0t | 0t
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [71 empty] | 13t | 13t | 13t | 13t | 13t | 13t | 13t | 13t | 13t | 13t | 10t
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [71 empty] | 13t | 13t | 13t | 13t | 13t | 13t | 13t | 13t | 13t | 13t | 10t
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [81 empty] | 1t | 5t | 5t | 4t
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [81 empty] | 1t | 5t | 5t | 4t
EEE1049-CWP-375 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 1t | 0t
EEE1049-CWP-375 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
EEE1049-CWP-375 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 1t | 0t
MEM1214-CWP-400 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [78 empty] | 8t | 9t
MEM1214-CWP-400 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM1214-CWP-400 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [78 empty] | 8t | 9t
MEM0623-CWP-410 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [83 empty] | 0t | 1t | 0t
MEM0623-CWP-410 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0623-CWP-410 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [83 empty] | 0t | 1t | 0t
TTU0622-CWP-019 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [86 empty] | 1t
TTU0622-CWP-019 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
TTU0622-CWP-019 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [86 empty] | 1t
MEM0622-CWP-003 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [86 empty] | 3t | 8t | 5t
MEM0622-CWP-003 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0622-CWP-003 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [86 empty] | 3t | 8t | 5t
MEM0821-CWP-579 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [81 empty] | 0t | 1t
MEM0821-CWP-579 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-579 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [81 empty] | 0t | 1t
MEM0821-CWP-580 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 1t | 0t
MEM0821-CWP-580 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-580 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 1t | 0t
MEM0821-CWP-581 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 13t
MEM0821-CWP-581 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-581 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 13t
MEM0821-CWP-582 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | [82 empty] | 9t | 4t
MEM0821-CWP-582 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Actual Units
MEM0821-CWP-582 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | [82 empty] | 9t | 4t
MEM0817-CWP-031 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [84 empty] | 1un
MEM0817-CWP-031 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM0817-CWP-031 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [84 empty] | 1un
MSD0817-CWP-033 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [73 empty] | 1un
MSD0817-CWP-033 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MSD0817-CWP-033 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [73 empty] | 1un
MEM0822-CWP-174 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [84 empty] | 0un | 2un
MEM0822-CWP-174 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM0822-CWP-174 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [84 empty] | 0un | 2un
MEM0822-CWP-175 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [84 empty] | 1un | 3un
MEM0822-CWP-175 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM0822-CWP-175 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [84 empty] | 1un | 3un
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [92 empty] | 108un | 289un | 289un | 289un | 289un | 289un | 181un
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [92 empty] | 108un | 289un | 289un | 289un | 289un | 289un | 181un
MSD0827-CWP-367 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [57 empty] | 4un | 6un
MSD0827-CWP-367 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MSD0827-CWP-367 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [57 empty] | 4un | 6un
MSD0827-CWP-323 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [73 empty] | 1un
MSD0827-CWP-323 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MSD0827-CWP-323 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [73 empty] | 1un
MEM0827-CWP-335 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [94 empty] | 1un
MEM0827-CWP-335 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM0827-CWP-335 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [94 empty] | 1un
MSD1214-CWP-374 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [81 empty] | 1un | 0un
MSD1214-CWP-374 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MSD1214-CWP-374 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [81 empty] | 1un | 0un
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [53 empty] | 1un | 1un | 1un | 1un | 1un | 1un | 1un | 1un | 1un | 1un | 1un |  |  | 1un | 0un
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [53 empty] | 1un | 1un | 1un | 1un | 1un | 1un | 1un | 1un | 1un | 1un | 1un |  |  | 1un | 0un
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [53 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un |  |  | 0un | 0un
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [53 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un |  |  | 0un | 0un
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [53 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un |  |  | 0un | 0un
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [53 empty] | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un | 0un |  |  | 0un | 0un
MEM1214-CWP-398 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [82 empty] | 1un | 2un
MEM1214-CWP-398 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-398 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [82 empty] | 1un | 2un
MEM1214-CWP-512 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [89 empty] | 1un | 1un
MEM1214-CWP-512 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-512 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [89 empty] | 1un | 1un
MEM1214-CWP-513 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [90 empty] | 1un | 0un
MEM1214-CWP-513 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-513 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [90 empty] | 1un | 0un
MEM1214-CWP-514 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [91 empty] | 0un | 1un
MEM1214-CWP-514 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-514 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [91 empty] | 0un | 1un
MEM1214-CWP-515 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [92 empty] | 1un
MEM1214-CWP-515 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-515 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [92 empty] | 1un
MEM1214-CWP-516 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [93 empty] | 1un
MEM1214-CWP-516 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-516 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [93 empty] | 1un
MEM1214-CWP-517 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [93 empty] | 0un | 1un
MEM1214-CWP-517 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-517 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [93 empty] | 0un | 1un
MEM1214-CWP-518 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [94 empty] | 1un | 0un
MEM1214-CWP-518 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-518 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [94 empty] | 1un | 0un
MEM1214-CWP-519 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [95 empty] | 1un
MEM1214-CWP-519 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-519 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [95 empty] | 1un
MEM1214-CWP-520 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [80 empty] | 1un
MEM1214-CWP-520 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-520 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [80 empty] | 1un
MEM1214-CWP-521 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [80 empty] | 1un | 0un
MEM1214-CWP-521 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-521 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [80 empty] | 1un | 0un
MEM1214-CWP-522 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [81 empty] | 1un
MEM1214-CWP-522 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-522 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [81 empty] | 1un
MEM1214-CWP-523 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [81 empty] | 1un | 0un
MEM1214-CWP-523 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-523 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [81 empty] | 1un | 0un
MEM1214-CWP-524 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [87 empty] | 1un | 0un
MEM1214-CWP-524 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-524 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [87 empty] | 1un | 0un
MEM1214-CWP-525 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | [88 empty] | 1un | 0un
MEM1214-CWP-525 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Actual Units
MEM1214-CWP-525 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | [88 empty] | 1un | 0un
MCD0817-CWP-030 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units
MCD0817-CWP-030 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0817-CWP-030 | CALDEIRARIA - PLATEWORK | Material | At Completion Units
MEM0817-CWP-498 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [93 empty] | 0t | 2t
MEM0817-CWP-498 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MEM0817-CWP-498 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [93 empty] | 0t | 2t
MEM0817-CWP-039 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units
MEM0817-CWP-039 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MEM0817-CWP-039 | CALDEIRARIA - PLATEWORK | Material | At Completion Units
MCD0817-CWP-044 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units
MCD0817-CWP-044 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0817-CWP-044 | CALDEIRARIA - PLATEWORK | Material | At Completion Units
MEM0821-CWP-076 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units
MEM0821-CWP-076 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MEM0821-CWP-076 | CALDEIRARIA - PLATEWORK | Material | At Completion Units
MEM0821-CWP-077 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units
MEM0821-CWP-077 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MEM0821-CWP-077 | CALDEIRARIA - PLATEWORK | Material | At Completion Units
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [93 empty] | 5t | 14t | 14t | 14t | 11t
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [93 empty] | 5t | 14t | 14t | 14t | 11t
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [90 empty] | 1t | 1t | 1t | 1t | 0t
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [90 empty] | 1t | 1t | 1t | 1t | 0t
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [71 empty] | 0t | 0t | 0t | 0t | 0t | 0t | 0t | 0t | 0t | 0t | 0t
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [71 empty] | 0t | 0t | 0t | 0t | 0t | 0t | 0t | 0t | 0t | 0t | 0t
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [77 empty] | 4t | 4t | 3t | 4t | 1t
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | Actual Units
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [77 empty] | 4t | 4t | 3t | 4t | 1t
TTU0822-CWP-205 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [53 empty] | 67t | 53t
TTU0822-CWP-205 | CALDEIRARIA - PLATEWORK | Material | Actual Units
TTU0822-CWP-205 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [53 empty] | 67t | 53t
MCD0822-CWP-242 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [67 empty] | 3t | 2t
MCD0822-CWP-242 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0822-CWP-242 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [67 empty] | 3t | 2t
MRF0822-CWP-243 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [69 empty] | 1t | 1t | 0t
MRF0822-CWP-243 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MRF0822-CWP-243 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [69 empty] | 1t | 1t | 0t
MCD0822-CWP-244 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [69 empty] | 2t | 3t
MCD0822-CWP-244 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0822-CWP-244 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [69 empty] | 2t | 3t
MRF0822-CWP-245 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [71 empty] | 0t | 1t | 0t
MRF0822-CWP-245 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MRF0822-CWP-245 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [71 empty] | 0t | 1t | 0t
MCD0823-CWP-264 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [78 empty] | 4t | 4t | 1t
MCD0823-CWP-264 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0823-CWP-264 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [78 empty] | 4t | 4t | 1t
MCD0824-CWP-502 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [80 empty] | 0t | 4t | 3t
MCD0824-CWP-502 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0824-CWP-502 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [80 empty] | 0t | 4t | 3t
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [84 empty] | 11t | 47t | 47t | 36t
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [84 empty] | 11t | 47t | 47t | 36t
MCD0827-CWP-320 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units
MCD0827-CWP-320 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0827-CWP-320 | CALDEIRARIA - PLATEWORK | Material | At Completion Units
MEM0827-CWP-329 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units
MEM0827-CWP-329 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MEM0827-CWP-329 | CALDEIRARIA - PLATEWORK | Material | At Completion Units
MCD0827-CWP-334 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units
MCD0827-CWP-334 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0827-CWP-334 | CALDEIRARIA - PLATEWORK | Material | At Completion Units
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [67 empty] | 9t | 11t | 11t | 11t | 2t
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [67 empty] | 9t | 11t | 11t | 11t | 2t
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [71 empty] | 0t | 0t | 0t | 0t
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [71 empty] | 0t | 0t | 0t | 0t
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [77 empty] | 1t | 1t | 1t | 1t
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [77 empty] | 1t | 1t | 1t | 1t
MEM0830-CWP-503 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [67 empty] | 37t | 92t | 37t
MEM0830-CWP-503 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MEM0830-CWP-503 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [67 empty] | 37t | 92t | 37t
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [71 empty] | 0t | 0t | 0t | 0t
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | Actual Units
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [71 empty] | 0t | 0t | 0t | 0t
MCD0622-CWP-497 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | [82 empty] | 8t | 96t
MCD0622-CWP-497 | CALDEIRARIA - PLATEWORK | Material | Actual Units
MCD0622-CWP-497 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | [82 empty] | 8t | 96t
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [56 empty] | 4t | 17t | 17t | 17t | 17t | 17t | 11t
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [56 empty] | 4t | 17t | 17t | 17t | 17t | 17t | 11t
MSD0822-CWP-508 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [59 empty] | 1t | 1t
MSD0822-CWP-508 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-508 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [59 empty] | 1t | 1t
MSD0822-CWP-509 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [59 empty] | 22t | 22t
MSD0822-CWP-509 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-509 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [59 empty] | 22t | 22t
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [57 empty] | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 7t
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [57 empty] | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 12t | 7t
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [27 empty] | 2t | 3t | 3t | 3t | 3t | 3t | 3t | 1t
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [27 empty] | 2t | 3t | 3t | 3t | 3t | 3t | 3t | 1t
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [45 empty] | 3t | 3t | 3t | 1t | bar: 2023-07-09 to 2023-07-30
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [45 empty] | 3t | 3t | 3t | 1t | bar: 2023-07-09 to 2023-07-30
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [27 empty] | 2t | 3t | 3t | 3t | 3t | 3t | 3t | 1t
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [27 empty] | 2t | 3t | 3t | 3t | 3t | 3t | 3t | 1t
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [45 empty] | 3t | 3t | 3t | 1t | bar: 2023-07-09 to 2023-07-30
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [45 empty] | 3t | 3t | 3t | 1t | bar: 2023-07-09 to 2023-07-30
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [27 empty] | 2t | 3t | 3t | 3t | 3t | 3t | 3t | 1t
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [27 empty] | 2t | 3t | 3t | 3t | 3t | 3t | 3t | 1t
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [45 empty] | 3t | 3t | 3t | 1t | bar: 2023-07-09 to 2023-07-30
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [45 empty] | 3t | 3t | 3t | 1t | bar: 2023-07-09 to 2023-07-30
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [34 empty] | 2t | 3t | bar: 2023-06-04 to 2023-07-09
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [81 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 0t
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [81 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 0t
MSD0827-CWP-492 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 1t | 0t
MSD0827-CWP-492 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0827-CWP-492 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 1t | 0t
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 0t
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 0t
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [78 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [78 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 0t
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 1t | 0t
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 260Meter | 260Meter | 260Meter | 260Meter | 260Meter
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 260Meter | 260Meter | 260Meter | 260Meter | 260Meter
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [59 empty] | 92Meter | 3683Meter | 3683Meter | 3591Meter
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [59 empty] | 92Meter | 3683Meter | 3683Meter | 3591Meter
ESD0800-CWP-483 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [60 empty] | 23750Meter
ESD0800-CWP-483 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD0800-CWP-483 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [60 empty] | 23750Meter
ESD0820-CWP-057 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units
ESD0820-CWP-057 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD0820-CWP-057 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 3363Meter | 3363Meter | 3363Meter | 3363Meter | 3363Meter | 3363Meter | 3363Meter | 3363Meter
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 3363Meter | 3363Meter | 3363Meter | 3363Meter | 3363Meter | 3363Meter | 3363Meter | 3363Meter
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 13Meter | 13Meter | 13Meter | 13Meter | 13Meter
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 13Meter | 13Meter | 13Meter | 13Meter | 13Meter
ESD1062-CWP-486 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 333Meter | 333Meter | 333Meter
ESD1062-CWP-486 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD1062-CWP-486 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 333Meter | 333Meter | 333Meter
ESD1214-CWP-487 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 28Meter | 28Meter
ESD1214-CWP-487 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD1214-CWP-487 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 28Meter | 28Meter
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [59 empty] | 22Meter | 877Meter | 877Meter | 855Meter
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [59 empty] | 22Meter | 877Meter | 877Meter | 855Meter
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 848Meter | 848Meter | 848Meter | 509Meter
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 848Meter | 848Meter | 848Meter | 509Meter
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [53 empty] | 63Meter | 63Meter | 63Meter | 63Meter | 63Meter
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [53 empty] | 63Meter | 63Meter | 63Meter | 63Meter | 63Meter
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [59 empty] | 10Meter | 400Meter | 400Meter | 390Meter
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [59 empty] | 10Meter | 400Meter | 400Meter | 390Meter
ESD0600-CWP-480 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | [62 empty] | 60Meter | 2340Meter
ESD0600-CWP-480 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Actual Units
ESD0600-CWP-480 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | [62 empty] | 60Meter | 2340Meter
ESD0822-CWP-493 | DESMONTAGEM ELETRICA | Material | Budgeted Units | [75 empty] | 2unid | 3unid | 1unid
ESD0822-CWP-493 | DESMONTAGEM ELETRICA | Material | Actual Units
ESD0822-CWP-493 | DESMONTAGEM ELETRICA | Material | At Completion Units | [75 empty] | 2unid | 3unid | 1unid
JSD0822-CWP-494 | DESMONTAGEM ELETRICA | Material | Budgeted Units | [53 empty] | 23unid | 23unid
JSD0822-CWP-494 | DESMONTAGEM ELETRICA | Material | Actual Units
JSD0822-CWP-494 | DESMONTAGEM ELETRICA | Material | At Completion Units | [53 empty] | 23unid | 23unid
MSD0822-CWP-203 | DESMONTAGEM ELETRICA | Material | Budgeted Units | [57 empty] | 19unid | 19unid | 8unid
MSD0822-CWP-203 | DESMONTAGEM ELETRICA | Material | Actual Units
MSD0822-CWP-203 | DESMONTAGEM ELETRICA | Material | At Completion Units | [57 empty] | 19unid | 19unid | 8unid
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | Budgeted Units | [92 empty] | 0unid | 1unid | 1unid | 1unid | 1unid | 0unid
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | Actual Units
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | At Completion Units | [92 empty] | 0unid | 1unid | 1unid | 1unid | 1unid | 0unid
ESD1042-CWP-511 | DESMONTAGEM ELETRICA | Material | Budgeted Units | [53 empty] | 5unid | 1unid
ESD1042-CWP-511 | DESMONTAGEM ELETRICA | Material | Actual Units
ESD1042-CWP-511 | DESMONTAGEM ELETRICA | Material | At Completion Units | [53 empty] | 5unid | 1unid
ESD1048-CWP-470 | DESMONTAGEM ELETRICA | Material | Budgeted Units | [73 empty] | 3unid | 0unid
ESD1048-CWP-470 | DESMONTAGEM ELETRICA | Material | Actual Units
ESD1048-CWP-470 | DESMONTAGEM ELETRICA | Material | At Completion Units | [73 empty] | 3unid | 0unid
ESD1049-CWP-372 | DESMONTAGEM ELETRICA | Material | Budgeted Units | [82 empty] | 2unid | 1unid
ESD1049-CWP-372 | DESMONTAGEM ELETRICA | Material | Actual Units
ESD1049-CWP-372 | DESMONTAGEM ELETRICA | Material | At Completion Units | [82 empty] | 2unid | 1unid
EEE1062-CWP-382 | DESMONTAGEM ELETRICA | Material | Budgeted Units | [59 empty] | 0unid | 1unid
EEE1062-CWP-382 | DESMONTAGEM ELETRICA | Material | Actual Units
EEE1062-CWP-382 | DESMONTAGEM ELETRICA | Material | At Completion Units | [59 empty] | 0unid | 1unid
MMR0817-CWP-046 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [94 empty] | 6tons | 3tons
MMR0817-CWP-046 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0817-CWP-046 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [94 empty] | 6tons | 3tons
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [75 empty] | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 3tons
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [75 empty] | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 6tons | 3tons
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [74 empty] | 43tons | 201tons | 201tons | 201tons | 201tons | 134tons | 168tons | 168tons | 52tons
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [74 empty] | 43tons | 201tons | 201tons | 201tons | 201tons | 134tons | 168tons | 168tons | 52tons
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [77 empty] | 56tons | 78tons | 52tons | 65tons | 65tons | 65tons | 65tons | 65tons | 20tons
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [77 empty] | 56tons | 78tons | 52tons | 65tons | 65tons | 65tons | 65tons | 65tons | 20tons
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [82 empty] | 12tons | 65tons | 65tons | 65tons | 65tons | 65tons | 65tons | 65tons | 63tons
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [82 empty] | 12tons | 65tons | 65tons | 65tons | 65tons | 65tons | 65tons | 65tons | 63tons
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [90 empty] | 2tons | 84tons | 84tons | 54tons
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [90 empty] | 2tons | 84tons | 84tons | 54tons
MMR0822-CWP-147 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [92 empty] | 11tons | 12tons | 10tons
MMR0822-CWP-147 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0822-CWP-147 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [92 empty] | 11tons | 12tons | 10tons
MMR0822-CWP-148 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [92 empty] | 11tons | 12tons | 10tons
MMR0822-CWP-148 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0822-CWP-148 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [92 empty] | 11tons | 12tons | 10tons
MMR0822-CWP-149 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [92 empty] | 11tons | 12tons | 10tons
MMR0822-CWP-149 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0822-CWP-149 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [92 empty] | 11tons | 12tons | 10tons
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [89 empty] | 5tons | 9tons | 9tons | 9tons | 9tons | 4tons
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [89 empty] | 5tons | 9tons | 9tons | 9tons | 9tons | 4tons
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [83 empty] | 0tons | 3tons | 3tons | 3tons | 3tons | 2tons
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [83 empty] | 0tons | 3tons | 3tons | 3tons | 3tons | 2tons
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [83 empty] | 1tons | 18tons | 18tons | 18tons | 18tons | 12tons
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [83 empty] | 1tons | 18tons | 18tons | 18tons | 18tons | 12tons
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [74 empty] | 0tons | 9tons | 9tons | 9tons | 9tons
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [74 empty] | 0tons | 9tons | 9tons | 9tons | 9tons
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [76 empty] | 1tons | 2tons | 2tons | 2tons | 1tons
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [76 empty] | 1tons | 2tons | 2tons | 2tons | 1tons
MMR0827-CWP-336 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [97 empty] | 9tons
MMR0827-CWP-336 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0827-CWP-336 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [97 empty] | 9tons
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [85 empty] | 1tons | 3tons | 3tons | 3tons | 3tons | 3tons | 3tons | 2tons
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [85 empty] | 1tons | 3tons | 3tons | 3tons | 3tons | 3tons | 3tons | 2tons
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | [85 empty] | 3tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 3tons
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Actual Units
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | [85 empty] | 3tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 5tons | 3tons
MSD0822-CWP-200 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | [57 empty] | 4t | 4t
MSD0822-CWP-200 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0822-CWP-200 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | [57 empty] | 4t | 4t
MSD0822-CWP-230 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | [57 empty] | 4t | 3t
MSD0822-CWP-230 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0822-CWP-230 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | [57 empty] | 4t | 3t
MSD0822-CWP-238 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units
MSD0822-CWP-238 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0822-CWP-238 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units
MSD0822-CWP-241 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units
MSD0822-CWP-241 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0822-CWP-241 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units
MSD0827-CWP-302 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units
MSD0827-CWP-302 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0827-CWP-302 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units
MSD0827-CWP-305 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units
MSD0827-CWP-305 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0827-CWP-305 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | [53 empty] | 1t | 1t | 1t | 1t | 1t | 1t
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | [53 empty] | 1t | 1t | 1t | 1t | 1t | 1t
MSD0827-CWP-353 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units
MSD0827-CWP-353 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0827-CWP-353 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units
MSD0827-CWP-354 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units
MSD0827-CWP-354 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0827-CWP-354 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | [77 empty] | 2t | 2t | 2t | 2t | 2t | 2t
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | [77 empty] | 2t | 2t | 2t | 2t | 2t | 2t
MSD0622-CWP-005 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | [53 empty] | 11t | 14t | 3t
MSD0622-CWP-005 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Actual Units
MSD0622-CWP-005 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | [53 empty] | 11t | 14t | 3t
MSD0820-CWP-055 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units
MSD0820-CWP-055 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Actual Units
MSD0820-CWP-055 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | [59 empty] | 4t | 19t | 19t | 15t
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Actual Units
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | [59 empty] | 4t | 19t | 19t | 15t
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | [48 empty] | 56t | 63t | 63t | 63t | 63t | 63t | 63t | 63t | 63t | 63t | 50t
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Actual Units
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | [48 empty] | 56t | 63t | 63t | 63t | 63t | 63t | 63t | 63t | 63t | 63t | 50t
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | [53 empty] | 5t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 1t
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Actual Units
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | [53 empty] | 5t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 6t | 1t
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | [57 empty] | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 4t
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Actual Units
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | [57 empty] | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 8t | 4t
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | [70 empty] | 0t | 2t | 2t | 2t | 2t | 3t | 3t | 1t
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Actual Units
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | [70 empty] | 0t | 2t | 2t | 2t | 2t | 3t | 3t | 1t
CEC0800-CWP-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
CEC0800-CWP-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0800-CWP-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 27741h | 27741h | 27741h | 27741h | 27741h
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 27741h | 27741h | 27741h | 27741h | 27741h
ESD0800-CWP-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
ESD0800-CWP-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0800-CWP-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ESD0800-CWP-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [60 empty] | 2534104h
ESD0800-CWP-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0800-CWP-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [60 empty] | 2534104h
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 26715h | 26715h | 26715h | 26715h | 26715h | 26715h
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 26715h | 26715h | 26715h | 26715h | 26715h | 26715h
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 21372h; 2023-07-09: 26715h; 2023-07-16: 26715h; 2023-07-23: 26715h; 2023-07-30: 26715h | 26715h | 5343h
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 21372h; 2023-07-09: 26715h; 2023-07-16: 26715h; 2023-07-23: 26715h; 2023-07-30: 26715h | 26715h | 5343h
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 21372h; 2023-07-09: 26715h; 2023-07-16: 26715h; 2023-07-23: 26715h; 2023-07-30: 26715h | 26715h | 5343h
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 21372h; 2023-07-09: 26715h; 2023-07-16: 26715h; 2023-07-23: 26715h; 2023-07-30: 26715h | 26715h | 5343h
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 21372h; 2023-07-09: 26715h; 2023-07-16: 26715h; 2023-07-23: 26715h; 2023-07-30: 26715h | 26715h | 5343h
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 21372h; 2023-07-09: 26715h; 2023-07-16: 26715h; 2023-07-23: 26715h; 2023-07-30: 26715h | 26715h | 5343h
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 2387h | 2387h | 2387h | 2387h
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 2387h | 2387h | 2387h | 2387h
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 637h | 2228h | 2228h | 2228h | 2228h
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 637h | 2228h | 2228h | 2228h | 2228h
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 1157h
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 1157h
RIN0800-CWP-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
RIN0800-CWP-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
RIN0800-CWP-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 9016h | 40073h | 40073h | 40073h | 31056h
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 9016h | 40073h | 40073h | 40073h | 31056h
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 40073h | 40073h | 40073h | 40073h
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 40073h | 40073h | 40073h | 40073h
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 40073h | 40073h | 40073h | 40073h
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 40073h | 40073h | 40073h | 40073h
KMT0800-CWP-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
KMT0800-CWP-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0800-CWP-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EEE0800-CWP-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EEE0800-CWP-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0800-CWP-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EBD0800-CWP-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EBD0800-CWP-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0800-CWP-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 63319h | 158297h | 158297h | 158297h | 158297h | 158297h | 158297h | 158297h | 158297h | 94978h
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 63319h | 158297h | 158297h | 158297h | 158297h | 158297h | 158297h | 158297h | 158297h | 94978h
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 9016h | 40073h | 40073h | 40073h | 31056h
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 9016h | 40073h | 40073h | 40073h | 31056h
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 2938h | 13056h | 13056h | 13056h | 10118h
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 2938h | 13056h | 13056h | 13056h | 10118h
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 5440h | 12186h | 12186h | 12186h | 10227h
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 5440h | 12186h | 12186h | 12186h | 10227h
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 7121h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 30860h
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 7121h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 31651h | 30860h
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 2609h | 11596h | 11596h | 11596h | 8987h
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 2609h | 11596h | 11596h | 11596h | 8987h
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 6378h | 10823h | 10823h | 10823h | 7537h
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 6378h | 10823h | 10823h | 10823h | 7537h
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 10436h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 35947h
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 10436h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 35947h
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 20022h | 20892h | 20892h | 7835h
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 20022h | 20892h | 20892h | 7835h
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 22105h | 98243h | 98243h | 98243h | 98243h | 98243h | 76139h
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 22105h | 98243h | 98243h | 98243h | 98243h | 98243h | 76139h
ELU0817-CWP-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [98 empty] | 191856h
ELU0817-CWP-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0817-CWP-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [98 empty] | 191856h
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MMR0817-CWP-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 139672h
MMR0817-CWP-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0817-CWP-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 139672h
MEM0817-CWP-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 23280h
MEM0817-CWP-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 23280h
CPI0817-CWP-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 10864h
CPI0817-CWP-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CPI0817-CWP-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 10864h
MEM0817-CWP-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 5432h
MEM0817-CWP-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 5432h
MEM0817-CWP-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 139672h
MEM0817-CWP-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 139672h
SSD0817-CWP-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 23280h
SSD0817-CWP-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SSD0817-CWP-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 23280h
SSD0817-CWP-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SSD0817-CWP-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SSD0817-CWP-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SES0817-CWP-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 7760h
SES0817-CWP-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-CWP-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 7760h
MCD0817-CWP-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MCD0817-CWP-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-CWP-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0817-CWP-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 19400h
MEM0817-CWP-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 19400h
STP0817-CWP-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 13968h
STP0817-CWP-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0817-CWP-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 13968h
MSD0817-CWP-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 9700h | 9700h
MSD0817-CWP-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0817-CWP-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 9700h | 9700h
MEM0817-CWP-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 4656h
MEM0817-CWP-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 4656h
MEM0817-CWP-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MEM0817-CWP-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MMR0817-CWP-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 23280h
MMR0817-CWP-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0817-CWP-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 23280h
SES0817-CWP-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 46560h
SES0817-CWP-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-CWP-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 46560h
MEM0817-CWP-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MEM0817-CWP-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 11905h; 2023-06-25: 26668h; 2023-07-02: 26668h; 2023-07-09: 26668h; 2023-07-16: 22382h
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 11905h; 2023-06-25: 26668h; 2023-07-02: 26668h; 2023-07-09: 26668h; 2023-07-16: 22382h
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 37879h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 2023-06-04: 60606h; 2023-06-11: 60606h; 2023-06-18: 34849h
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 37879h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 60606h | 2023-06-04: 60606h; 2023-06-11: 60606h; 2023-06-18: 34849h
MEM0817-CWP-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MEM0817-CWP-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 11909h | 19055h | 19055h | 19055h | 19055h | 19055h | 7145h
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 11909h | 19055h | 19055h | 19055h | 19055h | 19055h | 7145h
MEM0817-CWP-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 2328h | 2328h
MEM0817-CWP-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 2328h | 2328h
MMR0817-CWP-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 23280h | 11640h
MMR0817-CWP-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0817-CWP-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 23280h | 11640h
MEM0817-CWP-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 39576h
MEM0817-CWP-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 39576h
SES0817-CWP-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SES0817-CWP-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-CWP-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SES0817-CWP-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 3880h | 3880h
SES0817-CWP-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-CWP-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 3880h | 3880h
SES0817-CWP-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [97 empty] | 37248h
SES0817-CWP-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-CWP-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [97 empty] | 37248h
MEM0817-CWP-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MEM0817-CWP-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MCD0817-CWP-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 59360h
MCD0817-CWP-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0817-CWP-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 59360h
MEM0817-CWP-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 3880h
MEM0817-CWP-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-CWP-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 3880h
EEL0817-CWP-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [97 empty] | 145496h
EEL0817-CWP-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEL0817-CWP-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [97 empty] | 145496h
SES0817-CWP-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [97 empty] | 8149h | 4075h
SES0817-CWP-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0817-CWP-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [97 empty] | 8149h | 4075h
JIL0817-CWP-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [99 empty] | 46560h
JIL0817-CWP-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0817-CWP-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [99 empty] | 46560h
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SWP-007-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 21910h | 6668h
SWP-007-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-007-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 21910h | 6668h
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 23710h | 23710h | 23710h | 23710h | 23710h | 23710h | 23710h | 23710h | 23710h
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 23710h | 23710h | 23710h | 23710h | 23710h | 23710h | 23710h | 23710h | 23710h
B41873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B41853 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41853 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41853 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B41843 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41843 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41843 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B41863 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41863 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41863 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B41903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 37220h | 93051h | 93051h | 93051h | 93051h | 93051h | 93051h | 93051h | 93051h | 93051h | 55831h
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 37220h | 93051h | 93051h | 93051h | 93051h | 93051h | 93051h | 93051h | 93051h | 93051h | 55831h
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 32058h; 2023-07-09: 40073h; 2023-07-16: 40073h; 2023-07-23: 40073h; 2023-07-30: 8015h
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 32058h; 2023-07-09: 40073h; 2023-07-16: 40073h; 2023-07-23: 40073h; 2023-07-30: 8015h
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 40073h | 40073h | 40073h | 40073h
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 40073h | 40073h | 40073h | 40073h
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 26435h; 2023-07-09: 33044h; 2023-07-16: 33044h; 2023-07-23: 33044h; 2023-07-30: 6609h
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 26435h; 2023-07-09: 33044h; 2023-07-16: 33044h; 2023-07-23: 33044h; 2023-07-30: 6609h
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 40073h | 40073h | 40073h | 40073h
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 40073h | 40073h | 40073h | 40073h
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 5463h | 5463h |  |  | 4370h | 5463h | 5463h | 5463h | 5463h | 5463h | 5463h | 5463h | 5463h | 5463h | 3824h
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 5463h | 5463h |  |  | 4370h | 5463h | 5463h | 5463h | 5463h | 5463h | 5463h | 5463h | 5463h | 5463h | 3824h
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 468h | 1226h | 1226h | 817h | 1022h | 1022h | 1022h | 1022h | 519h
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 468h | 1226h | 1226h | 817h | 1022h | 1022h | 1022h | 1022h | 519h
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 165h | 6583h | 6583h | 6583h | 6583h | 6583h | 6418h
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 165h | 6583h | 6583h | 6583h | 6583h | 6583h | 6418h
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 143h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 2710h
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 143h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 5706h | 2710h
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 24240h; 2023-07-09: 30300h; 2023-07-16: 30300h; 2023-07-23: 30300h; 2023-07-30: 6060h
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 24240h; 2023-07-09: 30300h; 2023-07-16: 30300h; 2023-07-23: 30300h; 2023-07-30: 6060h
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 40073h | 40073h | 40073h | 40073h
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 40073h | 40073h | 40073h | 40073h
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 824h | 824h | 824h | 824h
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 824h | 824h | 824h | 824h
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 879h | 1538h | 1538h | 1538h | 1099h
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 879h | 1538h | 1538h | 1538h | 1099h
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 743h
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 3714h | 743h
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 40073h | 40073h | 40073h | 40073h
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 40073h | 40073h | 40073h | 40073h
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 40073h | 40073h | 40073h | 40073h
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 40073h | 40073h | 40073h | 40073h
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 33060h; 2023-07-09: 40073h; 2023-07-16: 40073h; 2023-07-23: 40073h; 2023-07-30: 7013h
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 33060h; 2023-07-09: 40073h; 2023-07-16: 40073h; 2023-07-23: 40073h; 2023-07-30: 7013h
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 27690h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 5874h
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 27690h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 5874h
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 11321h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 45285h
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 11321h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 56606h | 45285h
ESD0822-CWP-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 7275h | 11640h | 4365h
ESD0822-CWP-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0822-CWP-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 7275h | 11640h | 4365h
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 21372h; 2023-07-09: 26715h; 2023-07-16: 26715h; 2023-07-23: 26715h; 2023-07-30: 26715h | 26715h | 5343h
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 21372h; 2023-07-09: 26715h; 2023-07-16: 26715h; 2023-07-23: 26715h; 2023-07-30: 26715h | 26715h | 5343h
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 14248h | 17810h | 17810h | 17810h | 17810h | 17810h | 17810h | 17810h | 17810h | 3562h
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 14248h | 17810h | 17810h | 17810h | 17810h | 17810h | 17810h | 17810h | 17810h | 3562h
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
JIL0800-CWP-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 31659h | 158296h | 126637h
JIL0800-CWP-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0800-CWP-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 31659h | 158296h | 126637h
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 37828h | 94571h | 94571h | 94571h | 94571h | 94571h | 56742h
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 37828h | 94571h | 94571h | 94571h | 94571h | 94571h | 56742h
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 25046h | 40073h | 40073h | 40073h | 15027h
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 25046h | 40073h | 40073h | 40073h | 15027h
SWP-003-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 20540h | 50904h
SWP-003-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-003-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 20540h | 50904h
SWP-004-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 14765h | 13813h
SWP-004-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-004-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 14765h | 13813h
SWP-005-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 28578h
SWP-005-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-005-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 28578h
JIL0820-CWP-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 11873h | 27936h | 16063h
JIL0820-CWP-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0820-CWP-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 11873h | 27936h | 16063h
SWP-006-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 21910h | 6668h
SWP-006-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-006-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 21910h | 6668h
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 88671h | 88671h | 88671h | 88671h
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 88671h | 88671h | 88671h | 88671h
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 87084h | 87084h | 87084h | 87084h
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 87084h | 87084h | 87084h | 87084h
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 58056h | 81278h | 81278h | 81278h | 46445h
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 58056h | 81278h | 81278h | 81278h | 46445h
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 15834h
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 79168h | 15834h
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 88671h | 88671h | 88671h | 88671h
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 88671h | 88671h | 88671h | 88671h
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 19724h; 2023-07-09: 19724h; 2023-07-16: 19724h; 2023-07-23: 19724h; 2023-07-30: 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 19724h; 2023-07-09: 19724h; 2023-07-16: 19724h; 2023-07-23: 19724h; 2023-07-30: 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 39449h | 55228h | 55228h | 55228h | 31559h
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 39449h | 55228h | 55228h | 55228h | 31559h
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 47816h; 2023-07-09: 47816h; 2023-07-16: 47816h; 2023-07-23: 47816h; 2023-07-30: 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 28690h
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 47816h; 2023-07-09: 47816h; 2023-07-16: 47816h; 2023-07-23: 47816h; 2023-07-30: 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 28690h
MEM0821-CWP-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 27644h | 184293h | 64503h
MEM0821-CWP-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 27644h | 184293h | 64503h
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 39478h | 39478h | 39478h | 39478h
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 39478h | 39478h | 39478h | 39478h
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h | 307h
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 1319h | 3104h | 3104h | 3104h | 3104h | 3104h | 1785h
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 1319h | 3104h | 3104h | 3104h | 3104h | 3104h | 1785h
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 55419h | 88671h | 88671h | 88671h | 33251h
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 55419h | 88671h | 88671h | 88671h | 33251h
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 2217h | 88671h | 88671h | 88671h | 86454h
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 2217h | 88671h | 88671h | 88671h | 86454h
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 2217h | 88671h | 88671h | 88671h | 86454h
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 2217h | 88671h | 88671h | 88671h | 86454h
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 55419h; 2023-07-30: 88671h | 88671h | 88671h | 33251h
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 55419h; 2023-07-30: 88671h | 88671h | 88671h | 33251h
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 2217h | 88671h | 88671h | 88671h | 86454h
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 2217h | 88671h | 88671h | 88671h | 86454h
MEM0821-CWP-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 128912h | 329136h | 35656h
MEM0821-CWP-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 128912h | 329136h | 35656h
MEM0821-CWP-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 608233h | 1050583h
MEM0821-CWP-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 608233h | 1050583h
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 2165h; 2023-07-09: 3465h; 2023-07-16: 3465h; 2023-07-23: 3465h; 2023-07-30: 1299h
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 2165h; 2023-07-09: 3465h; 2023-07-16: 3465h; 2023-07-23: 3465h; 2023-07-30: 1299h
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 41h; 2023-07-16: 1657h; 2023-07-23: 1657h; 2023-07-30: 1657h | 1657h | 1657h | 1657h | 1616h
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 41h; 2023-07-16: 1657h; 2023-07-23: 1657h; 2023-07-30: 1657h | 1657h | 1657h | 1657h | 1616h
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 5146h | 8233h | 8233h | 8233h | 3087h
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 5146h | 8233h | 8233h | 8233h | 3087h
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [69 empty] | 1235h | 7684h | 7684h | 7684h | 7684h | 961h
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [69 empty] | 1235h | 7684h | 7684h | 7684h | 7684h | 961h
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 7841h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 4705h
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 7841h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 4705h
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 55419h; 2023-07-30: 88671h | 88671h | 88671h | 33251h
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 55419h; 2023-07-30: 88671h | 88671h | 88671h | 33251h
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 4925h | 7881h | 7881h | 7881h | 2955h
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 4925h | 7881h | 7881h | 7881h | 2955h
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 982h | 3234h | 3234h | 3234h | 3176h
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 982h | 3234h | 3234h | 3234h | 3176h
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 403h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 371h
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 403h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 371h
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 4334h | 7355h | 7355h | 7355h | 5122h
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 4334h | 7355h | 7355h | 7355h | 5122h
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 753h | 1686h | 1686h | 1686h | 1415h
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 753h | 1686h | 1686h | 1686h | 1415h
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 4419h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 15222h
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 4419h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 15222h
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 523h | 714h | 714h | 191h
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 523h | 714h | 714h | 191h
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 1883h; 2023-07-09: 3012h; 2023-07-16: 3012h; 2023-07-23: 3012h; 2023-07-30: 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 527h
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 1883h; 2023-07-09: 3012h; 2023-07-16: 3012h; 2023-07-23: 3012h; 2023-07-30: 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 527h
B38263 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38263 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38263 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 5653h | 8586h | 8586h | 8586h | 8586h | 8586h | 8586h | 8586h | 8586h | 8586h | 4365h
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 5653h | 8586h | 8586h | 8586h | 8586h | 8586h | 8586h | 8586h | 8586h | 8586h | 4365h
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 83h; 2023-07-16: 3314h; 2023-07-23: 3314h; 2023-07-30: 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3231h
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 83h; 2023-07-16: 3314h; 2023-07-23: 3314h; 2023-07-30: 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3314h | 3231h
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 88671h | 88671h
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 88671h | 88671h
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 13811h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 13811h
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 13811h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 13811h
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [69 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [69 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 931h | 1164h | 1164h | 1164h | 233h
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 931h | 1164h | 1164h | 1164h | 233h
MEM0821-CWP-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 493704h
MEM0821-CWP-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 493704h
EEE0821-CWP-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 22989h | 34920h | 11931h
EEE0821-CWP-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-CWP-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 22989h | 34920h | 11931h
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h | 161h
TTU0821-CWP-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 19784h
TTU0821-CWP-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-CWP-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 19784h
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 1237h | 2910h | 2910h | 2910h | 1673h
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 1237h | 2910h | 2910h | 2910h | 1673h
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 71943h | 345326h | 345326h | 345326h | 345326h | 345326h | 215829h
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 71943h | 345326h | 345326h | 345326h | 345326h | 345326h | 215829h
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 80h
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 134h | 80h
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 10946h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 13573h
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 10946h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 13573h
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 620h; 2023-07-09: 24810h; 2023-07-16: 24810h; 2023-07-23: 24810h; 2023-07-30: 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24190h
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 620h; 2023-07-09: 24810h; 2023-07-16: 24810h; 2023-07-23: 24810h; 2023-07-30: 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24810h | 24190h
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 55347h | 55812h | 55812h | 55812h | 55812h | 55812h | 55812h | 55812h | 55812h | 55812h | 9767h
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 55347h | 55812h | 55812h | 55812h | 55812h | 55812h | 55812h | 55812h | 55812h | 55812h | 9767h
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 66211h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 14045h
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 66211h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 80256h | 14045h
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 88671h | 88671h | 88671h | 88671h
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 88671h | 88671h | 88671h | 88671h
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 37685h | 88671h | 88671h | 88671h | 50986h
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 37685h | 88671h | 88671h | 88671h | 50986h
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 9836h | 23143h | 23143h | 23143h | 13307h
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 9836h | 23143h | 23143h | 23143h | 13307h
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 12729h | 21600h | 21600h | 21600h | 15043h
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 12729h | 21600h | 21600h | 21600h | 15043h
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 23845h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 43481h
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 23845h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 43481h
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 19951h | 88671h | 88671h | 88671h | 68720h
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 19951h | 88671h | 88671h | 88671h | 68720h
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 2609h | 11596h | 11596h | 11596h | 8987h
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 2609h | 11596h | 11596h | 11596h | 8987h
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 6378h | 10823h | 10823h | 10823h | 7537h
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 6378h | 10823h | 10823h | 10823h | 7537h
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 10436h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 35947h
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 10436h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 35947h
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 405587h | 408996h | 408996h | 408996h | 408996h | 71574h
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 405587h | 408996h | 408996h | 408996h | 408996h | 71574h
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 184334h | 184334h | 184334h | 184334h | 92167h
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 184334h | 184334h | 184334h | 184334h | 92167h
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 111006h | 532829h | 532829h | 421823h
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 111006h | 532829h | 532829h | 421823h
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 149186h | 380901h | 380901h | 406295h | 457082h | 457082h | 53961h
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 149186h | 380901h | 380901h | 406295h | 457082h | 457082h | 53961h
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 5063h | 6984h | 6984h | 6984h | 1921h
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 5063h | 6984h | 6984h | 6984h | 1921h
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 11989h | 11174h | 13968h | 13968h | 13968h | 4772h
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 11989h | 11174h | 13968h | 13968h | 13968h | 4772h
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 11085h
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 22171h | 11085h
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 3972h | 19066h | 19066h | 19066h | 19066h | 15889h |  | 19066h | 18272h
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 3972h | 19066h | 19066h | 19066h | 19066h | 15889h |  | 19066h | 18272h
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 3958h | 9894h | 9894h | 9894h | 5936h
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 3958h | 9894h | 9894h | 9894h | 5936h
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 698511h | 704381h | 704381h | 5870h
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 698511h | 704381h | 704381h | 5870h
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 931h | 1164h | 1164h | 1164h | 233h
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 931h | 1164h | 1164h | 1164h | 233h
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2398h | 2998h | 2998h | 2998h | 2998h | 2998h | 2398h
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2398h | 2998h | 2998h | 2998h | 2998h | 2998h | 2398h
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3146h | 3932h | 3932h | 3932h | 3932h | 3932h | 3932h | 2359h
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3146h | 3932h | 3932h | 3932h | 3932h | 3932h | 3932h | 2359h
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 1154h | 1442h | 1442h | 1442h | 1442h | 1442h | 1442h | 865h
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 1154h | 1442h | 1442h | 1442h | 1442h | 1442h | 1442h | 865h
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 4278h | 5348h | 5348h | 5348h | 5348h | 5348h | 5348h | 3209h
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 4278h | 5348h | 5348h | 5348h | 5348h | 5348h | 5348h | 3209h
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 88671h | 88671h | 88671h | 88671h
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 88671h | 88671h | 88671h | 88671h
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 55419h; 2023-07-30: 88671h | 88671h | 88671h | 33251h
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 55419h; 2023-07-30: 88671h | 88671h | 88671h | 33251h
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 88671h | 88671h
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 88671h | 88671h
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h | 153457h
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 13811h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 13811h
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 13811h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 96678h | 13811h
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h | 334815h
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 73153h | 88671h | 88671h | 88671h | 15517h
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 73153h | 88671h | 88671h | 88671h | 15517h
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 41382h | 50160h | 50160h | 50160h | 8778h
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 41382h | 50160h | 50160h | 50160h | 8778h
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 14212h | 46816h | 46816h | 46816h | 45980h
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 14212h | 46816h | 46816h | 46816h | 45980h
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 5146h | 8233h | 8233h | 8233h | 3087h
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 5146h | 8233h | 8233h | 8233h | 3087h
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [69 empty] | 1235h | 7684h | 7684h | 7684h | 7684h | 961h
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [69 empty] | 1235h | 7684h | 7684h | 7684h | 7684h | 961h
TTU0821-CWP-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 2698h | 17086h
TTU0821-CWP-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-CWP-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 2698h | 17086h
A3770 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3770 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3770 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B37843 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B37843 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B37843 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B37873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B37873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B37873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38863 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38863 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38863 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B37903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B37903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B37903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3860 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3860 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3860 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39773 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39773 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39773 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39783 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39783 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39783 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B37803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B37803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B37803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 78176h | 375243h | 375243h | 297067h
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 78176h | 375243h | 375243h | 297067h
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 7841h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 4705h
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 7841h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 12546h | 4705h
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 88671h | 88671h | 88671h | 88671h
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 88671h | 88671h | 88671h | 88671h
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 88671h | 88671h | 88671h | 88671h
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 88671h | 88671h | 88671h | 88671h
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 70936h; 2023-07-09: 88671h; 2023-07-16: 88671h; 2023-07-23: 88671h; 2023-07-30: 17734h
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 88671h | 88671h | 88671h | 88671h
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 88671h | 88671h | 88671h | 88671h
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 88671h | 88671h | 88671h | 88671h
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 88671h | 88671h | 88671h | 88671h
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 55419h | 88671h | 88671h | 88671h | 33251h
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 12328h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 7397h
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 12328h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 19724h | 7397h
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 24655h | 55228h | 55228h | 55228h | 46352h
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 24655h | 55228h | 55228h | 55228h | 46352h
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 29885h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 46621h
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 29885h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 47816h | 46621h
SWP-008-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 29471h | 53583h | 41974h
SWP-008-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-008-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 29471h | 53583h | 41974h
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 22558h | 31114h | 31114h | 31114h | 9127h
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 22558h | 31114h | 31114h | 31114h | 9127h
SWP-010-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 28578h
SWP-010-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-010-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 28578h
B40113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38853 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38853 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38853 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 31930h; 2023-07-30: 51089h | 51089h | 51089h | 19158h
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 31930h; 2023-07-30: 51089h | 51089h | 51089h | 19158h
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 31930h; 2023-07-30: 51089h | 51089h | 51089h | 19158h
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 31930h; 2023-07-30: 51089h | 51089h | 51089h | 19158h
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 31930h; 2023-07-30: 51089h | 51089h | 51089h | 19158h
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 31930h; 2023-07-30: 51089h | 51089h | 51089h | 19158h
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 51089h | 51089h | 51089h | 51089h
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 42245h | 112654h | 112654h | 112654h | 112654h | 112654h | 112654h | 112654h | 112654h | 112654h | 89185h
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 42245h | 112654h | 112654h | 112654h | 112654h | 112654h | 112654h | 112654h | 112654h | 112654h | 89185h
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 34059h | 34059h | 34059h | 34059h | 34059h | 34059h
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 34059h | 34059h | 34059h | 34059h | 34059h | 34059h
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 34059h | 34059h | 34059h | 34059h | 34059h | 34059h
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 34059h | 34059h | 34059h | 34059h | 34059h | 34059h
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 2165h; 2023-07-09: 3465h; 2023-07-16: 3465h; 2023-07-23: 3465h; 2023-07-30: 1299h
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 2165h; 2023-07-09: 3465h; 2023-07-16: 3465h; 2023-07-23: 3465h; 2023-07-30: 1299h
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 1254h | 1254h | 1254h | 1254h
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 1254h | 1254h | 1254h | 1254h
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 9836h | 23143h | 23143h | 23143h | 13307h
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 9836h | 23143h | 23143h | 23143h | 13307h
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 982h | 3234h | 3234h | 3234h | 3176h
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 982h | 3234h | 3234h | 3234h | 3176h
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 6557h | 21600h | 21600h | 21600h | 21215h
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 6557h | 21600h | 21600h | 21600h | 21215h
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 1883h; 2023-07-09: 3012h; 2023-07-16: 3012h; 2023-07-23: 3012h; 2023-07-30: 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 527h
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 1883h; 2023-07-09: 3012h; 2023-07-16: 3012h; 2023-07-23: 3012h; 2023-07-30: 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 527h
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 608h
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 608h
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 23845h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 43481h
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 23845h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 43481h
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 5371h | 7766h | 7766h | 7766h | 7766h | 7766h | 7766h | 7766h | 7766h | 7766h | 3689h
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 5371h | 7766h | 7766h | 7766h | 7766h | 7766h | 7766h | 7766h | 7766h | 7766h | 3689h
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 1294h
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 2589h | 1294h
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 30836h | 34964h | 23309h | 29137h | 29137h | 29137h | 29137h | 29137h | 29137h | 29137h | 3156h
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 30836h | 34964h | 23309h | 29137h | 29137h | 29137h | 29137h | 29137h | 29137h | 29137h | 3156h
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 21287h | 34059h | 34059h | 34059h | 34059h | 34059h | 12772h
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 21287h | 34059h | 34059h | 34059h | 34059h | 34059h | 12772h
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 34059h | 34059h | 34059h | 34059h | 34059h | 34059h
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 34059h | 34059h | 34059h | 34059h | 34059h | 34059h
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 14475h | 34059h | 34059h | 34059h | 34059h | 34059h | 19584h
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 14475h | 34059h | 34059h | 34059h | 34059h | 34059h | 19584h
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 11032h | 11032h | 11032h | 11032h
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 11032h | 11032h | 11032h | 11032h
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 1913h | 3060h | 3060h | 3060h | 1148h
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 1913h | 3060h | 3060h | 3060h | 1148h
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 1254h | 1254h | 1254h | 1254h
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 1254h | 1254h | 1254h | 1254h
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 4414h | 10298h | 10298h | 10298h | 8827h
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 4414h | 10298h | 10298h | 10298h | 8827h
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 2091h | 2856h | 2856h | 2856h | 1581h
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 2091h | 2856h | 2856h | 2856h | 1581h
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h | 16048h
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 4636h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 4266h
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 4636h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 4266h
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 608h
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 608h
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 4342h | 10216h | 10216h | 5874h
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 4342h | 10216h | 10216h | 5874h
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h | 20435h
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
MEM0822-CWP-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 19723h | 19723h | 19723h
MEM0822-CWP-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 19723h | 19723h | 19723h
MEM0822-CWP-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 42207h | 187588h | 145381h
MEM0822-CWP-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 42207h | 187588h | 145381h
MEM0822-CWP-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 138220h | 138220h
MEM0822-CWP-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 138220h | 138220h
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 1385h | 1385h | 1385h | 693h
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 1385h | 1385h | 1385h | 693h
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 3991h | 3991h | 3991h | 1995h
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 3991h | 3991h | 3991h | 1995h
MEM0822-CWP-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 6467h | 32333h
MEM0822-CWP-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 6467h | 32333h
MEM0822-CWP-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 12933h | 64667h
MEM0822-CWP-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 12933h | 64667h
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 14792h | 14792h | 14792h | 14792h
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 14792h | 14792h | 14792h | 14792h
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 33083h | 59252h | 63202h | 71103h | 71103h | 71103h | 71103h | 47402h | 59252h | 59252h | 26170h
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 33083h | 59252h | 63202h | 71103h | 71103h | 71103h | 71103h | 47402h | 59252h | 59252h | 26170h
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [74 empty] | 168016h | 780461h | 780461h | 780461h | 780461h | 520307h | 650384h | 650384h | 200535h
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [74 empty] | 168016h | 780461h | 780461h | 780461h | 780461h | 520307h | 650384h | 650384h | 200535h
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 40226h | 178781h | 178781h | 49165h
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 40226h | 178781h | 178781h | 49165h
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 40226h | 178781h | 178781h | 49165h
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 40226h | 178781h | 178781h | 49165h
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 40226h | 178781h | 178781h | 49165h
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 40226h | 178781h | 178781h | 49165h
EEE0820-CWP-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 147494h | 178781h | 120677h
EEE0820-CWP-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-CWP-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 147494h | 178781h | 120677h
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 75982h | 178781h | 178781h | 13409h
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 75982h | 178781h | 178781h | 13409h
EEE0820-CWP-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 111738h | 178781h | 156433h
EEE0820-CWP-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-CWP-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 111738h | 178781h | 156433h
SWP-019-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 32150h | 32150h
SWP-019-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-019-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 32150h | 32150h
SWP-012-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [100 empty] | 20540h | 50904h
SWP-012-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-012-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [100 empty] | 20540h | 50904h
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [99 empty] | 12056h | 53583h | 53583h | 5805h
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [99 empty] | 12056h | 53583h | 53583h | 5805h
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 21713h | 51089h | 51089h | 51089h | 29376h
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 21713h | 51089h | 51089h | 51089h | 29376h
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 21713h | 51089h | 51089h | 51089h | 29376h
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 21713h | 51089h | 51089h | 51089h | 29376h
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 51089h | 51089h | 51089h | 51089h
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 51089h | 51089h | 51089h | 51089h
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 4378h | 7004h | 7004h | 7004h | 2627h
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 4378h | 7004h | 7004h | 7004h | 2627h
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 4786h | 6537h | 6537h | 6537h | 3619h
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 4786h | 6537h | 6537h | 6537h | 3619h
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 10612h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 9763h
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 10612h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 9763h
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 38100h | 38100h | 38100h | 38100h
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 38100h | 38100h | 38100h | 38100h
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 10160h | 35560h | 35560h | 35560h | 35560h
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 10160h | 35560h | 35560h | 35560h | 35560h
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 18473h
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 92364h | 18473h
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 42148h; 2023-07-02: 51089h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 8941h
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 42148h; 2023-07-02: 51089h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 8941h
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 13633h | 23134h | 23134h | 23134h | 16111h
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 13633h | 23134h | 23134h | 23134h | 16111h
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 34613h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 7342h
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 34613h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 41955h | 7342h
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 1277h; 2023-07-30: 51089h | 51089h | 51089h | 49812h
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 1277h; 2023-07-30: 51089h | 51089h | 51089h | 49812h
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [37 empty] | 569h | 22748h | 22748h | 22748h | 22748h | 22748h | 22179h
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [37 empty] | 569h | 22748h | 22748h | 22748h | 22748h | 22748h | 22179h
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 11495h | 51089h | 51089h | 51089h | 39594h
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 11495h | 51089h | 51089h | 51089h | 39594h
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 108h | 478h | 478h | 478h | 370h
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 108h | 478h | 478h | 478h | 370h
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 72h | 446h | 446h | 446h | 446h | 56h
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 72h | 446h | 446h | 446h | 446h | 56h
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 260h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1129h
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 260h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1158h | 1129h
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 4925h | 7881h | 7881h | 7881h | 2955h
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 4925h | 7881h | 7881h | 7881h | 2955h
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 1023h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 421h
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 1023h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 3371h | 421h
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 3484h | 4223h | 4223h | 4223h | 739h
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 3484h | 4223h | 4223h | 4223h | 739h
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 1709h | 5631h | 5631h | 3922h
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 1709h | 5631h | 5631h | 3922h
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 3097h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 657h
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 3097h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 657h
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 11244h | 49974h | 49974h | 49974h | 49974h | 49974h | 49974h | 49974h | 49974h | 38730h
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 11244h | 49974h | 49974h | 49974h | 49974h | 49974h | 49974h | 49974h | 49974h | 38730h
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 5475h | 7915h | 7915h | 7915h | 7915h | 2441h
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 5475h | 7915h | 7915h | 7915h | 7915h | 2441h
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 3555h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 5545h
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 3555h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 7962h | 5545h
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [37 empty] | 682h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 26616h
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [37 empty] | 682h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 27298h | 26616h
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 21713h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h; 2023-06-25: 29376h
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 21713h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h; 2023-06-25: 29376h
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 27690h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 5874h
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 27690h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 5874h
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 40017h | 40017h | 40017h | 40017h
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 40017h | 40017h | 40017h | 40017h
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 5385h | 7355h | 7355h | 7355h | 4072h
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 5385h | 7355h | 7355h | 7355h | 4072h
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 11941h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 10986h
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 11941h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 19106h | 10986h
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 212290h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 250889h
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 212290h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 257322h | 250889h
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 83078h | 83078h | 83078h | 83078h
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 83078h | 83078h | 83078h | 83078h
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 44308h | 77539h | 77539h | 77539h | 55385h
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 44308h | 77539h | 77539h | 77539h | 55385h
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 69051h
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 86314h | 69051h
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 21713h | 51089h | 51089h | 51089h | 29376h
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 21713h | 51089h | 51089h | 51089h | 29376h
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 21713h | 51089h | 51089h | 51089h | 29376h
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 21713h | 51089h | 51089h | 51089h | 29376h
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 27690h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 5874h
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 27690h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 33564h | 5874h
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 48271h | 125925h | 125925h | 35679h
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 48271h | 125925h | 125925h | 35679h
MCD0822-CWP-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 248941h | 281820h | 220759h
MCD0822-CWP-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 248941h | 281820h | 220759h
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 37549h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 6626h
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 37549h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 88351h | 6626h
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 59400h | 220001h |  | 264001h | 264001h | 264001h | 264001h | 72600h
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 59400h | 220001h |  | 264001h | 264001h | 264001h | 264001h | 72600h
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 84725h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 69321h
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 84725h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 102697h | 69321h
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 274982h | 314265h | 314265h | 314265h | 314265h | 144038h
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 274982h | 314265h | 314265h | 314265h | 314265h | 144038h
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 33915h | 38760h | 38760h | 38760h | 38760h | 4845h
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 33915h | 38760h | 38760h | 38760h | 38760h | 4845h
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 16516h | 43086h | 43086h | 43086h | 43086h | 43086h | 43086h | 43086h | 43086h | 43086h | 26569h
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 16516h | 43086h | 43086h | 43086h | 43086h | 43086h | 43086h | 43086h | 43086h | 43086h | 26569h
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 44h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 11h
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 44h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 109h | 11h
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 63940h
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 127879h | 63940h
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 6669h | 32009h | 32009h | 32009h | 4001h
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 6669h | 32009h | 32009h | 32009h | 4001h
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 11628h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 16279h
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 11628h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 16279h
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 890h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 6230h
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 890h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 35601h | 6230h
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 12878h | 30300h | 30300h | 30300h | 17423h
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 12878h | 30300h | 30300h | 30300h | 17423h
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 85961h | 158698h | 158698h | 158698h | 158698h | 46287h
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 85961h | 158698h | 158698h | 158698h | 158698h | 46287h
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 3484h | 4223h | 4223h | 4223h | 739h
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 3484h | 4223h | 4223h | 4223h | 739h
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 1709h | 5631h | 5631h | 3922h
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 1709h | 5631h | 5631h | 3922h
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 3097h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 657h
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 3097h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 657h
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 34044h | 80105h | 80105h | 80105h | 46060h
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 34044h | 80105h | 80105h | 80105h | 46060h
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 33377h | 74764h | 74764h | 74764h | 62749h
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 33377h | 74764h | 74764h | 74764h | 62749h
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 38908h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 52640h
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 38908h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 52640h
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 12878h | 30300h | 30300h | 30300h | 17423h
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 12878h | 30300h | 30300h | 30300h | 17423h
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 34044h | 80105h | 80105h | 80105h | 46060h
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 34044h | 80105h | 80105h | 80105h | 46060h
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 33377h | 74764h | 74764h | 74764h | 62749h
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 33377h | 74764h | 74764h | 74764h | 62749h
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 38908h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 52640h
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 38908h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 52640h
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 12878h | 30300h | 30300h | 30300h | 17423h
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 12878h | 30300h | 30300h | 30300h | 17423h
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 34044h | 80105h | 80105h | 80105h | 46060h
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 34044h | 80105h | 80105h | 80105h | 46060h
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 33377h | 74764h | 74764h | 74764h | 62749h
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 33377h | 74764h | 74764h | 74764h | 62749h
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 38908h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 52640h
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 38908h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 91548h | 52640h
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 10491h | 10491h | 10491h | 10491h
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 10491h | 10491h | 10491h | 10491h
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 1399h | 9792h | 9792h | 9792h | 9792h | 1399h
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 1399h | 9792h | 9792h | 9792h | 9792h | 1399h
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 302h | 483h | 483h | 483h | 483h | 483h | 181h
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 302h | 483h | 483h | 483h | 483h | 483h | 181h
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 353h | 483h | 483h | 483h | 483h | 483h | 129h
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 353h | 483h | 483h | 483h | 483h | 483h | 129h
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 1097h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1010h
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 1097h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1010h
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 453h | 724h | 724h | 724h | 272h
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 453h | 724h | 724h | 724h | 272h
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 353h | 483h | 483h | 483h | 483h | 483h | 129h
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 353h | 483h | 483h | 483h | 483h | 483h | 129h
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 1097h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1010h
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 1097h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1010h
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 453h | 724h | 724h | 724h | 272h
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 453h | 724h | 724h | 724h | 272h
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 353h | 483h | 483h | 483h | 483h | 483h | 129h
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 353h | 483h | 483h | 483h | 483h | 483h | 129h
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 1097h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1010h
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 1097h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1756h | 1010h
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 11495h | 51089h | 51089h | 51089h | 39594h
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 11495h | 51089h | 51089h | 51089h | 39594h
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 418h | 1856h | 1856h | 1856h | 1438h
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 418h | 1856h | 1856h | 1856h | 1438h
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 773h | 1732h | 1732h | 1732h | 1454h
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 773h | 1732h | 1732h | 1732h | 1454h
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 1013h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4388h
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 1013h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4388h
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 4925h | 7881h | 7881h | 7881h | 2955h
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 4925h | 7881h | 7881h | 7881h | 2955h
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 4335h | 7357h | 7357h | 7357h | 5124h
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 4335h | 7357h | 7357h | 7357h | 5124h
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 10946h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 13573h
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 10946h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 17514h | 13573h
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [69 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [69 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
SWP-011-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [99 empty] | 29024h | 53583h | 6698h
SWP-011-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-011-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [99 empty] | 29024h | 53583h | 6698h
SWP-014-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [102 empty] | 35722h
SWP-014-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-014-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [102 empty] | 35722h
SWP-015-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [98 empty] | 21586h | 42713h
SWP-015-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-015-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [98 empty] | 21586h | 42713h
SWP-016-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [98 empty] | 39039h | 25261h
SWP-016-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-016-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [98 empty] | 39039h | 25261h
SWP-017-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [98 empty] | 39039h | 25261h
SWP-017-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-017-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [98 empty] | 39039h | 25261h
SWP-018-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [98 empty] | 39039h | 25261h
SWP-018-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-018-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [98 empty] | 39039h | 25261h
A3070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B37963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B37963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B37963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39413 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39413 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39413 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B41383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 106363h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h |  |  | 100106h | 250266h | 250266h | 168930h
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 106363h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h | 250266h |  |  | 100106h | 250266h | 250266h | 168930h
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 1277h | 51089h | 51089h | 51089h | 49812h
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 1277h | 51089h | 51089h | 51089h | 49812h
EEE0822-CWP-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 116h | 4656h | 4540h
EEE0822-CWP-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-CWP-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 116h | 4656h | 4540h
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 18436h | 22347h | 22347h | 22347h | 22347h | 3911h
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 18436h | 22347h | 22347h | 22347h | 22347h | 3911h
EEE0822-CWP-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 41553h | 97772h | 56219h
EEE0822-CWP-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-CWP-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 41553h | 97772h | 56219h
JIL0822-CWP-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 69836h | 69836h
JIL0822-CWP-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 69836h | 69836h
JIL0822-CWP-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 93115h | 93115h | 93115h
JIL0822-CWP-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 93115h | 93115h | 93115h
JIL0822-CWP-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 680677h | 1601592h | 920915h
JIL0822-CWP-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 680677h | 1601592h | 920915h
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 30300h | 30300h | 30300h | 30300h
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 30300h | 30300h | 30300h | 30300h
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 21342h | 37349h | 37349h | 37349h | 26678h
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 21342h | 37349h | 37349h | 37349h | 26678h
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 33261h
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 33261h
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 40017h | 40017h | 40017h | 40017h
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 40017h | 40017h | 40017h | 40017h
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 21342h | 37349h | 37349h | 37349h | 26678h
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 21342h | 37349h | 37349h | 37349h | 26678h
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 33261h
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 41576h | 33261h
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 155h
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 310h | 155h
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 33964h
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 67928h | 33964h
B37993 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B37993 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B37993 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38913 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38913 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38913 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 523h | 714h | 714h | 191h
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 523h | 714h | 714h | 191h
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 51089h | 51089h | 51089h | 51089h
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 51089h | 51089h | 51089h | 51089h
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 2387h | 2387h | 2387h | 2387h
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 2387h | 2387h | 2387h | 2387h
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 61534h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 13053h
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 61534h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 74586h | 13053h
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [60 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [60 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 21754h | 21754h | 21754h | 21754h
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 21754h | 21754h | 21754h | 21754h
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 8702h | 20304h | 20304h | 20304h | 17403h
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 8702h | 20304h | 20304h | 20304h | 17403h
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h | 31643h
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 4454h | 4454h | 4454h | 4454h
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 4454h | 4454h | 4454h | 4454h
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 51089h | 51089h | 51089h | 51089h
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 27549h | 122441h | 122441h | 122441h | 94892h
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 27549h | 122441h | 122441h | 122441h | 94892h
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1378h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1378h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 11495h | 51089h | 51089h | 51089h | 39594h
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 11495h | 51089h | 51089h | 51089h | 39594h
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 955h | 4243h | 4243h | 4243h | 3288h
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 955h | 4243h | 4243h | 4243h | 3288h
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 636h | 3960h | 3960h | 3960h | 3960h | 495h
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 636h | 3960h | 3960h | 3960h | 3960h | 495h
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 2314h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10029h
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 2314h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10029h
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 51089h | 51089h | 51089h | 51089h
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 612h | 2721h | 2721h | 2721h | 2721h | 2721h | 2023-06-04: 2721h; 2023-06-11: 2721h; 2023-06-18: 2721h; 2023-06-25: 2109h
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 612h | 2721h | 2721h | 2721h | 2721h | 2721h | 2023-06-04: 2721h; 2023-06-11: 2721h; 2023-06-18: 2721h; 2023-06-25: 2109h
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 1782h | 4157h | 4157h | 4157h | 3563h
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 1782h | 4157h | 4157h | 4157h | 3563h
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2969h | 2969h | 2969h | 2969h | 2969h | 2969h
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2969h | 2969h | 2969h | 2969h | 2969h | 2969h
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 2969h | 2969h | 2969h | 2969h | 2969h | 2969h
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 2969h | 2969h | 2969h | 2969h | 2969h | 2969h
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h | 6479h
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 51089h | 51089h | 51089h | 51089h
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 51089h | 51089h | 51089h | 51089h
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 7915h | 18624h | 18624h | 18624h | 10709h
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 7915h | 18624h | 18624h | 18624h | 10709h
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 21713h; 2023-07-02: 51089h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 29376h
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 21713h; 2023-07-02: 51089h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 29376h
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 17831h | 2023-06-04: 41955h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 24124h
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 17831h | 2023-06-04: 41955h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 24124h
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 17481h | 39158h | 39158h | 39158h | 32865h
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 17481h | 39158h | 39158h | 39158h | 32865h
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 23774h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 32165h
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 23774h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 32165h
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 17219h | 20872h | 20872h | 20872h | 3653h
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 17219h | 20872h | 20872h | 20872h | 3653h
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 3827h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 1739h
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 3827h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 6494h | 1739h
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 31309h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 29412h
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 31309h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 37950h | 29412h
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 22706h | 22706h | 22706h | 22706h | 22706h | 22706h | 22706h | 22706h | 22706h
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 22706h | 22706h | 22706h | 22706h | 22706h | 22706h | 22706h | 22706h | 22706h
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 204329h | 247672h | 247672h | 247672h | 43343h
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 204329h | 247672h | 247672h | 247672h | 43343h
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 103197h | 231161h | 231161h | 231161h | 194010h
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 103197h | 231161h | 231161h | 231161h | 194010h
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 80254h
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 160509h | 80254h
MSD0822-CWP-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 272380h | 311292h | 298321h
MSD0822-CWP-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 272380h | 311292h | 298321h
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 55235h | 265130h | 265130h | 265130h | 265130h | 265130h | 220942h |  | 254083h
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 55235h | 265130h | 265130h | 265130h | 265130h | 265130h | 220942h |  | 254083h
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 10491h | 10491h | 10491h | 10491h
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 10491h | 10491h | 10491h | 10491h
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 1399h | 9792h | 9792h | 9792h | 9792h | 1399h
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 1399h | 9792h | 9792h | 9792h | 9792h | 1399h
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 10491h | 10491h | 10491h | 10491h
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 10491h | 10491h | 10491h | 10491h
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 1399h | 9792h | 9792h | 9792h | 9792h | 1399h
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 1399h | 9792h | 9792h | 9792h | 9792h | 1399h
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h | 23980h
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 42148h | 51089h | 51089h | 51089h | 8941h
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 3484h | 4223h | 4223h | 4223h | 739h
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 3484h | 4223h | 4223h | 4223h | 739h
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 1709h | 5631h | 5631h | 3922h
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 1709h | 5631h | 5631h | 3922h
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 3097h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 657h
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 3097h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 3754h | 657h
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 51089h | 2023-06-04: 51089h; 2023-06-11: 51089h; 2023-06-18: 51089h
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 42148h; 2023-07-09: 51089h; 2023-07-16: 51089h; 2023-07-23: 51089h; 2023-07-30: 8941h
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 34613h; 2023-06-11: 41955h; 2023-06-18: 41955h; 2023-06-25: 41955h; 2023-07-02: 7342h
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [60 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [60 empty] | 28669h | 39158h | 39158h | 39158h | 21677h
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 46150h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 9789h
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 46150h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 55940h | 9789h
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 2023-06-04: 3061h; 2023-06-11: 3061h; 2023-06-18: 2372h
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 215714h | 301581h | 201054h | 251317h | 251317h | 251317h | 251317h | 251317h | 77489h
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 215714h | 301581h | 201054h | 251317h | 251317h | 251317h | 251317h | 251317h | 77489h
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 47446h
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 47446h
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 6734h; 2023-07-09: 11428h; 2023-07-16: 11428h; 2023-07-23: 11428h; 2023-07-30: 7959h
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 6734h; 2023-07-09: 11428h; 2023-07-16: 11428h; 2023-07-23: 11428h; 2023-07-30: 7959h
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 13605h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 2023-06-04: 21767h; 2023-06-11: 21767h; 2023-06-18: 21767h; 2023-06-25: 21767h; 2023-07-02: 8163h
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 13605h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 2023-06-04: 21767h; 2023-06-11: 21767h; 2023-06-18: 21767h; 2023-06-25: 21767h; 2023-07-02: 8163h
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 48169h | 251317h | 251317h | 251317h | 251317h | 251317h | 251317h | 251317h | 245034h
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 48169h | 251317h | 251317h | 251317h | 251317h | 251317h | 251317h | 251317h | 245034h
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 8136h | 325430h | 325430h | 208818h
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 8136h | 325430h | 325430h | 208818h
MMR0822-CWP-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 41815h | 47788h | 37832h
MMR0822-CWP-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-CWP-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 41815h | 47788h | 37832h
MMR0822-CWP-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 41815h | 47788h | 37832h
MMR0822-CWP-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-CWP-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 41815h | 47788h | 37832h
MMR0822-CWP-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 41815h | 47788h | 37832h
MMR0822-CWP-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-CWP-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 41815h | 47788h | 37832h
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 17545h | 17545h | 17545h | 17545h | 8772h
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 17545h | 17545h | 17545h | 17545h | 8772h
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 18697h | 34517h | 34517h | 34517h | 34517h | 10067h
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 18697h | 34517h | 34517h | 34517h | 34517h | 10067h
MCD0822-CWP-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 279347h | 55869h
MCD0822-CWP-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 279347h | 55869h
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 119281h
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 238563h | 119281h
MCD0822-CWP-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 38800h | 7760h
MCD0822-CWP-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 38800h | 7760h
MCD0822-CWP-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 562573h | 112515h
MCD0822-CWP-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 562573h | 112515h
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 47051h
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 94102h | 47051h
JSD0822-CWP-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 104756h | 104756h
JSD0822-CWP-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JSD0822-CWP-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 104756h | 104756h
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 27247h; 2023-07-09: 34059h; 2023-07-16: 34059h; 2023-07-23: 34059h; 2023-07-30: 34059h | 34059h | 6812h
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 27247h; 2023-07-09: 34059h; 2023-07-16: 34059h; 2023-07-23: 34059h; 2023-07-30: 34059h | 34059h | 6812h
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 27247h; 2023-07-09: 34059h; 2023-07-16: 34059h; 2023-07-23: 34059h; 2023-07-30: 34059h | 34059h | 6812h
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 27247h; 2023-07-09: 34059h; 2023-07-16: 34059h; 2023-07-23: 34059h; 2023-07-30: 34059h | 34059h | 6812h
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 4419h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 15222h
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 4419h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 15222h
B38383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 7442h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 1860h
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 7442h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 18604h | 1860h
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 244h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h |  |  | 488h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1099h
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 244h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h |  |  | 488h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1221h | 1099h
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 1117h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 44696h | 21230h
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 637h | 2228h | 2228h | 2228h | 2228h
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 637h | 2228h | 2228h | 2228h | 2228h
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 1157h
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 1157h
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 6122h | 6122h | 6122h | 6122h
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 6122h | 6122h | 6122h | 6122h
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 1633h | 11428h | 11428h | 11428h | 11428h | 1633h
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 1633h | 11428h | 11428h | 11428h | 11428h | 1633h
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 2372h
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 2372h
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 51089h | 51089h | 51089h | 51089h
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15742h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 54224h
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 2372h
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 689h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 2372h
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 3469h | 11428h | 11428h | 11428h | 11224h
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 43108h | 43108h | 43108h | 43108h
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 43108h | 43108h | 43108h | 43108h
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 17243h | 40234h | 40234h | 40234h | 34486h
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 17243h | 40234h | 40234h | 40234h | 34486h
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h | 62703h
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 51089h | 51089h | 51089h | 51089h
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [60 empty] | 1277h | 51089h | 51089h | 51089h | 49812h
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [60 empty] | 1277h | 51089h | 51089h | 51089h | 49812h
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 367h | 14686h | 14686h | 14686h | 14319h
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 367h | 14686h | 14686h | 14686h | 14319h
B39453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39813 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39813 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39813 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B37923 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B37923 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B37923 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 136732h |  | 349104h | 349104h | 349104h | 349104h | 154188h
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 136732h |  | 349104h | 349104h | 349104h | 349104h | 154188h
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 4952h | 12919h | 12919h | 12273h
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 4952h | 12919h | 12919h | 12273h
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 2907h | 58140h | 58140h | 58140h | 16473h
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 2907h | 58140h | 58140h | 58140h | 16473h
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 119h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 2266h
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 119h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 4770h | 2266h
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 3469h | 11428h | 11428h | 11428h | 11224h
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 4898h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 21767h | 16870h
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 31930h | 51089h | 51089h | 51089h | 19158h
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 4898h | 6122h | 2023-06-04: 6122h; 2023-06-11: 6122h; 2023-06-18: 1224h
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 4898h | 6122h | 2023-06-04: 6122h; 2023-06-11: 6122h; 2023-06-18: 1224h
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 78399h | 97999h | 97999h | 97999h | 97999h | 97999h | 97999h | 19600h
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 78399h | 97999h | 97999h | 97999h | 97999h | 97999h | 97999h | 19600h
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 18106h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 27159h
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 18106h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 27159h
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 8163h | 11428h | 11428h | 11428h | 6530h
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 8163h | 11428h | 11428h | 11428h | 6530h
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 9795h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 2449h
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 9795h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 2449h
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 6887h | 30610h | 30610h | 30610h | 30610h | 30610h | 30610h | 30610h | 23723h
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 6887h | 30610h | 30610h | 30610h | 30610h | 30610h | 30610h | 30610h | 23723h
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 12244h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 7346h
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 12244h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 7346h
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 53455h | 66818h | 66818h | 66818h | 66818h | 66818h | 66818h | 13364h
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 53455h | 66818h | 66818h | 66818h | 66818h | 66818h | 66818h | 13364h
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 56159h | 83820h |  | 100584h | 100584h | 100584h | 100584h | 100584h | 100584h | 61189h
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 56159h | 83820h |  | 100584h | 100584h | 100584h | 100584h | 100584h | 100584h | 61189h
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 47446h
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 47446h
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [38 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [38 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 78399h; 2023-07-16: 97999h; 2023-07-23: 97999h; 2023-07-30: 97999h | 97999h | 97999h | 97999h | 19600h
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 78399h; 2023-07-16: 97999h; 2023-07-23: 97999h; 2023-07-30: 97999h | 97999h | 97999h | 97999h | 19600h
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 18106h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 27159h
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 18106h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 27159h
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 6122h | 27209h | 27209h | 27209h | 27209h | 27209h | 27209h | 27209h | 27209h | 21087h
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 6122h | 27209h | 27209h | 27209h | 27209h | 27209h | 27209h | 27209h | 27209h | 21087h
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 4898h; 2023-07-16: 6122h; 2023-07-23: 6122h; 2023-07-30: 6122h | 1224h
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 4898h; 2023-07-16: 6122h; 2023-07-23: 6122h; 2023-07-30: 6122h | 1224h
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 6530h | 11428h | 11428h | 11428h | 8163h
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 6530h | 11428h | 11428h | 11428h | 8163h
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 8905h; 2023-07-16: 11131h; 2023-07-23: 11131h; 2023-07-30: 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 4452h
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 8905h; 2023-07-16: 11131h; 2023-07-23: 11131h; 2023-07-30: 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 4452h
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 8746h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 5247h
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 8746h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 5247h
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 52656h | 65820h | 65820h | 65820h | 65820h | 65820h | 65820h | 13164h
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 52656h | 65820h | 65820h | 65820h | 65820h | 65820h | 65820h | 13164h
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 39395h | 100584h | 107290h | 120701h | 120701h | 120701h | 120701h | 74600h
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 39395h | 100584h | 107290h | 120701h | 120701h | 120701h | 120701h | 74600h
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 47446h
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 47446h
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 78399h | 97999h | 97999h | 97999h | 97999h | 97999h | 97999h | 19600h
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 78399h | 97999h | 97999h | 97999h | 97999h | 97999h | 97999h | 19600h
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 18106h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 27159h
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 18106h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 27159h
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 47446h
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 47446h
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [38 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [38 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 4898h | 6122h | 2023-06-04: 6122h; 2023-06-11: 6122h; 2023-06-18: 1224h
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 4898h | 6122h | 2023-06-04: 6122h; 2023-06-11: 6122h; 2023-06-18: 1224h
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 8163h | 11428h | 11428h | 11428h | 6530h
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 8163h | 11428h | 11428h | 11428h | 6530h
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 9795h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 2449h
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 9795h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 2449h
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 12244h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 7346h
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 12244h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 7346h
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 53455h | 66818h | 66818h | 66818h | 66818h | 66818h | 66818h | 13364h
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 53455h | 66818h | 66818h | 66818h | 66818h | 66818h | 66818h | 13364h
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 56159h | 83820h |  | 100584h | 100584h | 100584h | 100584h | 100584h | 100584h | 61189h
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 56159h | 83820h |  | 100584h | 100584h | 100584h | 100584h | 100584h | 100584h | 61189h
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 47446h
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 47446h
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 78399h; 2023-07-16: 97999h; 2023-07-23: 97999h; 2023-07-30: 97999h | 97999h | 97999h | 97999h | 19600h
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 78399h; 2023-07-16: 97999h; 2023-07-23: 97999h; 2023-07-30: 97999h | 97999h | 97999h | 97999h | 19600h
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 16457h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 24685h
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 16457h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 41142h | 24685h
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 4898h | 6122h | 6122h | 6122h | 1224h
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 4898h | 6122h | 6122h | 6122h | 1224h
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 4898h; 2023-07-16: 6122h; 2023-07-23: 6122h; 2023-07-30: 6122h | 1224h
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 4898h; 2023-07-16: 6122h; 2023-07-23: 6122h; 2023-07-30: 6122h | 1224h
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 6530h | 11428h | 11428h | 11428h | 8163h
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 6530h | 11428h | 11428h | 11428h | 8163h
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 8905h; 2023-07-16: 11131h; 2023-07-23: 11131h; 2023-07-30: 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 4452h
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 8905h; 2023-07-16: 11131h; 2023-07-23: 11131h; 2023-07-30: 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 4452h
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1275h | 2041h | 2041h | 2041h | 765h
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1275h | 2041h | 2041h | 2041h | 765h
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 8746h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 5247h
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 8746h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 5247h
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 52656h | 65820h | 65820h | 65820h | 65820h | 65820h | 65820h | 13164h
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 52656h | 65820h | 65820h | 65820h | 65820h | 65820h | 65820h | 13164h
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 32228h | 82284h | 87770h | 98741h | 98741h | 98741h | 98741h | 61027h
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 32228h | 82284h | 87770h | 98741h | 98741h | 98741h | 98741h | 61027h
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 459h | 2041h | 2041h | 2041h | 1582h
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 459h | 2041h | 2041h | 2041h | 1582h
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 459h | 2041h | 2041h | 2041h | 1582h
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 459h | 2041h | 2041h | 2041h | 1582h
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 53455h | 66818h | 66818h | 66818h | 66818h | 66818h | 66818h | 13364h
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 53455h | 66818h | 66818h | 66818h | 66818h | 66818h | 66818h | 13364h
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 78399h | 97999h | 97999h | 97999h | 97999h | 97999h | 97999h | 19600h
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 78399h | 97999h | 97999h | 97999h | 97999h | 97999h | 97999h | 19600h
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 18106h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 27159h
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 18106h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 45265h | 27159h
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 27549h | 122441h | 122441h | 122441h | 94892h
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 27549h | 122441h | 122441h | 122441h | 94892h
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [38 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [38 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 4898h | 6122h | 2023-06-04: 6122h; 2023-06-11: 6122h; 2023-06-18: 1224h
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 4898h | 6122h | 2023-06-04: 6122h; 2023-06-11: 6122h; 2023-06-18: 1224h
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 8163h | 11428h | 11428h | 11428h | 6530h
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 8163h | 11428h | 11428h | 11428h | 6530h
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 9795h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 2449h
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 9795h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 12244h | 2449h
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 12244h | 54418h | 54418h | 54418h | 54418h | 54418h | 54418h | 54418h | 54418h | 42174h
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 12244h | 54418h | 54418h | 54418h | 54418h | 54418h | 54418h | 54418h | 54418h | 42174h
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 12244h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 7346h
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 12244h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 19591h | 7346h
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 45942h | 68570h |  | 82284h | 82284h | 82284h | 82284h | 82284h | 82284h | 50056h
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 45942h | 68570h |  | 82284h | 82284h | 82284h | 82284h | 82284h | 82284h | 50056h
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 78399h; 2023-07-16: 97999h; 2023-07-23: 97999h; 2023-07-30: 97999h | 97999h | 97999h | 97999h | 19600h
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 78399h; 2023-07-16: 97999h; 2023-07-23: 97999h; 2023-07-30: 97999h | 97999h | 97999h | 97999h | 19600h
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 18377h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 27566h
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 18377h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 45943h | 27566h
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 47446h
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 13775h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 47446h
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 2449h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 612h
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 4898h; 2023-07-16: 6122h; 2023-07-23: 6122h; 2023-07-30: 6122h | 1224h
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 4898h; 2023-07-16: 6122h; 2023-07-23: 6122h; 2023-07-30: 6122h | 1224h
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 6530h | 11428h | 11428h | 11428h | 8163h
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 6530h | 11428h | 11428h | 11428h | 8163h
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 8905h; 2023-07-16: 11131h; 2023-07-23: 11131h; 2023-07-30: 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 4452h
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 8905h; 2023-07-16: 11131h; 2023-07-23: 11131h; 2023-07-30: 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 11131h | 4452h
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1913h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 3061h | 1148h
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 3826h | 6122h | 6122h | 6122h | 2296h
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 1684h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 2857h | 1582h
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 8746h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 5247h
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 8746h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 13993h | 5247h
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 52656h | 65820h | 65820h | 65820h | 65820h | 65820h | 65820h | 13164h
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 52656h | 65820h | 65820h | 65820h | 65820h | 65820h | 65820h | 13164h
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 39395h | 100584h | 107290h | 120701h | 120701h | 120701h | 120701h | 74600h
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 39395h | 100584h | 107290h | 120701h | 120701h | 120701h | 120701h | 74600h
TTU0822-CWP-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 7502h | 33340h | 12503h
TTU0822-CWP-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 7502h | 33340h | 12503h
MEM0822-CWP-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 2020h | 2020h | 404h
MEM0822-CWP-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 2020h | 2020h | 404h
MEM0822-CWP-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 1616h | 2020h | 1212h
MEM0822-CWP-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 1616h | 2020h | 1212h
MEM0822-CWP-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 808h | 2020h | 2020h
MEM0822-CWP-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 808h | 2020h | 2020h
MEM0822-CWP-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2020h | 2020h | 808h
MEM0822-CWP-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2020h | 2020h | 808h
MEM0822-CWP-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2020h | 2020h | 808h
MEM0822-CWP-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2020h | 2020h | 808h
MEM0822-CWP-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2020h | 2020h | 808h
MEM0822-CWP-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2020h | 2020h | 808h
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 29099h | 1163947h | 1163947h | 1134848h
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 29099h | 1163947h | 1163947h | 1134848h
ECB0822-CWP-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 94571h | 236427h | 236427h
ECB0822-CWP-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-CWP-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 94571h | 236427h | 236427h
JIL0822-CWP-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 715826h | 1193043h | 954435h
JIL0822-CWP-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 715826h | 1193043h | 954435h
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 26319h | 26319h | 26319h | 26319h | 26319h | 26319h
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 26319h | 26319h | 26319h | 26319h | 26319h | 26319h
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 1649h | 1649h | 1649h | 1649h | 1649h | 1649h
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 1649h | 1649h | 1649h | 1649h | 1649h | 1649h
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 808823h | 808823h | 808823h | 808823h | 808823h | 808823h
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 808823h | 808823h | 808823h | 808823h | 808823h | 808823h
MSD0822-CWP-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 87297h | 87297h | 34919h
MSD0822-CWP-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 87297h | 87297h | 34919h
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 263310h | 263310h | 263310h | 263310h | 263310h | 263310h | 263310h | 263310h | 263310h
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 263310h | 263310h | 263310h | 263310h | 263310h | 263310h | 263310h | 263310h | 263310h
JIL0822-CWP-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 96997h | 96997h | 38799h
JIL0822-CWP-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 96997h | 96997h | 38799h
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 1212h | 48497h | 48497h | 47284h
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 1212h | 48497h | 48497h | 47284h
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 40584h | 101459h | 101459h | 60876h
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 40584h | 101459h | 101459h | 60876h
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 2949h | 7372h | 7372h | 7372h | 4423h
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 2949h | 7372h | 7372h | 7372h | 4423h
TTU0822-CWP-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 7112h | 8890h | 5334h
TTU0822-CWP-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 7112h | 8890h | 5334h
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 3038h | 13500h | 13500h | 2363h
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 3038h | 13500h | 13500h | 2363h
JIL0822-CWP-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 8003h | 9700h | 5578h
JIL0822-CWP-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 8003h | 9700h | 5578h
ECB0822-CWP-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 94571h | 236427h | 236427h
ECB0822-CWP-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-CWP-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 94571h | 236427h | 236427h
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 2000h | 8890h | 8890h | 1556h
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 2000h | 8890h | 8890h | 1556h
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 25607h | 128033h | 128033h | 25607h
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 25607h | 128033h | 128033h | 25607h
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 606h | 24250h | 24250h | 9094h
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 606h | 24250h | 24250h | 9094h
ECB0822-CWP-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 94571h | 236427h | 236427h
ECB0822-CWP-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-CWP-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 94571h | 236427h | 236427h
MEM0822-CWP-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 103688h | 172813h | 138251h
MEM0822-CWP-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 103688h | 172813h | 138251h
MEM0822-CWP-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 8890h | 8890h | 3556h
MEM0822-CWP-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 8890h | 8890h | 3556h
MEM0822-CWP-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 5334h | 8890h | 7112h
MEM0822-CWP-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 5334h | 8890h | 7112h
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 1778h | 8890h | 8890h | 1778h
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 1778h | 8890h | 8890h | 1778h
JIL0822-CWP-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 209510h | 349183h | 279347h
JIL0822-CWP-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 209510h | 349183h | 279347h
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 1455h | 7273h | 7273h | 1455h
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 1455h | 7273h | 7273h | 1455h
ECB0822-CWP-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 94571h | 236427h | 236427h
ECB0822-CWP-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-CWP-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 94571h | 236427h | 236427h
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 4001h | 17783h | 17783h | 3112h
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 4001h | 17783h | 17783h | 3112h
JIL0822-CWP-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 25608h | 31040h | 17848h
JIL0822-CWP-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 25608h | 31040h | 17848h
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 606h | 24250h | 24250h | 23644h
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 606h | 24250h | 24250h | 23644h
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 206h | 8243h | 8243h | 3091h
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 206h | 8243h | 8243h | 3091h
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 3001h | 13337h | 13337h | 2334h
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 3001h | 13337h | 13337h | 2334h
JIL0822-CWP-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 51213h | 62077h | 35694h
JIL0822-CWP-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 51213h | 62077h | 35694h
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 364h | 14550h | 14550h | 14186h
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 364h | 14550h | 14550h | 14186h
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 412h | 16490h | 16490h | 6184h
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 412h | 16490h | 16490h | 6184h
ECB0822-CWP-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 94571h | 236427h | 236427h
ECB0822-CWP-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-CWP-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 94571h | 236427h | 236427h
ECB0822-CWP-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 94571h | 236427h | 236427h
ECB0822-CWP-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0822-CWP-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 94571h | 236427h | 236427h
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 1510h | 6710h | 6710h | 1174h
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 1510h | 6710h | 6710h | 1174h
JIL0822-CWP-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 3201h | 3880h | 2231h
JIL0822-CWP-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 3201h | 3880h | 2231h
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 1001h | 4447h | 4447h | 778h
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 1001h | 4447h | 4447h | 778h
JIL0822-CWP-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 3880h | 3880h | 1552h
JIL0822-CWP-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0822-CWP-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 3880h | 3880h | 1552h
MCD0822-CWP-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 32980h | 32980h | 13192h
MCD0822-CWP-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 32980h | 32980h | 13192h
MRF0822-CWP-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [69 empty] | 9894h | 16490h | 13192h
MRF0822-CWP-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-CWP-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [69 empty] | 9894h | 16490h | 13192h
MCD0822-CWP-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [69 empty] | 19788h | 32980h | 26384h
MCD0822-CWP-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [69 empty] | 19788h | 32980h | 26384h
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 1649h | 8243h | 8243h | 1649h
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 1649h | 8243h | 8243h | 1649h
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 2178h | 7624h | 7624h | 7624h | 7624h
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 2178h | 7624h | 7624h | 7624h | 7624h
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 580h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 533h
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 580h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 927h | 533h
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 3960h
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 3960h
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 76h
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 380h | 76h
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 450h | 10809h | 10809h | 10809h | 10809h | 6755h
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 450h | 10809h | 10809h | 10809h | 10809h | 6755h
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 330h | 1649h | 1649h | 1649h | 1319h
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 330h | 1649h | 1649h | 1649h | 1319h
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 11566h | 30844h | 30844h | 30844h | 30844h | 30844h | 19278h
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 11566h | 30844h | 30844h | 30844h | 30844h | 30844h | 19278h
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h | 1275h
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 3684h | 147365h | 147365h | 147365h | 143681h
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 3684h | 147365h | 147365h | 147365h | 143681h
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 92103h; 2023-07-30: 147365h | 147365h | 147365h | 55262h
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 92103h; 2023-07-30: 147365h | 147365h | 147365h | 55262h
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 147365h | 147365h | 147365h | 147365h
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 147365h | 147365h | 147365h | 147365h
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 147365h | 147365h | 147365h | 147365h
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 147365h | 147365h | 147365h | 147365h
MEM0823-CWP-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 221h | 1020h | 119h
MEM0823-CWP-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-CWP-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 221h | 1020h | 119h
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 5588h | 9861h | 9861h | 9861h | 9861h | 9861h | 4273h
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 5588h | 9861h | 9861h | 9861h | 9861h | 9861h | 4273h
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 2979h | 71499h | 71499h | 71499h | 71499h | 44687h
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 2979h | 71499h | 71499h | 71499h | 71499h | 44687h
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 2557h | 12787h | 12787h | 12787h | 12787h | 12787h | 12787h | 12787h | 12787h | 12787h | 10230h
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 2557h | 12787h | 12787h | 12787h | 12787h | 12787h | 12787h | 12787h | 12787h | 12787h | 10230h
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 368008h | 460009h | 460009h | 460009h | 460009h | 460009h | 460009h | 460009h | 322007h
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 368008h | 460009h | 460009h | 460009h | 460009h | 460009h | 460009h | 460009h | 322007h
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 78595h; 2023-07-09: 98243h; 2023-07-16: 98243h; 2023-07-23: 98243h; 2023-07-30: 98243h | 98243h | 19649h
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 78595h; 2023-07-09: 98243h; 2023-07-16: 98243h; 2023-07-23: 98243h; 2023-07-30: 98243h | 98243h | 19649h
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 223h | 1116h | 1116h | 1116h | 893h
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 223h | 1116h | 1116h | 1116h | 893h
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 15300h | 24481h | 24481h | 24481h | 9180h
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 15300h | 24481h | 24481h | 24481h | 9180h
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 8169h | 8169h | 8169h | 8169h
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 8169h | 8169h | 8169h | 8169h
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 10034h | 10034h | 10034h | 10034h
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 10034h | 10034h | 10034h | 10034h
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 753h | 1686h | 1686h | 1686h | 1415h
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 753h | 1686h | 1686h | 1686h | 1415h
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 2091h | 2856h | 2856h | 2856h | 1581h
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 2091h | 2856h | 2856h | 2856h | 1581h
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 147365h | 147365h | 147365h | 147365h
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 147365h | 147365h | 147365h | 147365h
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3684h | 147365h | 147365h | 147365h | 143681h
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3684h | 147365h | 147365h | 147365h | 143681h
B38033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38923 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38923 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38923 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 147365h | 147365h | 147365h | 147365h
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 147365h | 147365h | 147365h | 147365h
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 147365h | 147365h | 147365h | 147365h
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 147365h | 147365h | 147365h | 147365h
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 121576h; 2023-07-02: 147365h; 2023-07-09: 147365h; 2023-07-16: 147365h; 2023-07-23: 25789h
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 121576h; 2023-07-02: 147365h; 2023-07-09: 147365h; 2023-07-16: 147365h; 2023-07-23: 25789h
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 13633h | 23134h | 23134h | 23134h | 16111h
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 13633h | 23134h | 23134h | 23134h | 16111h
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 3684h | 147365h | 147365h | 147365h | 143681h
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 3684h | 147365h | 147365h | 147365h | 143681h
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 271h | 1686h | 1686h | 1686h | 1686h | 211h
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 271h | 1686h | 1686h | 1686h | 1686h | 211h
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 637h | 2228h | 2228h | 2228h | 2228h
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 637h | 2228h | 2228h | 2228h | 2228h
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 147365h | 147365h | 147365h | 147365h
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 147365h | 147365h | 147365h | 147365h
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 1578h | 2525h | 2525h | 2525h | 947h
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 1578h | 2525h | 2525h | 2525h | 947h
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [74 empty] | 1725h | 2356h | 2356h | 2356h | 1304h
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [74 empty] | 1725h | 2356h | 2356h | 2356h | 1304h
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 3825h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 3519h
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 3825h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 3519h
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 45h | 62h | 66h | 75h | 75h | 61h
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 45h | 62h | 66h | 75h | 75h | 61h
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 10453h
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 10453h
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 301h | 1446h | 1446h | 1446h | 1446h | 1446h | 1386h
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 301h | 1446h | 1446h | 1446h | 1446h | 1446h | 1386h
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 3971h | 19856h | 19856h |  |  | 15885h | 19856h | 19856h | 19856h | 19856h | 19856h | 9928h
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 3971h | 19856h | 19856h |  |  | 15885h | 19856h | 19856h | 19856h | 19856h | 19856h | 9928h
TTU0823-CWP-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [74 empty] | 8854h | 12482h
TTU0823-CWP-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-CWP-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [74 empty] | 8854h | 12482h
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 78595h | 98243h | 98243h | 98243h | 98243h | 98243h | 19649h
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 78595h | 98243h | 98243h | 98243h | 98243h | 98243h | 19649h
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 22105h | 98243h | 98243h | 98243h | 98243h | 98243h | 76139h
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 22105h | 98243h | 98243h | 98243h | 98243h | 98243h | 76139h
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 43384h | 216918h | 216918h | 216918h | 216918h | 43384h
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 43384h | 216918h | 216918h | 216918h | 216918h | 43384h
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 9836h | 23143h | 23143h | 23143h | 13307h
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 9836h | 23143h | 23143h | 23143h | 13307h
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 2387h | 2387h | 2387h | 2387h
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 2387h | 2387h | 2387h | 2387h
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 12729h | 21600h | 21600h | 21600h | 15043h
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 12729h | 21600h | 21600h | 21600h | 15043h
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 523h | 714h | 714h | 191h
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 523h | 714h | 714h | 191h
MCD0823-CWP-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 71078h | 85294h | 21324h
MCD0823-CWP-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0823-CWP-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 71078h | 85294h | 21324h
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 23845h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 43481h
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 23845h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 43481h
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 1157h
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 1157h
SWP-020-0823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [101 empty] | 30313h | 33987h
SWP-020-0823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-020-0823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [101 empty] | 30313h | 33987h
B38133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 206309h | 1061019h | 707346h | 884182h | 884182h | 383146h
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 206309h | 1061019h | 707346h | 884182h | 884182h | 383146h
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 847h | 4233h | 4233h | 4233h | 4233h | 847h
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 847h | 4233h | 4233h | 4233h | 4233h | 847h
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 122h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 183h
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 122h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 611h | 183h
B39493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38163 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38163 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38163 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B41393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38943 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38943 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38943 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38953 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38953 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38953 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39853 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39853 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39853 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39833 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39833 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39833 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39843 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39843 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39843 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 62630h | 147365h | 147365h | 147365h | 84735h
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 62630h | 147365h | 147365h | 147365h | 84735h
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [69 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [69 empty] | 92103h | 147365h | 147365h | 147365h | 55262h
B39583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39593 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39593 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39593 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3890 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3890 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3890 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0824-CWP-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [97 empty] | 36953h | 41833h | 39742h
MEM0824-CWP-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-CWP-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [97 empty] | 36953h | 41833h | 39742h
MEM0824-CWP-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 36953h | 41833h | 39742h
MEM0824-CWP-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-CWP-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 36953h | 41833h | 39742h
MEM0824-CWP-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [97 empty] | 14979h | 4805h
MEM0824-CWP-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-CWP-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [97 empty] | 14979h | 4805h
MEM0824-CWP-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 14979h | 4805h
MEM0824-CWP-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-CWP-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 14979h | 4805h
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
B39863 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39863 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39863 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39873 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [74 empty] | 897h | 35888h | 35888h | 35888h | 34991h
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [74 empty] | 897h | 35888h | 35888h | 35888h | 34991h
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 1658h | 66314h | 66314h | 66314h | 66314h | 66314h | 66314h | 66314h | 64656h
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 1658h | 66314h | 66314h | 66314h | 66314h | 66314h | 66314h | 66314h | 64656h
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 442h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17225h
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 442h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17225h
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 13581h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 7619h
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 13581h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 7619h
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 7950h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 13250h
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 7950h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 13250h
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 23052h | 23052h | 23052h | 23052h | 23052h | 23052h
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 23052h | 23052h | 23052h | 23052h | 23052h | 23052h
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 1658h | 66314h | 66314h | 66314h | 66314h | 66314h | 66314h | 66314h | 64656h
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 1658h | 66314h | 66314h | 66314h | 66314h | 66314h | 66314h | 66314h | 64656h
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 386h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15065h
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 386h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15065h
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 12023h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 6518h
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 12023h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 16224h | 6518h
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 7339h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 11202h
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 7339h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 11202h
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 56367h | 132628h | 132628h | 132628h | 76261h
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 56367h | 132628h | 132628h | 132628h | 76261h
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 7508h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 10158h
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 7508h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 10158h
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 16231h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 4969h
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 16231h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 4969h
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 22525h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 48142h
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 22525h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 48142h
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 56367h | 132628h | 132628h | 132628h | 76261h
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 56367h | 132628h | 132628h | 132628h | 76261h
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 6567h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 8884h
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 6567h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 8884h
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 606h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 5862h
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 606h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 5862h
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 48502h | 114122h | 114122h | 8559h
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 48502h | 114122h | 114122h | 8559h
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 1189h | 47553h | 47553h | 47553h | 47553h | 47553h | 46365h
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 1189h | 47553h | 47553h | 47553h | 47553h | 47553h | 46365h
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 19700h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 42105h
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 19700h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 42105h
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 56367h | 132628h | 132628h | 132628h | 76261h
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 56367h | 132628h | 132628h | 132628h | 76261h
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 7508h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 10158h
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 7508h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 17667h | 10158h
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 16231h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 4969h
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 16231h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 18550h | 4969h
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 22525h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 48142h
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 22525h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 49467h | 48142h
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 56367h | 132628h | 132628h | 132628h | 76261h
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 56367h | 132628h | 132628h | 132628h | 76261h
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 6567h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 8884h
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 6567h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 15451h | 8884h
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 606h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 5862h
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 606h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 22638h | 5862h
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 19700h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 42105h
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 19700h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 43263h | 42105h
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 4419h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 15222h
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 4419h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 15222h
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 658h | 26319h | 26319h | 26319h | 26319h | 26319h | 25661h
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 658h | 26319h | 26319h | 26319h | 26319h | 26319h | 25661h
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 132628h | 132628h | 132628h | 132628h
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 132628h | 132628h | 132628h | 132628h
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 132628h | 132628h | 132628h | 132628h
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 132628h | 132628h | 132628h | 132628h
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 1578h | 2525h | 2525h | 2525h | 947h
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 1578h | 2525h | 2525h | 2525h | 947h
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [74 empty] | 1725h | 2356h | 2356h | 2356h | 1304h
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [74 empty] | 1725h | 2356h | 2356h | 2356h | 1304h
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 3825h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 3519h
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 3825h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 3519h
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [97 empty] | 56669h | 103035h | 103035h | 103035h | 29193h
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [97 empty] | 56669h | 103035h | 103035h | 103035h | 29193h
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 1578h | 2525h | 2525h | 2525h | 947h
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 1578h | 2525h | 2525h | 2525h | 947h
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [74 empty] | 1725h | 2356h | 2356h | 2356h | 1304h
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [74 empty] | 1725h | 2356h | 2356h | 2356h | 1304h
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 3825h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 3519h
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 3825h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 6120h | 3519h
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 1520h | 2432h | 2432h | 2432h | 912h
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 1520h | 2432h | 2432h | 2432h | 912h
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 1662h | 2270h | 2270h | 2270h | 1257h
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 1662h | 2270h | 2270h | 2270h | 1257h
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3684h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 3390h
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3684h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 3390h
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 2210h | 88419h | 88419h | 88419h | 88419h | 88419h | 86208h
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 2210h | 88419h | 88419h | 88419h | 88419h | 88419h | 86208h
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 19894h; 2023-07-30: 88419h | 88419h | 88419h | 88419h | 88419h | 68525h
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 19894h; 2023-07-30: 88419h | 88419h | 88419h | 88419h | 88419h | 68525h
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 660h | 1552h | 1552h | 1552h | 1552h | 1552h | 892h
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 660h | 1552h | 1552h | 1552h | 1552h | 1552h | 892h
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MEM0824-CWP-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 19301h | 483h
MEM0824-CWP-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-CWP-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 19301h | 483h
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [97 empty] | 10994h | 19989h | 19989h | 19989h | 5664h
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [97 empty] | 10994h | 19989h | 19989h | 19989h | 5664h
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [95 empty] | 8596h | 11994h | 11994h | 11994h | 1399h
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [95 empty] | 8596h | 11994h | 11994h | 11994h | 1399h
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
SWP-021-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [98 empty] | 29471h | 13396h
SWP-021-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-021-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [98 empty] | 29471h | 13396h
SWP-022-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [101 empty] | 30313h | 33987h
SWP-022-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-022-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [101 empty] | 30313h | 33987h
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 3298h | 7760h | 7760h | 7760h | 4462h
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 3298h | 7760h | 7760h | 7760h | 4462h
MCD0824-CWP-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 1453h | 291h
MCD0824-CWP-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-CWP-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 1453h | 291h
MCD0824-CWP-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 9053h | 1811h
MCD0824-CWP-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-CWP-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 9053h | 1811h
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [95 empty] | 30655h | 42775h | 42775h | 42775h | 42775h | 42775h | 12119h
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [95 empty] | 30655h | 42775h | 42775h | 42775h | 42775h | 42775h | 12119h
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 82893h | 132628h | 132628h | 132628h | 49736h
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 82893h; 2023-07-30: 132628h | 132628h | 132628h | 49736h
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 82893h; 2023-07-30: 132628h | 132628h | 132628h | 49736h
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 82893h; 2023-07-30: 132628h | 132628h | 132628h | 49736h
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 82893h; 2023-07-30: 132628h | 132628h | 132628h | 49736h
A3080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38973 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38973 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38973 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39603 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39603 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39603 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39613 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39613 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39613 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3760 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3760 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3760 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 523h | 714h | 714h | 191h
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 523h | 714h | 714h | 191h
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 637h | 2228h | 2228h | 2228h | 2228h
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 637h | 2228h | 2228h | 2228h | 2228h
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 12276h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 7365h
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 12276h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 7365h
B39913 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39913 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39913 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39903 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 3328h | 14792h | 14792h | 14792h | 11464h
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 3328h | 14792h | 14792h | 14792h | 11464h
MRF0826-CWP-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 23280h | 23280h
MRF0826-CWP-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0826-CWP-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 23280h | 23280h
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 621h | 776h | 776h | 776h | 776h | 776h | 155h
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 621h | 776h | 776h | 776h | 776h | 776h | 155h
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 582h | 23279h | 23279h | 23279h | 23279h | 23279h | 22697h
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 582h | 23279h | 23279h | 23279h | 23279h | 23279h | 22697h
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 23278h | 23278h | 23278h | 23278h
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 23278h | 23278h | 23278h | 23278h
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 23278h | 23278h | 23278h | 23278h
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 23278h | 23278h | 23278h | 23278h
EEE0826-CWP-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 8407h | 9700h | 1293h
EEE0826-CWP-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-CWP-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 8407h | 9700h | 1293h
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 1837h; 2023-07-30: 11428h | 11428h | 11428h | 11428h | 1428h
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 1837h; 2023-07-30: 11428h | 11428h | 11428h | 11428h | 1428h
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 6679h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 28941h
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 6679h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 28941h
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 18366h | 81627h | 81627h | 81627h | 81627h | 81627h | 63261h
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 18366h | 81627h | 81627h | 81627h | 81627h | 81627h | 63261h
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 27549h | 122441h | 122441h | 122441h | 94892h
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 27549h | 122441h | 122441h | 122441h | 94892h
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 137573h; 2023-07-02: 166755h; 2023-07-09: 166755h; 2023-07-16: 166755h; 2023-07-23: 29182h
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 137573h; 2023-07-02: 166755h; 2023-07-09: 166755h; 2023-07-16: 166755h; 2023-07-23: 29182h
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 13633h | 23134h | 23134h | 23134h | 16111h
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 13633h | 23134h | 23134h | 23134h | 16111h
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 18366h | 81627h | 81627h | 81627h | 81627h | 81627h | 63261h
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 18366h | 81627h | 81627h | 81627h | 81627h | 81627h | 63261h
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 133404h | 166755h | 166755h | 166755h | 33351h
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 133404h | 166755h | 166755h | 166755h | 33351h
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 55973h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 13993h
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 55973h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 13993h
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 137573h; 2023-07-02: 166755h; 2023-07-09: 166755h; 2023-07-16: 166755h; 2023-07-23: 29182h
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 137573h; 2023-07-02: 166755h; 2023-07-09: 166755h; 2023-07-16: 166755h; 2023-07-23: 29182h
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 13633h | 23134h | 23134h | 23134h | 16111h
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 13633h | 23134h | 23134h | 23134h | 16111h
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 55973h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 13993h
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 55973h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 13993h
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 20844h | 166755h | 166755h | 166755h | 145910h
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 20844h | 166755h | 166755h | 166755h | 145910h
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 18366h | 81627h | 81627h | 81627h | 81627h | 81627h | 63261h
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 18366h | 81627h | 81627h | 81627h | 81627h | 81627h | 63261h
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 1561h | 6936h | 6936h | 6936h | 5375h
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 1561h | 6936h | 6936h | 6936h | 5375h
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 10912h | 48497h | 48497h | 48497h | 48497h | 48497h | 37585h
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 10912h | 48497h | 48497h | 48497h | 48497h | 48497h | 37585h
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 400h | 1779h | 1779h | 1779h | 1779h | 1779h | 1378h
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 400h | 1779h | 1779h | 1779h | 1779h | 1779h | 1378h
JPA0826-CWP-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 1995h | 2661h
JPA0826-CWP-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0826-CWP-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 1995h | 2661h
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 1157h
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 5787h | 1157h
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
MEM0826-CWP-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 825h | 32980h | 5772h
MEM0826-CWP-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-CWP-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 825h | 32980h | 5772h
SWP-023-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [97 empty] | 48225h | 16075h
SWP-023-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-023-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [97 empty] | 48225h | 16075h
SWP-024-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [99 empty] | 48225h | 16075h
SWP-024-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-024-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [99 empty] | 48225h | 16075h
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 2958h | 13148h | 13148h | 13148h | 13148h | 3616h
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 2958h | 13148h | 13148h | 13148h | 13148h | 3616h
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 582h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 22697h
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 582h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 23279h | 22697h
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 1397h | 2328h | 2328h | 2328h | 931h
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 1397h | 2328h | 2328h | 2328h | 931h
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h | 776h
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [69 empty] | 104222h | 166755h | 166755h | 166755h | 62533h
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [69 empty] | 104222h | 166755h | 166755h | 166755h | 62533h
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 1013h | 2270h | 2270h | 2270h | 1905h
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 1013h | 2270h | 2270h | 2270h | 1905h
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 1326h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5748h
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 1326h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5748h
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 166755h | 166755h | 166755h | 166755h
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 166755h | 166755h | 166755h | 166755h
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 4169h | 166755h | 166755h | 166755h | 162586h
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 4169h | 166755h | 166755h | 166755h | 162586h
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 1837h | 11428h | 11428h | 11428h | 11428h | 1428h
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 1837h | 11428h | 11428h | 11428h | 11428h | 1428h
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 6679h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 2023-06-04: 29683h; 2023-06-11: 29683h; 2023-06-18: 29683h; 2023-06-25: 28941h
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 6679h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 2023-06-04: 29683h; 2023-06-11: 29683h; 2023-06-18: 29683h; 2023-06-25: 28941h
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 787h | 3498h | 3498h | 3498h | 3498h | 3498h | 2023-06-04: 3498h; 2023-06-11: 2711h
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1377h | 6122h | 6122h | 6122h | 4745h
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 1837h | 11428h | 11428h | 11428h | 11428h | 1428h
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 1837h | 11428h | 11428h | 11428h | 11428h | 1428h
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 6679h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 2023-06-04: 29683h; 2023-06-11: 29683h; 2023-06-18: 29683h; 2023-06-25: 28941h
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 6679h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 29683h | 2023-06-04: 29683h; 2023-06-11: 29683h; 2023-06-18: 29683h; 2023-06-25: 28941h
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 166755h | 166755h | 166755h | 166755h
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 166755h | 166755h | 166755h | 166755h
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 37520h | 166755h | 166755h | 166755h | 129235h
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 37520h | 166755h | 166755h | 166755h | 129235h
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 547h | 2432h | 2432h | 2432h | 1885h
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 547h | 2432h | 2432h | 2432h | 1885h
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 2387h | 2387h | 2387h | 2387h
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 2387h | 2387h | 2387h | 2387h
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
A3780 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3780 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3780 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A4910 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A4910 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A4910 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A4860 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A4860 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A4860 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A4870 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A4870 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A4870 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A4880 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A4880 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A4880 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MSD0827-CWP-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 14131h | 5653h
MSD0827-CWP-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 14131h | 5653h
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 21212h; 2023-07-09: 26515h; 2023-07-16: 26515h; 2023-07-23: 26515h; 2023-07-30: 26515h | 26515h | 5303h
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 21212h; 2023-07-09: 26515h; 2023-07-16: 26515h; 2023-07-23: 26515h; 2023-07-30: 26515h | 26515h | 5303h
MSD0822-CWP-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 41143h | 41143h | 16457h
MSD0822-CWP-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 41143h | 41143h | 16457h
MSD0822-CWP-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 24686h | 41143h | 32915h
MSD0822-CWP-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0822-CWP-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 24686h | 41143h | 32915h
EEL0827-CWP-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 46075h | 12125h
EEL0827-CWP-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEL0827-CWP-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 46075h | 12125h
ELU0827-CWP-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 2328h
ELU0827-CWP-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-CWP-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 2328h
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [60 empty] | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [60 empty] | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h | 18517h
JIL0827-CWP-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [98 empty] | 36375h | 10185h
JIL0827-CWP-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-CWP-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [98 empty] | 36375h | 10185h
MSD0827-CWP-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 17321h | 21479h
MSD0827-CWP-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 17321h | 21479h
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 15378h | 68345h | 68345h | 25629h
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 15378h | 68345h | 68345h | 25629h
MEM0827-CWP-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 5432h
MEM0827-CWP-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 5432h
MEM0827-CWP-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 65956h | 65956h
MEM0827-CWP-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 65956h | 65956h
MSD0827-CWP-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 23280h
MSD0827-CWP-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 23280h
SES0827-CWP-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SES0827-CWP-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-CWP-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SES0827-CWP-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 7760h
SES0827-CWP-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-CWP-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 7760h
MCD0827-CWP-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MCD0827-CWP-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-CWP-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0827-CWP-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 316008h
MEM0827-CWP-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 316008h
STP0827-CWP-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 13968h
STP0827-CWP-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-CWP-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 13968h
MSD0827-CWP-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 19400h
MSD0827-CWP-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 19400h
MEM0827-CWP-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 23280h
MEM0827-CWP-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 23280h
MEM0827-CWP-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MEM0827-CWP-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MMR0827-CWP-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 23280h
MMR0827-CWP-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-CWP-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 23280h
STP0827-CWP-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 11640h | 34920h
STP0827-CWP-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-CWP-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 11640h | 34920h
MEM0827-CWP-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MEM0827-CWP-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0827-CWP-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 59360h
MEM0827-CWP-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 59360h
SES0827-CWP-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SES0827-CWP-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-CWP-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SES0827-CWP-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 7760h
SES0827-CWP-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-CWP-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 7760h
SES0827-CWP-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 37248h
SES0827-CWP-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-CWP-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 37248h
MCD0827-CWP-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 59360h
MCD0827-CWP-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-CWP-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 59360h
MEM0827-CWP-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 19400h
MEM0827-CWP-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 19400h
MMR0827-CWP-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [97 empty] | 23280h | 11640h
MMR0827-CWP-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-CWP-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [97 empty] | 23280h | 11640h
SES0827-CWP-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [95 empty] | 12224h
SES0827-CWP-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-CWP-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [95 empty] | 12224h
4 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
4 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
4 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0827-CWP-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 23280h
MEM0827-CWP-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 23280h
CPI0827-CWP-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 10864h
CPI0827-CWP-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CPI0827-CWP-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 10864h
7 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
7 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
7 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
8 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
8 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
8 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
9 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
9 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
9 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
10 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
10 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
10 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
11 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
11 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
11 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
12 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
12 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
12 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
13 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
13 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
13 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MMR0827-CWP-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 139672h
MMR0827-CWP-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-CWP-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 139672h
MEM0827-CWP-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MEM0827-CWP-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0827-CWP-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 3880h
MEM0827-CWP-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 3880h
SWP-027-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [100 empty] | 125028h
SWP-027-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-027-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [100 empty] | 125028h
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 8169h | 8169h | 8169h | 8169h
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 8169h | 8169h | 8169h | 8169h
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 1254h | 1254h | 1254h | 1254h
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 1254h | 1254h | 1254h | 1254h
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 335h | 536h | 536h | 536h | 201h
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17608h | 28172h | 28172h | 28172h | 10565h
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17608h | 28172h | 28172h | 28172h | 10565h
B40133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40163 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40163 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40163 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 168493h | 207376h | 207376h | 207376h | 38883h
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 168493h | 207376h | 207376h | 207376h | 38883h
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 113534h | 113534h | 113534h | 113534h
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 113534h | 113534h | 113534h | 113534h
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 290h | 290h | 290h | 290h
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 290h | 290h | 290h | 290h
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 696136h | 696136h | 696136h | 696136h
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 696136h | 696136h | 696136h | 696136h
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 1746h | 7760h | 7760h | 7760h | 6014h
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 1746h | 7760h | 7760h | 7760h | 6014h
JIL0827-CWP-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 11873h | 27936h | 2095h
JIL0827-CWP-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-CWP-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 11873h | 27936h | 2095h
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
JPA0827-CWP-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 2968h | 6984h | 4016h
JPA0827-CWP-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0827-CWP-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 2968h | 6984h | 4016h
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 4419h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 15222h
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 4419h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 27498h | 15222h
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 12729h | 21600h | 21600h | 21600h | 15043h
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 12729h | 21600h | 21600h | 21600h | 15043h
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 39772h | 39772h | 39772h | 39772h
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 39772h | 39772h | 39772h | 39772h
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 24858h | 39772h | 39772h | 39772h | 2023-06-04: 14915h
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 24858h | 39772h | 39772h | 39772h | 2023-06-04: 14915h
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [23 empty] | 7954h | 39772h | 39772h | 39772h | 31818h
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [23 empty] | 7954h | 39772h | 39772h | 39772h | 31818h
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 11905h | 19049h | 19049h | 19049h | 19049h | 19049h | 7143h
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 11905h | 19049h | 19049h | 19049h | 19049h | 19049h | 7143h
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 1851h | 74056h | 74056h | 74056h | 72205h
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 1851h | 74056h | 74056h | 74056h | 72205h
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 728h | 728h | 728h | 728h
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 728h | 728h | 728h | 728h
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 9894h | 9894h | 9894h | 9894h
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 9894h | 9894h | 9894h | 9894h
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 10328h | 23134h | 23134h | 23134h | 19416h
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 10328h | 23134h | 23134h | 23134h | 19416h
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 2178h | 7624h | 7624h | 7624h | 7624h
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 2178h | 7624h | 7624h | 7624h | 7624h
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 16572h | 26515h | 26515h | 26515h | 26515h | 26515h | 9943h
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 16572h | 26515h | 26515h | 26515h | 26515h | 26515h | 9943h
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 15874h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 9524h
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 15874h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 9524h
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 39772h | 39772h | 39772h | 39772h
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 39772h | 39772h | 39772h | 39772h
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 1520h | 2432h | 2432h | 2432h | 912h
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 1520h | 2432h | 2432h | 2432h | 912h
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 523h | 714h | 714h | 191h
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 523h | 714h | 714h | 191h
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 3982h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 4867h
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 3982h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 17700h | 4867h
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 16268h | 72303h | 72303h | 72303h | 72303h | 72303h | 72303h | 56035h
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 16268h | 72303h | 72303h | 72303h | 72303h | 72303h | 72303h | 56035h
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 23845h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 43481h
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 23845h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 56105h | 43481h
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 16524h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 20029h | 15523h
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 3960h
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 19802h | 3960h
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 608h
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 3040h | 608h
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 812h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 747h
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
SWP-025-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [95 empty] | 21910h | 6668h
SWP-025-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-025-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [95 empty] | 21910h | 6668h
SWP-026-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [95 empty] | 21127h | 43173h
SWP-026-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-026-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [95 empty] | 21127h | 43173h
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 16037h | 16037h | 16037h | 16037h | 8019h
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 16037h | 16037h | 16037h | 16037h | 8019h
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 29h | 581h | 581h | 581h | 165h
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 29h | 581h | 581h | 581h | 165h
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 2093h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 3349h | 586h
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 178580h | 285728h | 285728h | 285728h | 107148h
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 178580h | 285728h | 285728h | 285728h | 107148h
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 178580h | 285728h | 285728h | 285728h | 107148h
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 178580h | 285728h | 285728h | 285728h | 107148h
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 24858h; 2023-07-30: 39772h | 39772h | 39772h | 14915h
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 24858h; 2023-07-30: 39772h | 39772h | 39772h | 14915h
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 95462h; 2023-07-02: 152740h; 2023-07-09: 152740h; 2023-07-16: 152740h; 2023-07-23: 57277h
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 76h
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 153h | 76h
EEE0827-CWP-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 32592h | 32592h
EEE0827-CWP-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-CWP-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 32592h | 32592h
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 8465h | 8465h | 8465h | 8465h | 8465h | 4233h
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 8465h | 8465h | 8465h | 8465h | 8465h | 4233h
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 1084h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 1325h
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 1084h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 4817h | 1325h
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 2794h | 3386h | 3386h | 3386h | 3386h | 2286h
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 2794h | 3386h | 3386h | 3386h | 3386h | 2286h
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 37h | 1475h | 1475h | 701h
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 37h | 1475h | 1475h | 701h
JIL0827-CWP-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 32592h
JIL0827-CWP-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-CWP-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 32592h
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 16572h | 26515h | 26515h | 26515h | 26515h | 26515h | 9943h
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 16572h | 26515h | 26515h | 26515h | 26515h | 26515h | 9943h
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 38263h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 22958h
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 38263h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 61221h | 22958h
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 994h | 39772h | 39772h | 39772h | 38778h
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 994h | 39772h | 39772h | 39772h | 38778h
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 16903h | 39772h | 39772h | 39772h | 22869h
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 16903h | 39772h | 39772h | 39772h | 22869h
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 32812h; 2023-07-02: 39772h; 2023-07-09: 39772h; 2023-07-16: 39772h; 2023-07-23: 6960h
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 32812h; 2023-07-02: 39772h; 2023-07-09: 39772h; 2023-07-16: 39772h; 2023-07-23: 6960h
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 39772h | 39772h | 39772h | 39772h
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 39772h | 39772h | 39772h | 39772h
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 39772h | 39772h | 39772h | 39772h
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 39772h | 39772h | 39772h | 39772h
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 27893h; 2023-06-11: 38097h; 2023-06-18: 38097h; 2023-06-25: 10205h
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 27893h; 2023-06-11: 38097h; 2023-06-18: 38097h; 2023-06-25: 10205h
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 43292h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 39829h
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 43292h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 69267h | 39829h
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 2061h | 3297h | 3297h | 3297h | 3297h | 3297h | 1237h
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 2061h | 3297h | 3297h | 3297h | 3297h | 3297h | 1237h
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 5620h | 18514h | 18514h | 18514h | 18183h
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 15874h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 9524h
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 15874h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 25398h | 9524h
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 15715h | 26668h | 26668h | 26668h | 18572h
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 1662h | 2270h | 2270h | 2270h | 1257h
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 1662h | 2270h | 2270h | 2270h | 1257h
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3684h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 3390h
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3684h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 5895h | 3390h
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [69 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [69 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 9836h | 23143h | 23143h | 23143h | 13307h
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 9836h | 23143h | 23143h | 23143h | 13307h
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 20449h | 2023-06-04: 24786h; 2023-06-11: 24786h; 2023-06-18: 24786h; 2023-06-25: 4338h
A3790 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3790 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3790 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40413 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40413 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40413 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39633 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39633 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39633 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38993 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38993 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38993 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39643 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39643 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39643 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39653 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39653 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39653 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38983 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38983 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38983 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39663 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39663 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39663 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3730 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3730 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3730 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 16893h | 16893h | 16893h | 16893h | 16893h | 16893h | 16893h | 16893h | 3167h
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 16893h | 16893h | 16893h | 16893h | 16893h | 16893h | 16893h | 16893h | 3167h
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 7659h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 10723h
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 7659h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 12255h | 10723h
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 3297h | 3297h | 3297h | 3297h | 3297h | 3297h
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 3297h | 3297h | 3297h | 3297h | 3297h | 3297h
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 83804h | 372462h | 372462h | 372462h | 288658h
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 83804h | 372462h | 372462h | 372462h | 288658h
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 7888h | 35057h | 35057h | 35057h | 35057h | 35057h | 35057h | 27169h
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 7888h | 35057h | 35057h | 35057h | 35057h | 35057h | 35057h | 27169h
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 307h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 375h
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 307h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 1364h | 375h
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 204720h
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 259962h | 204720h
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 5036h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 6813h
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 5036h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 23698h | 6813h
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h | 564h
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 16457h | 16457h | 16457h | 16457h | 16457h | 16457h
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 16457h | 16457h | 16457h | 16457h | 16457h | 16457h
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 3297h | 3297h | 3297h | 3297h | 3297h | 3297h
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 3297h | 3297h | 3297h | 3297h | 3297h | 3297h
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 3297h | 3297h | 3297h | 3297h | 3297h | 3297h
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 3297h | 3297h | 3297h | 3297h | 3297h | 3297h
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
B39943 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39943 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39943 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39923 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39923 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39923 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 4286h | 26668h | 26668h | 26668h | 26668h | 3333h
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 20409h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 32655h | 12245h
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 43729h | 69966h | 69966h | 69966h | 69966h | 69966h | 69966h | 26237h
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17858h | 28573h | 28573h | 28573h | 10715h
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 250h | 400h | 400h | 400h | 150h
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 250h | 400h | 400h | 400h | 150h
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2746h | 4393h | 4393h | 4393h | 1648h
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 659h | 4101h | 4101h | 4101h | 4101h | 513h
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 3432h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5492h | 5355h
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 994h | 39772h | 39772h | 39772h | 38778h
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 994h | 39772h | 39772h | 39772h | 38778h
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 753h | 1686h | 1686h | 1686h | 1415h
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 753h | 1686h | 1686h | 1686h | 1415h
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 39772h | 39772h | 39772h | 39772h
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 39772h | 39772h | 39772h | 39772h
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 16164h | 16164h | 16164h | 16164h
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 16164h | 16164h | 16164h | 16164h
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 4310h | 15085h | 15085h | 15085h | 15085h
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 4310h | 15085h | 15085h | 15085h | 15085h
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 7837h
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 39184h | 7837h
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 8949h | 39772h | 39772h | 39772h | 30824h
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 8949h | 39772h | 39772h | 39772h | 30824h
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 24858h | 39772h | 39772h | 39772h | 14915h
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 8949h | 39772h | 39772h | 39772h | 30824h
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 8949h | 39772h | 39772h | 39772h | 30824h
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 39772h | 39772h | 39772h | 39772h
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 39772h | 39772h | 39772h | 39772h
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 39772h | 39772h | 39772h | 39772h
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 39772h | 39772h | 39772h | 39772h
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 251h | 401h | 401h | 401h | 151h
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 251h | 401h | 401h | 401h | 151h
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 17608h | 28172h | 28172h | 28172h | 10565h
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 17608h | 28172h | 28172h | 28172h | 10565h
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 42775h | 42775h | 42775h | 42775h | 42775h | 42775h
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 42775h | 42775h | 42775h | 42775h | 42775h | 42775h
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 24686h | 24686h | 24686h | 24686h
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 24686h | 24686h | 24686h | 24686h
JIL0827-CWP-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 139672h
JIL0827-CWP-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0827-CWP-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 139672h
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 191h | 7633h | 7633h | 7633h | 7633h | 7633h | 1336h
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 191h | 7633h | 7633h | 7633h | 7633h | 7633h | 1336h
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 17650h | 21394h | 21394h | 21394h | 3744h
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 17650h | 21394h | 21394h | 21394h | 3744h
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 6402h | 16004h | 16004h | 16004h | 16004h | 16004h | 9602h
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 6402h | 16004h | 16004h | 16004h | 16004h | 16004h | 9602h
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 429h | 429h | 429h | 429h | 429h | 429h | 429h | 429h | 257h
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 429h | 429h | 429h | 429h | 429h | 429h | 429h | 429h | 257h
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 20200h | 20200h | 20200h | 20200h | 20200h | 20200h
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 20200h | 20200h | 20200h | 20200h | 20200h | 20200h
MEM0830-EWPc-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MEM0830-EWPc-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0830-EWPc-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ESD1042-CWP-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 387232h | 96808h
ESD1042-CWP-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1042-CWP-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 387232h | 96808h
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 22000h | 26667h | 26667h | 26667h | 26667h | 26667h | 4667h
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 22000h | 26667h | 26667h | 26667h | 26667h | 26667h | 4667h
JPA1062-CWP-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 38412h | 31428h
JPA1062-CWP-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-CWP-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 38412h | 31428h
JPA1062-CWP-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 23280h
JPA1062-CWP-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-CWP-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 23280h
SWP-034-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SWP-034-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-034-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 3501h; 2023-07-30: 4782h | 4782h | 4782h | 2647h
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 3501h; 2023-07-30: 4782h | 4782h | 4782h | 2647h
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 683h | 4782h | 4782h | 4782h | 4782h | 683h
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 683h | 4782h | 4782h | 4782h | 4782h | 683h
ESD1048-CWP-470 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
ESD1048-CWP-470 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1048-CWP-470 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SMS57530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SMS57530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SMS57530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EEE1049-CWP-471 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EEE1049-CWP-471 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-CWP-471 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EEE1048-CWP-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 62888h | 48913h
EEE1048-CWP-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1048-CWP-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 62888h | 48913h
EEE1048-CWP-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 37267h | 37267h | 37267h
EEE1048-CWP-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1048-CWP-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 37267h | 37267h | 37267h
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 6039h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 1281h
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 6039h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 1281h
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h | 7321h
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 2818h | 3416h | 3416h | 3416h | 598h
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 2818h | 3416h | 3416h | 3416h | 598h
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 3416h | 3416h | 3416h | 3416h
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 3416h | 3416h | 3416h | 3416h
SMS55810 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SMS55810 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SMS55810 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 267208h | 323888h | 323888h | 323888h | 323888h | 323888h | 323888h | 323888h | 251013h
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 267208h | 323888h | 323888h | 323888h | 323888h | 323888h | 323888h | 323888h | 251013h
MSD1214-CWP-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 182476h | 139540h
MSD1214-CWP-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD1214-CWP-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 182476h | 139540h
EEE1049-CWP-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 217814h | 24202h
EEE1049-CWP-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-CWP-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 217814h | 24202h
EEE1049-CWP-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 114047h | 268347h | 154299h
EEE1049-CWP-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-CWP-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 114047h | 268347h | 154299h
EEE1049-CWP-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 114047h | 268347h | 154299h
EEE1049-CWP-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-CWP-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 114047h | 268347h | 154299h
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 16500h | 20000h | 20000h | 20000h | 3500h
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 16500h | 20000h | 20000h | 20000h | 3500h
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 30300h | 30300h | 30300h | 30300h
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 30300h | 30300h | 30300h | 30300h
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 3986h | 3986h | 3986h | 3986h
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 3986h | 3986h | 3986h | 3986h
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 531h | 3720h | 3720h | 3720h | 3720h | 3720h | 3720h | 1063h
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 531h | 3720h | 3720h | 3720h | 3720h | 3720h | 3720h | 1063h
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h | 8541h
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 23268h; 2023-07-09: 37229h; 2023-07-16: 37229h; 2023-07-23: 37229h; 2023-07-30: 13961h
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 23268h; 2023-07-09: 37229h; 2023-07-16: 37229h; 2023-07-23: 37229h; 2023-07-30: 13961h
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 16500h | 20000h | 20000h | 2023-06-04: 20000h; 2023-06-11: 3500h
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 16500h | 20000h | 20000h | 2023-06-04: 20000h; 2023-06-11: 3500h
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 2107h | 2554h | 2554h | 2554h | 447h
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 2107h | 2554h | 2554h | 2554h | 447h
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 1745h | 2384h | 2384h | 2384h | 1320h
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 1745h | 2384h | 2384h | 2384h | 1320h
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 1405h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 298h
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 1405h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 1703h | 298h
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 19384h | 23496h | 23496h | 2023-06-04: 23496h; 2023-06-11: 4112h
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 19384h | 23496h | 23496h | 2023-06-04: 23496h; 2023-06-11: 4112h
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 19384h | 23496h | 23496h | 23496h | 4112h
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 19384h | 23496h | 23496h | 23496h | 4112h
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 16056h | 21930h | 21930h | 21930h | 12140h
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 16056h | 21930h | 21930h | 21930h | 12140h
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 11308h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 2399h
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 11308h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 2399h
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 19384h | 23496h | 23496h | 2023-06-04: 23496h; 2023-06-11: 4112h
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 19384h | 23496h | 23496h | 2023-06-04: 23496h; 2023-06-11: 4112h
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 19384h | 23496h | 23496h | 23496h | 4112h
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 19384h | 23496h | 23496h | 23496h | 4112h
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 16056h | 21930h | 21930h | 21930h | 12140h
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 16056h | 21930h | 21930h | 21930h | 12140h
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 11308h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 2399h
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 11308h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 13706h | 2399h
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 19384h | 23496h | 23496h | 2023-06-04: 23496h; 2023-06-11: 4112h
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 19384h | 23496h | 23496h | 2023-06-04: 23496h; 2023-06-11: 4112h
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 19384h | 23496h | 23496h | 23496h | 4112h
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 19384h | 23496h | 23496h | 23496h | 4112h
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 16056h | 21930h | 21930h | 21930h | 12140h
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 16056h | 21930h | 21930h | 21930h | 12140h
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 9692h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 2056h
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 9692h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 11748h | 2056h
EEE1049-CWP-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 114047h | 268347h | 154299h
EEE1049-CWP-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-CWP-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 114047h | 268347h | 154299h
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 30714h | 37229h | 37229h | 37229h | 6515h
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 30714h | 37229h | 37229h | 37229h | 6515h
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 8377h | 37229h | 37229h | 37229h | 28852h
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 8377h | 37229h | 37229h | 37229h | 28852h
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 931h | 37229h | 37229h | 37229h | 36298h
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 931h | 37229h | 37229h | 37229h | 36298h
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA1062-PWPl-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 66289h | 228330h
JPA1062-PWPl-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-PWPl-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 66289h | 228330h
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 589h; 2023-07-09: 23570h; 2023-07-16: 23570h; 2023-07-23: 23570h; 2023-07-30: 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 23570h | 22980h
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 465h | 18614h | 18614h | 18614h | 18614h | 18614h | 18614h | 18614h | 18149h
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 465h | 18614h | 18614h | 18614h | 18614h | 18614h | 18614h | 18614h | 18149h
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 246h; 2023-07-09: 9821h; 2023-07-16: 9821h; 2023-07-23: 9821h; 2023-07-30: 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9821h | 9575h
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 7365h | 45830h | 45830h | 45830h | 45830h | 45830h | 45830h | 12276h
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 7365h | 45830h | 45830h | 45830h | 45830h | 45830h | 45830h | 12276h
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 655h; 2023-07-09: 26189h; 2023-07-16: 26189h; 2023-07-23: 26189h; 2023-07-30: 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 25534h
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 655h; 2023-07-09: 26189h; 2023-07-16: 26189h; 2023-07-23: 26189h; 2023-07-30: 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 26189h | 25534h
ESD1049-CWP-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 130689h | 111327h
ESD1049-CWP-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1049-CWP-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 130689h | 111327h
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 114135h | 130440h | 130440h | 59785h
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 114135h | 130440h | 130440h | 59785h
SMS50880 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SMS50880 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SMS50880 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 1358h | 1358h | 1358h | 1358h | 1358h
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 1358h | 1358h | 1358h | 1358h | 1358h
ESD1062-CWP-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
ESD1062-CWP-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1062-CWP-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 19855h; 2023-07-09: 24819h; 2023-07-16: 24819h; 2023-07-23: 24819h; 2023-07-30: 24819h | 24819h | 4964h
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 19855h; 2023-07-09: 24819h; 2023-07-16: 24819h; 2023-07-23: 24819h; 2023-07-30: 24819h | 24819h | 4964h
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 773h | 1732h | 1732h | 1732h | 1454h
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 773h | 1732h | 1732h | 1732h | 1454h
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 792h | 1862h | 1862h | 140h
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 792h | 1862h | 1862h | 140h
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 7554h | 7554h | 7554h | 7554h
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 7554h | 7554h | 7554h | 7554h
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 5036h | 7050h | 7050h | 7050h | 4029h
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 5036h | 7050h | 7050h | 7050h | 4029h
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 8241h
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 13735h | 8241h
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 7032h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 9514h
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 7032h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 9514h
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 1666h | 3920h | 3920h | 3920h | 2254h
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 1666h | 3920h | 3920h | 3920h | 2254h
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 2679h | 3659h | 3659h | 3659h | 2025h
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 2679h | 3659h | 3659h | 3659h | 2025h
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2665h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 3606h
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2665h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 6271h | 3606h
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 10341h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 6205h
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 10341h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 6205h
EEE1062-CWP-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 10942h | 12338h
EEE1062-CWP-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-CWP-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 10942h | 12338h
EEE1062-CWP-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 2188h | 2468h
EEE1062-CWP-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-CWP-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 2188h | 2468h
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 15790h | 25265h | 25265h | 25265h | 25265h | 25265h | 9474h
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 15790h | 25265h | 25265h | 25265h | 25265h | 25265h | 9474h
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 5684h | 35370h | 35370h | 35370h | 35370h | 4421h
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 5684h | 35370h | 35370h | 35370h | 35370h | 4421h
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 37897h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 22738h
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 37897h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 22738h
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 17551h | 21274h | 21274h | 21274h | 21274h | 21274h | 21274h | 3723h
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 17551h | 21274h | 21274h | 21274h | 21274h | 21274h | 21274h | 3723h
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 4145h | 5024h | 5024h | 5024h | 879h
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 4145h | 5024h | 5024h | 5024h | 879h
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 2034h | 6699h | 6699h | 4665h
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 2034h | 6699h | 6699h | 4665h
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 6141h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 5769h
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 6141h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 7444h | 5769h
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 1013h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4388h
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 1013h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4500h | 4388h
SWP-029-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 11941h | 52358h
SWP-029-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-029-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 11941h | 52358h
SWP-030-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 41336h | 55114h | 13779h
SWP-030-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-030-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 41336h | 55114h | 13779h
EBD1062-CWP-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 27620h | 78612h
EBD1062-CWP-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD1062-CWP-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 27620h | 78612h
EEE1062-CWP-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 2514h | 6798h
EEE1062-CWP-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-CWP-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 2514h | 6798h
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 559h | 22349h | 22349h | 10616h
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 559h | 22349h | 22349h | 10616h
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 8377h | 37229h | 37229h | 37229h | 28852h
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 8377h | 37229h | 37229h | 37229h | 28852h
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 3723h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 12823h
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 3723h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 16546h | 12823h
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 24819h | 24819h | 24819h | 24819h | 24819h | 24819h
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 24819h | 24819h | 24819h | 24819h | 24819h | 24819h
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 418h | 1856h | 1856h | 1856h | 1438h
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 418h | 1856h | 1856h | 1856h | 1438h
B38613 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38613 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38613 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3950 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3950 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3950 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 1490h | 3725h | 3725h | 372h
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 1490h | 3725h | 3725h | 372h
EEE1062-CWP-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 1257h | 3399h
EEE1062-CWP-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1062-CWP-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 1257h | 3399h
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 30998h | 72937h | 72937h | 72937h | 41939h
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 30998h | 72937h | 72937h | 72937h | 41939h
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 72937h | 72937h | 72937h | 72937h
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 72937h | 72937h | 72937h | 72937h
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 30998h | 72937h | 72937h | 72937h | 41939h
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 30998h | 72937h | 72937h | 72937h | 41939h
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 48624h | 48624h | 48624h | 48624h | 48624h | 48624h
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 48624h | 48624h | 48624h | 48624h | 48624h | 48624h
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 45585h | 72937h | 72937h | 72937h | 27351h
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 45585h | 72937h | 72937h | 72937h | 27351h
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 1823h; 2023-07-23: 72937h; 2023-07-30: 72937h | 72937h | 71113h
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 1823h; 2023-07-23: 72937h; 2023-07-30: 72937h | 72937h | 71113h
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 819h; 2023-06-25: 32766h; 2023-07-02: 32766h; 2023-07-09: 32766h; 2023-07-16: 31947h
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 819h; 2023-06-25: 32766h; 2023-07-02: 32766h; 2023-07-09: 32766h; 2023-07-16: 31947h
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 13653h | 30582h | 30582h | 30582h | 25667h
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 13653h | 30582h | 30582h | 30582h | 25667h
B38663 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38663 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38663 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [38 empty] | 662h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 15224h
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [38 empty] | 662h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 26477h | 15224h
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 16411h | 72937h | 72937h | 72937h | 56526h
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 16411h | 72937h | 72937h | 72937h | 56526h
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 1563h | 6946h | 6946h | 6946h | 5383h
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 1563h | 6946h | 6946h | 6946h | 5383h
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [74 empty] | 3820h | 6483h | 6483h | 6483h | 4515h
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [74 empty] | 3820h | 6483h | 6483h | 6483h | 4515h
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 3572h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 12303h
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 3572h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 15875h | 12303h
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 48624h | 48624h | 48624h | 48624h | 48624h | 48624h
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 48624h | 48624h | 48624h | 48624h | 48624h | 48624h
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 58349h; 2023-07-09: 72937h; 2023-07-16: 72937h; 2023-07-23: 72937h; 2023-07-30: 14587h
B39223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 2037h | 9053h | 9053h | 7016h
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 2037h | 9053h | 9053h | 7016h
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 5380h | 24832h | 24832h | 19452h
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 5380h | 24832h | 24832h | 19452h
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 2444h | 10864h | 10864h | 8420h
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 2444h | 10864h | 10864h | 8420h
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 181h | 7243h | 7243h | 7243h | 7243h | 7243h | 7243h | 7243h | 7243h | 7062h
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 181h | 7243h | 7243h | 7243h | 7243h | 7243h | 7243h | 7243h | 7243h | 7062h
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h |  |  | 12721h | 6360h
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h | 15901h |  |  | 12721h | 6360h
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h |  |  | 3880h | 970h
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h | 4850h |  |  | 3880h | 970h
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h |  |  | 1293h | 323h
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h | 1617h |  |  | 1293h | 323h
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 72937h | 72937h | 72937h | 72937h
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 72937h | 72937h | 72937h | 72937h
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 16411h | 72937h | 72937h | 72937h | 56526h
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 16411h | 72937h | 72937h | 72937h | 56526h
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 16411h | 72937h | 72937h | 72937h | 56526h
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 16411h | 72937h | 72937h | 72937h | 56526h
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 121h | 536h | 536h | 536h | 415h
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 121h | 536h | 536h | 536h | 415h
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 45h | 198h | 198h | 198h | 153h
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 45h | 198h | 198h | 198h | 153h
MEM0823-CWP-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 32592h
MEM0823-CWP-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0823-CWP-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 32592h
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 233h | 1035h | 1035h | 802h
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 233h | 1035h | 1035h | 802h
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 3442h | 8979h | 8979h | 8979h | 8979h | 8979h | 8979h | 5537h
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 3442h | 8979h | 8979h | 8979h | 8979h | 8979h | 8979h | 5537h
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 2689h | 11950h | 9959h |  | 11950h | 11950h | 11253h
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 2689h | 11950h | 9959h |  | 11950h | 11950h | 11253h
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [68 empty] | 71940h | 128848h | 128848h | 128848h | 128848h | 56908h
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [68 empty] | 71940h | 128848h | 128848h | 128848h | 128848h | 56908h
SWP-031-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 37955h | 53583h | 33490h
SWP-031-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-031-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 37955h | 53583h | 33490h
SWP-042-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 41336h | 22964h
SWP-042-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-042-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 41336h | 22964h
SWP-033-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 41336h | 22964h
SWP-033-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-033-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 41336h | 22964h
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 292h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1266h
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 292h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1299h | 1266h
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 108h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 467h
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 108h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 479h | 467h
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 12609h | 58196h | 58196h | 45587h
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 12609h | 58196h | 58196h | 45587h
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 25128h | 45005h | 45005h | 19877h
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 25128h | 45005h | 45005h | 19877h
MEM1214-CWP-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 12610h | 45590h
MEM1214-CWP-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 12610h | 45590h
MEM1214-CWP-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 156707h | 179093h
MEM1214-CWP-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 156707h | 179093h
A3090 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3090 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3090 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 59975h | 67896h | 67896h | 7921h
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 59975h | 67896h | 67896h | 7921h
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 223h | 500h | 500h | 500h | 420h
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 223h | 500h | 500h | 500h | 420h
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 83h | 185h | 185h | 185h | 155h
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 83h | 185h | 185h | 185h | 155h
B39243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38783 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38783 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38783 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38753 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38753 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38753 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39263 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39263 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39263 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39733 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39733 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39733 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39723 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39723 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39723 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B38683 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B38683 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B38683 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ESD1214-CWP-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 2908h | 2908h
ESD1214-CWP-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1214-CWP-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 2908h | 2908h
ESD1214-CWP-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
ESD1214-CWP-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1214-CWP-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 90476h | 90476h | 90476h | 54285h
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 90476h | 90476h | 90476h | 54285h
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 2633h | 45144h | 45144h | 45144h | 48154h | 54173h | 54173h | 21443h
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 2633h | 45144h | 45144h | 45144h | 48154h | 54173h | 54173h | 21443h
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 38900h; 2023-07-09: 48624h; 2023-07-16: 48624h; 2023-07-23: 48624h; 2023-07-30: 48624h | 48624h | 9725h
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 38900h; 2023-07-09: 48624h; 2023-07-16: 48624h; 2023-07-23: 48624h; 2023-07-30: 48624h | 48624h | 9725h
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 38900h; 2023-07-09: 48624h; 2023-07-16: 48624h; 2023-07-23: 48624h; 2023-07-30: 48624h | 48624h | 9725h
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 38900h; 2023-07-09: 48624h; 2023-07-16: 48624h; 2023-07-23: 48624h; 2023-07-30: 48624h | 48624h | 9725h
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 38900h; 2023-07-09: 48624h; 2023-07-16: 48624h; 2023-07-23: 48624h; 2023-07-30: 48624h | 48624h | 9725h
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 38900h; 2023-07-09: 48624h; 2023-07-16: 48624h; 2023-07-23: 48624h; 2023-07-30: 48624h | 48624h | 9725h
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 38900h; 2023-07-09: 48624h; 2023-07-16: 48624h; 2023-07-23: 48624h; 2023-07-30: 48624h | 48624h | 9725h
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 38900h; 2023-07-09: 48624h; 2023-07-16: 48624h; 2023-07-23: 48624h; 2023-07-30: 48624h | 48624h | 9725h
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 689h | 3060h | 3060h | 3060h | 2372h
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 689h | 3060h | 3060h | 3060h | 2372h
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 459h | 2856h | 2856h | 2856h | 2856h | 357h
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 459h | 2856h | 2856h | 2856h | 2856h | 357h
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 1669h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7233h
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 1669h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7418h | 7233h
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 13192h | 13192h | 13192h | 13192h | 13192h
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 13192h | 13192h | 13192h | 13192h | 13192h
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 10941h | 48624h | 48624h | 48624h | 48624h | 48624h | 37684h
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 10941h | 48624h | 48624h | 48624h | 48624h | 48624h | 37684h
TTU1340-EWPc-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 208391h | 83356h
TTU1340-EWPc-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU1340-EWPc-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 208391h | 83356h
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 1589h | 7061h | 7061h | 7061h | 7061h | 5472h
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 1589h | 7061h | 7061h | 7061h | 7061h | 5472h
A302490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A302490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A302490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A302500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A302500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A302500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A302510 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A302510 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A302510 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A302520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A302520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A302520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A302530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A302530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A302530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A302540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A302540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A302540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A303160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A303160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A303160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A163470 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A163470 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A163470 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A295440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A295440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A295440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A295450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A295450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A295450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A295460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A295460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A295460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300710 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300710 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300710 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300830 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300830 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300830 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300930 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300930 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300930 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300940 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300940 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300940 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300970 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300970 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300970 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A300380 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A300380 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A300380 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A302480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A302480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A302480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
5 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
5 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
5 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
3 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
3 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
3 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 305811h | 122325h
EWPp-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 305811h | 122325h
EWPp-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 183487h | 244649h
EWPp-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 183487h | 244649h
EWPp-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 305811h | 122325h
EWPp-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 305811h | 122325h
EWPp-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 244649h; 2023-07-09: 183487h
EWPp-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 244649h; 2023-07-09: 183487h
EWPp-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 183487h | 244649h
EWPp-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 183487h | 244649h
EWPp-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 305811h | 122325h
EWPp-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 305811h | 122325h
X3080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3090 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3090 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3090 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3100 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3100 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3100 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 244649h | 183487h
EWPp-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 244649h | 183487h
EWPp-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 305811h | 122325h
EWPp-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 305811h | 122325h
EWPp-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 305811h | 122325h
EWPp-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 305811h | 122325h
EWPp-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 305811h | 122325h
EWPp-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 305811h | 122325h
EWPp-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 305811h | 122325h
EWPp-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 305811h | 122325h
EWPp-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 122325h | 305811h
EWPp-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 122325h | 305811h
EWPp-DD-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 93080h
EWPp-DD-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 93080h
EWPp-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 305811h | 122325h
EWPp-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 305811h | 122325h
EWPp-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 183487h | 244649h
EWPp-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 183487h | 244649h
EWPp-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 244649h | 183487h
EWPp-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 244649h | 183487h
EWPp-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 305811h | 122325h
EWPp-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 305811h | 122325h
EWPp-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 305811h | 122325h
EWPp-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 305811h | 122325h
EWPp-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 305811h | 122325h
EWPp-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 305811h | 122325h
EWPp-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 361951h | 289561h
EWPp-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 361951h | 289561h
EWPp-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 465364h | 372292h
EWPp-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 465364h | 372292h
B39173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 305811h | 122325h
EWPp-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 305811h | 122325h
EWPp-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 305811h | 122325h
EWPp-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 305811h | 122325h
EWPp-DD-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [14 empty] | 99723h | 99723h | 79778h
EWPp-DD-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [14 empty] | 99723h | 99723h | 79778h
EWPp-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 305811h | 122325h
EWPp-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 305811h | 122325h
EWPp-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 305811h | 122325h
EWPp-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 305811h | 122325h
EWPp-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [14 empty] | 305811h | 122325h
EWPp-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [14 empty] | 305811h | 122325h
EWPp-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 305811h | 122325h
EWPp-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 305811h | 122325h
EWPp-OU-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EWPp-OU-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-OU-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EWPp-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 244649h | 183487h
EWPp-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 244649h | 183487h
EWPp-DD-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 99723h | 99723h | 79778h
EWPp-DD-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 99723h | 99723h | 79778h
EWPp-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [16 empty] | 244649h | 183487h
EWPp-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [16 empty] | 244649h | 183487h
EWPp-DD-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [14 empty] | 99723h | 99723h | 79778h
EWPp-DD-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [14 empty] | 99723h | 99723h | 79778h
EWPp-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [24 empty] | 244649h | 183487h
EWPp-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [24 empty] | 244649h | 183487h
EWPp-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 61162h | 305811h | 61162h
EWPp-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 61162h | 305811h | 61162h
EWPp-DD-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EWPp-DD-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units |  |  |  | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units |  |  |  | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | 34728h | -15338h | -15338h | -6135h
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [23 empty] | 39188h | 97971h | 97971h | 97971h | 39188h
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [23 empty] | 39188h | 97971h | 97971h | 97971h | 39188h
EWPp-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [23 empty] | 122325h | 305811h
EWPp-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [23 empty] | 122325h | 305811h
X3120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3150 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3150 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3150 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 305811h; 2023-07-09: 122325h
EWPp-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 305811h; 2023-07-09: 122325h
X3240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3260 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3260 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3260 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [24 empty] | 305811h | 122325h
EWPp-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [24 empty] | 305811h | 122325h
B7163 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7163 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7163 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 305811h | 122325h
EWPp-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 305811h | 122325h
EWPp-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 305811h | 122325h
EWPp-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 305811h | 122325h
A4840 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A4840 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A4840 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A4950 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A4950 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A4950 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B7513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B7513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B7513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B37693 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B37693 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B37693 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40753 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40753 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40753 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3010 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3010 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3010 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MIS30270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MIS30270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MIS30270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 183487h | 244649h
EWPp-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 183487h | 244649h
EWPp-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 183487h | 244649h
EWPp-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 183487h | 244649h
A3970 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3970 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3970 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3990 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3990 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3990 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A5140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A5140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A5140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [18 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [18 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [18 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [18 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 103413h | 82731h
EWPp-DD-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 103413h | 82731h
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 58782h | 97971h | 97971h | 97971h | 19594h
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 58782h | 97971h | 97971h | 97971h | 19594h
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 78376h | 97971h | 97971h | 97971h
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 78376h | 97971h | 97971h | 97971h
X3020 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 104712h | 62827h
X3020 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3020 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 104712h | 62827h
EWPp-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 122325h | 305811h
EWPp-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 122325h | 305811h
EWPp-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 305811h; 2023-06-11: 122325h
EWPp-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 305811h; 2023-06-11: 122325h
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 97971h | 97971h | 97971h | 78376h
EWPp-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 305811h | 122325h
EWPp-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 305811h | 122325h
EWPp-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 305811h | 122325h
EWPp-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 305811h | 122325h
EWPp-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 305811h | 122325h
EWPp-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 305811h | 122325h
EWPp-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 305811h | 122325h
EWPp-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 305811h | 122325h
EWPp-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 183487h | 244649h
EWPp-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 183487h | 244649h
EWPp-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 183487h | 244649h
EWPp-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 183487h | 244649h
EWPp-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 183487h; 2023-07-30: 244649h
EWPp-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 183487h; 2023-07-30: 244649h
EWPp-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 305811h | 122325h
EWPp-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 305811h | 122325h
EWPp-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [24 empty] | 305811h | 122325h
EWPp-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [24 empty] | 305811h | 122325h
EWPp-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 183487h; 2023-07-30: 244649h
EWPp-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 183487h; 2023-07-30: 244649h
EWPp-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 183487h; 2023-07-30: 244649h
EWPp-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 183487h; 2023-07-30: 244649h
EWPp-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 305811h | 122325h
EWPp-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 305811h | 122325h
EWPp-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 305810h | 183486h
EWPp-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 305810h | 183486h
EWPp-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 305811h | 122325h
EWPp-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 305811h | 122325h
EWPp-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 61162h | 305811h | 61162h
EWPp-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 61162h | 305811h | 61162h
EWPp-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 305811h | 122325h
EWPp-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 305811h | 122325h
EWPp-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 305811h | 122325h
EWPp-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 305811h | 122325h
B40813 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40813 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40813 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39993 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39993 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39993 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3660 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3660 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3660 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A5100 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A5100 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A5100 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A5110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A5110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A5110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A5120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A5120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A5120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 244649h | 183487h
EWPp-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 244649h | 183487h
EWPp-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 183487h | 244649h
EWPp-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 183487h | 244649h
B40603 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40603 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40603 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 1505417h | 1505417h | 1505417h | 1505417h | 2023-06-04: 1505417h; 2023-06-11: 1505417h
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 1505417h | 1505417h | 1505417h | 1505417h | 2023-06-04: 1505417h; 2023-06-11: 1505417h
C3060 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
C3060 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
C3060 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
C3080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
C3080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
C3080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
C3040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
C3040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
C3040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
C3110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
C3110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
C3110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EWPp-OU-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 378496h | 630827h | 126165h
EWPp-OU-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-OU-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 378496h | 630827h | 126165h
EWPp-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 103413h | 82731h
EWPp-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 103413h | 82731h
EWPp-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [23 empty] | 122325h | 305811h
EWPp-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [23 empty] | 122325h | 305811h
EWPp-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 122325h | 305811h
EWPp-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EWPp-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 122325h | 305811h
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [14 empty] | 8872h | 31051h | 31051h | 31051h | 26615h
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [14 empty] | 8872h | 31051h | 31051h | 31051h | 26615h
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [18 empty] | 35487h | 62102h | 62102h | 62102h | 35487h
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [18 empty] | 35487h | 62102h | 62102h | 62102h | 35487h
SUWP-AT-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [16 empty] | 85760h | 120064h | 51456h
SUWP-AT-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [16 empty] | 85760h | 120064h | 51456h
SUWP-AS-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [20 empty] | 285867h | 228693h
SUWP-AS-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [20 empty] | 285867h | 228693h
SUWP-OC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [14 empty] | 31051h | 31051h | 31051h | 31051h | 4436h
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [14 empty] | 31051h | 31051h | 31051h | 31051h | 4436h
SUWP-RP-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 1387h | 1618h | 1387h
SUWP-RP-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 1387h | 1618h | 1387h
SUWP-AT-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 3768h; 2023-06-18: 4396h; 2023-06-25: 628h
SUWP-AT-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 3768h; 2023-06-18: 4396h; 2023-06-25: 628h
SUWP-AS-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 17576h
SUWP-AS-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 17576h
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 6013h | 6013h | 6013h | 6013h | 859h
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 6013h | 6013h | 6013h | 6013h | 859h
SUWP-AT-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 10678h | 24916h | 14238h
SUWP-AT-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 10678h | 24916h | 14238h
SUWP-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 1904h
SUWP-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 1904h
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 2699h | 6297h | 6297h | 6297h | 4498h
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 2699h | 6297h | 6297h | 6297h | 4498h
SUWP-AT-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 22365h | 26092h | 3727h
SUWP-AT-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 22365h | 26092h | 3727h
SUWP-AS-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 52180h | 52180h
SUWP-AS-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 52180h | 52180h
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 4014h | 5620h | 5620h | 5620h | 5620h | 5620h | 5620h | 5620h | 5620h | 3211h
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 4014h | 5620h | 5620h | 5620h | 5620h | 5620h | 5620h | 5620h | 5620h | 3211h
SUWP-OC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-OC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 1244h | 3732h
SUWP-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 1244h | 3732h
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 204h | 713h | 713h | 306h
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 204h | 713h | 713h | 306h
SUWP-AT-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 552h | 1932h | 1380h
SUWP-AT-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 552h | 1932h | 1380h
SUWP-AS-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 7728h
SUWP-AS-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 7728h
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [38 empty] | 416h | 416h | 416h | 416h | 416h | 416h | 416h | 416h | 416h | 119h
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [38 empty] | 416h | 416h | 416h | 416h | 416h | 416h | 416h | 416h | 416h | 119h
SUWP-OC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 2124h | 2023-06-04: 6372h
SUWP-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 2124h | 2023-06-04: 6372h
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 52h; 2023-07-02: 52h; 2023-07-09: 52h; 2023-07-16: 52h; 2023-07-23: 7h
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 52h; 2023-07-02: 52h; 2023-07-09: 52h; 2023-07-16: 52h; 2023-07-23: 7h
SUWP-AT-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 220h | 220h
SUWP-AT-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 220h | 220h
SUWP-AS-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 872h
SUWP-AS-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 872h
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 34h | 47h | 47h | 47h | 47h | 47h | 47h | 47h | 47h | 27h
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 34h | 47h | 47h | 47h | 47h | 47h | 47h | 47h | 47h | 27h
SUWP-AS-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 23472h; 2023-06-11: 23472h
SUWP-AS-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 23472h; 2023-06-11: 23472h
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 361h | 2528h | 2528h | 2528h | 2528h | 2528h | 2528h | 2528h | 2528h | 2528h | 361h
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 361h | 2528h | 2528h | 2528h | 2528h | 2528h | 2528h | 2528h | 2528h | 2528h | 361h
SUWP-OC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 2934h | 8802h
SUWP-EC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 2934h | 8802h
SUWP-AS-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 125280h | 2023-06-04: 41760h
SUWP-AS-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 125280h | 2023-06-04: 41760h
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 2570h | 8994h | 8994h | 8994h | 8994h | 8994h | 8994h | 8994h | 8994h | 8994h
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 2570h | 8994h | 8994h | 8994h | 8994h | 8994h | 8994h | 8994h | 8994h | 8994h
SUWP-OC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 41760h
SUWP-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 41760h
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 615h | 1076h | 1076h | 154h
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 615h | 1076h | 1076h | 154h
SUWP-AT-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 2083h | 2916h | 833h
SUWP-AT-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 2083h | 2916h | 833h
SUWP-AS-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 11672h
SUWP-AS-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 11672h
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 359h | 628h | 628h | 628h | 628h | 628h | 628h | 628h | 628h | 449h
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 359h | 628h | 628h | 628h | 628h | 628h | 628h | 628h | 628h | 449h
SUWP-AS-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 51640h
SUWP-AS-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 51640h
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 2384h | 2781h | 2781h | 2781h | 2781h | 2781h | 2781h | 2781h | 2781h | 1192h
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 2384h | 2781h | 2781h | 2781h | 2781h | 2781h | 2781h | 2781h | 2781h | 1192h
SUWP-OC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-AS-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 13760h
SUWP-AS-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 13760h
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 741h | 741h | 741h | 741h | 741h | 741h | 741h | 741h | 741h | 212h
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 741h | 741h | 741h | 741h | 741h | 741h | 741h | 741h | 741h | 212h
SUWP-OC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units |  |  | 48684h | 68158h | 68158h | 68158h | 29210h
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units |  |  | 17648h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 17648h
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units |  |  | 17648h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 24707h | 17648h
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [13 empty] | 9737h | 68158h | 68158h | 68158h | 68158h
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | [13 empty] | 8557h
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [13 empty] | 8557h | 70224h | 70224h | 70224h | 70224h | 10032h
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [18 empty] | 30253h | 70591h | 70591h | 30253h
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [18 empty] | 30253h | 70591h | 70591h | 30253h
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 194h | 1356h | 1356h | 2023-06-04: 1356h; 2023-06-11: 1356h
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 194h | 1356h | 1356h | 2023-06-04: 1356h; 2023-06-11: 1356h
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 1162h; 2023-06-25: 1356h; 2023-07-02: 1356h; 2023-07-09: 1356h; 2023-07-16: 387h
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 1162h; 2023-06-25: 1356h; 2023-07-02: 1356h; 2023-07-09: 1356h; 2023-07-16: 387h
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 1548h; 2023-07-23: 2709h; 2023-07-30: 2709h | 2709h | 1548h
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 1548h; 2023-07-23: 2709h; 2023-07-30: 2709h | 2709h | 1548h
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 576h | 2015h | 2015h | 2015h | 2015h | 2015h | 576h
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 576h | 2015h | 2015h | 2015h | 2015h | 2015h | 576h
SUWP-AS-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 17965h | 4491h
SUWP-AS-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 17965h | 4491h
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [14 empty] | 9717h | 9717h | 9717h | 9717h | 1388h
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [14 empty] | 9717h | 9717h | 9717h | 9717h | 1388h
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [15 empty] | 5553h | 9717h | 9717h | 9717h | 5553h
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [15 empty] | 5553h | 9717h | 9717h | 9717h | 5553h
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [19 empty] | 5552h | 19432h | 19432h | 19432h | 16656h
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [19 empty] | 5552h | 19432h | 19432h | 19432h | 16656h
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 1830h | 12807h | 12807h | 12807h | 12807h | 12807h | 12807h | 1830h
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 1830h | 12807h | 12807h | 12807h | 12807h | 12807h | 12807h | 1830h
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 32202h | 56353h | 56353h | 16101h
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 32202h | 56353h | 56353h | 16101h
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 1745h | 12212h | 12212h | 12212h | 12212h
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 1745h | 12212h | 12212h | 12212h | 12212h
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 10467h | 12212h | 2023-06-04: 12212h; 2023-06-11: 12212h; 2023-06-18: 3489h
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 10467h | 12212h | 2023-06-04: 12212h; 2023-06-11: 12212h; 2023-06-18: 3489h
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 13956h; 2023-06-25: 24424h; 2023-07-02: 24424h; 2023-07-09: 24424h; 2023-07-16: 13956h
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 13956h; 2023-06-25: 24424h; 2023-07-02: 24424h; 2023-07-09: 24424h; 2023-07-16: 13956h
SUWP-OC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [17 empty] | 137884h | 137884h
SUWP-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [17 empty] | 137884h | 137884h
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 756h | 2647h | 2647h | 1134h
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 756h | 2647h | 2647h | 1134h
SUWP-AT-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 2053h | 7184h | 5131h
SUWP-AT-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 2053h | 7184h | 5131h
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 889h; 2023-06-25: 1556h; 2023-07-02: 1556h; 2023-07-09: 1334h
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 889h; 2023-06-25: 1556h; 2023-07-02: 1556h; 2023-07-09: 1334h
SUWP-OC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 666h | 1998h
SUWP-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 666h | 1998h
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 2201h | 7703h | 7703h | 2023-06-04: 7703h; 2023-06-11: 6602h
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 2201h | 7703h | 7703h | 2023-06-04: 7703h; 2023-06-11: 6602h
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 152h | 177h | 177h | 177h | 177h | 177h | 177h | 177h | 177h | 76h
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 152h | 177h | 177h | 177h | 177h | 177h | 177h | 177h | 177h | 76h
SUWP-OC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 412h | 412h
SUWP-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 412h | 412h
SUWP-RP-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 1373h | 1373h | 981h
SUWP-RP-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 1373h | 1373h | 981h
SUWP-AT-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 3732h | 3732h
SUWP-AT-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 3732h | 3732h
SUWP-AS-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [60 empty] | 11190h | 3730h
SUWP-AS-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [60 empty] | 11190h | 3730h
SUWP-OC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 78h | 26h
SUWP-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 78h | 26h
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 606h | 606h | 2023-06-04: 606h; 2023-06-11: 606h; 2023-06-18: 87h
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 606h | 606h | 2023-06-04: 606h; 2023-06-11: 606h; 2023-06-18: 87h
SUWP-AT-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 2512h; 2023-07-23: 2512h
SUWP-AT-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 2512h; 2023-07-23: 2512h
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 4599h; 2023-07-23: 16097h; 2023-07-30: 16097h | 16097h | 16097h | 16097h | 16097h
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 4599h; 2023-07-23: 16097h; 2023-07-30: 16097h | 16097h | 16097h | 16097h | 16097h
SUWP-AS-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 121421h | 80947h
SUWP-AS-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 121421h | 80947h
SUWP-AS-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 28736h
SUWP-AS-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 28736h
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 442h | 1547h | 1547h | 1547h | 1547h | 1547h | 1547h | 1547h | 1547h | 1547h
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 442h | 1547h | 1547h | 1547h | 1547h | 1547h | 1547h | 1547h | 1547h | 1547h
SUWP-OC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 3592h | 3592h
SUWP-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 3592h | 3592h
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [18 empty] | 30838h | 30838h | 30838h | 30838h | 30838h | 30838h | 8811h
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [18 empty] | 30838h | 30838h | 30838h | 30838h | 30838h | 30838h | 8811h
SUWP-AT-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [23 empty] | 215378h | 172302h
SUWP-AT-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [23 empty] | 215378h | 172302h
SUWP-AT-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 9118h; 2023-06-25: 31912h; 2023-07-02: 22794h
SUWP-AT-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 9118h; 2023-06-25: 31912h; 2023-07-02: 22794h
SUWP-AS-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 127648h
SUWP-AS-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 127648h
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 6873h; 2023-07-30: 6873h | 6873h | 6873h | 6873h | 6873h | 6873h | 6873h | 6873h | 1964h
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 6873h; 2023-07-30: 6873h | 6873h | 6873h | 6873h | 6873h | 6873h | 6873h | 6873h | 1964h
SUWP-OC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 31912h
SUWP-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 31912h
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 574h | 804h | 804h | 804h | 804h | 804h | 804h | 804h | 804h | 459h
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 574h | 804h | 804h | 804h | 804h | 804h | 804h | 804h | 804h | 459h
SUWP-OC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 2796h | 932h
SUWP-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 2796h | 932h
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 47h | 165h | 165h | 71h
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 47h | 165h | 165h | 71h
SUWP-AT-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 128h; 2023-07-09: 448h; 2023-07-16: 320h
SUWP-AT-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 128h; 2023-07-09: 448h; 2023-07-16: 320h
SUWP-AS-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 193840h | 581520h
SUWP-AS-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 193840h | 581520h
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 15824h | 55383h | 55383h | 55383h | 55383h | 55383h | 55383h | 39559h
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 15824h | 55383h | 55383h | 55383h | 55383h | 55383h | 55383h | 39559h
SUWP-OC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [14 empty] | 193840h
SUWP-EC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [14 empty] | 193840h
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 8983h | 10480h | 10480h | 10480h | 2994h
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 8983h | 10480h | 10480h | 10480h | 2994h
SUWP-AT-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 24809h | 43416h | 18607h
SUWP-AT-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 24809h | 43416h | 18607h
SUWP-AS-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 173672h
SUWP-AS-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 173672h
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 9351h | 9351h | 9351h | 9351h | 9351h | 9351h | 9351h | 9351h | 9351h | 2672h
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 9351h | 9351h | 9351h | 9351h | 9351h | 9351h | 9351h | 9351h | 9351h | 2672h
SUWP-OC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 21708h | 21708h
SUWP-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 21708h | 21708h
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 28h | 96h | 96h | 96h | 96h | 96h | 96h | 96h | 96h | 96h
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 28h | 96h | 96h | 96h | 96h | 96h | 96h | 96h | 96h | 96h
SUWP-OC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 448h
SUWP-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 448h
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 423h | 592h | 592h | 592h | 592h | 592h | 592h | 592h | 592h | 338h
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 423h | 592h | 592h | 592h | 592h | 592h | 592h | 592h | 592h | 338h
SUWP-OC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 2064h | 688h
SUWP-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 2064h | 688h
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 117h | 821h | 821h | 821h | 821h
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 117h | 821h | 821h | 821h | 821h
SUWP-AT-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 486h; 2023-06-18: 3404h; 2023-06-25: 2918h
SUWP-AT-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 486h; 2023-06-18: 3404h; 2023-06-25: 2918h
SUWP-AS-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 2346h | 782h
SUWP-AS-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 2346h | 782h
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 72h | 168h | 168h | 168h | 168h | 168h | 168h | 168h | 168h | 144h
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 72h | 168h | 168h | 168h | 168h | 168h | 168h | 168h | 168h | 144h
SUWP-OC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-AS-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 3402h | 10206h
SUWP-AS-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 3402h | 10206h
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 105h; 2023-07-30: 733h | 733h | 733h | 733h | 733h | 733h | 733h | 733h | 733h | 105h
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 105h; 2023-07-30: 733h | 733h | 733h | 733h | 733h | 733h | 733h | 733h | 733h | 105h
SUWP-OC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-OC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 362h | 2532h | 362h
SUWP-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 362h | 2532h | 362h
SUWP-RP-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 857h | 1200h | 2023-06-04: 1200h
SUWP-RP-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 857h | 1200h | 2023-06-04: 1200h
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 551h | 772h | 772h | 772h | 772h | 772h | 772h | 772h | 551h
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 551h | 772h | 772h | 772h | 772h | 772h | 772h | 772h | 551h
SUWP-AT-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 3613h; 2023-07-23: 2891h
SUWP-AT-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 3613h; 2023-07-23: 2891h
SUWP-AS-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 3423h | 4792h | 4792h
SUWP-AS-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 3423h | 4792h | 4792h
SUWP-OC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 26422h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 6605h
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 26422h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 33027h | 6605h
SUWP-AS-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 99656h
SUWP-AS-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 99656h
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 1533h | 5367h | 5367h | 5367h | 5367h | 5367h | 5367h | 5367h | 5367h | 5367h
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 1533h | 5367h | 5367h | 5367h | 5367h | 5367h | 5367h | 5367h | 5367h | 5367h
SUWP-OC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [24 empty] | 18684h | 6228h
SUWP-EC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [24 empty] | 18684h | 6228h
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 3794h | 4426h | 4426h | 4426h | 1265h
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 3794h | 4426h | 4426h | 4426h | 1265h
SUWP-AT-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 10475h | 18332h | 7857h
SUWP-AT-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 10475h | 18332h | 7857h
SUWP-AS-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 18334h; 2023-07-02: 55002h
SUWP-AS-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 18334h; 2023-07-02: 55002h
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 476h | 1665h | 1665h | 1665h | 1427h
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 476h | 1665h | 1665h | 1665h | 1427h
SUWP-AT-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 6896h | 6896h
SUWP-AT-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 6896h | 6896h
SUWP-AS-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 13796h; 2023-06-11: 13796h
SUWP-AS-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 13796h; 2023-06-11: 13796h
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 212h | 1485h | 1485h | 1485h | 1485h | 1485h | 1485h | 1485h | 1485h | 1485h | 212h
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 212h | 1485h | 1485h | 1485h | 1485h | 1485h | 1485h | 1485h | 1485h | 1485h | 212h
SUWP-OC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 6896h
SUWP-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 6896h
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 131h | 460h | 460h | 460h | 394h
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 131h | 460h | 460h | 460h | 394h
SUWP-AT-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 543h; 2023-07-02: 1900h; 2023-07-09: 1357h
SUWP-AT-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 543h; 2023-07-02: 1900h; 2023-07-09: 1357h
SUWP-AS-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 3804h | 3804h
SUWP-AS-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 3804h | 3804h
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 812h; 2023-07-23: 947h; 2023-07-30: 947h | 947h | 947h | 947h | 947h | 947h | 947h | 406h
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 812h; 2023-07-23: 947h; 2023-07-30: 947h | 947h | 947h | 947h | 947h | 947h | 947h | 406h
SUWP-OC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 2196h | 2196h
SUWP-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 2196h | 2196h
SUWP-OC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 162h; 2023-06-18: 54h
SUWP-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 162h; 2023-06-18: 54h
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 745h; 2023-06-18: 745h; 2023-06-25: 745h; 2023-07-02: 745h; 2023-07-09: 106h
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 745h; 2023-06-18: 745h; 2023-06-25: 745h; 2023-07-02: 745h; 2023-07-09: 106h
SUWP-AT-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 883h; 2023-07-23: 3092h; 2023-07-30: 2209h
SUWP-AT-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 883h; 2023-07-23: 3092h; 2023-07-30: 2209h
SUWP-AS-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 6184h | 6184h
SUWP-AS-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 6184h | 6184h
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 666h | 666h | 666h | 666h | 666h | 666h | 666h | 666h | 666h | 190h
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 666h | 666h | 666h | 666h | 666h | 666h | 666h | 666h | 666h | 190h
SUWP-OC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 12296h | 28691h | 28691h | 28691h | 28691h | 28691h | 28691h | 16395h
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 12296h | 28691h | 28691h | 28691h | 28691h | 28691h | 28691h | 16395h
SUWP-OC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [13 empty] | 37656h | 12552h
SUWP-EC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | [13 empty] | 25104h
SUWP-EC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [13 empty] | 25104h | -20082h
SUWP-OU-PF1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [8 empty] | 7956h | 39780h
SUWP-OU-PF1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | [8 empty] | 7956h | 39780h
SUWP-OU-PF1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [8 empty] | 7956h | 39780h
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [14 empty] | 13167h | 23043h | 23043h | 23043h | 13167h
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [14 empty] | 13167h | 23043h | 23043h | 23043h | 13167h
SUWP-AT-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [18 empty] | 27275h | 47732h | 20457h
SUWP-AT-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [18 empty] | 27275h | 47732h | 20457h
SUWP-AS-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-AS-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 8812h | 20561h | 20561h | 20561h | 20561h | 20561h | 20561h | 20561h | 20561h | 17624h
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 8812h | 20561h | 20561h | 20561h | 20561h | 20561h | 20561h | 20561h | 20561h | 17624h
SUWP-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 19566h | 6522h
SUWP-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 19566h | 6522h
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 1383h; 2023-06-11: 1937h; 2023-06-18: 1937h; 2023-06-25: 1937h; 2023-07-02: 830h
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 1383h; 2023-06-11: 1937h; 2023-06-18: 1937h; 2023-06-25: 1937h; 2023-07-02: 830h
SUWP-AT-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 8020h; 2023-07-23: 8020h
SUWP-AT-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 8020h; 2023-07-23: 8020h
SUWP-AS-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 10048h
SUWP-AS-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 10048h
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 541h | 541h | 541h | 541h | 541h | 541h | 541h | 541h | 541h | 155h
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 541h | 541h | 541h | 541h | 541h | 541h | 541h | 541h | 541h | 155h
SUWP-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 2580h | 860h
SUWP-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 2580h | 860h
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 151h | 353h | 2023-06-04: 353h; 2023-06-11: 353h; 2023-06-18: 252h
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 151h | 353h | 2023-06-04: 353h; 2023-06-11: 353h; 2023-06-18: 252h
SUWP-AT-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 627h; 2023-07-23: 1464h; 2023-07-30: 837h
SUWP-AT-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 627h; 2023-07-23: 1464h; 2023-07-30: 837h
SUWP-AS-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 4386h | 1462h
SUWP-AS-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 4386h | 1462h
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 135h | 315h | 315h | 315h | 315h | 315h | 315h | 315h | 315h | 270h
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 135h | 315h | 315h | 315h | 315h | 315h | 315h | 315h | 315h | 270h
SUWP-OC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 1098h | 366h
SUWP-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 1098h | 366h
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 83h | 83h | 83h | 83h | 12h
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 83h | 83h | 83h | 83h | 12h
SUWP-AT-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 149h | 348h | 199h
SUWP-AT-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 149h | 348h | 199h
SUWP-AS-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 900h | 900h
SUWP-AS-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 900h | 900h
SUWP-OC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 1884h | 628h
SUWP-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 1884h | 628h
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 664h | 664h | 664h | 664h | 95h
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 664h | 664h | 664h | 664h | 95h
SUWP-AT-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 2748h | 2748h
SUWP-AT-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 2748h | 2748h
SUWP-AS-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 10992h
SUWP-AS-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 10992h
SUWP-AS-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 1038h | 346h
SUWP-AS-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 1038h | 346h
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 32h | 75h | 75h | 75h | 75h | 75h | 75h | 75h | 75h | 64h
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 32h | 75h | 75h | 75h | 75h | 75h | 75h | 75h | 75h | 64h
SUWP-OC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 258h | 86h
SUWP-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 258h | 86h
SUWP-RP-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 419h; 2023-06-18: 587h; 2023-06-25: 587h
SUWP-RP-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 419h; 2023-06-18: 587h; 2023-06-25: 587h
SUWP-AT-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 1140h | 1596h | 456h
SUWP-AT-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 1140h | 1596h | 456h
SUWP-AS-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 6376h
SUWP-AS-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 6376h
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 1117h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1397h
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 1117h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1397h
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 1054h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 1054h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h | 3688h
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [37 empty] | 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 4233h
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [37 empty] | 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 4233h
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 5644h; 2023-07-30: 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 8466h
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 5644h; 2023-07-30: 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 9877h | 8466h
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 4215h
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 14752h | 4215h
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 246h | 344h | 344h | 344h | 344h | 344h | 344h | 344h | 344h | 196h
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 246h | 344h | 344h | 344h | 344h | 344h | 344h | 344h | 344h | 196h
SUWP-OC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 398h | 2023-06-04: 1194h
SUWP-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 398h | 2023-06-04: 1194h
SUWP-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 144h | 1008h | 144h
SUWP-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 144h | 1008h | 144h
SUWP-RP-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 463h | 648h | 2023-06-04: 185h
SUWP-RP-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 463h | 648h | 2023-06-04: 185h
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 268h | 626h | 626h | 626h | 447h
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 268h | 626h | 626h | 626h | 447h
SUWP-AT-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 2016h; 2023-07-09: 576h
SUWP-AT-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 2016h; 2023-07-09: 576h
SUWP-OC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 16552h | 115862h | 115862h | 115862h | 115862h
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 16552h | 115862h | 115862h | 115862h | 115862h
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 22069h | 2023-06-04: 154483h; 2023-06-11: 154483h; 2023-06-18: 154483h; 2023-06-25: 154483h
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 22069h | 2023-06-04: 154483h; 2023-06-11: 154483h; 2023-06-18: 154483h; 2023-06-25: 154483h
SUWP-AT-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 320000h | 320000h
SUWP-AT-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 320000h | 320000h
SUWP-AS-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 426667h; 2023-06-25: 1493333h
SUWP-AS-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 426667h; 2023-06-25: 1493333h
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 1767h | 1767h | 1767h | 1767h | 252h
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 1767h | 1767h | 1767h | 1767h | 252h
SUWP-AT-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 3139h | 7324h | 4185h
SUWP-AT-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 3139h | 7324h | 4185h
SUWP-AS-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 21972h | 7324h
SUWP-AS-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 21972h | 7324h
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 676h | 1577h | 1577h | 1577h | 1577h | 1577h | 1577h | 1577h | 1577h | 1352h
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 676h | 1577h | 1577h | 1577h | 1577h | 1577h | 1577h | 1577h | 1577h | 1352h
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 189h | 189h | 189h | 189h | 27h
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 189h | 189h | 189h | 189h | 27h
SUWP-AT-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 780h | 780h
SUWP-AT-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 780h | 780h
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 143h | 1000h | 1000h | 1000h | 1000h
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 143h | 1000h | 1000h | 1000h | 1000h
SUWP-OC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 5490h | 1830h
SUWP-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 5490h | 1830h
SUWP-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 588h | 196h
SUWP-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 588h | 196h
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 110h | 110h | 110h | 110h | 16h
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 110h | 110h | 110h | 110h | 16h
SUWP-AT-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 130h | 456h | 326h
SUWP-AT-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 130h | 456h | 326h
SUWP-AS-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 1832h
SUWP-AS-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 1832h
SUWP-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 3400h
SUWP-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 3400h
SUWP-RP-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 486h | 486h | 347h
SUWP-RP-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 486h | 486h | 347h
SUWP-AT-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 1320h; 2023-06-25: 1320h
SUWP-AT-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 1320h; 2023-06-25: 1320h
SUWP-AS-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 5280h
SUWP-AS-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 5280h
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 284h; 2023-07-30: 284h | 284h | 284h | 284h | 284h | 284h | 284h | 284h | 81h
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 284h; 2023-07-30: 284h | 284h | 284h | 284h | 284h | 284h | 284h | 284h | 81h
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 857h | 1000h | 1000h | 1000h | 286h
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 857h | 1000h | 1000h | 1000h | 286h
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 1142h | 1999h | 1999h | 1999h | 1142h
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 1142h | 1999h | 1999h | 1999h | 1142h
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 376h | 1317h | 1317h | 1317h | 1317h | 1317h | 1317h
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 376h | 1317h | 1317h | 1317h | 1317h | 1317h | 1317h
SUWP-AS-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 7643h | 8917h
SUWP-AS-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 7643h | 8917h
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [22 empty] | 397680h | 636287h | 636287h | 636287h | 493123h
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [22 empty] | 397680h | 636287h | 636287h | 636287h | 493123h
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [18 empty] | 12130h | 84908h | 84908h | 84908h | 84908h
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [18 empty] | 12130h | 84908h | 84908h | 84908h | 84908h
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 16552h | 115862h | 115862h | 115862h | 115862h
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 16552h | 115862h | 115862h | 115862h | 115862h
SUWP-AS-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [24 empty] | 469013h | 938027h
SUWP-AS-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [24 empty] | 469013h | 938027h
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 179h | 1253h | 1253h | 1253h | 1253h
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 179h | 1253h | 1253h | 1253h | 1253h
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 98h | 98h | 98h | 98h | 98h | 98h | 98h | 98h | 98h | 28h
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 98h | 98h | 98h | 98h | 98h | 98h | 98h | 98h | 98h | 28h
SUWP-OC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 342h | 114h
SUWP-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 342h | 114h
SUWP-OC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 990h | 330h
SUWP-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 990h | 330h
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 265h | 371h | 371h | 371h | 159h
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 265h | 371h | 371h | 371h | 159h
SUWP-AT-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 1097h; 2023-06-18: 1536h; 2023-06-25: 439h
SUWP-AT-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 1097h; 2023-06-18: 1536h; 2023-06-25: 439h
SUWP-AS-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 6144h
SUWP-AS-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 6144h
SUWP-AS-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 16419h | 19156h | 5473h
SUWP-AS-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 16419h | 19156h | 5473h
SUWP-RP-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 83h; 2023-07-30: 83h | 59h
SUWP-RP-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 83h; 2023-07-30: 83h | 59h
SUWP-AT-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 163h | 228h | 65h
SUWP-AT-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 163h | 228h | 65h
SUWP-AS-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 904h
SUWP-AS-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 904h
SUWP-AT-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 17400h; 2023-07-16: 24360h; 2023-07-23: 6960h
SUWP-AT-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 17400h; 2023-07-16: 24360h; 2023-07-23: 6960h
SUWP-AS-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 97448h
SUWP-AS-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 97448h
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 750h | 5247h | 5247h | 5247h | 5247h | 5247h | 5247h | 5247h | 5247h | 5247h | 750h
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 750h | 5247h | 5247h | 5247h | 5247h | 5247h | 5247h | 5247h | 5247h | 5247h | 750h
SUWP-OC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 18270h | 2023-06-04: 6090h
SUWP-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 18270h | 2023-06-04: 6090h
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 1105h | 1105h | 1105h | 1105h | 2023-06-04: 158h
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 1105h | 1105h | 1105h | 1105h | 2023-06-04: 158h
SUWP-AT-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 4580h; 2023-07-09: 4580h
SUWP-AT-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 4580h; 2023-07-09: 4580h
SUWP-AS-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 18320h
SUWP-AS-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 18320h
SUWP-OC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 12636h | 4212h
SUWP-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 12636h | 4212h
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 12586h | 12586h | 12586h | 12586h | 1798h
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 12586h | 12586h | 12586h | 12586h | 1798h
SUWP-AT-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 52140h | 52140h
SUWP-AT-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 52140h | 52140h
SUWP-AS-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 208568h
SUWP-AS-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 208568h
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 5332h | 18663h | 18663h | 7998h
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 5332h | 18663h | 18663h | 7998h
SUWP-AT-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 50652h | 50652h
SUWP-AT-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 50652h | 50652h
SUWP-AS-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 151956h; 2023-07-16: 50652h
SUWP-AS-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 151956h; 2023-07-16: 50652h
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [37 empty] | 7793h | 10910h | 10910h | 10910h | 10910h | 10910h | 10910h | 10910h | 10910h | 6234h
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [37 empty] | 7793h | 10910h | 10910h | 10910h | 10910h | 10910h | 10910h | 10910h | 10910h | 6234h
SUWP-OC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 50656h
SUWP-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 50656h
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 836h | 2023-06-04: 836h; 2023-06-11: 836h; 2023-06-18: 836h; 2023-06-25: 119h
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 836h | 2023-06-04: 836h; 2023-06-11: 836h; 2023-06-18: 836h; 2023-06-25: 119h
SUWP-AT-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 1486h; 2023-06-25: 3468h; 2023-07-02: 1982h
SUWP-AT-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 1486h; 2023-06-25: 3468h; 2023-07-02: 1982h
SUWP-AS-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 13864h
SUWP-AS-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 13864h
SUWP-OC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 2920h
SUWP-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 2920h
SUWP-RP-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 3342h | 3342h | 2387h
SUWP-RP-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 3342h | 3342h | 2387h
SUWP-AT-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 9076h; 2023-06-25: 9076h
SUWP-AT-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 9076h; 2023-06-25: 9076h
SUWP-AS-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 36304h
SUWP-AS-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 36304h
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 1955h; 2023-07-30: 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 559h
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 1955h; 2023-07-30: 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 1955h | 559h
SUWP-OC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 6804h | 2268h
SUWP-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 6804h | 2268h
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 35h | 49h | 49h | 49h | 49h | 49h | 49h | 49h | 49h | 28h
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 35h | 49h | 49h | 49h | 49h | 49h | 49h | 49h | 49h | 28h
SUWP-OC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 168h; 2023-07-16: 56h
SUWP-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 168h; 2023-07-16: 56h
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 10h | 10h | 2023-06-04: 10h; 2023-06-11: 10h; 2023-06-18: 1h
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 10h | 10h | 2023-06-04: 10h; 2023-06-11: 10h; 2023-06-18: 1h
SUWP-AT-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 40h; 2023-07-02: 40h
SUWP-AT-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 40h; 2023-07-02: 40h
SUWP-AS-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 126h | 42h
SUWP-AS-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 126h | 42h
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 9h | 9h | 9h | 9h | 9h | 9h | 9h | 5h | bar: 2023-07-23 to 2023-07-30
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 9h | 9h | 9h | 9h | 9h | 9h | 9h | 5h | bar: 2023-07-23 to 2023-07-30
SUWP-OC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 986h | 986h | 986h | 986h | 986h | 986h | 986h | 986h | 986h | 282h
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 986h | 986h | 986h | 986h | 986h | 986h | 986h | 986h | 986h | 282h
SUWP-OC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 3432h | 1144h
SUWP-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 3432h | 1144h
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 211h | 295h | 295h | 295h | 127h
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 211h | 295h | 295h | 295h | 127h
SUWP-AT-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 523h | 1220h | 697h
SUWP-AT-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 523h | 1220h | 697h
SUWP-AS-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 4888h
SUWP-AS-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 4888h
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 150h | 263h | 263h | 263h | 263h | 263h | 263h | 263h | 263h | 188h
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 150h | 263h | 263h | 263h | 263h | 263h | 263h | 263h | 263h | 188h
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [16 empty] | 48519h | 84908h | 84908h | 84908h | 48519h
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [16 empty] | 48519h | 84908h | 84908h | 84908h | 48519h
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 83468h | 83468h | 83468h | 83468h | 83468h | 83468h | 83468h | 83468h | 35772h
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 83468h | 83468h | 83468h | 83468h | 83468h | 83468h | 83468h | 83468h | 35772h
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [23 empty] | 95935h | 111924h | 111924h | 111924h | 111924h | 111924h | 47967h
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [23 empty] | 95935h | 111924h | 111924h | 111924h | 111924h | 111924h | 47967h
SUWP-EC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 61h | 429h | 429h
SUWP-EC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 61h | 429h | 429h
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 215h | 215h | 215h | 215h | 61h
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 215h | 215h | 215h | 215h | 61h
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 209h | 293h | 2023-06-04: 293h; 2023-06-11: 293h; 2023-06-18: 293h; 2023-06-25: 293h; 2023-07-02: 167h
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 209h | 293h | 2023-06-04: 293h; 2023-06-11: 293h; 2023-06-18: 293h; 2023-06-25: 293h; 2023-07-02: 167h
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 92h; 2023-07-09: 215h; 2023-07-16: 215h; 2023-07-23: 215h; 2023-07-30: 215h | 215h | 215h | 215h | 215h | 31h
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 92h; 2023-07-09: 215h; 2023-07-16: 215h; 2023-07-23: 215h; 2023-07-30: 215h | 215h | 215h | 215h | 215h | 31h
SUWP-AS-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 1472h | 1717h | 491h
SUWP-AS-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 1472h | 1717h | 491h
SUWP-EC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 1063h | 2481h
SUWP-EC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 1063h | 2481h
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 827h | 827h | 827h | 827h | 236h
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 827h | 827h | 827h | 827h | 236h
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 1181h | 1654h | 1654h | 2023-06-04: 1654h; 2023-06-11: 945h
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 1181h | 1654h | 1654h | 2023-06-04: 1654h; 2023-06-11: 945h
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [37 empty] | 532h | 1240h | 1240h | 1240h | 1240h | 1240h | 354h
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [37 empty] | 532h | 1240h | 1240h | 1240h | 1240h | 1240h | 354h
SUWP-AS-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 7088h; 2023-07-30: 7088h
SUWP-AS-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 7088h; 2023-07-30: 7088h
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 464h | 2023-06-04: 3248h; 2023-06-11: 3248h; 2023-06-18: 3248h; 2023-06-25: 2784h
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 464h | 2023-06-04: 3248h; 2023-06-11: 3248h; 2023-06-18: 3248h; 2023-06-25: 2784h
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [37 empty] | 4813h | 11230h | 11230h | 11230h | 11230h | 11230h | 11230h | 11230h | 11230h | 9626h
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [37 empty] | 4813h | 11230h | 11230h | 11230h | 11230h | 11230h | 11230h | 11230h | 11230h | 9626h
SUWP-OC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 39108h | 13036h
SUWP-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 39108h | 13036h
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 3015h; 2023-06-18: 4221h; 2023-06-25: 4221h; 2023-07-02: 4221h; 2023-07-09: 1809h
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 3015h; 2023-06-18: 4221h; 2023-06-25: 4221h; 2023-07-02: 4221h; 2023-07-09: 1809h
SUWP-AT-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 12494h; 2023-07-23: 17492h; 2023-07-30: 4998h
SUWP-AT-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 12494h; 2023-07-23: 17492h; 2023-07-30: 4998h
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 1156h; 2023-07-16: 2023h; 2023-07-23: 2023h; 2023-07-30: 1734h
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 1156h; 2023-07-16: 2023h; 2023-07-23: 2023h; 2023-07-30: 1734h
SUWP-OC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 1732h | 1732h
SUWP-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 1732h | 1732h
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 218h | 255h | 255h | 255h | 73h
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 218h | 255h | 255h | 255h | 73h
SUWP-AT-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 905h | 1056h | 151h
SUWP-AT-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 905h | 1056h | 151h
SUWP-AS-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 4232h
SUWP-AS-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 4232h
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 2549h | 2549h | 2549h | 2549h | 364h
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 2549h | 2549h | 2549h | 2549h | 364h
SUWP-AT-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 9051h | 2023-06-04: 10560h; 2023-06-11: 1509h
SUWP-AT-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 9051h | 2023-06-04: 10560h; 2023-06-11: 1509h
SUWP-AS-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 42240h
SUWP-AS-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 42240h
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 1950h; 2023-07-16: 2274h; 2023-07-23: 2274h; 2023-07-30: 2274h | 2274h | 2274h | 2274h | 2274h | 2274h | 975h
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 1950h; 2023-07-16: 2274h; 2023-07-23: 2274h; 2023-07-30: 2274h | 2274h | 2274h | 2274h | 2274h | 2274h | 975h
SUWP-OC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 7920h | 2640h
SUWP-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 7920h | 2640h
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 15805h | 55319h | 55319h | 23708h
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 15805h | 55319h | 55319h | 23708h
SUWP-AT-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 107254h | 150156h | 42902h
SUWP-AT-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 107254h | 150156h | 42902h
SUWP-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 30h | 10h
SUWP-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 30h | 10h
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 1079h | 1510h | 1510h | 1510h | 647h
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 1079h | 1510h | 1510h | 1510h | 647h
SUWP-AT-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 4466h | 6252h | 1786h
SUWP-AT-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 4466h | 6252h | 1786h
SUWP-AS-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 25008h
SUWP-AS-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 25008h
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 962h | 1347h | 1347h | 1347h | 1347h | 1347h | 1347h | 1347h | 1347h | 769h
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 962h | 1347h | 1347h | 1347h | 1347h | 1347h | 1347h | 1347h | 1347h | 769h
SUWP-OC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 1564h | 4692h
SUWP-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 1564h | 4692h
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [46 empty] | 509h | 713h | 713h | 713h | 305h
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [46 empty] | 509h | 713h | 713h | 713h | 305h
SUWP-OC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 306h | 918h
SUWP-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 306h | 918h
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 560h | 560h | 560h | 560h | 80h
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 560h | 560h | 560h | 560h | 80h
SUWP-AT-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-04: 2324h; 2023-06-11: 2324h
SUWP-AT-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-04: 2324h; 2023-06-11: 2324h
SUWP-AS-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 9288h
SUWP-AS-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 9288h
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 501h; 2023-07-23: 501h; 2023-07-30: 501h | 501h | 501h | 501h | 501h | 501h | 501h | 143h
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 501h; 2023-07-23: 501h; 2023-07-30: 501h | 501h | 501h | 501h | 501h | 501h | 501h | 143h
SUWP-OC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 858h | 1201h | 1201h | 1201h | 515h
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 858h | 1201h | 1201h | 1201h | 515h
SUWP-AT-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 3554h; 2023-07-02: 4976h; 2023-07-09: 1422h
SUWP-AT-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 3554h; 2023-07-02: 4976h; 2023-07-09: 1422h
SUWP-AS-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 19912h
SUWP-AS-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 19912h
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 766h | 1072h | 1072h | 1072h | 1072h | 1072h | 1072h | 1072h | 1072h | 612h
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 766h | 1072h | 1072h | 1072h | 1072h | 1072h | 1072h | 1072h | 1072h | 612h
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 236h; 2023-07-30: 331h | 331h | 331h | 331h | 331h | 331h | 331h | 331h | 189h
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 236h; 2023-07-30: 331h | 331h | 331h | 331h | 331h | 331h | 331h | 331h | 189h
SUWP-OC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 384h | 1152h
SUWP-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 384h | 1152h
SUWP-RP-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 2236h; 2023-06-18: 3130h; 2023-06-25: 3130h
SUWP-RP-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 2236h; 2023-06-18: 3130h; 2023-06-25: 3130h
SUWP-AT-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 4855h | 8496h | 3641h
SUWP-AT-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 4855h | 8496h | 3641h
SUWP-AS-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 33984h
SUWP-AS-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 33984h
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 1830h | 1830h | 1830h | 1830h | 1830h | 1830h | 1830h | 1830h | 1830h | 523h
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 1830h | 1830h | 1830h | 1830h | 1830h | 1830h | 1830h | 1830h | 1830h | 523h
SUWP-OC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 40904h | 143164h | 102260h
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 40904h | 143164h | 102260h
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 40904h | 143164h | 102260h
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2820h | 3948h | 3948h | 3948h | 3948h | 3948h | 3948h | 3948h | 3948h | 2256h
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2820h | 3948h | 3948h | 3948h | 3948h | 3948h | 3948h | 3948h | 3948h | 2256h
SUWP-OC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 9168h | 9168h
SUWP-EC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 9168h | 9168h
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [8 empty] | 8368h | 41840h
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | [8 empty] | 1569h | 10983h | 10983h | 10983h | 10983h | 4707h
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [8 empty] | 1569h | 10983h | 10983h | 10983h | 10983h | 4707h
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [14 empty] | 9129h | 15977h | 15977h | 15977h | 15977h | 15977h | 11412h
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [14 empty] | 9129h | 15977h | 15977h | 15977h | 15977h | 15977h | 11412h
SUWP-AS-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 32088h
SUWP-AS-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 32088h
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 1727h | 1727h | 1727h | 1727h | 1727h | 1727h | 1727h | 1727h | 1727h | 494h
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 1727h | 1727h | 1727h | 1727h | 1727h | 1727h | 1727h | 1727h | 1727h | 494h
SUWP-OC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 2006h | 6018h
SUWP-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 2006h | 6018h
SUWP-RP-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 10989h | 15385h | 15385h
SUWP-RP-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 10989h | 15385h | 15385h
SUWP-AT-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 5966h | 41760h | 35794h
SUWP-AT-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 5966h | 41760h | 35794h
SUWP-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 1936h
SUWP-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 1936h
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 956h | 956h | 956h | 2023-06-04: 956h; 2023-06-11: 137h
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 956h | 956h | 956h | 2023-06-04: 956h; 2023-06-11: 137h
SUWP-AT-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 3960h; 2023-06-25: 3960h
SUWP-AT-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 3960h; 2023-06-25: 3960h
SUWP-AS-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 15840h
SUWP-AS-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 15840h
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 609h; 2023-07-23: 853h; 2023-07-30: 853h | 853h | 853h | 853h | 853h | 853h | 853h | 487h
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 609h; 2023-07-23: 853h; 2023-07-30: 853h | 853h | 853h | 853h | 853h | 853h | 853h | 487h
SUWP-OC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 2970h | 990h
SUWP-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 2970h | 990h
SUWP-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1740h | 580h
SUWP-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1740h | 580h
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 3136h; 2023-07-09: 3136h; 2023-07-16: 3136h; 2023-07-23: 3136h; 2023-07-30: 448h
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 3136h; 2023-07-09: 3136h; 2023-07-16: 3136h; 2023-07-23: 3136h; 2023-07-30: 448h
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 3021h | 4230h | 4230h | 4230h | 4230h | 4230h | 1813h
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 3021h | 4230h | 4230h | 4230h | 4230h | 4230h | 1813h
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 1321h | 3083h | 3083h | 3083h | 3083h | 3083h | 3083h | 3083h | 3083h
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 1321h | 3083h | 3083h | 3083h | 3083h | 3083h | 3083h | 3083h | 3083h
SUWP-AS-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 51968h
SUWP-AS-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 51968h
SUWP-EC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 684h | 4790h | 4790h
SUWP-EC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 684h | 4790h | 4790h
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 2395h | 2395h | 2395h | 2395h | 684h
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 2395h | 2395h | 2395h | 2395h | 684h
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 2333h | 3266h | 3266h | 3266h | 2023-06-04: 3266h; 2023-06-11: 3266h; 2023-06-18: 1866h
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 2333h | 3266h | 3266h | 3266h | 2023-06-04: 3266h; 2023-06-11: 3266h; 2023-06-18: 1866h
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [38 empty] | 1026h | 2395h | 2395h | 2395h | 2395h | 2395h | 2395h | 2395h | 2395h | 342h
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [38 empty] | 1026h | 2395h | 2395h | 2395h | 2395h | 2395h | 2395h | 2395h | 2395h | 342h
SUWP-AS-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 69960h
SUWP-AS-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 69960h
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 2691h | 3768h | 3768h | 3768h | 3768h | 3768h | 3768h | 3768h | 3768h | 2153h
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 2691h | 3768h | 3768h | 3768h | 3768h | 3768h | 3768h | 3768h | 3768h | 2153h
SUWP-OC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 352h | 616h | 616h | 528h
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 352h | 616h | 616h | 528h
SUWP-OC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 264h | 792h
SUWP-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 264h | 792h
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 55h | 384h | 384h | 384h | 384h
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 55h | 384h | 384h | 384h | 384h
SUWP-AT-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 227h | 1592h | 1365h
SUWP-AT-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 227h | 1592h | 1365h
SUWP-AS-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 1590h; 2023-07-16: 4770h
SUWP-AS-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 1590h; 2023-07-16: 4770h
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 796h; 2023-06-25: 929h; 2023-07-02: 929h; 2023-07-09: 531h
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 796h; 2023-06-25: 929h; 2023-07-02: 929h; 2023-07-09: 531h
SUWP-AS-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 450462h | 150154h
SUWP-AS-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 450462h | 150154h
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [32 empty] | 18481h | 32341h | 32341h | 32341h | 32341h | 32341h | 32341h | 32341h | 32341h | 23101h
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [32 empty] | 18481h | 32341h | 32341h | 32341h | 32341h | 32341h | 32341h | 32341h | 32341h | 23101h
SUWP-OC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 75076h | 75076h
SUWP-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 75076h | 75076h
SUWP-RP-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 6829h | 6829h | 4878h
SUWP-RP-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 6829h | 6829h | 4878h
SUWP-AT-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 18540h | 18540h
SUWP-AT-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 18540h | 18540h
SUWP-AT-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 2106h | 2948h | 842h
SUWP-AT-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 2106h | 2948h | 842h
SUWP-AS-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 11792h
SUWP-AS-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 11792h
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 454h | 635h | 635h | 635h | 635h | 635h | 635h | 635h | 635h | 363h
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 454h | 635h | 635h | 635h | 635h | 635h | 635h | 635h | 635h | 363h
SUWP-OC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 738h | 2214h
SUWP-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 738h | 2214h
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [47 empty] | 191h | 191h | 191h | 191h | 27h
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [47 empty] | 191h | 191h | 191h | 191h | 27h
SUWP-AT-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 225h | 788h | 563h
SUWP-AT-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 225h | 788h | 563h
SUWP-AS-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 3160h
SUWP-AS-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 3160h
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 452h | 452h | 452h | 452h | 65h
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 452h | 452h | 452h | 452h | 65h
SUWP-AT-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 1876h; 2023-06-18: 1876h
SUWP-AT-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 1876h; 2023-06-18: 1876h
SUWP-AS-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 7504h
SUWP-AS-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 7504h
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 404h; 2023-07-30: 404h | 404h | 404h | 404h | 404h | 404h | 404h | 404h | 115h
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 404h; 2023-07-30: 404h | 404h | 404h | 404h | 404h | 404h | 404h | 404h | 115h
SUWP-OC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 1404h | 468h
SUWP-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 1404h | 468h
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [17 empty] | 129h | 129h | 129h | 129h | 18h
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [17 empty] | 129h | 129h | 129h | 129h | 18h
SUWP-AT-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [25 empty] | 536h | 536h
SUWP-AT-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [25 empty] | 536h | 536h
SUWP-AS-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 2152h
SUWP-AS-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 2152h
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units |  |  | 119303h | 167025h | 167025h | 119303h
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units |  |  | 27799h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units |  |  | 27799h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | 38918h | -22216h | -22216h | -22216h
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [17 empty] | 136658h | 136658h | 136658h | 136658h | 136658h | 136658h | 39045h
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [17 empty] | 136658h | 136658h | 136658h | 136658h | 136658h | 136658h | 39045h
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [18 empty] | 77649h | 135885h | 135885h | 135885h | 135885h | 135885h | 135885h | 135885h | 116473h
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [18 empty] | 77649h | 135885h | 135885h | 135885h | 135885h | 135885h | 135885h | 135885h | 116473h
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 4868h | 34079h | 34079h | 34079h | 34079h
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2353h | 16471h | 16471h | 16471h | 16471h | 16471h | 16471h | 16471h | 16471h | 7059h
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2353h | 16471h | 16471h | 16471h | 16471h | 16471h | 16471h | 16471h | 16471h | 7059h
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units |  | 34079h | 34079h | 34079h | 34079h | 4868h
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units |  | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 3574h
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units |  | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 12510h | 3574h
SUWP-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 4372h | 2023-06-04: 13116h
SUWP-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 4372h | 2023-06-04: 13116h
SUWP-RP-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [19 empty] | 87085h | 101599h | 87085h
SUWP-RP-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [19 empty] | 87085h | 101599h | 87085h
SUWP-AT-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [23 empty] | 157582h | 275768h | 118186h
SUWP-AT-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [23 empty] | 157582h | 275768h | 118186h
SUWP-AS-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 1103072h
SUWP-AS-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 1103072h
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [24 empty] | 8485h | 59396h | 59396h | 59396h | 59396h | 59396h | 59396h | 59396h | 59396h | 59396h | 8485h
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [24 empty] | 8485h | 59396h | 59396h | 59396h | 59396h | 59396h | 59396h | 59396h | 59396h | 59396h | 8485h
SUWP-OC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 1194h | 398h
SUWP-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 1194h | 398h
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [29 empty] | 551h | 643h | 643h | 643h | 184h
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [29 empty] | 551h | 643h | 643h | 643h | 184h
SUWP-AT-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [34 empty] | 2287h | 2668h | 2023-06-04: 381h
SUWP-AT-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [34 empty] | 2287h | 2668h | 2023-06-04: 381h
SUWP-AS-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-16: 10672h
SUWP-AS-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-16: 10672h
SUWP-AS-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 55614h | 18538h
SUWP-AS-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 55614h | 18538h
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 2852h | 3993h | 3993h | 3993h | 3993h | 3993h | 3993h | 3993h | 3993h | 2282h
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 2852h | 3993h | 3993h | 3993h | 3993h | 3993h | 3993h | 3993h | 3993h | 2282h
SUWP-OC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 13902h | 4634h
SUWP-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 13902h | 4634h
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 170h | 2023-06-04: 199h; 2023-06-11: 199h; 2023-06-18: 199h; 2023-06-25: 57h
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 170h | 2023-06-04: 199h; 2023-06-11: 199h; 2023-06-18: 199h; 2023-06-25: 57h
SUWP-AT-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 118h; 2023-07-09: 824h; 2023-07-16: 706h
SUWP-AT-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 118h; 2023-07-09: 824h; 2023-07-16: 706h
SUWP-AS-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 3304h
SUWP-AS-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 3304h
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 170h | 170h | 170h | 170h | 170h | 170h | 170h | 170h | 170h | 48h
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 170h | 170h | 170h | 170h | 170h | 170h | 170h | 170h | 170h | 48h
SUWP-OC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 594h | 198h
SUWP-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 594h | 198h
SUWP-RP-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 38h | 2023-06-04: 38h; 2023-06-11: 27h
SUWP-RP-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 38h | 2023-06-04: 38h; 2023-06-11: 27h
SUWP-AT-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 100h; 2023-07-09: 100h
SUWP-AT-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 100h; 2023-07-09: 100h
SUWP-AS-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 300h | 100h
SUWP-AS-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 300h | 100h
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 15h | 22h | 22h | 22h | 22h | 22h | 22h | 22h | 22h | 12h
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 15h | 22h | 22h | 22h | 22h | 22h | 22h | 22h | 22h | 12h
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 115h | 115h | 115h | 115h | 115h | 2023-06-04: 115h; 2023-06-11: 115h; 2023-06-18: 115h; 2023-06-25: 115h; 2023-07-02: 33h
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 115h | 115h | 115h | 115h | 115h | 2023-06-04: 115h; 2023-06-11: 115h; 2023-06-18: 115h; 2023-06-25: 115h; 2023-07-02: 33h
SUWP-OC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [15 empty] | 402h | 134h
SUWP-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [15 empty] | 402h | 134h
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [30 empty] | 830h | 830h | 830h | 830h | 119h
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [30 empty] | 830h | 830h | 830h | 830h | 119h
SUWP-AT-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-18: 3440h; 2023-06-25: 3440h
SUWP-AT-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-18: 3440h; 2023-06-25: 3440h
SUWP-AT-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [18 empty] | 28693h | 50212h | 21519h
SUWP-AT-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [18 empty] | 28693h | 50212h | 21519h
SUWP-AS-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-AS-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 117h | 409h | 409h | 409h | 409h | 409h | 409h | 409h | 409h | 409h
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 117h | 409h | 409h | 409h | 409h | 409h | 409h | 409h | 409h | 409h
SUWP-OC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-RP-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 4077h; 2023-07-30: 4757h | 4077h
SUWP-RP-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 4077h; 2023-07-30: 4757h | 4077h
SUWP-AT-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 11067h | 12912h | 1845h
SUWP-AT-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 11067h | 12912h | 1845h
SUWP-RP-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 309h; 2023-06-18: 433h; 2023-06-25: 433h
SUWP-RP-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 309h; 2023-06-18: 433h; 2023-06-25: 433h
SUWP-AT-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 672h | 1176h | 504h
SUWP-AT-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 672h | 1176h | 504h
SUWP-AS-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 4704h
SUWP-AS-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 4704h
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [49 empty] | 145h | 253h | 253h | 253h | 253h | 253h | 253h | 253h | 253h | 181h
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [49 empty] | 145h | 253h | 253h | 253h | 253h | 253h | 253h | 253h | 253h | 181h
SUWP-OC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 294h | 2023-06-04: 882h
SUWP-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 294h | 2023-06-04: 882h
SUWP-RP-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-11: 8975h; 2023-06-18: 8975h; 2023-06-25: 6411h
SUWP-RP-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-11: 8975h; 2023-06-18: 8975h; 2023-06-25: 6411h
SUWP-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 2316h | 2023-06-04: 772h
SUWP-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 2316h | 2023-06-04: 772h
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 4067h | 4067h | 4067h | 4067h | 581h
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 4067h | 4067h | 4067h | 4067h | 581h
SUWP-AT-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [33 empty] | 16848h | 16848h
SUWP-AT-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [33 empty] | 16848h | 16848h
SUWP-AS-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 67400h
SUWP-AS-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AS-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 67400h
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [39 empty] | 3629h | 3629h | 3629h | 3629h | 3629h | 3629h | 3629h | 3629h | 3629h | 1037h
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [39 empty] | 3629h | 3629h | 3629h | 3629h | 3629h | 3629h | 3629h | 3629h | 3629h | 1037h
SUWP-OC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-OC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-OC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-EC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [13 empty] | 35802h | 11934h
SUWP-EC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | [13 empty] | 23868h
SUWP-EC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [13 empty] | 23868h | -19093h
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 2023h | 2833h | 2833h | 2833h | 1214h
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 2023h | 2833h | 2833h | 2833h | 1214h
SUWP-AT-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [31 empty] | 11736h | 11736h
SUWP-AT-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-AT-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [31 empty] | 11736h | 11736h
SUWP-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 6456h; 2023-07-16: 6456h
SUWP-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 6456h; 2023-07-16: 6456h
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 140103h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 29719h
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 140103h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 169822h | 29719h
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 33728h | 57236h | 57236h | 57236h | 39861h
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 33728h | 57236h | 57236h | 57236h | 39861h
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 2817h | 4508h | 4508h | 4508h | 4508h | 4508h | 4508h | 4508h | 4395h
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 2817h | 4508h | 4508h | 4508h | 4508h | 4508h | 4508h | 4508h | 4395h
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 735h | 1004h | 1004h | 1004h | 556h
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 735h | 1004h | 1004h | 1004h | 556h
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 58704h | 82186h | 82186h | 82186h | 46963h
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 58704h | 82186h | 82186h | 82186h | 46963h
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h | 243847h
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 11040h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 38028h
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 11040h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 49068h | 38028h
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 3797h | 23624h | 23624h | 19827h
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 3797h | 23624h | 23624h | 19827h
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h | 5914h
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 1424h | 1994h | 1994h | 1994h | 1139h
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 1424h | 1994h | 1994h | 1994h | 1139h
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 64160h | 224560h | 224560h | 224560h | 224560h
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 64160h | 224560h | 224560h | 224560h | 224560h
B30413 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B30413 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B30413 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B30423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B30423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B30423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 253263h | 253263h | 253263h | 202611h
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 253263h | 253263h | 253263h | 202611h
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [45 empty] | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 150965h
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [45 empty] | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 251608h | 150965h
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 32559h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 19536h
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 32559h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 52095h | 19536h
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [65 empty] | 7838h | 17558h | 17558h | 17558h | 14736h
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [65 empty] | 7838h | 17558h | 17558h | 17558h | 14736h
A3670 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3670 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3670 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EF1500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EF1500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EF1500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EF1510 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EF1510 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EF1510 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A5400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A5400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A5400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A5410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A5410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A5410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 40000h | 40000h | 40000h | 40000h
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 40000h | 40000h | 40000h | 40000h
EF1490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
EF1490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EF1490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM1110-CWP-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MEM1110-CWP-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1110-CWP-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [26 empty] | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 1794210h
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [26 empty] | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 2242763h | 1794210h
B40623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 49320h | 197280h
B40623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 49320h | 197280h
B40643 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40643 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40643 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 40h; 2023-07-09: 50h; 2023-07-16: 50h; 2023-07-23: 50h; 2023-07-30: 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 10h
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 40h; 2023-07-09: 50h; 2023-07-16: 50h; 2023-07-23: 50h; 2023-07-30: 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 50h | 10h
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 578h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 867h
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 578h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 2891h | 867h
B40893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 110571h | 442285h
B40893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 110571h | 442285h
A5170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A5170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A5170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A302900 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A302900 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A302900 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A303030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 63248h | 79060h | 32612h
A303030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A303030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 63248h | 79060h | 32612h
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 2245h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 8979h
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 2245h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 11224h | 8979h
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [21 empty] | 196088h | 313740h | 313740h | 313740h | 313740h | 313740h | 313740h | 313740h | 313740h | 117653h
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [21 empty] | 196088h | 313740h | 313740h | 313740h | 313740h | 313740h | 313740h | 313740h | 313740h | 117653h
SMS55840 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SMS55840 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SMS55840 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MIS30300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MIS30300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MIS30300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
X3300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
X3300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
X3300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MIS30330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MIS30330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MIS30330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MIS30340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MIS30340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MIS30340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39093 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [103 empty] | 372288h
B39093 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39093 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [103 empty] | 372288h
B40033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MEM0623-CWP-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [83 empty] | 989h | 18795h
MEM0623-CWP-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0623-CWP-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [83 empty] | 989h | 18795h
TTU0623-CWP-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 384h
TTU0623-CWP-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0623-CWP-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 384h
TTU0622-CWP-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 19784h
TTU0622-CWP-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0622-CWP-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 19784h
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [48 empty] | 2864h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 111687h
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [48 empty] | 2864h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 111687h
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 41h; 2023-07-16: 1657h; 2023-07-23: 1657h; 2023-07-30: 1657h | 1657h | 1657h | 1657h | 1616h
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 41h; 2023-07-16: 1657h; 2023-07-23: 1657h; 2023-07-30: 1657h | 1657h | 1657h | 1657h | 1616h
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 403h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 371h
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 403h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 902h | 371h
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-09: 77h; 2023-07-16: 3093h; 2023-07-23: 3093h; 2023-07-30: 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3016h
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-09: 77h; 2023-07-16: 3093h; 2023-07-23: 3093h; 2023-07-30: 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3093h | 3016h
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 2667h | 11855h | 11855h | 11855h | 11855h | 11855h | 11855h | 11855h | 11855h | 9188h
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 2667h | 11855h | 11855h | 11855h | 11855h | 11855h | 11855h | 11855h | 11855h | 9188h
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 45h | 1806h | 1806h | 1806h | 1761h
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 1254h | 1254h | 1254h | 1254h
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 1254h | 1254h | 1254h | 1254h
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 753h | 1686h | 1686h | 1686h | 1415h
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 753h | 1686h | 1686h | 1686h | 1415h
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [66 empty] | 335h | 1171h | 1171h | 1171h | 1171h
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 6443h | 257739h | 257739h | 257739h | 251296h
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 6443h | 257739h | 257739h | 257739h | 251296h
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [64 empty] | 48684h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 65867h
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [64 empty] | 48684h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 114551h | 65867h
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 66h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2627h | 2562h
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [52 empty] | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 608h
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [52 empty] | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 3041h | 608h
A3060 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3060 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3060 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40263 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40263 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40263 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A4820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A4820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A4820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A3220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A3220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A3220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39763 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39763 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39763 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B39753 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B39753 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B39753 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B40083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B40083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B40083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 6750h | 6750h | 6750h | 6750h | 6750h
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 6750h | 6750h | 6750h | 6750h | 6750h
ESD0600-CWP-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
ESD0600-CWP-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0600-CWP-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ESD0600-CWP-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [62 empty] | 6402h | 249670h
ESD0600-CWP-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0600-CWP-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [62 empty] | 6402h | 249670h
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 8687h; 2023-07-09: 10858h; 2023-07-16: 10858h; 2023-07-23: 10858h; 2023-07-30: 10858h | 10858h | 2172h
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 8687h; 2023-07-09: 10858h; 2023-07-16: 10858h; 2023-07-23: 10858h; 2023-07-30: 10858h | 10858h | 2172h
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 8687h; 2023-07-09: 10858h; 2023-07-16: 10858h; 2023-07-23: 10858h; 2023-07-30: 10858h | 10858h | 2172h
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 8687h; 2023-07-09: 10858h; 2023-07-16: 10858h; 2023-07-23: 10858h; 2023-07-30: 10858h | 10858h | 2172h
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 8687h; 2023-07-09: 10858h; 2023-07-16: 10858h; 2023-07-23: 10858h; 2023-07-30: 10858h | 10858h | 2172h
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 8687h; 2023-07-09: 10858h; 2023-07-16: 10858h; 2023-07-23: 10858h; 2023-07-30: 10858h | 10858h | 2172h
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 19855h; 2023-07-09: 24819h; 2023-07-16: 24819h; 2023-07-23: 24819h; 2023-07-30: 24819h | 24819h | 4964h
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 19855h; 2023-07-09: 24819h; 2023-07-16: 24819h; 2023-07-23: 24819h; 2023-07-30: 24819h | 24819h | 4964h
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 16288h | 16288h | 16288h | 16288h
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 16288h | 16288h | 16288h | 16288h
RIN1110-CWP-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
RIN1110-CWP-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
RIN1110-CWP-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ECB0600-CWP-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
ECB0600-CWP-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0600-CWP-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
ELU0600-CWP-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 48419h | 72629h
ELU0600-CWP-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0600-CWP-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 48419h | 72629h
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 2165h; 2023-07-09: 3465h; 2023-07-16: 3465h; 2023-07-23: 3465h; 2023-07-30: 1299h
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 2165h; 2023-07-09: 3465h; 2023-07-16: 3465h; 2023-07-23: 3465h; 2023-07-30: 1299h
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 982h | 3234h | 3234h | 3234h | 3176h
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 982h | 3234h | 3234h | 3234h | 3176h
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 1883h; 2023-07-09: 3012h; 2023-07-16: 3012h; 2023-07-23: 3012h; 2023-07-30: 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 527h
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 1883h; 2023-07-09: 3012h; 2023-07-16: 3012h; 2023-07-23: 3012h; 2023-07-30: 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 527h
MCD0622-CWP-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 51345h | 1026892h | 975547h
MCD0622-CWP-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0622-CWP-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 51345h | 1026892h | 975547h
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 30539h | 48863h | 48863h | 48863h | 48863h | 48863h | 18324h
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 30539h | 48863h | 48863h | 48863h | 48863h | 48863h | 18324h
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 15270h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 9162h
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 15270h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 9162h
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 10612h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 9763h
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 10612h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 16979h | 9763h
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 214h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 244h
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 214h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 305h | 244h
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-30: 15270h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 9162h
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-30: 15270h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 24431h | 9162h
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 2165h; 2023-07-09: 3465h; 2023-07-16: 3465h; 2023-07-23: 3465h; 2023-07-30: 1299h
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 2165h; 2023-07-09: 3465h; 2023-07-16: 3465h; 2023-07-23: 3465h; 2023-07-30: 1299h
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 982h | 3234h | 3234h | 3234h | 3176h
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 982h | 3234h | 3234h | 3234h | 3176h
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-02: 1883h; 2023-07-09: 3012h; 2023-07-16: 3012h; 2023-07-23: 3012h; 2023-07-30: 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 527h
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-02: 1883h; 2023-07-09: 3012h; 2023-07-16: 3012h; 2023-07-23: 3012h; 2023-07-30: 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 3012h | 527h
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 652h | 931h | 931h | 931h | 931h | 931h | 931h | 931h | 931h | 931h | 279h
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 652h | 931h | 931h | 931h | 931h | 931h | 931h | 931h | 931h | 931h | 279h
SWP-001-0622 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 41336h | 22964h
SWP-001-0622 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-001-0622 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 41336h | 22964h
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 30539h | 48863h | 48863h | 48863h | 48863h | 48863h | 18324h
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 30539h | 48863h | 48863h | 48863h | 48863h | 48863h | 18324h
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 2652h | 4243h | 4243h | 4243h | 1591h
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 2899h | 3960h | 3960h | 3960h | 2192h
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 6429h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 10286h | 5914h
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [27 empty] | 33506h | 41883h | 41883h | 41883h | 41883h | 41883h | 41883h | 8377h
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [27 empty] | 33506h | 41883h | 41883h | 41883h | 41883h | 41883h | 41883h | 8377h
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 10994h | 48863h | 48863h | 48863h | 48863h | 48863h | 37869h
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 10994h | 48863h | 48863h | 48863h | 48863h | 48863h | 37869h
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 2609h | 11596h | 11596h | 11596h | 8987h
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 2609h | 11596h | 11596h | 11596h | 8987h
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 6378h | 10823h | 10823h | 10823h | 7537h
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 6378h | 10823h | 10823h | 10823h | 7537h
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 10436h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 35947h
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 10436h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 46384h | 35947h
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [54 empty] | 48863h | 48863h | 48863h | 48863h | 48863h | 48863h
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [54 empty] | 48863h | 48863h | 48863h | 48863h | 48863h | 48863h
B41813 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41813 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41813 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B41793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B41783 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41783 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41783 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B41803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B41803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B41803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 30539h | 48863h | 48863h | 48863h | 48863h | 48863h | 18324h
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 30539h | 48863h | 48863h | 48863h | 48863h | 48863h | 18324h
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 4378h | 7004h | 7004h | 7004h | 2627h
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 4378h | 7004h | 7004h | 7004h | 2627h
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 4786h | 6537h | 6537h | 6537h | 3619h
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 4786h | 6537h | 6537h | 6537h | 3619h
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 10217h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 10217h
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 10217h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 20434h | 10217h
MEM0622-CWP-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 61885h | 158004h | 96119h
MEM0622-CWP-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0622-CWP-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 61885h | 158004h | 96119h
JIL0622-CWP-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 1630h | 2328h | 698h
JIL0622-CWP-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
JIL0622-CWP-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 1630h | 2328h | 698h
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 73716h | 92145h | 92145h | 92145h | 92145h | 92145h | 18429h
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 73716h | 92145h | 92145h | 92145h | 92145h | 92145h | 18429h
SUWP-MO-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SUWP-MO-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SUWP-MO-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SWP-035-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 31257h | 40187h
SWP-035-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-035-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 31257h | 40187h
SWP-036-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [76 empty] | 28578h
SWP-036-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-036-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [76 empty] | 28578h
SWP-037-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 28578h
SWP-037-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-037-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 28578h
SWP-040-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [98 empty] | 17861h
SWP-040-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-040-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [98 empty] | 17861h
SWP-041-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 17861h
SWP-041-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-041-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 17861h
SWP-039-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 11610h | 6251h
SWP-039-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-039-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 11610h | 6251h
MEM1214-CWP-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 11946h | 11946h
MEM1214-CWP-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 11946h | 11946h
MEM1214-CWP-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 16799h | 7093h
MEM1214-CWP-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 16799h | 7093h
MEM1214-CWP-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 9333h | 14559h
MEM1214-CWP-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 9333h | 14559h
MEM1214-CWP-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 23892h
MEM1214-CWP-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 23892h
MEM1214-CWP-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 23892h
MEM1214-CWP-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 23892h
MEM1214-CWP-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 373h | 23519h
MEM1214-CWP-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 373h | 23519h
MEM1214-CWP-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 21279h | 2613h
MEM1214-CWP-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 21279h | 2613h
MEM1214-CWP-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [95 empty] | 23892h
MEM1214-CWP-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [95 empty] | 23892h
MEM1214-CWP-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 23892h
MEM1214-CWP-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 23892h
MEM1214-CWP-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 20906h | 2987h
MEM1214-CWP-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 20906h | 2987h
MEM1214-CWP-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 23892h
MEM1214-CWP-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 23892h
MEM1214-CWP-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 17916h | 5972h
MEM1214-CWP-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 17916h | 5972h
MEM1214-CWP-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 17170h | 6719h
MEM1214-CWP-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 17170h | 6719h
MEM1214-CWP-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 16796h | 7092h
MEM1214-CWP-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-CWP-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 16796h | 7092h
ECB1214-CWP-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [90 empty] | 36179h | 72359h
ECB1214-CWP-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [90 empty] | 36179h | 72359h
ECB1214-CWP-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [91 empty] | 108538h
ECB1214-CWP-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [91 empty] | 108538h
ECB1214-CWP-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [92 empty] | 108538h
ECB1214-CWP-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [92 empty] | 108538h
ECB1214-CWP-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [93 empty] | 108538h
ECB1214-CWP-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [93 empty] | 108538h
ECB1214-CWP-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 108538h
ECB1214-CWP-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 108538h
ECB1214-CWP-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 72359h | 36179h
ECB1214-CWP-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 72359h | 36179h
ECB1214-CWP-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [95 empty] | 108538h
ECB1214-CWP-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [95 empty] | 108538h
ECB1214-CWP-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [95 empty] | 36179h | 72359h
ECB1214-CWP-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [95 empty] | 36179h | 72359h
ECB1214-CWP-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 108538h
ECB1214-CWP-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 108538h
ECB1214-CWP-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 108538h
ECB1214-CWP-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 108538h
ECB1214-CWP-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 108538h
ECB1214-CWP-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 108538h
ECB1214-CWP-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 108538h
ECB1214-CWP-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 108538h
ECB1214-CWP-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 108538h
ECB1214-CWP-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 108538h
ECB1214-CWP-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [89 empty] | 108538h
ECB1214-CWP-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [89 empty] | 108538h
MCD0822-CWP-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 347581h | 887440h | 7395h
MCD0822-CWP-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 347581h | 887440h | 7395h
MCD0822-CWP-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 880045h | 362371h
MCD0822-CWP-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-CWP-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 880045h | 362371h
SES0822-CWP-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [79 empty] | 137084h | 326894h
SES0822-CWP-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [79 empty] | 137084h | 326894h
SES0822-CWP-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [80 empty] | 305804h | 158174h
SES0822-CWP-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [80 empty] | 305804h | 158174h
SES0822-CWP-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 463978h
SES0822-CWP-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 463978h
SES0822-CWP-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [74 empty] | 463978h
SES0822-CWP-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [74 empty] | 463978h
SES0822-CWP-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 161459h | 26421h
SES0822-CWP-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 161459h | 26421h
SES0822-CWP-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 187880h
SES0822-CWP-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 187880h
SES0822-CWP-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [73 empty] | 137974h | 49906h
SES0822-CWP-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [73 empty] | 137974h | 49906h
SES0822-CWP-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 187880h
SES0822-CWP-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-CWP-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 187880h
ECB0823-CWP-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 189141h
ECB0823-CWP-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0823-CWP-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 189141h
ECB0823-CWP-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 141856h | 47285h
ECB0823-CWP-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0823-CWP-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 141856h | 47285h
ECB0823-CWP-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 94571h | 94571h
ECB0823-CWP-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0823-CWP-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 94571h | 94571h
ECB0824-CWP-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [86 empty] | 189141h
ECB0824-CWP-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0824-CWP-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [86 empty] | 189141h
ECB0824-CWP-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [85 empty] | 141856h | 47285h
ECB0824-CWP-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0824-CWP-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [85 empty] | 141856h | 47285h
ECB0824-CWP-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [84 empty] | 94571h | 94571h
ECB0824-CWP-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0824-CWP-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [84 empty] | 94571h | 94571h
ECB0826-CWP-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [96 empty] | 319779h | 89538h
ECB0826-CWP-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0826-CWP-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [96 empty] | 319779h | 89538h
ECB0826-CWP-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [95 empty] | 217450h | 191868h
ECB0826-CWP-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0826-CWP-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [95 empty] | 217450h | 191868h
ECB0826-CWP-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 115121h | 294197h
ECB0826-CWP-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0826-CWP-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 115121h | 294197h
ECB0827-CWP-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 970504h | 970504h
ECB0827-CWP-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0827-CWP-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 970504h | 970504h
ECB0827-CWP-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 1941008h
ECB0827-CWP-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0827-CWP-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 1941008h
ECB0827-CWP-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [94 empty] | 2138495h
ECB0827-CWP-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0827-CWP-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [94 empty] | 2138495h
ECB1062-CWP-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 62789h | 188366h
ECB1062-CWP-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1062-CWP-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 62789h | 188366h
ECB1062-CWP-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 251155h
ECB1062-CWP-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1062-CWP-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 251155h
ECB1062-CWP-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 251155h
ECB1062-CWP-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1062-CWP-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 251155h
ECB1214-CWP-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 18090h | 90448h
ECB1214-CWP-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 18090h | 90448h
ECB1214-CWP-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [87 empty] | 36746h | 183730h
ECB1214-CWP-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-CWP-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [87 empty] | 36746h | 183730h
MEM1214-EWPc-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
MEM1214-EWPc-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-EWPc-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 206654h; 2023-07-30: 85093h
ECB1214-EWPc-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 145873h | 145873h
ECB1214-EWPc-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 145873h | 145873h
ECB1214-EWPc-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
ECB1214-EWPc-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 291747h
ECB1214-EWPc-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 291747h
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 28950h; 2023-07-02: 68118h; 2023-07-09: 68118h; 2023-07-16: 39168h
ECB0817-EWPc-550 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 79545h | 79545h
ECB0817-EWPc-550 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0817-EWPc-550 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 79545h | 79545h
ECB0817-EWPc-551 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 79545h | 79545h
ECB0817-EWPc-551 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0817-EWPc-551 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 79545h | 79545h
ECB0817-EWPc-552 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 79545h | 79545h
ECB0817-EWPc-552 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0817-EWPc-552 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 79545h | 79545h
ECB0821-EWPc-553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 177341h | 177341h
ECB0821-EWPc-553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0821-EWPc-553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 177341h | 177341h
ECB0821-EWPc-554 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 177341h | 177341h
ECB0821-EWPc-554 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0821-EWPc-554 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 177341h | 177341h
ECB0823-EWPc-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 294730h | 294730h
ECB0823-EWPc-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0823-EWPc-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 294730h | 294730h
ECB0823-EWPc-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 294730h | 294730h
ECB0823-EWPc-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0823-EWPc-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 294730h | 294730h
ECB0823-EWPc-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 294730h | 294730h
ECB0823-EWPc-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0823-EWPc-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 294730h | 294730h
ECB0824-EWPc-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 265256h | 265256h
ECB0824-EWPc-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0824-EWPc-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 265256h | 265256h
ECB0824-EWPc-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 265256h | 265256h
ECB0824-EWPc-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0824-EWPc-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 265256h | 265256h
ECB0824-EWPc-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 265256h | 265256h
ECB0824-EWPc-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0824-EWPc-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 265256h | 265256h
ECB0826-EWPc-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 333510h | 333510h
ECB0826-EWPc-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0826-EWPc-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 333510h | 333510h
ECB0826-EWPc-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 333510h | 333510h
ECB0826-EWPc-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0826-EWPc-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 333510h | 333510h
ECB0826-EWPc-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 333510h | 333510h
ECB0826-EWPc-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0826-EWPc-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 333510h | 333510h
ECB0827-EWPc-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 79545h | 79545h
ECB0827-EWPc-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0827-EWPc-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 79545h | 79545h
ECB0827-EWPc-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 79545h | 79545h
ECB0827-EWPc-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0827-EWPc-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 79545h | 79545h
ECB0827-EWPc-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 79545h | 79545h
ECB0827-EWPc-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB0827-EWPc-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 79545h | 79545h
ECB1049-EWPc-570 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 60600h | 60600h
ECB1049-EWPc-570 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1049-EWPc-570 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 60600h | 60600h
ECB1049-EWPc-571 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 60600h | 60600h
ECB1049-EWPc-571 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1049-EWPc-571 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 60600h | 60600h
ECB1049-EWPc-572 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 60600h | 60600h
ECB1049-EWPc-572 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1049-EWPc-572 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 60600h | 60600h
ECB1062-EWPc-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 74458h | 74458h
ECB1062-EWPc-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1062-EWPc-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 74458h | 74458h
ECB1062-EWPc-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 74458h | 74458h
ECB1062-EWPc-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1062-EWPc-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 74458h | 74458h
ECB1062-EWPc-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 74458h | 74458h
ECB1062-EWPc-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1062-EWPc-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 74458h | 74458h
ECB1214-EWPc-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 145873h | 145873h
ECB1214-EWPc-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 145873h | 145873h
ECB1214-EWPc-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 145873h | 145873h
ECB1214-EWPc-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
ECB1214-EWPc-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 145873h | 145873h
MEM1214-PWPe-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 15928h
MEM1214-PWPe-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPe-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 15928h
MCD0822-PWPe-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
MCD0822-PWPe-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
MCD0822-PWPe-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
MCD0822-PWPe-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPe-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
SES0822-PWPe-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
SES0822-PWPe-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
SES0822-PWPe-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
SES0822-PWPe-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
SES0822-PWPe-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
SES0822-PWPe-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
SES0822-PWPe-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
SES0822-PWPe-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
SES0822-PWPe-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
SES0822-PWPe-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
SES0822-PWPe-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
SES0822-PWPe-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
SES0822-PWPe-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
SES0822-PWPe-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
SES0822-PWPe-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 167819h
SES0822-PWPe-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPe-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 167819h
MEM1214-PWPl-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MEM1214-PWPl-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 15928h
MEM1214-PWPl-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPl-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 15928h
MCD0822-PWPl-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 167819h
MCD0822-PWPl-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 167819h
MCD0822-PWPl-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 167819h
MCD0822-PWPl-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPl-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 167819h
SES0822-PWPl-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 167819h
SES0822-PWPl-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 167819h
SES0822-PWPl-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 167819h
SES0822-PWPl-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 167819h
SES0822-PWPl-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 167819h
SES0822-PWPl-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 167819h
SES0822-PWPl-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 167819h
SES0822-PWPl-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 167819h
SES0822-PWPl-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [63 empty] | 167819h
SES0822-PWPl-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [63 empty] | 167819h
SES0822-PWPl-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 167819h
SES0822-PWPl-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 167819h
SES0822-PWPl-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [67 empty] | 167819h
SES0822-PWPl-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [67 empty] | 167819h
SES0822-PWPl-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [61 empty] | 167819h
SES0822-PWPl-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPl-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [61 empty] | 167819h
MEM1214-PWPp-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103532h
MEM1214-PWPp-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103528h
MEM1214-PWPp-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103528h
MEM1214-PWPp-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103528h
MEM1214-PWPp-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103528h
MEM1214-PWPp-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-07-23: 103528h
MEM1214-PWPp-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM1214-PWPp-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-07-23: 103528h
MCD0822-PWPp-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 1342554h
MCD0822-PWPp-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 1342554h
MCD0822-PWPp-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [36 empty] | 2023-06-25: 1342554h
MCD0822-PWPp-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MCD0822-PWPp-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [36 empty] | 2023-06-25: 1342554h
SES0822-PWPp-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 1342554h
SES0822-PWPp-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 1342554h
SES0822-PWPp-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 1342554h
SES0822-PWPp-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 1342554h
SES0822-PWPp-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 1342554h
SES0822-PWPp-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 1342554h
SES0822-PWPp-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 1342554h
SES0822-PWPp-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 1342554h
SES0822-PWPp-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 1342554h
SES0822-PWPp-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 1342554h
SES0822-PWPp-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 1342554h
SES0822-PWPp-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 1342554h
SES0822-PWPp-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 1342554h
SES0822-PWPp-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 1342554h
SES0822-PWPp-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [35 empty] | 1342554h
SES0822-PWPp-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SES0822-PWPp-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [35 empty] | 1342554h
MEM0821-CWP-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [81 empty] | 8h | 184h
MEM0821-CWP-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [81 empty] | 8h | 184h
MEM0821-CWP-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 7007h | 2885h
MEM0821-CWP-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 7007h | 2885h
MEM0821-CWP-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 246852h
MEM0821-CWP-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 246852h
MEM0821-CWP-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [82 empty] | 164568h | 82284h
MEM0821-CWP-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-CWP-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [82 empty] | 164568h | 82284h
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 25123h | 59114h | 59114h | 59114h | 59114h | 59114h | 33990h
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 25123h | 59114h | 59114h | 59114h | 59114h | 59114h | 33990h
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 25123h | 59114h | 59114h | 59114h | 59114h | 59114h | 33990h
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 25123h | 59114h | 59114h | 59114h | 59114h | 59114h | 33990h
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 2956h | 118227h | 118227h | 115272h
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 2956h | 118227h | 118227h | 115272h
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 2956h | 118227h | 118227h | 115272h
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 2956h | 118227h | 118227h | 115272h
MEM0821-PWPe-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 2080h
MEM0821-PWPe-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 2080h
MEM0821-PWPe-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 2080h
MEM0821-PWPe-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 2080h
MEM0821-PWPe-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 1397h | 9779h
MEM0821-PWPe-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 1397h | 9779h
MEM0821-PWPe-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 1397h | 9779h
MEM0821-PWPe-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPe-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 1397h | 9779h
MEM0821-PWPp-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 16640h
MEM0821-PWPp-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 16640h
MEM0821-PWPp-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 16640h
MEM0821-PWPp-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 16640h
MEM0821-PWPp-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 11175h | 78222h
MEM0821-PWPp-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 11175h | 78222h
MEM0821-PWPp-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [59 empty] | 11175h | 78222h
MEM0821-PWPp-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPp-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [59 empty] | 11175h | 78222h
MEM0821-PWPl-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 2080h
MEM0821-PWPl-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 2080h
MEM0821-PWPl-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 2080h
MEM0821-PWPl-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 2080h
MEM0821-PWPl-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 11176h
MEM0821-PWPl-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 11176h
MEM0821-PWPl-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [77 empty] | 11176h
MEM0821-PWPl-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MEM0821-PWPl-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [77 empty] | 11176h
EEE1063-CWP-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 18000h | 62000h
EEE1063-CWP-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1063-CWP-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 18000h | 62000h
EEE1061-CWP-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [75 empty] | 26696h
EEE1061-CWP-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1061-CWP-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [75 empty] | 26696h
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 31024h | 49639h | 49639h | 18614h
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 31024h | 49639h | 49639h | 18614h
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 31024h | 49639h | 49639h | 18614h
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 31024h | 49639h | 49639h | 18614h
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [56 empty] | 5584h | 24819h | 24819h | 24819h | 24819h | 24819h | 19235h
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [56 empty] | 5584h | 24819h | 24819h | 24819h | 24819h | 24819h | 19235h
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 15790h | 25265h | 25265h | 25265h | 25265h | 25265h | 9474h
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 15790h | 25265h | 25265h | 25265h | 25265h | 25265h | 9474h
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 15790h | 25265h | 25265h | 25265h | 25265h | 25265h | 9474h
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 15790h | 25265h | 25265h | 25265h | 25265h | 25265h | 9474h
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 5685h | 25265h | 25265h | 25265h | 25265h | 25265h | 19580h
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 5685h | 25265h | 25265h | 25265h | 25265h | 25265h | 19580h
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 37897h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 22738h
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 37897h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 22738h
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [51 empty] | 37897h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 22738h
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [51 empty] | 37897h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 22738h
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [50 empty] | 13643h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 46992h
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [50 empty] | 13643h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 60635h | 46992h
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 20843h | 35370h | 35370h | 35370h | 24633h
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 20843h | 35370h | 35370h | 35370h | 24633h
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [71 empty] | 20843h | 35370h | 35370h | 35370h | 24633h
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [71 empty] | 20843h | 35370h | 35370h | 35370h | 24633h
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 10737h | 35370h | 35370h | 35370h | 34738h
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 10737h | 35370h | 35370h | 35370h | 34738h
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h | 106930h
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h | 213861h
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [28 empty] | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h | 193165h
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [55 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [55 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [58 empty] | 6238h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h | 43663h
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 8408h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 5045h
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 8408h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 13452h | 5045h
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 757h | 4708h | 4708h | 4708h | 4708h | 589h
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 757h | 4708h | 4708h | 4708h | 4708h | 589h
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [70 empty] | 2102h | 4708h | 4708h | 4708h | 3952h
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [70 empty] | 2102h | 4708h | 4708h | 4708h | 3952h
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 3153h | 5045h | 5045h | 5045h | 1892h
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 3154h | 5046h | 5046h | 5046h | 1892h
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 3154h | 5046h | 5046h | 5046h | 1892h
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [57 empty] | 7643h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 12229h | 7032h
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [72 empty] | 3447h | 4708h | 4708h | 4708h | 2606h
SWP-035-1052 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SWP-035-1052 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-035-1052 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MIS30350 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
MIS30350 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MIS30350 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
B42033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
B42033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
B42033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 10453h
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 10453h
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [78 empty] | 17247h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 14111h
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [78 empty] | 17247h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 14111h
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [53 empty] | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 10453h
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [53 empty] | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 20905h | 10453h
A305360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A305360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A305360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
A305370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
A305370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
A305370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
SWP-0xx-0817 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units
SWP-0xx-0817 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
SWP-0xx-0817 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units
EBD0600-CWP-589 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | [88 empty] | 2h | 3h
EBD0600-CWP-589 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units
EBD0600-CWP-589 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | [88 empty] | 2h | 3h
CEC0800-CWP-475 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 38h | 114h
CEC0800-CWP-475 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CEC0800-CWP-475 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 38h | 114h
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 1144h | 1144h | 1144h | 1144h | 1144h
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 1144h | 1144h | 1144h | 1144h | 1144h
ESD0800-CWP-482 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 1520h | 47105h
ESD0800-CWP-482 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD0800-CWP-482 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 1520h | 47105h
ESD0800-CWP-483 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [60 empty] | 104504h
ESD0800-CWP-483 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD0800-CWP-483 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [60 empty] | 104504h
RIN0800-CWP-021 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 6h | 186h
RIN0800-CWP-021 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
RIN0800-CWP-021 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 6h | 186h
KMT0800-CWP-415 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 162h | 414h
KMT0800-CWP-415 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
KMT0800-CWP-415 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 162h | 414h
EEE0800-CWP-416 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 192h
EEE0800-CWP-416 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0800-CWP-416 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 192h
EBD0800-CWP-417 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 4125h | 127875h
EBD0800-CWP-417 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0800-CWP-417 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 4125h | 127875h
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 7834h | 19584h | 19584h | 11750h
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 7834h | 19584h | 19584h | 11750h
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 826h | 862h | 862h | 323h
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 826h | 862h | 862h | 323h
ELU0817-CWP-050 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [98 empty] | 96h
ELU0817-CWP-050 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ELU0817-CWP-050 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [98 empty] | 96h
MMR0817-CWP-022 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 5400h | 360h
MMR0817-CWP-022 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0817-CWP-022 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 5400h | 360h
MEM0817-CWP-023 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 960h
MEM0817-CWP-023 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-023 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 960h
CPI0817-CWP-024 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 448h
CPI0817-CWP-024 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CPI0817-CWP-024 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 448h
MEM0817-CWP-025 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 224h
MEM0817-CWP-025 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-025 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 224h
MEM0817-CWP-026 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 5760h
MEM0817-CWP-026 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-026 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 5760h
SSD0817-CWP-027 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 960h
SSD0817-CWP-027 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SSD0817-CWP-027 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 960h
SSD0817-CWP-028 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 160h
SSD0817-CWP-028 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SSD0817-CWP-028 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 160h
SES0817-CWP-029 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 320h
SES0817-CWP-029 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0817-CWP-029 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 320h
MCD0817-CWP-030 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units
MCD0817-CWP-030 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0817-CWP-030 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units
MEM0817-CWP-031 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 800h
MEM0817-CWP-031 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-031 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 800h
STP0817-CWP-032 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 576h
STP0817-CWP-032 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
STP0817-CWP-032 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 576h
MSD0817-CWP-033 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [73 empty] | 800h
MSD0817-CWP-033 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0817-CWP-033 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [73 empty] | 800h
MEM0817-CWP-034 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 192h
MEM0817-CWP-034 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-034 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 192h
MEM0817-CWP-035 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 960h
MEM0817-CWP-035 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-035 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 960h
MMR0817-CWP-036 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 960h
MMR0817-CWP-036 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0817-CWP-036 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 960h
SES0817-CWP-037 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 1920h
SES0817-CWP-037 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0817-CWP-037 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 1920h
MEM0817-CWP-038 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 576h
MEM0817-CWP-038 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-038 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 576h
MEM0817-CWP-498 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 58h | 1574h
MEM0817-CWP-498 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-498 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 58h | 1574h
MEM0817-CWP-045 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 102h | 90h
MEM0817-CWP-045 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-045 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 102h | 90h
MMR0817-CWP-046 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 1002h | 438h
MMR0817-CWP-046 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0817-CWP-046 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 1002h | 438h
MEM0817-CWP-039 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 1632h
MEM0817-CWP-039 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-039 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 1632h
SES0817-CWP-040 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 320h
SES0817-CWP-040 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0817-CWP-040 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 320h
SES0817-CWP-041 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 320h
SES0817-CWP-041 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0817-CWP-041 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 320h
SES0817-CWP-042 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [97 empty] | 1536h
SES0817-CWP-042 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0817-CWP-042 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [97 empty] | 1536h
MEM0817-CWP-043 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units
MEM0817-CWP-043 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-043 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units
MCD0817-CWP-044 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 2448h
MCD0817-CWP-044 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0817-CWP-044 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 2448h
MEM0817-CWP-047 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 160h
MEM0817-CWP-047 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0817-CWP-047 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 160h
EEL0817-CWP-048 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [97 empty] | 6000h
EEL0817-CWP-048 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEL0817-CWP-048 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [97 empty] | 6000h
SES0817-CWP-049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [97 empty] | 336h | 168h
SES0817-CWP-049 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0817-CWP-049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [97 empty] | 336h | 168h
JIL0817-CWP-051 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [99 empty] | 1920h
JIL0817-CWP-051 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0817-CWP-051 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [99 empty] | 1920h
SWP-007-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 4710h | 1434h
SWP-007-0820 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-007-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 4710h | 1434h
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 978h | 978h | 978h | 978h | 978h | 978h | 978h | 978h | 978h
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 978h | 978h | 978h | 978h | 978h | 978h | 978h | 978h | 978h
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 1535h | 3837h | 3837h | 3837h | 3837h | 3837h | 3837h | 3837h | 3837h | 3837h | 2302h
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 1535h | 3837h | 3837h | 3837h | 3837h | 3837h | 3837h | 3837h | 3837h | 3837h | 2302h
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [62 empty] | 223h | 223h |  |  | 179h | 223h | 223h | 223h | 223h | 223h | 223h | 223h | 223h | 223h | 179h
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [62 empty] | 223h | 223h |  |  | 179h | 223h | 223h | 223h | 223h | 223h | 223h | 223h | 223h | 223h | 179h
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 19h | 50h | 50h | 34h | 42h | 42h | 42h | 42h | 23h
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 19h | 50h | 50h | 34h | 42h | 42h | 42h | 42h | 23h
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 7h | 271h | 271h | 271h | 271h | 271h | 265h
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 7h | 271h | 271h | 271h | 271h | 271h | 265h
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 15h | 600h | 600h | 600h | 600h | 600h | 600h | 600h | 585h
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 15h | 600h | 600h | 600h | 600h | 600h | 600h | 600h | 585h
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [61 empty] | 467h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 1868h
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [61 empty] | 467h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 2334h | 1868h
ESD0822-CWP-493 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [75 empty] | 300h | 480h | 180h
ESD0822-CWP-493 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD0822-CWP-493 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [75 empty] | 300h | 480h | 180h
JIL0800-CWP-058 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 1306h | 6528h | 5222h
JIL0800-CWP-058 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0800-CWP-058 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 1306h | 6528h | 5222h
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 1560h | 3900h | 3900h | 3900h | 3900h | 3900h | 2340h
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 1560h | 3900h | 3900h | 3900h | 3900h | 3900h | 2340h
SWP-003-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 4416h | 10944h
SWP-003-0820 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-003-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 4416h | 10944h
SWP-004-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [75 empty] | 3174h | 2970h
SWP-004-0820 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-004-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [75 empty] | 3174h | 2970h
SWP-005-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 6144h
SWP-005-0820 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-005-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 6144h
JIL0820-CWP-418 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 490h | 1152h | 662h
JIL0820-CWP-418 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0820-CWP-418 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 490h | 1152h | 662h
SWP-006-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 4710h | 1434h
SWP-006-0820 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-006-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 4710h | 1434h
MEM0821-CWP-421 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 1221h | 8143h | 2036h
MEM0821-CWP-421 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-421 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 1221h | 8143h | 2036h
MEM0821-CWP-422 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 2171h | 2171h | 2171h
MEM0821-CWP-422 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-422 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 2171h | 2171h | 2171h
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h | 13h
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 54h | 128h | 128h | 128h | 128h | 128h | 74h
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 54h | 128h | 128h | 128h | 128h | 128h | 74h
MEM0821-CWP-083 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 5696h | 14543h | 121h
MEM0821-CWP-083 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-083 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 5696h | 14543h | 121h
MEM0821-CWP-084 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 26875h | 41533h
MEM0821-CWP-084 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-084 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 26875h | 41533h
EBD0821-CWP-081 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 2370h | 1230h
EBD0821-CWP-081 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0821-CWP-081 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 2370h | 1230h
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 38h | 48h | 48h | 48h | 10h
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 38h | 48h | 48h | 48h | 10h
MEM0821-CWP-087 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 20360h
MEM0821-CWP-087 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-087 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 20360h
EEE0821-CWP-089 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 948h | 1440h | 492h
EEE0821-CWP-089 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0821-CWP-089 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 948h | 1440h | 492h
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 0h
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 2h | 0h
TTU0821-CWP-420 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 213h | 340h | 264h
TTU0821-CWP-420 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0821-CWP-420 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 213h | 340h | 264h
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 51h | 120h | 120h | 120h | 69h
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 51h | 120h | 120h | 120h | 69h
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [56 empty] | 2967h | 14241h | 14241h | 14241h | 14241h | 14241h | 8901h
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [56 empty] | 2967h | 14241h | 14241h | 14241h | 14241h | 14241h | 8901h
MCD0821-CWP-066 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 27h | 27h | 11h
MCD0821-CWP-066 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0821-CWP-066 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 27h | 27h | 11h
ECB0821-CWP-082 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 23205h | 195h
ECB0821-CWP-082 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0821-CWP-082 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 23205h | 195h
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 16619h | 16758h | 16758h | 16758h | 4609h
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 16619h | 16758h | 16758h | 16758h | 4609h
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 8145h | 8145h | 8145h | 8145h | 1629h
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 8145h | 8145h | 8145h | 8145h | 1629h
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [56 empty] | 4578h | 21973h | 21973h | 17396h
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [56 empty] | 4578h | 21973h | 21973h | 17396h
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 6152h | 15708h | 15708h | 16755h | 18850h | 18850h | 2225h
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 6152h | 15708h | 15708h | 16755h | 18850h | 18850h | 2225h
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 209h | 288h | 288h | 288h | 79h
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 209h | 288h | 288h | 288h | 79h
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [78 empty] | 494h | 461h | 576h | 576h | 576h | 197h
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [78 empty] | 494h | 461h | 576h | 576h | 576h | 197h
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [75 empty] | 914h | 914h | 914h | 914h | 914h | 914h | 914h | 914h | 914h | 914h | 457h
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [75 empty] | 914h | 914h | 914h | 914h | 914h | 914h | 914h | 914h | 914h | 914h | 457h
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 164h | 786h | 786h | 786h | 786h | 655h |  | 786h | 754h
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 164h | 786h | 786h | 786h | 786h | 655h |  | 786h | 754h
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [58 empty] | 172h | 429h | 429h | 429h | 172h
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [58 empty] | 172h | 429h | 429h | 429h | 172h
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 28806h | 29048h | 29048h | 242h
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 28806h | 29048h | 29048h | 242h
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 38h | 48h | 48h | 48h | 10h
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 38h | 48h | 48h | 48h | 10h
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 102h | 128h | 128h | 128h | 128h | 128h | 77h
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 102h | 128h | 128h | 128h | 128h | 128h | 77h
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 130h | 162h | 162h | 162h | 162h | 162h | 162h | 97h
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 130h | 162h | 162h | 162h | 162h | 162h | 162h | 97h
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 48h | 59h | 59h | 59h | 59h | 59h | 59h | 36h
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 48h | 59h | 59h | 59h | 59h | 59h | 59h | 36h
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 218h | 272h | 272h | 272h | 272h | 272h | 54h
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 218h | 272h | 272h | 272h | 272h | 272h | 54h
TTU0821-CWP-419 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 51h | 765h
TTU0821-CWP-419 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0821-CWP-419 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 51h | 765h
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 3224h | 15475h | 15475h | 12251h
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 3224h | 15475h | 15475h | 12251h
SWP-008-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 6336h | 11520h | 9024h
SWP-008-0821 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-008-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 6336h | 11520h | 9024h
SWP-009-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 8352h | 11520h | 7008h
SWP-009-0821 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-009-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 8352h | 11520h | 7008h
SWP-010-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 6144h
SWP-010-0821 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-010-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 6144h
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 4217h | 11246h | 11246h | 11246h | 9278h
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 4217h | 11246h | 11246h | 11246h | 9278h
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 536h | 775h | 775h | 775h | 394h
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 536h | 775h | 775h | 775h | 394h
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 258h | 258h | 258h | 258h | 258h | 258h | 258h | 258h | 258h | 258h | 258h
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 258h | 258h | 258h | 258h | 258h | 258h | 258h | 258h | 258h | 258h | 258h
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 3078h | 3490h | 2327h | 2909h | 412h
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 3078h | 3490h | 2327h | 2909h | 412h
TTU0822-CWP-428 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [65 empty] | 537h | 727h
TTU0822-CWP-428 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-428 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [65 empty] | 537h | 727h
MEM0822-CWP-168 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 813h | 813h | 813h
MEM0822-CWP-168 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-168 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 813h | 813h | 813h
MEM0822-CWP-169 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 1741h | 7736h | 5995h
MEM0822-CWP-169 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-169 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 1741h | 7736h | 5995h
MEM0822-CWP-170 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 5700h | 5700h
MEM0822-CWP-170 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-170 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 5700h | 5700h
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 50h | 50h | 50h | 50h
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 50h | 50h | 50h | 50h
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 144h | 144h | 144h | 144h
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 144h | 144h | 144h | 144h
MEM0822-CWP-174 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 320h | 1280h
MEM0822-CWP-174 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-174 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 320h | 1280h
MEM0822-CWP-175 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 640h | 2560h
MEM0822-CWP-175 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-175 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 640h | 2560h
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h | 960h
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 610h | 610h | 610h | 610h
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 610h | 610h | 610h | 610h
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [72 empty] | 1364h | 2444h | 2606h | 2932h | 2932h | 2932h | 2932h | 1955h | 2444h | 2444h | 1079h
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [72 empty] | 1364h | 2444h | 2606h | 2932h | 2932h | 2932h | 2932h | 1955h | 2444h | 2444h | 1079h
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [74 empty] | 6929h | 32185h | 32185h | 32185h | 32185h | 21457h | 26821h | 26821h | 8270h
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [74 empty] | 6929h | 32185h | 32185h | 32185h | 32185h | 21457h | 26821h | 26821h | 8270h
ERE0822-CWP-134 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 576h | 22464h
ERE0822-CWP-134 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ERE0822-CWP-134 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 576h | 22464h
ERE0822-CWP-135 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 576h | 22464h
ERE0822-CWP-135 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ERE0822-CWP-135 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 576h | 22464h
ERE0822-CWP-136 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 576h | 22464h
ERE0822-CWP-136 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ERE0822-CWP-136 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 576h | 22464h
ERE0822-CWP-137 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 576h | 22464h
ERE0822-CWP-137 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ERE0822-CWP-137 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 576h | 22464h
EEE1042-CWP-138 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 5925h | 26331h | 20407h
EEE1042-CWP-138 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1042-CWP-138 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 5925h | 26331h | 20407h
EEE1042-CWP-139 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 5925h | 26331h | 20407h
EEE1042-CWP-139 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1042-CWP-139 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 5925h | 26331h | 20407h
EEE1042-CWP-140 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 5925h | 26331h | 20407h
EEE1042-CWP-140 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1042-CWP-140 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 5925h | 26331h | 20407h
EEE0820-CWP-141 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 18432h
EEE0820-CWP-141 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0820-CWP-141 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 18432h
EEE0820-CWP-142 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 10805h | 7627h
EEE0820-CWP-142 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0820-CWP-142 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 10805h | 7627h
EEE0820-CWP-143 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 14400h | 4032h
EEE0820-CWP-143 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0820-CWP-143 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 14400h | 4032h
SWP-019-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 6912h | 6912h
SWP-019-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-019-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 6912h | 6912h
SWP-012-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [100 empty] | 4542h | 11257h
SWP-012-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-012-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [100 empty] | 4542h | 11257h
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [99 empty] | 2666h | 11849h | 11849h | 1284h
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [99 empty] | 2666h | 11849h | 11849h | 1284h
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 226h | 326h | 326h | 326h | 326h | 101h
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 226h | 326h | 326h | 326h | 326h | 101h
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 1896h | 4946h | 4946h | 2061h
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 1896h | 4946h | 4946h | 2061h
MCD0822-CWP-103 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 9777h | 11069h | 10146h
MCD0822-CWP-103 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-103 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 9777h | 11069h | 10146h
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 1536h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 633h
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 1536h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 3615h | 633h
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [63 empty] | 2450h | 9073h |  | 10887h | 10887h | 10887h | 10887h | 2994h
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [63 empty] | 2450h | 9073h |  | 10887h | 10887h | 10887h | 10887h | 2994h
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 3348h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 710h
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 3348h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 4059h | 710h
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 11340h | 12960h | 12960h | 12960h | 12960h | 5940h
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 11340h | 12960h | 12960h | 12960h | 12960h | 5940h
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 1399h | 1598h | 1598h | 1598h | 1598h | 200h
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 1399h | 1598h | 1598h | 1598h | 1598h | 200h
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 681h | 1777h | 1777h | 1777h | 1777h | 1777h | 1777h | 1777h | 1777h | 1777h | 1096h
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 681h | 1777h | 1777h | 1777h | 1777h | 1777h | 1777h | 1777h | 1777h | 1777h | 1096h
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [79 empty] | 2h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 1h
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [79 empty] | 2h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 4h | 1h
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [67 empty] | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 3139h
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [67 empty] | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 5232h | 3139h
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [79 empty] | 275h | 1320h | 1320h | 1320h | 165h
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [79 empty] | 275h | 1320h | 1320h | 1320h | 165h
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 4875h | 7800h | 7800h | 7800h | 2925h
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 4875h | 7800h | 7800h | 7800h | 2925h
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 3427h | 6326h | 6326h | 6326h | 6326h | 2900h
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 3427h | 6326h | 6326h | 6326h | 6326h | 2900h
SWP-011-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [99 empty] | 6240h | 11520h | 1440h
SWP-011-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-011-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [99 empty] | 6240h | 11520h | 1440h
SWP-014-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [102 empty] | 19200h
SWP-014-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-014-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [102 empty] | 19200h
SWP-015-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [98 empty] | 4641h | 9183h
SWP-015-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-015-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [98 empty] | 4641h | 9183h
SWP-016-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [98 empty] | 8393h | 5431h
SWP-016-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-016-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [98 empty] | 8393h | 5431h
SWP-017-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [98 empty] | 8393h | 5431h
SWP-017-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-017-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [98 empty] | 8393h | 5431h
SWP-018-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [98 empty] | 8393h | 5431h
SWP-018-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-018-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [98 empty] | 8393h | 5431h
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 22200h | 52235h | 52235h | 52235h | 52235h | 52235h | 52235h | 52235h | 30035h
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 22200h | 52235h | 52235h | 52235h | 52235h | 52235h | 52235h | 52235h | 30035h
EEE0822-CWP-158 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 5h | 192h | 187h
EEE0822-CWP-158 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0822-CWP-158 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 5h | 192h | 187h
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 760h | 922h | 922h | 922h | 922h | 161h
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 760h | 922h | 922h | 922h | 922h | 161h
EEE0822-CWP-162 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 1714h | 4032h | 2318h
EEE0822-CWP-162 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0822-CWP-162 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 1714h | 4032h | 2318h
JIL0822-CWP-164 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 2880h | 2880h
JIL0822-CWP-164 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-164 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 2880h | 2880h
JIL0822-CWP-165 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 3840h | 3840h | 3840h
JIL0822-CWP-165 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-165 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 3840h | 3840h | 3840h
JIL0822-CWP-166 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 19910h | 46848h | 26938h
JIL0822-CWP-166 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-166 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 19910h | 46848h | 26938h
MSD0822-CWP-508 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 80h | 80h
MSD0822-CWP-508 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-508 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 80h | 80h
MSD0822-CWP-509 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 17508h | 17508h
MSD0822-CWP-509 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-509 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 17508h | 17508h
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 326h | 768h | 768h | 768h | 442h
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 326h | 768h | 768h | 768h | 442h
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 5458h
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 6822h | 5458h
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [48 empty] | 45228h | 51689h | 51689h | 51689h | 51689h | 51689h | 51689h | 51689h | 51689h | 51689h | 40921h
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [48 empty] | 45228h | 51689h | 51689h | 51689h | 51689h | 51689h | 51689h | 51689h | 51689h | 51689h | 40921h
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [58 empty] | 2278h | 10934h | 10934h | 10934h | 10934h | 10934h | 9111h |  | 10478h
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [58 empty] | 2278h | 10934h | 10934h | 10934h | 10934h | 10934h | 9111h |  | 10478h
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 8896h | 12437h | 8291h | 10364h | 10364h | 10364h | 10364h | 10364h | 3196h
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 8896h | 12437h | 8291h | 10364h | 10364h | 10364h | 10364h | 10364h | 3196h
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 1986h | 10364h | 10364h | 10364h | 10364h | 10364h | 10364h | 10364h | 10105h
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 1986h | 10364h | 10364h | 10364h | 10364h | 10364h | 10364h | 10364h | 10105h
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 336h | 13420h | 13420h | 8611h
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 336h | 13420h | 13420h | 8611h
MMR0822-CWP-147 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 1724h | 1971h | 1560h
MMR0822-CWP-147 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0822-CWP-147 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 1724h | 1971h | 1560h
MMR0822-CWP-148 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 1724h | 1971h | 1560h
MMR0822-CWP-148 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0822-CWP-148 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 1724h | 1971h | 1560h
MMR0822-CWP-149 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 1724h | 1971h | 1560h
MMR0822-CWP-149 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0822-CWP-149 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 1724h | 1971h | 1560h
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 775h | 775h | 775h | 775h | 155h
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 775h | 775h | 775h | 775h | 155h
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 745h | 1376h | 1376h | 1376h | 1376h | 631h
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 745h | 1376h | 1376h | 1376h | 1376h | 631h
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 2304h | 2304h | 2304h | 2304h | 2304h | 2304h
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 2304h | 2304h | 2304h | 2304h | 2304h | 2304h
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 5856h
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 9760h | 5856h
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 320h | 320h | 320h | 320h | 320h | 320h
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 320h | 320h | 320h | 320h | 320h | 320h
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 4640h | 4640h | 4640h | 4640h | 4640h | 4640h
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 4640h | 4640h | 4640h | 4640h | 4640h | 4640h
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 14795h | 14795h | 14795h | 14795h | 14795h | 14795h | 14795h | 14795h
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 14795h | 14795h | 14795h | 14795h | 14795h | 14795h | 14795h | 14795h
JSD0822-CWP-494 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 4320h | 4320h
JSD0822-CWP-494 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JSD0822-CWP-494 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 4320h | 4320h
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3120h | 7800h | 7800h | 4680h
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3120h | 7800h | 7800h | 4680h
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 102h | 512h | 512h | 410h
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 102h | 512h | 512h | 410h
ERE0822-CWP-132 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 576h | 22464h
ERE0822-CWP-132 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ERE0822-CWP-132 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 576h | 22464h
ERE0822-CWP-133 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 576h | 22464h
ERE0822-CWP-133 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ERE0822-CWP-133 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 576h | 22464h
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [64 empty] | 5451h |  | 13917h | 13917h | 13917h | 13917h | 8466h
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [64 empty] | 5451h |  | 13917h | 13917h | 13917h | 13917h | 8466h
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 204h | 533h | 533h | 506h
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 204h | 533h | 533h | 506h
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 120h | 2398h | 2398h | 2398h | 679h
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 120h | 2398h | 2398h | 2398h | 679h
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 18h | 714h | 714h | 714h | 714h | 714h | 714h | 714h | 714h | 268h
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 18h | 714h | 714h | 714h | 714h | 714h | 714h | 714h | 714h | 268h
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [34 empty] | 1882h | 2353h | 2353h | 2353h | 2353h | 2353h | 2353h | 471h
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [34 empty] | 1882h | 2353h | 2353h | 2353h | 2353h | 2353h | 2353h | 471h
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [70 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [70 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [27 empty] | 2761h | 3451h | 3451h | 3451h | 3451h | 3451h | 3451h | 690h
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [27 empty] | 2761h | 3451h | 3451h | 3451h | 3451h | 3451h | 3451h | 690h
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [63 empty] | 2316h | 3457h |  | 4148h | 4148h | 4148h | 4148h | 4148h | 4148h | 2523h
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [63 empty] | 2316h | 3457h |  | 4148h | 4148h | 4148h | 4148h | 4148h | 4148h | 2523h
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [36 empty] | 2023-07-09: 1882h; 2023-07-16: 2353h; 2023-07-23: 2353h; 2023-07-30: 2353h | 2353h | 2353h | 2353h | 471h
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [36 empty] | 2023-07-09: 1882h; 2023-07-16: 2353h; 2023-07-23: 2353h; 2023-07-30: 2353h | 2353h | 2353h | 2353h | 471h
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [34 empty] | 2694h | 3368h | 3368h | 3368h | 3368h | 3368h | 3368h | 674h
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [34 empty] | 2694h | 3368h | 3368h | 3368h | 3368h | 3368h | 3368h | 674h
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [72 empty] | 1329h | 3394h | 3620h | 4073h | 4073h | 4073h | 4073h | 2517h
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [72 empty] | 1329h | 3394h | 3620h | 4073h | 4073h | 4073h | 4073h | 2517h
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [34 empty] | 1810h | 2262h | 2262h | 2262h | 2262h | 2262h | 2262h | 452h
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [34 empty] | 1810h | 2262h | 2262h | 2262h | 2262h | 2262h | 2262h | 452h
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [70 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [70 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [27 empty] | 2655h | 3318h | 3318h | 3318h | 3318h | 3318h | 3318h | 664h
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [27 empty] | 2655h | 3318h | 3318h | 3318h | 3318h | 3318h | 3318h | 664h
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [63 empty] | 2316h | 3457h |  | 4148h | 4148h | 4148h | 4148h | 4148h | 4148h | 2523h
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [63 empty] | 2316h | 3457h |  | 4148h | 4148h | 4148h | 4148h | 4148h | 4148h | 2523h
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [36 empty] | 2023-07-09: 1810h; 2023-07-16: 2262h; 2023-07-23: 2262h; 2023-07-30: 2262h | 2262h | 2262h | 2262h | 452h
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [36 empty] | 2023-07-09: 1810h; 2023-07-16: 2262h; 2023-07-23: 2262h; 2023-07-30: 2262h | 2262h | 2262h | 2262h | 452h
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [34 empty] | 2694h | 3368h | 3368h | 3368h | 3368h | 3368h | 3368h | 674h
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [34 empty] | 2694h | 3368h | 3368h | 3368h | 3368h | 3368h | 3368h | 674h
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [72 empty] | 1329h | 3393h | 3620h | 4072h | 4072h | 4072h | 4072h | 2517h
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [72 empty] | 1329h | 3393h | 3620h | 4072h | 4072h | 4072h | 4072h | 2517h
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [27 empty] | 2655h | 3318h | 3318h | 3318h | 3318h | 3318h | 3318h | 664h
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [27 empty] | 2655h | 3318h | 3318h | 3318h | 3318h | 3318h | 3318h | 664h
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [34 empty] | 1810h | 2262h | 2262h | 2262h | 2262h | 2262h | 2262h | 452h
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [34 empty] | 1810h | 2262h | 2262h | 2262h | 2262h | 2262h | 2262h | 452h
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [70 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [70 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [63 empty] | 1895h | 2828h |  | 3393h | 3393h | 3393h | 3393h | 3393h | 3393h | 2064h
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [63 empty] | 1895h | 2828h |  | 3393h | 3393h | 3393h | 3393h | 3393h | 3393h | 2064h
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [36 empty] | 2023-07-09: 1810h; 2023-07-16: 2262h; 2023-07-23: 2262h; 2023-07-30: 2262h | 2262h | 2262h | 2262h | 452h
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [36 empty] | 2023-07-09: 1810h; 2023-07-16: 2262h; 2023-07-23: 2262h; 2023-07-30: 2262h | 2262h | 2262h | 2262h | 452h
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 679h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1697h | 1018h
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [34 empty] | 2694h | 3368h | 3368h | 3368h | 3368h | 3368h | 3368h | 674h
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [34 empty] | 2694h | 3368h | 3368h | 3368h | 3368h | 3368h | 3368h | 674h
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [72 empty] | 1329h | 3394h | 3620h | 4073h | 4073h | 4073h | 4073h | 2517h
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [72 empty] | 1329h | 3394h | 3620h | 4073h | 4073h | 4073h | 4073h | 2517h
TTU0822-CWP-190 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 309h | 1375h | 516h
TTU0822-CWP-190 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-190 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 309h | 1375h | 516h
MEM0822-CWP-191 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 83h | 83h | 17h
MEM0822-CWP-191 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-191 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 83h | 83h | 17h
MEM0822-CWP-192 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 67h | 83h | 50h
MEM0822-CWP-192 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-192 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 67h | 83h | 50h
MEM0822-CWP-193 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 33h | 83h | 83h
MEM0822-CWP-193 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-193 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 33h | 83h | 83h
MEM0822-CWP-194 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 83h | 83h | 33h
MEM0822-CWP-194 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-194 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 83h | 83h | 33h
MEM0822-CWP-195 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 83h | 83h | 33h
MEM0822-CWP-195 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-195 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 83h | 83h | 33h
MEM0822-CWP-196 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 83h | 83h | 33h
MEM0822-CWP-196 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-196 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 83h | 83h | 33h
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 1200h | 48000h | 48000h | 46800h
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 1200h | 48000h | 48000h | 46800h
ECB0822-CWP-198 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3900h | 9750h | 9750h
ECB0822-CWP-198 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0822-CWP-198 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3900h | 9750h | 9750h
JIL0822-CWP-199 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [55 empty] | 29520h | 49200h | 39360h
JIL0822-CWP-199 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-199 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [55 empty] | 29520h | 49200h | 39360h
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 1085h | 1085h | 1085h | 1085h | 1085h | 1085h
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 1085h | 1085h | 1085h | 1085h | 1085h | 1085h
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 68h | 68h | 68h | 68h | 68h | 68h
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 68h | 68h | 68h | 68h | 68h | 68h
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 44792h | 44792h | 44792h | 44792h | 44792h | 44792h
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 44792h | 44792h | 44792h | 44792h | 44792h | 44792h
MSD0822-CWP-203 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 3600h | 3600h | 1440h
MSD0822-CWP-203 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-203 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 3600h | 3600h | 1440h
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 10859h | 10859h | 10859h | 10859h | 10859h | 10859h | 10859h | 10859h | 10859h
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 10859h | 10859h | 10859h | 10859h | 10859h | 10859h | 10859h | 10859h | 10859h
JIL0822-CWP-206 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 4000h | 4000h | 1600h
JIL0822-CWP-206 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-206 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 4000h | 4000h | 1600h
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 50h | 2000h | 2000h | 1950h
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 50h | 2000h | 2000h | 1950h
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3900h | 9750h | 9750h | 5850h
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3900h | 9750h | 9750h | 5850h
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 122h | 304h | 304h | 304h | 182h
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 122h | 304h | 304h | 304h | 182h
TTU0822-CWP-211 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 293h | 367h | 220h
TTU0822-CWP-211 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-211 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 293h | 367h | 220h
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 125h | 557h | 557h | 97h
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 125h | 557h | 557h | 97h
JIL0822-CWP-213 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 330h | 400h | 230h
JIL0822-CWP-213 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-213 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 330h | 400h | 230h
ECB0822-CWP-214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3900h | 9750h | 9750h
ECB0822-CWP-214 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0822-CWP-214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3900h | 9750h | 9750h
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 83h | 367h | 367h | 64h
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 83h | 367h | 367h | 64h
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 1056h | 5280h | 5280h | 1056h
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 1056h | 5280h | 5280h | 1056h
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 25h | 1000h | 1000h | 375h
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 25h | 1000h | 1000h | 375h
ECB0822-CWP-219 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3900h | 9750h | 9750h
ECB0822-CWP-219 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0822-CWP-219 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3900h | 9750h | 9750h
MEM0822-CWP-220 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [55 empty] | 4276h | 7127h | 5701h
MEM0822-CWP-220 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-220 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [55 empty] | 4276h | 7127h | 5701h
MEM0822-CWP-221 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 367h | 367h | 147h
MEM0822-CWP-221 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-221 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 367h | 367h | 147h
MEM0822-CWP-222 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [55 empty] | 220h | 367h | 293h
MEM0822-CWP-222 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-222 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [55 empty] | 220h | 367h | 293h
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 73h | 367h | 367h | 73h
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 73h | 367h | 367h | 73h
JIL0822-CWP-224 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [55 empty] | 8640h | 14400h | 11520h
JIL0822-CWP-224 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-224 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [55 empty] | 8640h | 14400h | 11520h
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 60h | 300h | 300h | 60h
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 60h | 300h | 300h | 60h
ECB0822-CWP-226 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3900h | 9750h | 9750h
ECB0822-CWP-226 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0822-CWP-226 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3900h | 9750h | 9750h
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 165h | 733h | 733h | 128h
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 165h | 733h | 733h | 128h
JIL0822-CWP-228 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 1056h | 1280h | 736h
JIL0822-CWP-228 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-228 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 1056h | 1280h | 736h
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 25h | 1000h | 1000h | 975h
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 25h | 1000h | 1000h | 975h
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 9h | 340h | 340h | 128h
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 9h | 340h | 340h | 128h
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 124h | 550h | 550h | 96h
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 124h | 550h | 550h | 96h
JIL0822-CWP-233 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 2112h | 2560h | 1472h
JIL0822-CWP-233 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-233 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 2112h | 2560h | 1472h
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 15h | 600h | 600h | 585h
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 15h | 600h | 600h | 585h
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 17h | 680h | 680h | 255h
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 17h | 680h | 680h | 255h
ECB0822-CWP-251 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3900h | 9750h | 9750h
ECB0822-CWP-251 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0822-CWP-251 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3900h | 9750h | 9750h
ECB0822-CWP-252 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3900h | 9750h | 9750h
ECB0822-CWP-252 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0822-CWP-252 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3900h | 9750h | 9750h
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 62h | 277h | 277h | 48h
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 62h | 277h | 277h | 48h
JIL0822-CWP-237 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 132h | 160h | 92h
JIL0822-CWP-237 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-237 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 132h | 160h | 92h
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 41h | 183h | 183h | 32h
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 41h | 183h | 183h | 32h
JIL0822-CWP-240 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 160h | 160h | 64h
JIL0822-CWP-240 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0822-CWP-240 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 160h | 160h | 64h
MCD0822-CWP-242 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [67 empty] | 1360h | 1360h | 544h
MCD0822-CWP-242 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-242 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [67 empty] | 1360h | 1360h | 544h
MRF0822-CWP-243 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [69 empty] | 408h | 680h | 544h
MRF0822-CWP-243 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MRF0822-CWP-243 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [69 empty] | 408h | 680h | 544h
MCD0822-CWP-244 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [69 empty] | 816h | 1360h | 1088h
MCD0822-CWP-244 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-244 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [69 empty] | 816h | 1360h | 1088h
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 68h | 340h | 340h | 68h
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 68h | 340h | 340h | 68h
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 19h | 446h | 446h | 446h | 446h | 279h
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 19h | 446h | 446h | 446h | 446h | 279h
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 14h | 68h | 68h | 68h | 54h
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 14h | 68h | 68h | 68h | 54h
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 477h | 1272h | 1272h | 1272h | 1272h | 1272h | 795h
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 477h | 1272h | 1272h | 1272h | 1272h | 1272h | 795h
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h | 53h
MEM0823-CWP-439 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 9h | 42h | 5h
MEM0823-CWP-439 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0823-CWP-439 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 9h | 42h | 5h
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 230h | 407h | 407h | 407h | 407h | 407h | 176h
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 230h | 407h | 407h | 407h | 407h | 407h | 176h
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 123h | 2949h | 2949h | 2949h | 2949h | 1843h
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 123h | 2949h | 2949h | 2949h | 2949h | 1843h
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 105h | 527h | 527h | 527h | 527h | 527h | 527h | 527h | 527h | 527h | 422h
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 105h | 527h | 527h | 527h | 527h | 527h | 527h | 527h | 527h | 527h | 422h
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 4031h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 1008h
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 4031h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 5039h | 1008h
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 9h | 46h | 46h | 46h | 37h
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 9h | 46h | 46h | 46h | 37h
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [72 empty] | 2h | 3h | 3h | 3h | 3h | 2h
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [72 empty] | 2h | 3h | 3h | 3h | 3h | 2h
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 349h
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 349h
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [56 empty] | 13h | 61h | 61h | 61h | 61h | 61h | 49h
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [56 empty] | 13h | 61h | 61h | 61h | 61h | 61h | 49h
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [61 empty] | 166h | 829h | 829h |  |  | 663h | 829h | 829h | 829h | 829h | 829h | 331h
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [61 empty] | 166h | 829h | 829h |  |  | 663h | 829h | 829h | 829h | 829h | 829h | 331h
TTU0823-CWP-505 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [74 empty] | 365h | 515h
TTU0823-CWP-505 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0823-CWP-505 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [74 empty] | 365h | 515h
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 26h | 131h | 131h | 131h | 131h | 26h
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 26h | 131h | 131h | 131h | 131h | 26h
MCD0823-CWP-264 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [78 empty] | 2931h | 3517h | 879h
MCD0823-CWP-264 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0823-CWP-264 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [78 empty] | 2931h | 3517h | 879h
SWP-020-0823 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [101 empty] | 6517h | 7307h
SWP-020-0823 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-020-0823 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [101 empty] | 6517h | 7307h
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 8508h | 43755h | 29170h | 36463h | 36463h | 15801h
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 8508h | 43755h | 29170h | 36463h | 36463h | 15801h
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 35h | 175h | 175h | 175h | 175h | 35h
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 35h | 175h | 175h | 175h | 175h | 35h
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 37h | 183h | 183h | 183h | 183h
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 37h | 183h | 183h | 183h | 183h
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [97 empty] | 1439h | 1629h | 1629h | 190h
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [97 empty] | 1439h | 1629h | 1629h | 190h
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 1439h | 1629h | 1629h | 190h
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 1439h | 1629h | 1629h | 190h
MEM0824-CWP-272 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [97 empty] | 541h | 275h
MEM0824-CWP-272 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0824-CWP-272 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [97 empty] | 541h | 275h
MEM0824-CWP-273 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 541h | 275h
MEM0824-CWP-273 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0824-CWP-273 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 541h | 275h
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [74 empty] | 37h | 1480h | 1480h | 1480h | 1443h
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [74 empty] | 37h | 1480h | 1480h | 1480h | 1443h
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 951h | 951h | 951h | 951h | 951h | 951h
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 951h | 951h | 951h | 951h | 951h | 951h
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 27h | 1085h | 1085h | 1085h | 1085h | 1085h | 1058h
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 27h | 1085h | 1085h | 1085h | 1085h | 1085h | 1058h
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [97 empty] | 2240h | 4072h | 4072h | 4072h | 1832h
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [97 empty] | 2240h | 4072h | 4072h | 4072h | 1832h
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 27h | 64h | 64h | 64h | 64h | 64h | 37h
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 27h | 64h | 64h | 64h | 64h | 64h | 37h
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 204h | 204h | 204h | 204h
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 204h | 204h | 204h | 204h
MCD0824-CWP-278 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [97 empty] | 869h | 1580h | 711h
MCD0824-CWP-278 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0824-CWP-278 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [97 empty] | 869h | 1580h | 711h
MCD0824-CWP-279 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 679h | 948h | 269h
MCD0824-CWP-279 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0824-CWP-279 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 679h | 948h | 269h
SWP-021-0824 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [98 empty] | 6758h | 3072h
SWP-021-0824 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-021-0824 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [98 empty] | 6758h | 3072h
SWP-022-0824 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [101 empty] | 6517h | 7307h
SWP-022-0824 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-022-0824 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [101 empty] | 6517h | 7307h
MMR0824-CWP-445 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 453h | 827h
MMR0824-CWP-445 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0824-CWP-445 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 453h | 827h
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 21h | 21h | 21h | 8h
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 21h | 21h | 21h | 8h
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 133h | 133h | 133h | 50h
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 133h | 133h | 133h | 50h
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 1264h | 1764h | 1764h | 1764h | 1764h | 1764h | 500h
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 1264h | 1764h | 1764h | 1764h | 1764h | 1764h | 500h
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 982h | 982h | 982h | 982h | 982h | 982h | 982h | 982h | 785h
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 982h | 982h | 982h | 982h | 982h | 982h | 982h | 982h | 785h
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [62 empty] | 982h | 982h | 982h | 982h | 982h | 982h | 982h | 982h | 785h
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [62 empty] | 982h | 982h | 982h | 982h | 982h | 982h | 982h | 982h | 785h
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 137h | 610h | 610h | 610h | 473h
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 137h | 610h | 610h | 610h | 473h
MRF0826-CWP-291 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 1067h | 853h
MRF0826-CWP-291 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MRF0826-CWP-291 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 1067h | 853h
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 26h | 32h | 32h | 32h | 32h | 32h | 6h
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 26h | 32h | 32h | 32h | 32h | 32h | 6h
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 25h | 993h | 993h | 993h | 993h | 993h | 770h
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 25h | 993h | 993h | 993h | 993h | 993h | 770h
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 1011h | 1011h | 1011h | 808h
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 1011h | 1011h | 1011h | 808h
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 960h | 960h | 960h | 960h
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 960h | 960h | 960h | 960h
EEE0826-CWP-300 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 347h | 400h | 53h
EEE0826-CWP-300 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0826-CWP-300 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 347h | 400h | 53h
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 64h | 286h | 286h | 286h | 222h
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 64h | 286h | 286h | 286h | 222h
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 450h | 2000h | 2000h | 2000h | 2000h | 2000h | 1550h
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 450h | 2000h | 2000h | 2000h | 2000h | 2000h | 1550h
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 16h | 73h | 73h | 73h | 73h | 73h | 57h
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 16h | 73h | 73h | 73h | 73h | 73h | 57h
JPA0826-CWP-450 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 82h | 110h
JPA0826-CWP-450 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JPA0826-CWP-450 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 82h | 110h
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 10h | 408h | 408h | 408h | 398h
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 10h | 408h | 408h | 408h | 398h
SWP-023-0826 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [97 empty] | 10368h | 3456h
SWP-023-0826 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-023-0826 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [97 empty] | 10368h | 3456h
SWP-024-0826 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [99 empty] | 10368h | 3456h
SWP-024-0826 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-024-0826 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [99 empty] | 10368h | 3456h
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 92h | 407h | 407h | 407h | 407h | 407h | 315h
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 92h | 407h | 407h | 407h | 407h | 407h | 315h
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 24h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 757h
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 24h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 976h | 757h
EEE0826-CWP-448 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 192h | 192h
EEE0826-CWP-448 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0826-CWP-448 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 192h | 192h
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 96h | 96h | 96h | 96h
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 96h | 96h | 96h | 96h
MSD0827-CWP-492 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 583h | 233h
MSD0827-CWP-492 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-492 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 583h | 233h
MSD0822-CWP-238 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 1697h | 1697h | 679h
MSD0822-CWP-238 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-238 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 1697h | 1697h | 679h
MSD0822-CWP-241 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 1018h | 1697h | 1357h
MSD0822-CWP-241 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0822-CWP-241 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 1018h | 1697h | 1357h
EEL0827-CWP-338 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 1900h | 500h
EEL0827-CWP-338 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEL0827-CWP-338 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 1900h | 500h
ELU0827-CWP-340 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 96h
ELU0827-CWP-340 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ELU0827-CWP-340 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 96h
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [60 empty] | 2337h | 2337h | 2337h | 2337h | 2337h | 2337h | 2337h | 438h
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [60 empty] | 2337h | 2337h | 2337h | 2337h | 2337h | 2337h | 2337h | 438h
JIL0827-CWP-341 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [98 empty] | 1200h | 720h
JIL0827-CWP-341 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0827-CWP-341 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [98 empty] | 1200h | 720h
MSD0827-CWP-367 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [57 empty] | 714h | 886h
MSD0827-CWP-367 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-367 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [57 empty] | 714h | 886h
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [58 empty] | 634h | 2818h | 2818h | 1057h
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [58 empty] | 634h | 2818h | 2818h | 1057h
MEM0827-CWP-315 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 224h
MEM0827-CWP-315 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-315 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 224h
MEM0827-CWP-316 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 3400h | 2040h
MEM0827-CWP-316 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-316 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 3400h | 2040h
MSD0827-CWP-317 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 960h
MSD0827-CWP-317 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-317 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 960h
SES0827-CWP-318 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 160h
SES0827-CWP-318 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0827-CWP-318 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 160h
SES0827-CWP-319 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 320h
SES0827-CWP-319 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0827-CWP-319 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 320h
MCD0827-CWP-320 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units
MCD0827-CWP-320 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0827-CWP-320 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units
MEM0827-CWP-321 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 13032h
MEM0827-CWP-321 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-321 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 13032h
STP0827-CWP-322 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 576h
STP0827-CWP-322 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
STP0827-CWP-322 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 576h
MSD0827-CWP-323 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [73 empty] | 800h
MSD0827-CWP-323 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-323 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [73 empty] | 800h
MEM0827-CWP-324 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 960h
MEM0827-CWP-324 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-324 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 960h
MEM0827-CWP-325 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 960h
MEM0827-CWP-325 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-325 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 960h
MMR0827-CWP-326 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 960h
MMR0827-CWP-326 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0827-CWP-326 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 960h
STP0827-CWP-327 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 960h | 960h
STP0827-CWP-327 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
STP0827-CWP-327 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 960h | 960h
MEM0827-CWP-328 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 576h
MEM0827-CWP-328 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-328 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 576h
MEM0827-CWP-329 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 2448h
MEM0827-CWP-329 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-329 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 2448h
SES0827-CWP-330 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 320h
SES0827-CWP-330 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0827-CWP-330 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 320h
SES0827-CWP-331 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 320h
SES0827-CWP-331 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0827-CWP-331 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 320h
SES0827-CWP-332 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 1536h
SES0827-CWP-332 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0827-CWP-332 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 1536h
MCD0827-CWP-334 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 2448h
MCD0827-CWP-334 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0827-CWP-334 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 2448h
MEM0827-CWP-335 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 800h
MEM0827-CWP-335 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-335 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 800h
MMR0827-CWP-336 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [97 empty] | 960h | 480h
MMR0827-CWP-336 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0827-CWP-336 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [97 empty] | 960h | 480h
SES0827-CWP-339 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 504h
SES0827-CWP-339 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0827-CWP-339 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 504h
MEM0827-CWP-313 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 960h
MEM0827-CWP-313 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-313 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 960h
CPI0827-CWP-314 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 448h
CPI0827-CWP-314 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CPI0827-CWP-314 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 448h
MMR0827-CWP-312 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 5760h
MMR0827-CWP-312 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0827-CWP-312 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 5760h
MEM0827-CWP-333 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units
MEM0827-CWP-333 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-333 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units
MEM0827-CWP-337 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 160h
MEM0827-CWP-337 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-337 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 160h
SWP-027-0827 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [100 empty] | 1955h | 1117h
SWP-027-0827 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-027-0827 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [100 empty] | 1955h | 1117h
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [67 empty] | 6949h | 8552h | 8552h | 8552h | 1603h
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [67 empty] | 6949h | 8552h | 8552h | 8552h | 1603h
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [65 empty] | 4682h | 4682h | 4682h | 4682h
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [65 empty] | 4682h | 4682h | 4682h | 4682h
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 12h | 12h | 12h | 12h
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 12h | 12h | 12h | 12h
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [63 empty] | 28708h | 28708h | 28708h | 28708h
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [63 empty] | 28708h | 28708h | 28708h | 28708h
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [61 empty] | 72h | 320h | 320h | 320h | 248h
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [61 empty] | 72h | 320h | 320h | 320h | 248h
JIL0827-CWP-363 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 367h | 864h | 497h
JIL0827-CWP-363 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0827-CWP-363 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 367h | 864h | 497h
JPA0827-CWP-451 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 122h | 288h | 166h
JPA0827-CWP-451 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JPA0827-CWP-451 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 122h | 288h | 166h
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 76h | 3054h | 3054h | 3054h | 2978h
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 76h | 3054h | 3054h | 3054h | 2978h
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [73 empty] | 30h | 30h | 30h | 30h
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [73 empty] | 30h | 30h | 30h | 30h
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 408h | 408h | 408h | 408h
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 408h | 408h | 408h | 408h
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 340h | 1512h | 1512h | 1512h | 1512h | 1512h | 1512h | 1172h
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 340h | 1512h | 1512h | 1512h | 1512h | 1512h | 1512h | 1172h
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 671h | 2982h | 2982h | 2982h | 2982h | 2982h | 2982h | 2311h
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 671h | 2982h | 2982h | 2982h | 2982h | 2982h | 2982h | 2311h
SWP-025-0827 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 4710h | 1434h
SWP-025-0827 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-025-0827 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 4710h | 1434h
SWP-026-0827 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 4542h | 9282h
SWP-026-0827 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-026-0827 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 4542h | 9282h
MCD0827-CWP-342 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 1875h | 1101h
MCD0827-CWP-342 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0827-CWP-342 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 1875h | 1101h
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 1h | 24h | 24h | 24h | 7h
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 1h | 24h | 24h | 24h | 7h
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 48h | 48h | 48h | 48h | 48h | 48h
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 48h | 48h | 48h | 48h | 48h | 48h
EEE0827-CWP-345 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 1344h | 1344h
EEE0827-CWP-345 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0827-CWP-345 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 1344h | 1344h
ELU0827-CWP-346 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [73 empty] | 1067h | 853h
ELU0827-CWP-346 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ELU0827-CWP-346 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [73 empty] | 1067h | 853h
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 93h | 411h | 411h | 411h | 411h | 411h | 411h | 319h
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 93h | 411h | 411h | 411h | 411h | 411h | 411h | 319h
EEE0827-CWP-457 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 317h | 384h | 67h
EEE0827-CWP-457 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE0827-CWP-457 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 317h | 384h | 67h
MEM0827-CWP-348 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 3h | 127h | 22h
MEM0827-CWP-348 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-348 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 3h | 127h | 22h
JIL0827-CWP-349 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [73 empty] | 1344h
JIL0827-CWP-349 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0827-CWP-349 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [73 empty] | 1344h
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 85h | 136h | 136h | 136h | 136h | 136h | 51h
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 85h | 136h | 136h | 136h | 136h | 136h | 51h
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 697h | 697h | 697h | 697h | 697h | 697h | 697h | 697h | 131h
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 697h | 697h | 697h | 697h | 697h | 697h | 697h | 697h | 131h
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [65 empty] | 954h | 1527h | 1527h | 1527h | 1527h | 267h
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [65 empty] | 954h | 1527h | 1527h | 1527h | 1527h | 267h
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 136h | 136h | 136h | 136h | 136h | 136h
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 136h | 136h | 136h | 136h | 136h | 136h
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 3456h | 15360h | 15360h | 15360h | 11904h
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 3456h | 15360h | 15360h | 15360h | 11904h
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [78 empty] | 325h | 1446h | 1446h | 1446h | 1446h | 1446h | 1446h | 1120h
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [78 empty] | 325h | 1446h | 1446h | 1446h | 1446h | 1446h | 1446h | 1120h
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 38h | 170h | 170h | 170h | 170h | 98h
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 38h | 170h | 170h | 170h | 170h | 98h
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 8442h
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 10721h | 8442h
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 865h | 4072h | 4072h | 3207h
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 865h | 4072h | 4072h | 3207h
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 73h | 73h | 73h | 73h | 73h | 73h | 73h
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 73h | 73h | 73h | 73h | 73h | 73h | 73h
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 679h | 679h | 679h | 679h | 679h | 679h
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 679h | 679h | 679h | 679h | 679h | 679h
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 136h | 136h | 136h | 136h | 136h | 136h
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 136h | 136h | 136h | 136h | 136h | 136h
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [65 empty] | 136h | 136h | 136h | 136h | 136h | 136h
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [65 empty] | 136h | 136h | 136h | 136h | 136h | 136h
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 1764h | 1764h | 1764h | 1764h | 1764h | 1764h
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 1764h | 1764h | 1764h | 1764h | 1764h | 1764h
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [77 empty] | 1018h | 1018h | 1018h | 1018h
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [77 empty] | 1018h | 1018h | 1018h | 1018h
JIL0827-CWP-365 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 5760h
JIL0827-CWP-365 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0827-CWP-365 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 5760h
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 46h | 1846h | 1846h | 1846h | 1846h | 1846h | 323h
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 46h | 1846h | 1846h | 1846h | 1846h | 1846h | 323h
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 4826h | 5850h | 5850h | 5850h | 1024h
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 4826h | 5850h | 5850h | 5850h | 1024h
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [67 empty] | 264h | 660h | 660h | 660h | 660h | 660h | 396h
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [67 empty] | 264h | 660h | 660h | 660h | 660h | 660h | 396h
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 18h | 18h | 18h | 18h | 18h | 18h | 18h | 18h | 11h
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 18h | 18h | 18h | 18h | 18h | 18h | 18h | 18h | 11h
ESD1042-CWP-511 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 1138h | 14h
ESD1042-CWP-511 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD1042-CWP-511 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 1138h | 14h
JPA1062-CWP-388 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 1584h | 1296h
JPA1062-CWP-388 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JPA1062-CWP-388 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 1584h | 1296h
JPA1062-CWP-389 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 960h
JPA1062-CWP-389 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JPA1062-CWP-389 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 960h
ESD1048-CWP-470 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [73 empty] | 576h
ESD1048-CWP-470 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD1048-CWP-470 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [73 empty] | 576h
EEE1049-CWP-471 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 1152h
EEE1049-CWP-471 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1049-CWP-471 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 1152h
EEE1048-CWP-472 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [73 empty] | 4416h
EEE1048-CWP-472 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1048-CWP-472 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [73 empty] | 4416h
EEE1048-CWP-473 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 698h | 70h
EEE1048-CWP-473 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1048-CWP-473 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 698h | 70h
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 3168h | 3840h | 3840h | 3840h | 3840h | 3840h | 3840h | 3840h | 2976h
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 3168h | 3840h | 3840h | 3840h | 3840h | 3840h | 3840h | 3840h | 2976h
MSD1214-CWP-374 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 453h | 347h
MSD1214-CWP-374 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD1214-CWP-374 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 453h | 347h
EEE1049-CWP-375 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 734h | 82h
EEE1049-CWP-375 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1049-CWP-375 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 734h | 82h
EEE1049-CWP-376 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 816h | 336h
EEE1049-CWP-376 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1049-CWP-376 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 816h | 336h
EEE1049-CWP-377 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 4416h
EEE1049-CWP-377 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1049-CWP-377 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 4416h
EEE1049-CWP-378 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 68h | 160h | 92h
EEE1049-CWP-378 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1049-CWP-378 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 68h | 160h | 92h
ESD1049-CWP-372 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 311h | 265h
ESD1049-CWP-372 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD1049-CWP-372 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 311h | 265h
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 1075h | 1229h | 1229h | 563h
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 1075h | 1229h | 1229h | 563h
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 56h | 56h | 56h | 56h | 56h
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 56h | 56h | 56h | 56h | 56h
ESD1062-CWP-486 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 4400h
ESD1062-CWP-486 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD1062-CWP-486 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 4400h
EEE1062-CWP-383 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [79 empty] | 51h | 120h | 21h
EEE1062-CWP-383 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1062-CWP-383 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [79 empty] | 51h | 120h | 21h
EEE1062-CWP-384 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 470h | 1200h | 730h
EEE1062-CWP-384 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1062-CWP-384 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 470h | 1200h | 730h
EEE1062-CWP-386 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 94h | 98h
EEE1062-CWP-386 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1062-CWP-386 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 94h | 98h
SWP-029-1062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [70 empty] | 2567h | 11257h
SWP-029-1062 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-029-1062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [70 empty] | 2567h | 11257h
SWP-030-1062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 8185h | 5639h
SWP-030-1062 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-030-1062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 8185h | 5639h
EBD1062-CWP-459 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 1664h | 6016h
EBD1062-CWP-459 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD1062-CWP-459 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 1664h | 6016h
EEE1062-CWP-460 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 108h | 276h
EEE1062-CWP-460 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1062-CWP-460 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 108h | 276h
ELU1062-CWP-461 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 36h | 1440h | 828h
ELU1062-CWP-461 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ELU1062-CWP-461 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 36h | 1440h | 828h
EEE1062-CWP-381 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [68 empty] | 64h | 160h | 160h
EEE1062-CWP-381 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1062-CWP-381 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [68 empty] | 64h | 160h | 160h
EEE1062-CWP-382 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 54h | 138h
EEE1062-CWP-382 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1062-CWP-382 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 54h | 138h
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 84h | 373h | 373h | 289h
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 84h | 373h | 373h | 289h
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 222h | 1024h | 1024h | 802h
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 222h | 1024h | 1024h | 802h
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 101h | 448h | 448h | 347h
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 101h | 448h | 448h | 347h
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [70 empty] | 7h | 299h | 299h | 299h | 299h | 299h | 299h | 299h | 299h | 291h
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [70 empty] | 7h | 299h | 299h | 299h | 299h | 299h | 299h | 299h | 299h | 291h
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 667h | 667h | 667h | 667h | 667h | 667h | 667h | 667h | 667h | 667h | 667h |  |  | 533h | 133h
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 667h | 667h | 667h | 667h | 667h | 667h | 667h | 667h | 667h | 667h | 667h |  |  | 533h | 133h
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 200h | 200h | 200h | 200h | 200h | 200h | 200h | 200h | 200h | 200h | 200h |  |  | 160h | 40h
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 200h | 200h | 200h | 200h | 200h | 200h | 200h | 200h | 200h | 200h | 200h |  |  | 160h | 40h
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 67h | 67h | 67h | 67h | 67h | 67h | 67h | 67h | 67h | 67h | 67h |  |  | 53h | 13h
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 67h | 67h | 67h | 67h | 67h | 67h | 67h | 67h | 67h | 67h | 67h |  |  | 53h | 13h
MEM0823-CWP-248 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 1344h
MEM0823-CWP-248 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0823-CWP-248 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 1344h
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [56 empty] | 10h | 43h | 43h | 33h
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [56 empty] | 10h | 43h | 43h | 33h
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 142h | 370h | 370h | 370h | 370h | 370h | 370h | 228h
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 142h | 370h | 370h | 370h | 370h | 370h | 370h | 228h
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [62 empty] | 111h | 493h | 411h |  | 493h | 493h | 464h
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [62 empty] | 111h | 493h | 411h |  | 493h | 493h | 464h
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [68 empty] | 2967h | 5314h | 5314h | 5314h | 5314h | 2347h
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [68 empty] | 2967h | 5314h | 5314h | 5314h | 5314h | 2347h
SWP-031-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 8160h | 11520h | 7200h
SWP-031-1214 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-031-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 8160h | 11520h | 7200h
SWP-042-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 8887h | 4937h
SWP-042-1214 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-042-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 8887h | 4937h
SWP-033-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 8887h | 4937h
SWP-033-1214 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-033-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 8887h | 4937h
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 520h | 2400h | 2400h | 1880h
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 520h | 2400h | 2400h | 1880h
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 1036h | 1856h | 1856h | 820h
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 1036h | 1856h | 1856h | 820h
MEM1214-CWP-398 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 520h | 1880h
MEM1214-CWP-398 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-398 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 520h | 1880h
MEM1214-CWP-400 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [78 empty] | 6462h | 7386h
MEM1214-CWP-400 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-400 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [78 empty] | 6462h | 7386h
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 2473h | 2800h | 2800h | 327h
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 2473h | 2800h | 2800h | 327h
ESD1214-CWP-487 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 120h | 120h
ESD1214-CWP-487 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD1214-CWP-487 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 120h | 120h
ESD1214-CWP-488 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 362h | 11214h
ESD1214-CWP-488 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD1214-CWP-488 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 362h | 11214h
ESD1214-CWP-489 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 13432h
ESD1214-CWP-489 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD1214-CWP-489 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 13432h
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [70 empty] | 109h | 1862h | 1862h | 1862h | 1986h | 2234h | 2234h | 884h
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [70 empty] | 109h | 1862h | 1862h | 1862h | 1986h | 2234h | 2234h | 884h
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 544h | 544h | 544h | 544h | 544h
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 544h | 544h | 544h | 544h | 544h
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 66h | 291h | 291h | 291h | 291h | 226h
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 66h | 291h | 291h | 291h | 291h | 226h
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 24h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 750h
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 24h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 968h | 750h
MEM0623-CWP-410 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [83 empty] | 16h | 628h | 173h
MEM0623-CWP-410 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0623-CWP-410 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [83 empty] | 16h | 628h | 173h
TTU0623-CWP-411 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [71 empty] | 11h | 5h
TTU0623-CWP-411 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0623-CWP-411 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [71 empty] | 11h | 5h
TTU0622-CWP-019 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 816h
TTU0622-CWP-019 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0622-CWP-019 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 816h
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 110h | 489h | 489h | 489h | 489h | 489h | 489h | 489h | 489h | 379h
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 110h | 489h | 489h | 489h | 489h | 489h | 489h | 489h | 489h | 379h
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 278h | 278h | 278h | 278h | 278h
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 278h | 278h | 278h | 278h | 278h
ESD0600-CWP-479 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [59 empty] | 165h | 5115h
ESD0600-CWP-479 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD0600-CWP-479 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [59 empty] | 165h | 5115h
ESD0600-CWP-480 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [62 empty] | 1320h | 9240h
ESD0600-CWP-480 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ESD0600-CWP-480 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [62 empty] | 1320h | 9240h
RIN1110-CWP-387 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 90h | 2790h
RIN1110-CWP-387 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
RIN1110-CWP-387 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 90h | 2790h
ECB0600-CWP-408 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 22800h | 22800h
ECB0600-CWP-408 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0600-CWP-408 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 22800h | 22800h
ELU0600-CWP-007 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 4992h
ELU0600-CWP-007 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ELU0600-CWP-007 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 4992h
MCD0622-CWP-497 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 2117h | 42348h | 40231h
MCD0622-CWP-497 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0622-CWP-497 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 2117h | 42348h | 40231h
KMT0622-CWP-006 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 122h | 175h | 87h
KMT0622-CWP-006 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
KMT0622-CWP-006 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 122h | 175h | 87h
JIL0622-CWP-409 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 26h | 38h | 11h
JIL0622-CWP-409 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0622-CWP-409 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 26h | 38h | 11h
SWP-001-0622 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 8887h | 4937h
SWP-001-0622 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-001-0622 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 8887h | 4937h
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 1090h | 2179h | 2179h | 2179h | 2179h | 2179h | 654h
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 1090h | 2179h | 2179h | 2179h | 2179h | 2179h | 654h
MEM0622-CWP-003 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 2552h | 6516h | 3964h
MEM0622-CWP-003 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0622-CWP-003 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 2552h | 6516h | 3964h
JIL0622-CWP-004 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 67h | 96h | 29h
JIL0622-CWP-004 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
JIL0622-CWP-004 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 67h | 96h | 29h
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 3040h | 3800h | 3800h | 3800h | 3800h | 3800h | 760h
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 3040h | 3800h | 3800h | 3800h | 3800h | 3800h | 760h
SWP-035-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 6720h | 8640h
SWP-035-0820 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-035-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 6720h | 8640h
SWP-036-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [76 empty] | 6144h
SWP-036-0820 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-036-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [76 empty] | 6144h
SWP-037-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 6144h
SWP-037-0820 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-037-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 6144h
SWP-040-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [98 empty] | 3950h
SWP-040-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-040-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [98 empty] | 3950h
SWP-041-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 3950h
SWP-041-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-041-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 3950h
SWP-039-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 2567h | 1382h
SWP-039-0822 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-039-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 2567h | 1382h
MEM1214-CWP-512 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 96h | 96h
MEM1214-CWP-512 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-512 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 96h | 96h
MEM1214-CWP-513 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 135h | 57h
MEM1214-CWP-513 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-513 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 135h | 57h
MEM1214-CWP-514 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 75h | 117h
MEM1214-CWP-514 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-514 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 75h | 117h
MEM1214-CWP-515 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 192h
MEM1214-CWP-515 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-515 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 192h
MEM1214-CWP-516 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 192h
MEM1214-CWP-516 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-516 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 192h
MEM1214-CWP-517 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 3h | 189h
MEM1214-CWP-517 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-517 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 3h | 189h
MEM1214-CWP-518 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 171h | 21h
MEM1214-CWP-518 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-518 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 171h | 21h
MEM1214-CWP-519 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 192h
MEM1214-CWP-519 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-519 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 192h
MEM1214-CWP-520 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 192h
MEM1214-CWP-520 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-520 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 192h
MEM1214-CWP-521 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 168h | 24h
MEM1214-CWP-521 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-521 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 168h | 24h
MEM1214-CWP-522 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 192h
MEM1214-CWP-522 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-522 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 192h
MEM1214-CWP-523 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 144h | 48h
MEM1214-CWP-523 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-523 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 144h | 48h
MEM1214-CWP-524 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 138h | 54h
MEM1214-CWP-524 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-524 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 138h | 54h
MEM1214-CWP-525 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 135h | 57h
MEM1214-CWP-525 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM1214-CWP-525 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 135h | 57h
ECB1214-CWP-526 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 4216h
ECB1214-CWP-526 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-526 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 4216h
ECB1214-CWP-527 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 4216h
ECB1214-CWP-527 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-527 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 4216h
ECB1214-CWP-528 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [92 empty] | 4216h
ECB1214-CWP-528 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-528 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [92 empty] | 4216h
ECB1214-CWP-529 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [93 empty] | 4216h
ECB1214-CWP-529 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-529 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [93 empty] | 4216h
ECB1214-CWP-530 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 4216h
ECB1214-CWP-530 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-530 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 4216h
ECB1214-CWP-531 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 4216h
ECB1214-CWP-531 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-531 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 4216h
ECB1214-CWP-532 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 4216h
ECB1214-CWP-532 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-532 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 4216h
ECB1214-CWP-533 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 4216h
ECB1214-CWP-533 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-533 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 4216h
ECB1214-CWP-534 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 4216h
ECB1214-CWP-534 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-534 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 4216h
ECB1214-CWP-535 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 4216h
ECB1214-CWP-535 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-535 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 4216h
ECB1214-CWP-536 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 4216h
ECB1214-CWP-536 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-536 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 4216h
ECB1214-CWP-537 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 4216h
ECB1214-CWP-537 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-537 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 4216h
ECB1214-CWP-538 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [88 empty] | 4216h
ECB1214-CWP-538 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-538 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [88 empty] | 4216h
ECB1214-CWP-539 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 4216h
ECB1214-CWP-539 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-539 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 4216h
MCD0822-CWP-540 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [70 empty] | 14335h | 36600h | 305h
MCD0822-CWP-540 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-540 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [70 empty] | 14335h | 36600h | 305h
MCD0822-CWP-541 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [72 empty] | 36295h | 14945h
MCD0822-CWP-541 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MCD0822-CWP-541 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [72 empty] | 36295h | 14945h
SES0822-CWP-542 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [79 empty] | 5654h | 13482h
SES0822-CWP-542 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-542 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [79 empty] | 5654h | 13482h
SES0822-CWP-543 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [80 empty] | 12612h | 6524h
SES0822-CWP-543 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-543 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [80 empty] | 12612h | 6524h
SES0822-CWP-544 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 19136h
SES0822-CWP-544 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-544 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 19136h
SES0822-CWP-545 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [74 empty] | 19136h
SES0822-CWP-545 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-545 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [74 empty] | 19136h
SES0822-CWP-546 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [72 empty] | 6662h | 1090h
SES0822-CWP-546 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-546 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [72 empty] | 6662h | 1090h
SES0822-CWP-547 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [73 empty] | 7752h
SES0822-CWP-547 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-547 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [73 empty] | 7752h
SES0822-CWP-548 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [73 empty] | 5693h | 2059h
SES0822-CWP-548 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-548 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [73 empty] | 5693h | 2059h
SES0822-CWP-549 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [72 empty] | 7752h
SES0822-CWP-549 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SES0822-CWP-549 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [72 empty] | 7752h
ECB0817-CWP-550 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 1043h | 1565h
ECB0817-CWP-550 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0817-CWP-550 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 1043h | 1565h
ECB0817-CWP-551 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 1043h | 1565h
ECB0817-CWP-551 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0817-CWP-551 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 1043h | 1565h
ECB0817-CWP-552 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 522h | 2086h
ECB0817-CWP-552 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0817-CWP-552 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 522h | 2086h
ECB0821-CWP-553 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [90 empty] | 11704h
ECB0821-CWP-553 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0821-CWP-553 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [90 empty] | 11704h
ECB0821-CWP-554 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [89 empty] | 7803h | 3901h
ECB0821-CWP-554 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0821-CWP-554 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [89 empty] | 7803h | 3901h
ECB0823-CWP-555 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 7800h
ECB0823-CWP-555 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0823-CWP-555 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 7800h
ECB0823-CWP-556 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 5850h | 1950h
ECB0823-CWP-556 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0823-CWP-556 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 5850h | 1950h
ECB0823-CWP-557 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3900h | 3900h
ECB0823-CWP-557 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0823-CWP-557 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3900h | 3900h
ECB0824-CWP-558 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [86 empty] | 7800h
ECB0824-CWP-558 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0824-CWP-558 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [86 empty] | 7800h
ECB0824-CWP-559 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [85 empty] | 5850h | 1950h
ECB0824-CWP-559 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0824-CWP-559 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [85 empty] | 5850h | 1950h
ECB0824-CWP-560 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [84 empty] | 3900h | 3900h
ECB0824-CWP-560 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0824-CWP-560 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [84 empty] | 3900h | 3900h
ECB0826-CWP-561 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [96 empty] | 6094h | 1706h
ECB0826-CWP-561 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0826-CWP-561 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [96 empty] | 6094h | 1706h
ECB0826-CWP-562 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [95 empty] | 4144h | 3656h
ECB0826-CWP-562 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0826-CWP-562 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [95 empty] | 4144h | 3656h
ECB0826-CWP-563 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 2194h | 5606h
ECB0826-CWP-563 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0826-CWP-563 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 2194h | 5606h
ECB0827-CWP-564 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 3900h | 3900h
ECB0827-CWP-564 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0827-CWP-564 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 3900h | 3900h
ECB0827-CWP-565 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 7800h
ECB0827-CWP-565 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0827-CWP-565 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 7800h
ECB0827-CWP-566 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [94 empty] | 7800h
ECB0827-CWP-566 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB0827-CWP-566 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [94 empty] | 7800h
ECB1048-CWP-567 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 800h
ECB1048-CWP-567 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1048-CWP-567 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 800h
ECB1048-CWP-568 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 800h
ECB1048-CWP-568 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1048-CWP-568 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 800h
ECB1048-CWP-569 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 800h
ECB1048-CWP-569 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1048-CWP-569 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 800h
ECB1049-CWP-570 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 100h | 700h
ECB1049-CWP-570 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1049-CWP-570 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 100h | 700h
ECB1049-CWP-571 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 800h
ECB1049-CWP-571 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1049-CWP-571 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 800h
ECB1049-CWP-572 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [91 empty] | 800h
ECB1049-CWP-572 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1049-CWP-572 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [91 empty] | 800h
ECB1062-CWP-573 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 2590h | 7770h
ECB1062-CWP-573 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1062-CWP-573 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 2590h | 7770h
ECB1062-CWP-574 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 10360h
ECB1062-CWP-574 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1062-CWP-574 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 10360h
ECB1062-CWP-575 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 10360h
ECB1062-CWP-575 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1062-CWP-575 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 10360h
ECB1214-CWP-576 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 703h | 3513h
ECB1214-CWP-576 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-576 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 703h | 3513h
ECB1214-CWP-577 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [87 empty] | 703h | 3513h
ECB1214-CWP-577 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
ECB1214-CWP-577 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [87 empty] | 703h | 3513h
MEM0821-CWP-579 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [81 empty] | 17h | 391h
MEM0821-CWP-579 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-579 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [81 empty] | 17h | 391h
MEM0821-CWP-580 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 289h | 119h
MEM0821-CWP-580 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-580 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 289h | 119h
MEM0821-CWP-581 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 10184h
MEM0821-CWP-581 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-581 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 10184h
MEM0821-CWP-582 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [82 empty] | 6789h | 3395h
MEM0821-CWP-582 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MEM0821-CWP-582 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [82 empty] | 6789h | 3395h
SWP-035-1052 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units
SWP-035-1052 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-035-1052 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 349h
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 349h
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [78 empty] | 720h | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 502h
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [78 empty] | 720h | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 502h
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [53 empty] | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 349h
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [53 empty] | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 872h | 349h
SWP-0xx-0817 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | [100 empty] | 1955h | 1117h
SWP-0xx-0817 | MAO DE OBRA - WORKFORCE | Labor | Actual Units
SWP-0xx-0817 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | [100 empty] | 1955h | 1117h