## Sheet1
activity_id | resource_name | resource_type | spreadsheet_field | data | valor | unidade | execucao_id | projeto_id
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-09-25 | 40904 | h | 223 | 1
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-09-25 | 40904 | h | 223 | 1
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-09-25 | 40904 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-09-25 | 4868 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-09-25 | 2353 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-09-25 | 2353 | h | 223 | 1
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-02 | 143164 | h | 223 | 1
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-02 | 143164 | h | 223 | 1
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-02 | 143164 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-02 | 34079 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-02 | 16471 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-02 | 16471 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-02 | 34079 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-02 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-02 | 12510 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-09 | 48684 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-09 | 17648 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-09 | 17648 | h | 223 | 1
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-09 | 102260 | h | 223 | 1
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-09 | 102260 | h | 223 | 1
SUWP-EC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-09 | 102260 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-09 | 119303 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-09 | 27799 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-09 | 27799 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-09 | 34079 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-09 | 16471 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-09 | 16471 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-09 | 34079 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-09 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-09 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-16 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-16 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-16 | 68158 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-16 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-16 | 24707 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-16 | 167025 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-16 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-16 | 38918 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-16 | 34079 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-16 | 16471 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-16 | 16471 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-16 | 34079 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-16 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-16 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-23 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-23 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-23 | 68158 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-23 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-23 | 24707 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-23 | 167025 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-23 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-23 | 38918 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-23 | 34079 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-23 | 16471 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-23 | 16471 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-23 | 34079 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-23 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-23 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-30 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-30 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-30 | 68158 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-30 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-30 | 24707 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-30 | 119303 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-30 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-30 | 38918 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-30 | 16471 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-30 | 16471 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-10-30 | 4868 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-10-30 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-10-30 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-06 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-06 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-11-06 | 29210 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-06 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-06 | 24707 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-06 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-06 | 38918 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-06 | 16471 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-06 | 16471 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-06 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-06 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-13 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-13 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-13 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-13 | 24707 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-13 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-13 | 38918 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-13 | 16471 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-13 | 16471 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-13 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-13 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-20 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-20 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-20 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-20 | 24707 | h | 223 | 1
SUWP-OU-PF1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-11-20 | 7956 | h | 223 | 1
SUWP-OU-PF1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-20 | 7956 | h | 223 | 1
SUWP-OU-PF1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-20 | 7956 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-11-20 | 8368 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-20 | 1569 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-20 | 1569 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-20 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-20 | 38918 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-20 | 16471 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-20 | 16471 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-20 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-20 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-27 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-27 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-27 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-27 | 24707 | h | 223 | 1
SUWP-OU-PF1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-11-27 | 39780 | h | 223 | 1
SUWP-OU-PF1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-27 | 39780 | h | 223 | 1
SUWP-OU-PF1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-27 | 39780 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-11-27 | 41840 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-27 | 10983 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-27 | 10983 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-27 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-27 | 38918 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-27 | 7059 | h | 223 | 1
SUWP-EC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-27 | 7059 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-11-27 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-11-27 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-04 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-04 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-04 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-04 | 24707 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-04 | 10983 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-04 | 10983 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-04 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-04 | 38918 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-04 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-04 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-11 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-11 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-11 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-11 | 24707 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-11 | 10983 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-11 | 10983 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-11 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-11 | 38918 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-11 | 12510 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-11 | 12510 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-18 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-18 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-18 | 24707 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-18 | 24707 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-18 | 10983 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-18 | 10983 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-18 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-18 | 38918 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-18 | 3574 | h | 223 | 1
SUWP-RP-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-18 | 3574 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-25 | 34728 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-25 | 34728 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-25 | 17648 | h | 223 | 1
SUWP-AT-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-25 | 17648 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-12-25 | 9737 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-25 | 8557 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-25 | 8557 | h | 223 | 1
SUWP-EC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-12-25 | 37656 | h | 223 | 1
SUWP-EC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-25 | 25104 | h | 223 | 1
SUWP-EC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-25 | 25104 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-25 | 4707 | h | 223 | 1
SUWP-OU-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-25 | 4707 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-25 | 38918 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-25 | 38918 | h | 223 | 1
SUWP-EC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2022-12-25 | 35802 | h | 223 | 1
SUWP-EC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Actual Units | 2022-12-25 | 23868 | h | 223 | 1
SUWP-EC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2022-12-25 | 23868 | h | 223 | 1
EWPp-DD-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 99723 | h | 223 | 1
EWPp-DD-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 99723 | h | 223 | 1
EWPp-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 305811 | h | 223 | 1
EWPp-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 305811 | h | 223 | 1
EWPp-DD-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 99723 | h | 223 | 1
EWPp-DD-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 99723 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 15338 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 8872 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 8872 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 31051 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 31051 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 68158 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 70224 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 9717 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 9717 | h | 223 | 1
SUWP-EC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 193840 | h | 223 | 1
SUWP-EC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 193840 | h | 223 | 1
SUWP-EC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 12552 | h | 223 | 1
SUWP-EC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 20082 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 13167 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 13167 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 9129 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 9129 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 22216 | h | 223 | 1
SUWP-EC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-01 | 11934 | h | 223 | 1
SUWP-EC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-01 | 19093 | h | 223 | 1
EWPp-DD-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 99723 | h | 223 | 1
EWPp-DD-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 99723 | h | 223 | 1
EWPp-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 122325 | h | 223 | 1
EWPp-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 122325 | h | 223 | 1
EWPp-DD-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 99723 | h | 223 | 1
EWPp-DD-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 99723 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 15338 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 31051 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 31051 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 31051 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 31051 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 68158 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 70224 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 9717 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 9717 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 5553 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 5553 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 23043 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 23043 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 15977 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 15977 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 22216 | h | 223 | 1
SUWP-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-08 | 402 | h | 223 | 1
SUWP-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-08 | 402 | h | 223 | 1
EWPp-DD-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 79778 | h | 223 | 1
EWPp-DD-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 79778 | h | 223 | 1
EWPp-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 244649 | h | 223 | 1
EWPp-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 244649 | h | 223 | 1
EWPp-DD-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 79778 | h | 223 | 1
EWPp-DD-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 79778 | h | 223 | 1
EWPp-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 6135 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 31051 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 31051 | h | 223 | 1
SUWP-AT-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 85760 | h | 223 | 1
SUWP-AT-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 85760 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 31051 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 31051 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 68158 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 70224 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 9717 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 9717 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 9717 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 9717 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 23043 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 23043 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 48519 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 48519 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 15977 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 15977 | h | 223 | 1
SUWP-RP-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 22216 | h | 223 | 1
SUWP-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-15 | 134 | h | 223 | 1
SUWP-EC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-15 | 134 | h | 223 | 1
EWPp-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 183487 | h | 223 | 1
EWPp-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 183487 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 31051 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 31051 | h | 223 | 1
SUWP-AT-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 120064 | h | 223 | 1
SUWP-AT-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 120064 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 31051 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 31051 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 68158 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 70224 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 9717 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 9717 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 9717 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 9717 | h | 223 | 1
SUWP-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 137884 | h | 223 | 1
SUWP-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 137884 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 23043 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 23043 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 84908 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 84908 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 15977 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 15977 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 129 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 129 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-22 | 136658 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-22 | 136658 | h | 223 | 1
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 97971 | h | 223 | 1
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 97971 | h | 223 | 1
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 97971 | h | 223 | 1
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 97971 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 26615 | h | 223 | 1
SUWP-RP-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 26615 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 35487 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 35487 | h | 223 | 1
SUWP-AT-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 51456 | h | 223 | 1
SUWP-AT-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 51456 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 4436 | h | 223 | 1
SUWP-EC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 4436 | h | 223 | 1
SUWP-AC-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 10032 | h | 223 | 1
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 30253 | h | 223 | 1
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 30253 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 1388 | h | 223 | 1
SUWP-EC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 1388 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 9717 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 9717 | h | 223 | 1
SUWP-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 137884 | h | 223 | 1
SUWP-EC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 137884 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 30838 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 30838 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 13167 | h | 223 | 1
SUWP-RP-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 13167 | h | 223 | 1
SUWP-AT-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 27275 | h | 223 | 1
SUWP-AT-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 27275 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 12130 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 12130 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 84908 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 84908 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 15977 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 15977 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 129 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 129 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 136658 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 136658 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 77649 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 77649 | h | 223 | 1
SUWP-AT-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-01-29 | 28693 | h | 223 | 1
SUWP-AT-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-01-29 | 28693 | h | 223 | 1
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 97971 | h | 223 | 1
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 97971 | h | 223 | 1
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 97971 | h | 223 | 1
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 97971 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 62102 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 62102 | h | 223 | 1
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 70591 | h | 223 | 1
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 70591 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 5553 | h | 223 | 1
SUWP-RP-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 5553 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 5552 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 5552 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 30838 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 30838 | h | 223 | 1
SUWP-AT-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 47732 | h | 223 | 1
SUWP-AT-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 47732 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 84908 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 84908 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 84908 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 84908 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 15977 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 15977 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 129 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 129 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 136658 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 136658 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 135885 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 135885 | h | 223 | 1
SUWP-RP-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 87085 | h | 223 | 1
SUWP-RP-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 87085 | h | 223 | 1
SUWP-AT-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-05 | 50212 | h | 223 | 1
SUWP-AT-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-05 | 50212 | h | 223 | 1
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 97971 | h | 223 | 1
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 97971 | h | 223 | 1
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 97971 | h | 223 | 1
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 97971 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 62102 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 62102 | h | 223 | 1
SUWP-AS-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 285867 | h | 223 | 1
SUWP-AS-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 285867 | h | 223 | 1
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 70591 | h | 223 | 1
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 70591 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 19432 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 19432 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 30838 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 30838 | h | 223 | 1
SUWP-AT-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 20457 | h | 223 | 1
SUWP-AT-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 20457 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 84908 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 84908 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 48519 | h | 223 | 1
SUWP-EC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 48519 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 11412 | h | 223 | 1
SUWP-RP-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 11412 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 129 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 129 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 136658 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 136658 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 135885 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 135885 | h | 223 | 1
SUWP-RP-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 101599 | h | 223 | 1
SUWP-RP-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 101599 | h | 223 | 1
SUWP-AT-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-12 | 21519 | h | 223 | 1
SUWP-AT-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-12 | 21519 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 88671 | h | 223 | 1
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 88671 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17608 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17608 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 43729 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 43729 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 15874 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 15874 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 178580 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 178580 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 43292 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 43292 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 15874 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 15874 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 20409 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 20409 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17858 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17858 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 24858 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 24858 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 17608 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 17608 | h | 223 | 1
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 78376 | h | 223 | 1
EWPp-DD-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 78376 | h | 223 | 1
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 78376 | h | 223 | 1
EWPp-DD-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 78376 | h | 223 | 1
EWPp-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 244649 | h | 223 | 1
EWPp-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 244649 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 62102 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 62102 | h | 223 | 1
SUWP-AS-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 228693 | h | 223 | 1
SUWP-AS-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 228693 | h | 223 | 1
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 30253 | h | 223 | 1
SUWP-AS-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 30253 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 19432 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 19432 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 30838 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 30838 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 84908 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 84908 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 83468 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 83468 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 18 | h | 223 | 1
SUWP-RP-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 18 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 136658 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 136658 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 135885 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 135885 | h | 223 | 1
SUWP-RP-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 87085 | h | 223 | 1
SUWP-RP-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 87085 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-19 | 196088 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-19 | 196088 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 88671 | h | 223 | 1
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 88671 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 3826 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 3826 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 13605 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 13605 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 3826 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28172 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28172 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 69966 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 69966 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 25398 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 285728 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 285728 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 25398 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 32655 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28573 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28573 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 39772 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 39772 | h | 223 | 1
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 39772 | h | 223 | 1
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 39772 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 28172 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 28172 | h | 223 | 1
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 99723 | h | 223 | 1
EWPp-DD-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 99723 | h | 223 | 1
EWPp-DD-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 103413 | h | 223 | 1
EWPp-DD-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 103413 | h | 223 | 1
X3020 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 104712 | h | 223 | 1
X3020 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 104712 | h | 223 | 1
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 97971 | h | 223 | 1
EWPp-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 183487 | h | 223 | 1
EWPp-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 183487 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 35487 | h | 223 | 1
SUWP-AC-PM-0202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 35487 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 19432 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 19432 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 1830 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 1830 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 30838 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 30838 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 12296 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 12296 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 8812 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 8812 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 397680 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 397680 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 84908 | h | 223 | 1
SUWP-RP-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 84908 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 83468 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 83468 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 136658 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 136658 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 135885 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 135885 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-02-26 | 313740 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-02-26 | 313740 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 88671 | h | 223 | 1
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 88671 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 6122 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 6122 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 21767 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 6122 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28172 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28172 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 7954 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 7954 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 69966 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 69966 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 25398 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 285728 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 285728 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 25398 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 32655 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28573 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28573 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 39772 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 39772 | h | 223 | 1
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 39772 | h | 223 | 1
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 39772 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28172 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28172 | h | 223 | 1
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 99723 | h | 223 | 1
EWPp-DD-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 99723 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 39188 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 39188 | h | 223 | 1
EWPp-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 122325 | h | 223 | 1
EWPp-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 122325 | h | 223 | 1
EWPp-DD-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 82731 | h | 223 | 1
EWPp-DD-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 82731 | h | 223 | 1
X3020 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 62827 | h | 223 | 1
X3020 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 62827 | h | 223 | 1
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 97971 | h | 223 | 1
EWPp-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 122325 | h | 223 | 1
EWPp-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 122325 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 16656 | h | 223 | 1
SUWP-AT-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 16656 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 12807 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 12807 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 30838 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 30838 | h | 223 | 1
SUWP-AT-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 215378 | h | 223 | 1
SUWP-AT-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 215378 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 28691 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 28691 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 20561 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 20561 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 636287 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 636287 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 83468 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 83468 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 95935 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 95935 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 39045 | h | 223 | 1
SUWP-AT-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 39045 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 135885 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 135885 | h | 223 | 1
SUWP-AT-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 157582 | h | 223 | 1
SUWP-AT-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 157582 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-05 | 313740 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-05 | 313740 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 88671 | h | 223 | 1
TTU0821-EWPc-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 88671 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 6122 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 6122 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 21767 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 6122 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28172 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28172 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 39772 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 39772 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 69966 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 69966 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 25398 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 285728 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 285728 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 25398 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 32655 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28573 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28573 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 39772 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 39772 | h | 223 | 1
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 39772 | h | 223 | 1
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 39772 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28172 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28172 | h | 223 | 1
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 79778 | h | 223 | 1
EWPp-DD-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 79778 | h | 223 | 1
EWPp-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 244649 | h | 223 | 1
EWPp-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 244649 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 305811 | h | 223 | 1
EWPp-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 305811 | h | 223 | 1
EWPp-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 305811 | h | 223 | 1
EWPp-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 305811 | h | 223 | 1
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 97971 | h | 223 | 1
EWPp-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 305811 | h | 223 | 1
EWPp-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 305811 | h | 223 | 1
EWPp-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 305811 | h | 223 | 1
EWPp-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 305811 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 12807 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 12807 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 8811 | h | 223 | 1
SUWP-RP-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 8811 | h | 223 | 1
SUWP-AT-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 172302 | h | 223 | 1
SUWP-AT-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 172302 | h | 223 | 1
SUWP-EC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 18684 | h | 223 | 1
SUWP-EC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 18684 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 28691 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 28691 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 20561 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 20561 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 636287 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 636287 | h | 223 | 1
SUWP-AS-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 469013 | h | 223 | 1
SUWP-AS-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 469013 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 83468 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 83468 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 111924 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 111924 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 135885 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 135885 | h | 223 | 1
SUWP-AT-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 275768 | h | 223 | 1
SUWP-AT-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 275768 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 8485 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 8485 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-12 | 313740 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-12 | 313740 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0817-PWPe-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 37879 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 37879 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 11909 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 11909 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 6122 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 6122 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 21767 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 6122 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10565 | h | 223 | 1
MEM0827-PWPe-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10565 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPe-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPe-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPe-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 39772 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 39772 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MRF0827-PWPe-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 69966 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 69966 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPe-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MCD0827-PWPe-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 25398 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPe-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPe-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 107148 | h | 223 | 1
EBD0827-EWPc-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 107148 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
EEE0827-PWPe-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 38263 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 38263 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPe-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
ELU0827-PWPe-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 25398 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
JIL0827-PWPe-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPe-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
JIL0827-PWPe-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 32655 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 43729 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 43729 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10715 | h | 223 | 1
SES0827-PWPe-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10715 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 250 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 250 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 14915 | h | 223 | 1
MSD0827-EWPc-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 14915 | h | 223 | 1
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 39772 | h | 223 | 1
MSD0827-EWPc-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 39772 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 251 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 251 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 10565 | h | 223 | 1
MRF0827-PWPe-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 10565 | h | 223 | 1
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 244649 | h | 223 | 1
EWPp-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 244649 | h | 223 | 1
EWPp-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 305811 | h | 223 | 1
EWPp-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 305811 | h | 223 | 1
EWPp-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 305811 | h | 223 | 1
EWPp-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 305811 | h | 223 | 1
EWPp-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 183487 | h | 223 | 1
EWPp-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 183487 | h | 223 | 1
EWPp-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 61162 | h | 223 | 1
EWPp-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 61162 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 97971 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 97971 | h | 223 | 1
EWPp-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 122325 | h | 223 | 1
EWPp-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 122325 | h | 223 | 1
EWPp-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 122325 | h | 223 | 1
EWPp-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 122325 | h | 223 | 1
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-DD-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 78376 | h | 223 | 1
EWPp-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 183487 | h | 223 | 1
EWPp-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 183487 | h | 223 | 1
EWPp-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 122325 | h | 223 | 1
EWPp-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 122325 | h | 223 | 1
EWPp-OU-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 378496 | h | 223 | 1
EWPp-OU-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 378496 | h | 223 | 1
SUWP-EC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 2934 | h | 223 | 1
SUWP-EC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 2934 | h | 223 | 1
SUWP-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 41760 | h | 223 | 1
SUWP-EC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 41760 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 12807 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 12807 | h | 223 | 1
SUWP-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 3592 | h | 223 | 1
SUWP-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 3592 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 15824 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 15824 | h | 223 | 1
SUWP-EC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 6228 | h | 223 | 1
SUWP-EC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 6228 | h | 223 | 1
SUWP-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 6896 | h | 223 | 1
SUWP-EC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 6896 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 28691 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 28691 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 20561 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 20561 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 636287 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 636287 | h | 223 | 1
SUWP-AS-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 938027 | h | 223 | 1
SUWP-AS-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 938027 | h | 223 | 1
SUWP-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 12636 | h | 223 | 1
SUWP-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 12636 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 83468 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 83468 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 111924 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 111924 | h | 223 | 1
SUWP-EC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 684 | h | 223 | 1
SUWP-EC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 684 | h | 223 | 1
SUWP-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 75076 | h | 223 | 1
SUWP-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 75076 | h | 223 | 1
SUWP-AT-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 536 | h | 223 | 1
SUWP-AT-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 536 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 135885 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 135885 | h | 223 | 1
SUWP-AT-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 118186 | h | 223 | 1
SUWP-AT-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 118186 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 59396 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 59396 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-19 | 313740 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-19 | 313740 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 60606 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 19055 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 19055 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 11244 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 11244 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 27549 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 27549 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1378 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1378 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4898 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4898 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 13775 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 13775 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1913 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1913 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 2296 | h | 223 | 1
JIL0822-PWPe-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 2296 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 21767 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15742 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15742 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 6887 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 6887 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPe-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 12244 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 13775 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 13775 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 6122 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 6122 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPe-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 8746 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 8746 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 13775 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 13775 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 13775 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 13775 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPe-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 12244 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 13775 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 13775 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1275 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1275 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPe-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 8746 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 8746 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 459 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 459 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 459 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 459 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 27549 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 27549 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 12244 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 12244 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPe-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 12244 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 13775 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 13775 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1913 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPe-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 2296 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 8746 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 8746 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 442 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 442 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 7950 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 7950 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 386 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 386 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 7339 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 7339 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 18366 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 18366 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 27549 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 27549 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 18366 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 18366 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 18366 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 18366 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 6679 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 6679 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1377 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 6679 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 6679 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 39772 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 39772 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 25398 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 61221 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 61221 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 25398 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32655 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 69966 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 69966 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 400 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 400 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 8949 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 8949 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 8949 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 8949 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 401 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 401 | h | 223 | 1
EWPp-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 183487 | h | 223 | 1
EWPp-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 183487 | h | 223 | 1
EWPp-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 361951 | h | 223 | 1
EWPp-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 361951 | h | 223 | 1
EWPp-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 122325 | h | 223 | 1
EWPp-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 122325 | h | 223 | 1
EWPp-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 122325 | h | 223 | 1
EWPp-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 122325 | h | 223 | 1
EWPp-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 97971 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 97971 | h | 223 | 1
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 97971 | h | 223 | 1
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 97971 | h | 223 | 1
EWPp-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 244649 | h | 223 | 1
EWPp-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 244649 | h | 223 | 1
EWPp-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 305811 | h | 223 | 1
EWPp-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 61162 | h | 223 | 1
EWPp-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 61162 | h | 223 | 1
EWPp-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 183487 | h | 223 | 1
EWPp-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 183487 | h | 223 | 1
EWPp-OU-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 630827 | h | 223 | 1
EWPp-OU-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 630827 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 6013 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 6013 | h | 223 | 1
SUWP-EC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 8802 | h | 223 | 1
SUWP-EC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 8802 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 12807 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 12807 | h | 223 | 1
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 32202 | h | 223 | 1
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 32202 | h | 223 | 1
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 756 | h | 223 | 1
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 756 | h | 223 | 1
SUWP-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 3592 | h | 223 | 1
SUWP-EC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 3592 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 55383 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 55383 | h | 223 | 1
SUWP-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 21708 | h | 223 | 1
SUWP-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 21708 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 476 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 476 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 28691 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 28691 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 20561 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 20561 | h | 223 | 1
SUWP-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 19566 | h | 223 | 1
SUWP-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 19566 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 493123 | h | 223 | 1
SUWP-MO-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 493123 | h | 223 | 1
SUWP-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4212 | h | 223 | 1
SUWP-EC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4212 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 83468 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 83468 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 111924 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 111924 | h | 223 | 1
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 15805 | h | 223 | 1
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 15805 | h | 223 | 1
SUWP-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 306 | h | 223 | 1
SUWP-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 306 | h | 223 | 1
SUWP-EC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 9168 | h | 223 | 1
SUWP-EC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 9168 | h | 223 | 1
SUWP-RP-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 10989 | h | 223 | 1
SUWP-RP-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 10989 | h | 223 | 1
SUWP-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1740 | h | 223 | 1
SUWP-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1740 | h | 223 | 1
SUWP-EC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 4790 | h | 223 | 1
SUWP-EC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 4790 | h | 223 | 1
SUWP-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 75076 | h | 223 | 1
SUWP-EC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 75076 | h | 223 | 1
SUWP-AT-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 536 | h | 223 | 1
SUWP-AT-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 536 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 116473 | h | 223 | 1
SUWP-AC-PF-1203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 116473 | h | 223 | 1
SUWP-AS-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 1103072 | h | 223 | 1
SUWP-AS-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 1103072 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 59396 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 59396 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 2242763 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-03-26 | 313740 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-03-26 | 313740 | h | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-02 | 2 | t | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-02 | 2 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-02 | 2 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-02 | 2 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-02 | 2 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-02 | 2 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 60606 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 19055 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 19055 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 49974 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 49974 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 122441 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 122441 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 61221 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 61221 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 3061 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 3061 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21767 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 30610 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 30610 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 19591 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 53455 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 53455 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 61221 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 61221 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 27209 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 27209 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 13993 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 61221 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 61221 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 61221 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 61221 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 19591 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 53455 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 53455 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 61221 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 61221 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 2041 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 2041 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 13993 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 2041 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 2041 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 2041 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 2041 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 53455 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 53455 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 122441 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 122441 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 54418 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 54418 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 19591 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 61221 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 61221 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 3061 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 13993 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 7508 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 7508 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 22525 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 22525 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6567 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6567 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 19700 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 19700 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 7508 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 7508 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 22525 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 22525 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6567 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6567 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 19700 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 19700 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 81627 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 81627 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 122441 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 122441 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 81627 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 81627 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 133404 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 133404 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 55973 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 55973 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 55973 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 55973 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 81627 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 81627 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 29683 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6122 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 31818 | h | 223 | 1
CPI0827-EWPc-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 31818 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 25398 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 61221 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 61221 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 25398 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 32655 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 69966 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 69966 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 400 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 400 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 39772 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 39772 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 39772 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 39772 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 401 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 401 | h | 223 | 1
EWPp-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 289561 | h | 223 | 1
EWPp-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 289561 | h | 223 | 1
EWPp-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 122325 | h | 223 | 1
EWPp-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 122325 | h | 223 | 1
EWPp-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 61162 | h | 223 | 1
EWPp-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 61162 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 39188 | h | 223 | 1
EWPp-DD-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 39188 | h | 223 | 1
EWPp-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 97971 | h | 223 | 1
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 97971 | h | 223 | 1
EWPp-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 122325 | h | 223 | 1
EWPp-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 122325 | h | 223 | 1
EWPp-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 122325 | h | 223 | 1
EWPp-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 122325 | h | 223 | 1
EWPp-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 305811 | h | 223 | 1
EWPp-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 244649 | h | 223 | 1
EWPp-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 244649 | h | 223 | 1
EWPp-OU-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 126165 | h | 223 | 1
EWPp-OU-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 126165 | h | 223 | 1
EWPp-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 103413 | h | 223 | 1
EWPp-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 103413 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6013 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6013 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 2699 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 2699 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 12807 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 12807 | h | 223 | 1
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 56353 | h | 223 | 1
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 56353 | h | 223 | 1
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 2647 | h | 223 | 1
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 2647 | h | 223 | 1
SUWP-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 666 | h | 223 | 1
SUWP-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 666 | h | 223 | 1
SUWP-AS-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 193840 | h | 223 | 1
SUWP-AS-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 193840 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 55383 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 55383 | h | 223 | 1
SUWP-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 21708 | h | 223 | 1
SUWP-EC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 21708 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 1665 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 1665 | h | 223 | 1
SUWP-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 2196 | h | 223 | 1
SUWP-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 2196 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 28691 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 28691 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 20561 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 20561 | h | 223 | 1
SUWP-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 6522 | h | 223 | 1
SUWP-EC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 6522 | h | 223 | 1
SUWP-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 50656 | h | 223 | 1
SUWP-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 50656 | h | 223 | 1
SUWP-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 2920 | h | 223 | 1
SUWP-EC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 2920 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 83468 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 83468 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 111924 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 111924 | h | 223 | 1
SUWP-EC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 61 | h | 223 | 1
SUWP-EC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 61 | h | 223 | 1
SUWP-EC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 1063 | h | 223 | 1
SUWP-EC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 1063 | h | 223 | 1
SUWP-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 39108 | h | 223 | 1
SUWP-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 39108 | h | 223 | 1
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 55319 | h | 223 | 1
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 55319 | h | 223 | 1
SUWP-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 918 | h | 223 | 1
SUWP-EC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 918 | h | 223 | 1
SUWP-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 384 | h | 223 | 1
SUWP-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 384 | h | 223 | 1
SUWP-EC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 9168 | h | 223 | 1
SUWP-EC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 9168 | h | 223 | 1
SUWP-RP-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 15385 | h | 223 | 1
SUWP-RP-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 15385 | h | 223 | 1
SUWP-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 1936 | h | 223 | 1
SUWP-EC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 1936 | h | 223 | 1
SUWP-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 580 | h | 223 | 1
SUWP-EC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 580 | h | 223 | 1
SUWP-EC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 4790 | h | 223 | 1
SUWP-EC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 4790 | h | 223 | 1
SUWP-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 1404 | h | 223 | 1
SUWP-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 1404 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 59396 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 59396 | h | 223 | 1
SUWP-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 1194 | h | 223 | 1
SUWP-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 1194 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 4067 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 4067 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 2023 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 2023 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 2242763 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 313740 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 313740 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-02 | 33506 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-02 | 33506 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-02 | 2761 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-02 | 2761 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-02 | 2655 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-02 | 2655 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-02 | 2655 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-02 | 2655 | h | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-09 | 3 | t | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-09 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-09 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-09 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-09 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-09 | 3 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 60606 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 19055 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 19055 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 49974 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 49974 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 122441 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 122441 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 61221 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 61221 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 3061 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 3061 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 21767 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 30610 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 30610 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 19591 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 66818 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 66818 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 61221 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 61221 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 27209 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 27209 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 13993 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 61221 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 61221 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 61221 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 61221 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 19591 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 66818 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 66818 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 61221 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 61221 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2041 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2041 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 13993 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2041 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2041 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2041 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2041 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 66818 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 66818 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 122441 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 122441 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 54418 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 54418 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 19591 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 61221 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 61221 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 3061 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 13993 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 43263 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 81627 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 81627 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 122441 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 122441 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 81627 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 81627 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 166755 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 166755 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 81627 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 81627 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 29683 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6122 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 26237 | h | 223 | 1
MEM0827-EWPc-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 26237 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 25398 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 61221 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 61221 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 25398 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 32655 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 69966 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 69966 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 400 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 400 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 39772 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 39772 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 39772 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 39772 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 401 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 401 | h | 223 | 1
EWPp-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 183487 | h | 223 | 1
EWPp-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 183487 | h | 223 | 1
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 97971 | h | 223 | 1
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 97971 | h | 223 | 1
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 78376 | h | 223 | 1
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 78376 | h | 223 | 1
EWPp-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 61162 | h | 223 | 1
EWPp-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 61162 | h | 223 | 1
EWPp-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 82731 | h | 223 | 1
EWPp-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 82731 | h | 223 | 1
EWPp-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 122325 | h | 223 | 1
EWPp-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 122325 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6013 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6013 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6297 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6297 | h | 223 | 1
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 204 | h | 223 | 1
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 204 | h | 223 | 1
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 615 | h | 223 | 1
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 615 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 12807 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 12807 | h | 223 | 1
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 56353 | h | 223 | 1
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 56353 | h | 223 | 1
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2647 | h | 223 | 1
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2647 | h | 223 | 1
SUWP-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 1998 | h | 223 | 1
SUWP-EC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 1998 | h | 223 | 1
SUWP-AS-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 581520 | h | 223 | 1
SUWP-AS-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 581520 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 55383 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 55383 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 8983 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 8983 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 3794 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 3794 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 1665 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 1665 | h | 223 | 1
SUWP-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2196 | h | 223 | 1
SUWP-EC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2196 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 28691 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 28691 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 20561 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 20561 | h | 223 | 1
SUWP-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2580 | h | 223 | 1
SUWP-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2580 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 1117 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 1117 | h | 223 | 1
SUWP-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 3400 | h | 223 | 1
SUWP-EC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 3400 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 16552 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 16552 | h | 223 | 1
SUWP-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 990 | h | 223 | 1
SUWP-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 990 | h | 223 | 1
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 5332 | h | 223 | 1
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 5332 | h | 223 | 1
SUWP-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 6804 | h | 223 | 1
SUWP-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 6804 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 211 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 211 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 83468 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 83468 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 111924 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 111924 | h | 223 | 1
SUWP-EC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 429 | h | 223 | 1
SUWP-EC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 429 | h | 223 | 1
SUWP-EC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2481 | h | 223 | 1
SUWP-EC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2481 | h | 223 | 1
SUWP-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 13036 | h | 223 | 1
SUWP-EC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 13036 | h | 223 | 1
SUWP-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 7920 | h | 223 | 1
SUWP-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 7920 | h | 223 | 1
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 55319 | h | 223 | 1
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 55319 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 560 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 560 | h | 223 | 1
SUWP-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 1152 | h | 223 | 1
SUWP-EC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 1152 | h | 223 | 1
SUWP-RP-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 15385 | h | 223 | 1
SUWP-RP-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 15385 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2395 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2395 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 55 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 55 | h | 223 | 1
SUWP-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 468 | h | 223 | 1
SUWP-EC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 468 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 59396 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 59396 | h | 223 | 1
SUWP-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 398 | h | 223 | 1
SUWP-EC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 398 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 4067 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 4067 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2833 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2833 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 2242763 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 313740 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 313740 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 41883 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 41883 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 106930 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-09 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-09 | 193165 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-09 | 3451 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-09 | 3451 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-09 | 3318 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-09 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-09 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-09 | 3318 | h | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-16 | 3 | t | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-16 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-16 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-16 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-16 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-16 | 3 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 60606 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 19055 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 19055 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 49974 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 49974 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 122441 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 122441 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 61221 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 61221 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 3061 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 3061 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 21767 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 30610 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 30610 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 19591 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 66818 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 66818 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 61221 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 61221 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 27209 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 27209 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 13993 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 61221 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 61221 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 61221 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 61221 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 19591 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 66818 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 66818 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 61221 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 61221 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2041 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2041 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 13993 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2041 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2041 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2041 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2041 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 66818 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 66818 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 122441 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 122441 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 54418 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 54418 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 19591 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 61221 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 61221 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 3061 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 13993 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 43263 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 81627 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 81627 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 122441 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 122441 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 81627 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 81627 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 166755 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 166755 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 81627 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 81627 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 29683 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6122 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 25398 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 61221 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 61221 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 25398 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 32655 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 69966 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 69966 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 150 | h | 223 | 1
MEM0827-EWPc-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 150 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 39772 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 39772 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 39772 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 39772 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 151 | h | 223 | 1
MRF0827-EWPc-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 151 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 22000 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 22000 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6039 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6039 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2818 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2818 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 16500 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 16500 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2107 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2107 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 1405 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 1405 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 19384 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 19384 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 11308 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 11308 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 19384 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 19384 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 11308 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 11308 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 19384 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 19384 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 9692 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 9692 | h | 223 | 1
EWPp-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 122325 | h | 223 | 1
EWPp-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 122325 | h | 223 | 1
EWPp-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 305811 | h | 223 | 1
EWPp-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 305811 | h | 223 | 1
EWPp-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 244649 | h | 223 | 1
EWPp-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 244649 | h | 223 | 1
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 78376 | h | 223 | 1
EWPp-DD-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 78376 | h | 223 | 1
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 97971 | h | 223 | 1
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 97971 | h | 223 | 1
EWPp-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 305811 | h | 223 | 1
EWPp-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 305811 | h | 223 | 1
SUWP-RP-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 1387 | h | 223 | 1
SUWP-RP-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 1387 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6013 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6013 | h | 223 | 1
SUWP-AT-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 10678 | h | 223 | 1
SUWP-AT-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 10678 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 6297 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 6297 | h | 223 | 1
SUWP-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 1244 | h | 223 | 1
SUWP-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 1244 | h | 223 | 1
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 713 | h | 223 | 1
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 713 | h | 223 | 1
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 1076 | h | 223 | 1
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 1076 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 1830 | h | 223 | 1
SUWP-AC-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 1830 | h | 223 | 1
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 16101 | h | 223 | 1
SUWP-AS-PF-0306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 16101 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 1745 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 1745 | h | 223 | 1
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 1134 | h | 223 | 1
SUWP-RP-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 1134 | h | 223 | 1
SUWP-AT-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2053 | h | 223 | 1
SUWP-AT-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2053 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 55383 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 55383 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 10480 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 10480 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 117 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 117 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 4426 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 4426 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 1665 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 1665 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 16395 | h | 223 | 1
SUWP-AC-PF-1108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 16395 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 20561 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 20561 | h | 223 | 1
SUWP-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 860 | h | 223 | 1
SUWP-EC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 860 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 1955 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 16552 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 16552 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 115862 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 115862 | h | 223 | 1
SUWP-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 330 | h | 223 | 1
SUWP-EC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 330 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 265 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 265 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 12586 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 12586 | h | 223 | 1
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 18663 | h | 223 | 1
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 18663 | h | 223 | 1
SUWP-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2268 | h | 223 | 1
SUWP-EC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2268 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 295 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 295 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 35772 | h | 223 | 1
SUWP-AT-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 35772 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 47967 | h | 223 | 1
SUWP-AC-PA-0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 47967 | h | 223 | 1
SUWP-EC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 429 | h | 223 | 1
SUWP-EC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 429 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 827 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 827 | h | 223 | 1
SUWP-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2640 | h | 223 | 1
SUWP-EC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2640 | h | 223 | 1
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 23708 | h | 223 | 1
SUWP-RP-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 23708 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 560 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 560 | h | 223 | 1
SUWP-AT-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 5966 | h | 223 | 1
SUWP-AT-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 5966 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2395 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2395 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 384 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 384 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 452 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 452 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 59396 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 59396 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 551 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 551 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 4067 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 4067 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2833 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2833 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 2242763 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 313740 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 313740 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 41883 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 41883 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 106930 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-16 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-16 | 193165 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-16 | 3451 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-16 | 3451 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-16 | 3318 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-16 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-16 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-16 | 3318 | h | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-23 | 3 | t | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-23 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-23 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-23 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-23 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-23 | 3 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 60606 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 19055 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 19055 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 334815 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 334815 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0822-PWPe-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPe-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
TTU0822-PWPe-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
TTU0822-PWPe-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
TTU0822-PWPe-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 49974 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 49974 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPe-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPe-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MRF0822-PWPe-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0822-PWPe-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MRF0822-PWPe-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0822-PWPe-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MRF0822-PWPe-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 94892 | h | 223 | 1
TTU0822-EWPc-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 94892 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
TTU0822-PWPe-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPe-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 689 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 689 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 612 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 612 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0822-PWPe-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPe-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1377 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPe-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 689 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPe-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 61221 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 61221 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3061 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3061 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 21767 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 30610 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 30610 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 19591 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 66818 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 66818 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 47446 | h | 223 | 1
MSD0822-EWPc-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 47446 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 27209 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 27209 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 13993 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 47446 | h | 223 | 1
MSD0822-EWPc-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 47446 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 47446 | h | 223 | 1
MSD0822-EWPc-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 47446 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 19591 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 66818 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 66818 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 47446 | h | 223 | 1
MSD0822-EWPc-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 47446 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 765 | h | 223 | 1
MEM0822-EWPc-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 765 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 13993 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1582 | h | 223 | 1
MSD0822-EWPc-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1582 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1582 | h | 223 | 1
MSD0822-EWPc-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1582 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 66818 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 66818 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 94892 | h | 223 | 1
MSD0822-EWPc-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 94892 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 54418 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 54418 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 19591 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 61221 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 61221 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3061 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 13993 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 43263 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0826-PWPe-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 6679 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 6679 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 81627 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 81627 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 94892 | h | 223 | 1
TTU0826-EWPc-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 94892 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 81627 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 81627 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 166755 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 166755 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 81627 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 81627 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0826-PWPe-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 29683 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 787 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 787 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0826-PWPe-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4745 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 25398 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 178580 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 178580 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 61221 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 61221 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 25398 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 32655 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 69966 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 69966 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 30824 | h | 223 | 1
CDC0827-EWPc-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 30824 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 30824 | h | 223 | 1
MSD0827-EWPc-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 30824 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 26667 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 26667 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 7321 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3416 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3416 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 20000 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 20000 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 2554 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 2554 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1703 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 23496 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 23496 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 13706 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 23496 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 23496 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 13706 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 23496 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 23496 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 11748 | h | 223 | 1
EWPp-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 305811 | h | 223 | 1
EWPp-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 305811 | h | 223 | 1
EWPp-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 244649 | h | 223 | 1
EWPp-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 244649 | h | 223 | 1
EWPp-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 305811 | h | 223 | 1
EWPp-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 305811 | h | 223 | 1
EWPp-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 122325 | h | 223 | 1
EWPp-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 122325 | h | 223 | 1
EWPp-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 244649 | h | 223 | 1
EWPp-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 244649 | h | 223 | 1
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 97971 | h | 223 | 1
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 97971 | h | 223 | 1
SUWP-RP-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1618 | h | 223 | 1
SUWP-RP-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1618 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 859 | h | 223 | 1
SUWP-RP-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 859 | h | 223 | 1
SUWP-AT-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 24916 | h | 223 | 1
SUWP-AT-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 24916 | h | 223 | 1
SUWP-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1904 | h | 223 | 1
SUWP-EC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1904 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 6297 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 6297 | h | 223 | 1
SUWP-AT-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 22365 | h | 223 | 1
SUWP-AT-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 22365 | h | 223 | 1
SUWP-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3732 | h | 223 | 1
SUWP-EC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3732 | h | 223 | 1
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 713 | h | 223 | 1
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 713 | h | 223 | 1
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1076 | h | 223 | 1
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1076 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 12212 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 12212 | h | 223 | 1
SUWP-AT-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 7184 | h | 223 | 1
SUWP-AT-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 7184 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 55383 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 55383 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 10480 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 10480 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 821 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 821 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4426 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4426 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1427 | h | 223 | 1
SUWP-RP-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1427 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 20561 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 20561 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 1955 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 115862 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 115862 | h | 223 | 1
SUWP-RP-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 486 | h | 223 | 1
SUWP-RP-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 486 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 115862 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 115862 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 371 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 371 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 12586 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 12586 | h | 223 | 1
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 18663 | h | 223 | 1
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 18663 | h | 223 | 1
SUWP-RP-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3342 | h | 223 | 1
SUWP-RP-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3342 | h | 223 | 1
SUWP-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 3432 | h | 223 | 1
SUWP-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 3432 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 295 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 295 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 215 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 215 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 827 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 827 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 2549 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 2549 | h | 223 | 1
SUWP-AT-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 107254 | h | 223 | 1
SUWP-AT-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 107254 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 560 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 560 | h | 223 | 1
SUWP-AT-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 41760 | h | 223 | 1
SUWP-AT-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 41760 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 2395 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 2395 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 384 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 384 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 452 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 452 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 59396 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 59396 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 643 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 643 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 830 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 830 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 4067 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 4067 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 2833 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 2833 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 2242763 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 117653 | h | 223 | 1
SUWP-MO-PF-1117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 117653 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 41883 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 41883 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 106930 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-23 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-23 | 193165 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-23 | 3451 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-23 | 3451 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-23 | 3318 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-23 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-23 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-23 | 3318 | h | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-30 | 3 | t | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-30 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-30 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-30 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-04-30 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-04-30 | 3 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 60606 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 7145 | h | 223 | 1
MEM0817-EWPc-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 7145 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 334815 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 334815 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 49974 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 49974 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 6122 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 2721 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 2721 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 6122 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 61221 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 61221 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 21767 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 30610 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 30610 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 19591 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 66818 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 66818 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 27209 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 27209 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 13993 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 19591 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 66818 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 66818 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 13993 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 66818 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 66818 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 54418 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 54418 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 19591 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 61221 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 61221 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3061 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 13993 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 43263 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 29683 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 81627 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 81627 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 81627 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 81627 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 33351 | h | 223 | 1
MSD0826-EWPc-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 33351 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 81627 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 81627 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 29683 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3498 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3498 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 25398 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 285728 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 285728 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 61221 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 61221 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 25398 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 32655 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 69966 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 69966 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 26667 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 26667 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 7321 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3416 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3416 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 20000 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 20000 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 2554 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 2554 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 1703 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 23496 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 23496 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 13706 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 23496 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 23496 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 13706 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 23496 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 23496 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 11748 | h | 223 | 1
EWPp-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 122325 | h | 223 | 1
EWPp-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 122325 | h | 223 | 1
EWPp-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 183487 | h | 223 | 1
EWPp-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 183487 | h | 223 | 1
EWPp-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 305811 | h | 223 | 1
EWPp-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 305811 | h | 223 | 1
EWPp-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 465364 | h | 223 | 1
EWPp-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 465364 | h | 223 | 1
EWPp-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 183487 | h | 223 | 1
EWPp-EC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 183487 | h | 223 | 1
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 97971 | h | 223 | 1
EWPp-DD-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 97971 | h | 223 | 1
EWPp-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 305811 | h | 223 | 1
EWPp-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 305811 | h | 223 | 1
SUWP-RP-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 1387 | h | 223 | 1
SUWP-RP-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 1387 | h | 223 | 1
SUWP-AT-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 14238 | h | 223 | 1
SUWP-AT-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 14238 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 4498 | h | 223 | 1
SUWP-RP-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 4498 | h | 223 | 1
SUWP-AT-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 26092 | h | 223 | 1
SUWP-AT-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 26092 | h | 223 | 1
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 306 | h | 223 | 1
SUWP-RP-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 306 | h | 223 | 1
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 154 | h | 223 | 1
SUWP-RP-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 154 | h | 223 | 1
SUWP-AT-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 2083 | h | 223 | 1
SUWP-AT-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 2083 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 12212 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 12212 | h | 223 | 1
SUWP-AT-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 5131 | h | 223 | 1
SUWP-AT-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 5131 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 55383 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 55383 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 10480 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 10480 | h | 223 | 1
SUWP-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 448 | h | 223 | 1
SUWP-EC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 448 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 821 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 821 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 4426 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 4426 | h | 223 | 1
SUWP-AT-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 6896 | h | 223 | 1
SUWP-AT-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 6896 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 131 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 131 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 17624 | h | 223 | 1
SUWP-AC-PF-1109 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 17624 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 1955 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 115862 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 115862 | h | 223 | 1
SUWP-RP-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 486 | h | 223 | 1
SUWP-RP-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 486 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 115862 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 115862 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 371 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 371 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 12586 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 12586 | h | 223 | 1
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 7998 | h | 223 | 1
SUWP-RP-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 7998 | h | 223 | 1
SUWP-RP-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 3342 | h | 223 | 1
SUWP-RP-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 3342 | h | 223 | 1
SUWP-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 1144 | h | 223 | 1
SUWP-EC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 1144 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 295 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 295 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 215 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 215 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 827 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 827 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 2549 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 2549 | h | 223 | 1
SUWP-AT-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 150156 | h | 223 | 1
SUWP-AT-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 150156 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 560 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 560 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 858 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 858 | h | 223 | 1
SUWP-AT-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 35794 | h | 223 | 1
SUWP-AT-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 35794 | h | 223 | 1
SUWP-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 2970 | h | 223 | 1
SUWP-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 2970 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 2395 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 2395 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 384 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 384 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 452 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 452 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 59396 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 59396 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 643 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 643 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 115 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 115 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 830 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 830 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 581 | h | 223 | 1
SUWP-RP-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 581 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 1214 | h | 223 | 1
SUWP-RP-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 1214 | h | 223 | 1
SUWP-AT-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 11736 | h | 223 | 1
SUWP-AT-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 11736 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 2242763 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 41883 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 41883 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 106930 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-04-30 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-04-30 | 193165 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-30 | 3451 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-30 | 3451 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-30 | 3318 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-30 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-04-30 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-04-30 | 3318 | h | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-07 | 3 | t | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-07 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-07 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-07 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-07 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-07 | 3 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 60606 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 334815 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 334815 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 49974 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 49974 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 6122 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 2721 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 2721 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 6122 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 61221 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 61221 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 21767 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 30610 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 30610 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 19591 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 66818 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 66818 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 27209 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 27209 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 13993 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 19591 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 66818 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 66818 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 13993 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 66818 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 66818 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 54418 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 54418 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 19591 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 61221 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 61221 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3061 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 13993 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 43263 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 29683 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 63261 | h | 223 | 1
EBD0826-EWPc-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 63261 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 63261 | h | 223 | 1
EBD0826-EWPc-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 63261 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69966 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 63261 | h | 223 | 1
EBD0826-EWPc-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 63261 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 29683 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3498 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3498 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-EWPc-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-EWPc-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-EWPc-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 24858 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 24858 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
MRF0827-EWPc-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
MCD0827-EWPc-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 25398 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-EWPc-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-EWPc-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 285728 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 285728 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
EEE0827-EWPc-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 61221 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 61221 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
ELU0827-EWPc-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 25398 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
JIL0827-EWPc-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-EWPc-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
JIL0827-EWPc-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 32655 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26237 | h | 223 | 1
SES0827-EWPc-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26237 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 26667 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 26667 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 7321 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3416 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3416 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 20000 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 20000 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 2554 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 2554 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 1703 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 23496 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 23496 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 13706 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 23496 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 23496 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 13706 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 23496 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 23496 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 11748 | h | 223 | 1
EWPp-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 122325 | h | 223 | 1
EWPp-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 122325 | h | 223 | 1
EWPp-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 305811 | h | 223 | 1
EWPp-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 305811 | h | 223 | 1
EWPp-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 372292 | h | 223 | 1
EWPp-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 372292 | h | 223 | 1
EWPp-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 305811 | h | 223 | 1
EWPp-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 305811 | h | 223 | 1
EWPp-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 122325 | h | 223 | 1
EWPp-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 122325 | h | 223 | 1
EWPp-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 305811 | h | 223 | 1
EWPp-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 305811 | h | 223 | 1
EWPp-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 305811 | h | 223 | 1
EWPp-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 305811 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 1505417 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 1505417 | h | 223 | 1
SUWP-AT-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 3727 | h | 223 | 1
SUWP-AT-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 3727 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 4014 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 4014 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 2570 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 2570 | h | 223 | 1
SUWP-AT-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 2916 | h | 223 | 1
SUWP-AT-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 2916 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 12212 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 12212 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 442 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 442 | h | 223 | 1
SUWP-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 31912 | h | 223 | 1
SUWP-EC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 31912 | h | 223 | 1
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 47 | h | 223 | 1
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 47 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 39559 | h | 223 | 1
SUWP-AC-PF-1104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 39559 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 2994 | h | 223 | 1
SUWP-RP-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 2994 | h | 223 | 1
SUWP-AT-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 24809 | h | 223 | 1
SUWP-AT-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 24809 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 821 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 821 | h | 223 | 1
SUWP-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 362 | h | 223 | 1
SUWP-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 362 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 1533 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 1533 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 1265 | h | 223 | 1
SUWP-RP-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 1265 | h | 223 | 1
SUWP-AT-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 10475 | h | 223 | 1
SUWP-AT-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 10475 | h | 223 | 1
SUWP-AT-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 6896 | h | 223 | 1
SUWP-AT-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 6896 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 460 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 460 | h | 223 | 1
SUWP-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 1884 | h | 223 | 1
SUWP-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 1884 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 1054 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 1054 | h | 223 | 1
SUWP-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 144 | h | 223 | 1
SUWP-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 144 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 115862 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 115862 | h | 223 | 1
SUWP-RP-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 347 | h | 223 | 1
SUWP-RP-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 347 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 115862 | h | 223 | 1
SUWP-EC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 115862 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 371 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 371 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 1105 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 1105 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 12586 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 12586 | h | 223 | 1
SUWP-RP-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 2387 | h | 223 | 1
SUWP-RP-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 2387 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 127 | h | 223 | 1
SUWP-RP-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 127 | h | 223 | 1
SUWP-AT-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 523 | h | 223 | 1
SUWP-AT-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 523 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 215 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 215 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 827 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 827 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 2549 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 2549 | h | 223 | 1
SUWP-AT-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 42902 | h | 223 | 1
SUWP-AT-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 42902 | h | 223 | 1
SUWP-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 30 | h | 223 | 1
SUWP-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 30 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 80 | h | 223 | 1
SUWP-RP-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 80 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 1201 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 1201 | h | 223 | 1
SUWP-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 990 | h | 223 | 1
SUWP-EC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 990 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 684 | h | 223 | 1
SUWP-RP-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 684 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 2333 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 2333 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 384 | h | 223 | 1
SUWP-RP-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 384 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 18481 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 18481 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 452 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 452 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 59396 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 59396 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 643 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 643 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 115 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 115 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 830 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 830 | h | 223 | 1
SUWP-AT-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 11736 | h | 223 | 1
SUWP-AT-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 11736 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 2242763 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 41883 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 41883 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 106930 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-07 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-07 | 193165 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-07 | 3451 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-07 | 3451 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-07 | 3318 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-07 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-07 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-07 | 3318 | h | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-14 | 3 | t | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-14 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-14 | 3 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-14 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-14 | 3 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-14 | 3 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 60606 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 334815 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 334815 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
TTU0822-EWPc-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
EBD0822-EWPc-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 49974 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 49974 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
TTU0822-EWPc-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
TTU0822-EWPc-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
EBD0822-EWPc-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 6122 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
EBD0822-EWPc-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 2721 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 2721 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
TTU0822-EWPc-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 6122 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 61221 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 61221 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
TTU0822-EWPc-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 21767 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
EBD0822-EWPc-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54224 | h | 223 | 1
TTU0822-EWPc-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54224 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 30610 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 30610 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 19591 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 66818 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 66818 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 27209 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 27209 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 13993 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 19591 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 66818 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 66818 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 13993 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 66818 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 66818 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 54418 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 54418 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 19591 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 61221 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 61221 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3061 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 13993 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 43263 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 29683 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 69966 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 69966 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 69966 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 29683 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3498 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3498 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 39772 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 39772 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 285728 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 285728 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 22958 | h | 223 | 1
MEM0827-EWPc-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 22958 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 69267 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 69267 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32655 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 26667 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 26667 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 7321 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 598 | h | 223 | 1
EEE1048-PWPe-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 598 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3500 | h | 223 | 1
ESD1049-EWPc-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3500 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 16500 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 16500 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 447 | h | 223 | 1
EEE1049-PWPe-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 447 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1703 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 19384 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 19384 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 4112 | h | 223 | 1
EEE1049-PWPe-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 4112 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 13706 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 19384 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 19384 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 4112 | h | 223 | 1
EEE1049-PWPe-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 4112 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 13706 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 19384 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 19384 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 4112 | h | 223 | 1
EEE1049-PWPe-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 4112 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 11748 | h | 223 | 1
EWPp-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 183487 | h | 223 | 1
EWPp-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 183487 | h | 223 | 1
EWPp-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 122325 | h | 223 | 1
EWPp-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 122325 | h | 223 | 1
EWPp-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 122325 | h | 223 | 1
EWPp-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 122325 | h | 223 | 1
EWPp-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 122325 | h | 223 | 1
EWPp-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 122325 | h | 223 | 1
EWPp-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 122325 | h | 223 | 1
EWPp-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 122325 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1505417 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1505417 | h | 223 | 1
SUWP-AS-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 52180 | h | 223 | 1
SUWP-AS-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 52180 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 5620 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 5620 | h | 223 | 1
SUWP-AT-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 552 | h | 223 | 1
SUWP-AT-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 552 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 361 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 361 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 8994 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 8994 | h | 223 | 1
SUWP-AT-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 833 | h | 223 | 1
SUWP-AT-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 833 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 359 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 359 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 194 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 194 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 12212 | h | 223 | 1
SUWP-EC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 12212 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 2201 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 2201 | h | 223 | 1
SUWP-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 412 | h | 223 | 1
SUWP-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 412 | h | 223 | 1
SUWP-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 78 | h | 223 | 1
SUWP-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 78 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1547 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1547 | h | 223 | 1
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 165 | h | 223 | 1
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 165 | h | 223 | 1
SUWP-AT-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 43416 | h | 223 | 1
SUWP-AT-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 43416 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 821 | h | 223 | 1
SUWP-RP-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 821 | h | 223 | 1
SUWP-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 2532 | h | 223 | 1
SUWP-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 2532 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 5367 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 5367 | h | 223 | 1
SUWP-AT-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 18332 | h | 223 | 1
SUWP-AT-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 18332 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 212 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 212 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 460 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 460 | h | 223 | 1
SUWP-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1098 | h | 223 | 1
SUWP-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1098 | h | 223 | 1
SUWP-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 628 | h | 223 | 1
SUWP-EC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 628 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3688 | h | 223 | 1
SUWP-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1008 | h | 223 | 1
SUWP-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1008 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 115862 | h | 223 | 1
SUWP-RP-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 115862 | h | 223 | 1
SUWP-AT-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 320000 | h | 223 | 1
SUWP-AT-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 320000 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 159 | h | 223 | 1
SUWP-RP-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 159 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1105 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1105 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1798 | h | 223 | 1
SUWP-RP-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1798 | h | 223 | 1
SUWP-AT-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 50652 | h | 223 | 1
SUWP-AT-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 50652 | h | 223 | 1
SUWP-AT-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1220 | h | 223 | 1
SUWP-AT-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1220 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 215 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 215 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 236 | h | 223 | 1
SUWP-RP-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 236 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1181 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1181 | h | 223 | 1
SUWP-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1732 | h | 223 | 1
SUWP-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1732 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 2549 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 2549 | h | 223 | 1
SUWP-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 10 | h | 223 | 1
SUWP-EC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 10 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 1201 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 1201 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 956 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 956 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 3266 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 3266 | h | 223 | 1
SUWP-AT-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 227 | h | 223 | 1
SUWP-AT-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 227 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 32341 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 32341 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 65 | h | 223 | 1
SUWP-RP-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 65 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 59396 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 59396 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 184 | h | 223 | 1
SUWP-RP-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 184 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 115 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 115 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 830 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 830 | h | 223 | 1
SUWP-AT-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 16848 | h | 223 | 1
SUWP-AT-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 16848 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 2242763 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 41883 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 41883 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 106930 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-14 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-14 | 193165 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-14 | 3451 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-14 | 3451 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-14 | 3318 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-14 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-14 | 3318 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-14 | 3318 | h | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-21 | 1 | t | 223 | 1
MSD0822-CWP-117 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-21 | 1 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-21 | 1 | t | 223 | 1
MSD0822-CWP-121 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-21 | 1 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-21 | 1 | t | 223 | 1
MSD0822-CWP-125 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-21 | 1 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-21 | 2 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-21 | 2 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 60606 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 334815 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 334815 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 49974 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 49974 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-EWPc-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-EWPc-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-EWPc-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 4745 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3061 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3061 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 2721 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 2721 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-EWPc-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-EWPc-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-EWPc-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 4745 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3061 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 47446 | h | 223 | 1
JIL0822-EWPc-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 47446 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1148 | h | 223 | 1
JIL0822-EWPc-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1148 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 21767 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 4898 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 4898 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 78399 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 78399 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 9795 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 9795 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 23723 | h | 223 | 1
MSD0822-EWPc-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 23723 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-EWPc-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 19591 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13364 | h | 223 | 1
MSD0822-CWP-117 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13364 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 27209 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 27209 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-EWPc-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13993 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 52656 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 52656 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 78399 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 78399 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 4898 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 4898 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 9795 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 9795 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 19591 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13364 | h | 223 | 1
MSD0822-CWP-121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13364 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-EWPc-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13993 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 52656 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 52656 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13364 | h | 223 | 1
MSD0822-CWP-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13364 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 78399 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 78399 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 4898 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 4898 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 9795 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 9795 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 54418 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 54418 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-EWPc-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 19591 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 47446 | h | 223 | 1
MSD0822-EWPc-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 47446 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-EWPc-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1148 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13993 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 52656 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 52656 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 43263 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 29683 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13993 | h | 223 | 1
MRF0826-EWPc-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13993 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13993 | h | 223 | 1
MRF0826-EWPc-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13993 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 29683 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3498 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3498 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 39772 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 39772 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 107148 | h | 223 | 1
TTU0827-EWPc-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 107148 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 39829 | h | 223 | 1
ELU0827-PWPp-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 39829 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32655 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 26667 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 26667 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 7321 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 20000 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 20000 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1703 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 23496 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 23496 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13706 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 23496 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 23496 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 13706 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 23496 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 23496 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 11748 | h | 223 | 1
EWPp-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 305811 | h | 223 | 1
EWPp-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 305811 | h | 223 | 1
EWPp-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 244649 | h | 223 | 1
EWPp-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 244649 | h | 223 | 1
EWPp-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 183487 | h | 223 | 1
EWPp-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 183487 | h | 223 | 1
EWPp-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 305811 | h | 223 | 1
EWPp-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 305811 | h | 223 | 1
EWPp-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 183487 | h | 223 | 1
EWPp-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 183487 | h | 223 | 1
EWPp-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 183487 | h | 223 | 1
EWPp-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 183487 | h | 223 | 1
EWPp-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 183487 | h | 223 | 1
EWPp-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 183487 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1505417 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1505417 | h | 223 | 1
SUWP-AS-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 52180 | h | 223 | 1
SUWP-AS-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 52180 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 5620 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 5620 | h | 223 | 1
SUWP-AT-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1932 | h | 223 | 1
SUWP-AT-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1932 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 2528 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 2528 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 8994 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 8994 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 628 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 628 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1356 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1356 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 10467 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 10467 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 7703 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 7703 | h | 223 | 1
SUWP-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 412 | h | 223 | 1
SUWP-EC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 412 | h | 223 | 1
SUWP-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 26 | h | 223 | 1
SUWP-EC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 26 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 606 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 606 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1547 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1547 | h | 223 | 1
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 165 | h | 223 | 1
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 165 | h | 223 | 1
SUWP-AT-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 18607 | h | 223 | 1
SUWP-AT-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 18607 | h | 223 | 1
SUWP-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 362 | h | 223 | 1
SUWP-EC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 362 | h | 223 | 1
SUWP-RP-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 857 | h | 223 | 1
SUWP-RP-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 857 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 5367 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 5367 | h | 223 | 1
SUWP-AT-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 7857 | h | 223 | 1
SUWP-AT-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 7857 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1485 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1485 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 460 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 460 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 151 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 151 | h | 223 | 1
SUWP-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 366 | h | 223 | 1
SUWP-EC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 366 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3688 | h | 223 | 1
SUWP-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 144 | h | 223 | 1
SUWP-EC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 144 | h | 223 | 1
SUWP-RP-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 463 | h | 223 | 1
SUWP-RP-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 463 | h | 223 | 1
SUWP-AT-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 320000 | h | 223 | 1
SUWP-AT-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 320000 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1105 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1105 | h | 223 | 1
SUWP-AT-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 52140 | h | 223 | 1
SUWP-AT-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 52140 | h | 223 | 1
SUWP-AT-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 50652 | h | 223 | 1
SUWP-AT-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 50652 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 10 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 10 | h | 223 | 1
SUWP-AT-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 697 | h | 223 | 1
SUWP-AT-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 697 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 61 | h | 223 | 1
SUWP-RP-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 61 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 209 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 209 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1654 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1654 | h | 223 | 1
SUWP-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1732 | h | 223 | 1
SUWP-EC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1732 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 364 | h | 223 | 1
SUWP-RP-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 364 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1201 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1201 | h | 223 | 1
SUWP-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 2006 | h | 223 | 1
SUWP-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 2006 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 956 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 956 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 3266 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 3266 | h | 223 | 1
SUWP-AT-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 1592 | h | 223 | 1
SUWP-AT-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 1592 | h | 223 | 1
SUWP-AS-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 450462 | h | 223 | 1
SUWP-AS-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 450462 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 32341 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 32341 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 8485 | h | 223 | 1
SUWP-AC-PF-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 8485 | h | 223 | 1
SUWP-AT-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 2287 | h | 223 | 1
SUWP-AT-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 2287 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 115 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 115 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 119 | h | 223 | 1
SUWP-RP-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 119 | h | 223 | 1
SUWP-AT-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 16848 | h | 223 | 1
SUWP-AT-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 16848 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 2242763 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 8377 | h | 223 | 1
MSD0622-EWPc-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 8377 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPe-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 106930 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-21 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-21 | 193165 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-21 | 1882 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-21 | 1882 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-21 | 690 | h | 223 | 1
MSD0822-CWP-117 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-21 | 690 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-21 | 2694 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-21 | 2694 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-21 | 1810 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-21 | 1810 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-21 | 664 | h | 223 | 1
MSD0822-CWP-121 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-21 | 664 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-21 | 2694 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-21 | 2694 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-21 | 664 | h | 223 | 1
MSD0822-CWP-125 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-21 | 664 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-21 | 1810 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-21 | 1810 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-21 | 2694 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-21 | 2694 | h | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-05-28 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-05-28 | 3 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 60606 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 334815 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 334815 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 16524 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 16524 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 38730 | h | 223 | 1
TTU0822-EWPc-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 38730 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21713 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21713 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 51089 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3061 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3061 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 2721 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 2721 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 17831 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 17831 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 23774 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 23774 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 22706 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 22706 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 51089 | h | 223 | 1
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 51089 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3061 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21767 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 6122 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 6122 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 97999 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 97999 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 19591 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 21087 | h | 223 | 1
MSD0822-EWPc-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 21087 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 13993 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 65820 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 65820 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 97999 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 97999 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 6122 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 6122 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 19591 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 13993 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 65820 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 65820 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 97999 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 97999 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 6122 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 6122 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 12244 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 42174 | h | 223 | 1
MSD0822-EWPc-125 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 42174 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 19591 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 13993 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 65820 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 65820 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 16524 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 16524 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 43263 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 29683 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 16524 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 16524 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 16524 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 16524 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 29683 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3498 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3498 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 39772 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 39772 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 16524 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 16524 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 20449 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32655 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 4667 | h | 223 | 1
ESD1042-EWPc-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 4667 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 7321 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 20000 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 20000 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1703 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 23496 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 23496 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 13706 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 23496 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 23496 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 13706 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 23496 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 23496 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 11748 | h | 223 | 1
EWPp-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 122325 | h | 223 | 1
EWPp-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 122325 | h | 223 | 1
EWPp-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 244649 | h | 223 | 1
EWPp-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 244649 | h | 223 | 1
EWPp-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 122325 | h | 223 | 1
EWPp-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 122325 | h | 223 | 1
EWPp-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 244649 | h | 223 | 1
EWPp-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 244649 | h | 223 | 1
EWPp-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 244649 | h | 223 | 1
EWPp-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 244649 | h | 223 | 1
EWPp-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 244649 | h | 223 | 1
EWPp-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 244649 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1505417 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1505417 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 5620 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 5620 | h | 223 | 1
SUWP-AT-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1380 | h | 223 | 1
SUWP-AT-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1380 | h | 223 | 1
SUWP-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 2124 | h | 223 | 1
SUWP-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 2124 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 2528 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 2528 | h | 223 | 1
SUWP-AS-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 125280 | h | 223 | 1
SUWP-AS-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 125280 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 8994 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 8994 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 628 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 628 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1356 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1356 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 12212 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 12212 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 7703 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 7703 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 606 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 606 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1547 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1547 | h | 223 | 1
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 71 | h | 223 | 1
SUWP-RP-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 71 | h | 223 | 1
SUWP-RP-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1200 | h | 223 | 1
SUWP-RP-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1200 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 5367 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 5367 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1485 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1485 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 394 | h | 223 | 1
SUWP-RP-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 394 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 353 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 353 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3688 | h | 223 | 1
SUWP-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 398 | h | 223 | 1
SUWP-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 398 | h | 223 | 1
SUWP-RP-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 648 | h | 223 | 1
SUWP-RP-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 648 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 22069 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 22069 | h | 223 | 1
SUWP-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 18270 | h | 223 | 1
SUWP-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 18270 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1105 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1105 | h | 223 | 1
SUWP-AT-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 52140 | h | 223 | 1
SUWP-AT-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 52140 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 836 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 836 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 10 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 10 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 150 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 150 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 293 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 293 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1654 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1654 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 464 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 464 | h | 223 | 1
SUWP-AT-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 9051 | h | 223 | 1
SUWP-AT-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 9051 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 515 | h | 223 | 1
SUWP-RP-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 515 | h | 223 | 1
SUWP-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 6018 | h | 223 | 1
SUWP-EC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 6018 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 956 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 956 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 3266 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 3266 | h | 223 | 1
SUWP-AT-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1365 | h | 223 | 1
SUWP-AT-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1365 | h | 223 | 1
SUWP-AS-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 150154 | h | 223 | 1
SUWP-AS-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 150154 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 32341 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 32341 | h | 223 | 1
SUWP-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 4372 | h | 223 | 1
SUWP-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 4372 | h | 223 | 1
SUWP-AT-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 2668 | h | 223 | 1
SUWP-AT-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 2668 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 170 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 170 | h | 223 | 1
SUWP-RP-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 38 | h | 223 | 1
SUWP-RP-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 38 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 115 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 115 | h | 223 | 1
SUWP-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 294 | h | 223 | 1
SUWP-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 294 | h | 223 | 1
SUWP-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 2316 | h | 223 | 1
SUWP-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 2316 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 2242763 | h | 223 | 1
MCD0822-PWPe-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
MCD0822-PWPe-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
MCD0822-PWPe-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
MCD0822-PWPe-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPe-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 167819 | h | 223 | 1
SES0822-PWPp-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 1342554 | h | 223 | 1
SES0822-PWPp-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 1342554 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-05-28 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-05-28 | 193165 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-28 | 2353 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-28 | 2353 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-28 | 3368 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-28 | 3368 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-28 | 2262 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-28 | 2262 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-28 | 3368 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-28 | 3368 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-28 | 2262 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-28 | 2262 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-05-28 | 3368 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-05-28 | 3368 | h | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-04 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-04 | 3 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 60606 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 34613 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 34613 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 27690 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 27690 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 334815 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 334815 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 20029 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 34613 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 34613 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 34613 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 34613 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 51089 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 51089 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 34613 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 34613 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 27690 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 27690 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 34613 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 34613 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 27690 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 27690 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 51089 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 34613 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 34613 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 61534 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 61534 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3061 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3061 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 2721 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 2721 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 41955 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 41955 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 55940 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 22706 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 22706 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 51089 | h | 223 | 1
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 51089 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 34613 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 34613 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 46150 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 46150 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3061 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 21767 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 6122 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 6122 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 97999 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 97999 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 19591 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 13993 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 65820 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 65820 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 97999 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 97999 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 6122 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 6122 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 19591 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 13993 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 65820 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 65820 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 97999 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 97999 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 6122 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 6122 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 19591 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 13993 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 65820 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 65820 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 20029 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 43263 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 29683 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 20029 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 20029 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 29683 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3498 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3498 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 14915 | h | 223 | 1
MEM0827-EWPc-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 14915 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 27893 | h | 223 | 1
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 27893 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 24786 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32655 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 7321 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 20000 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 20000 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1703 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 23496 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 23496 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 13706 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 23496 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 23496 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 13706 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 23496 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 23496 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 11748 | h | 223 | 1
EWPp-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 305811 | h | 223 | 1
EWPp-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 305811 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1505417 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1505417 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 5620 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 5620 | h | 223 | 1
SUWP-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 6372 | h | 223 | 1
SUWP-EC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 6372 | h | 223 | 1
SUWP-AS-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 23472 | h | 223 | 1
SUWP-AS-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 23472 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 2528 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 2528 | h | 223 | 1
SUWP-AS-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 41760 | h | 223 | 1
SUWP-AS-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 41760 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 8994 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 8994 | h | 223 | 1
SUWP-AS-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 11672 | h | 223 | 1
SUWP-AS-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 11672 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 628 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 628 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1356 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1356 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 12212 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 12212 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 7703 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 7703 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 606 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 606 | h | 223 | 1
SUWP-AS-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 28736 | h | 223 | 1
SUWP-AS-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 28736 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1547 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1547 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 9351 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 9351 | h | 223 | 1
SUWP-RP-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1200 | h | 223 | 1
SUWP-RP-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1200 | h | 223 | 1
SUWP-AS-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 99656 | h | 223 | 1
SUWP-AS-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 99656 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 5367 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 5367 | h | 223 | 1
SUWP-AS-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 13796 | h | 223 | 1
SUWP-AS-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 13796 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1485 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1485 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1383 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1383 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 353 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 353 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3688 | h | 223 | 1
SUWP-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1194 | h | 223 | 1
SUWP-EC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1194 | h | 223 | 1
SUWP-RP-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 185 | h | 223 | 1
SUWP-RP-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 185 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 154483 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 154483 | h | 223 | 1
SUWP-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 6090 | h | 223 | 1
SUWP-EC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 6090 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 158 | h | 223 | 1
SUWP-RP-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 158 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 836 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 836 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 10 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 10 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 263 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 263 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 293 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 293 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 1654 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 1654 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3248 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3248 | h | 223 | 1
SUWP-AT-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 10560 | h | 223 | 1
SUWP-AT-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 10560 | h | 223 | 1
SUWP-AT-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 2324 | h | 223 | 1
SUWP-AT-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 2324 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 2820 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 2820 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 956 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 956 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 3266 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 3266 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 32341 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 32341 | h | 223 | 1
SUWP-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 13116 | h | 223 | 1
SUWP-EC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 13116 | h | 223 | 1
SUWP-AT-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 381 | h | 223 | 1
SUWP-AT-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 381 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 199 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 199 | h | 223 | 1
SUWP-RP-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 38 | h | 223 | 1
SUWP-RP-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 38 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 115 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 115 | h | 223 | 1
SUWP-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 882 | h | 223 | 1
SUWP-EC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 882 | h | 223 | 1
SUWP-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 772 | h | 223 | 1
SUWP-EC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 772 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 2242763 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-04 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-04 | 193165 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-04 | 2353 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-04 | 2353 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-04 | 3368 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-04 | 3368 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-04 | 2262 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-04 | 2262 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-04 | 3368 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-04 | 3368 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-04 | 2262 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-04 | 2262 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-04 | 3368 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-04 | 3368 | h | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-11 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-11 | 3 | t | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 60606 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 60606 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 41955 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 41955 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 33564 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 334815 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 334815 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 20029 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0822-EWPc-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 569 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 569 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
TTU0822-EWPc-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
TTU0822-EWPc-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
TTU0822-EWPc-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 682 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 682 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 51089 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 51089 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 33564 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 33564 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 51089 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MRF0822-EWPc-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0822-EWPc-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 41955 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 74586 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MRF0822-EWPc-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0822-EWPc-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MRF0822-EWPc-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
TTU0822-EWPc-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3061 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3061 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2721 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2721 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MEM0822-EWPc-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0822-EWPc-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 41955 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 41955 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 55940 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 22706 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 22706 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 51089 | h | 223 | 1
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 51089 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 41955 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 41955 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 55940 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MEM0822-EWPc-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3061 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 21767 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 6122 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 6122 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 97999 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 97999 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 19591 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 13993 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 65820 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 65820 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 97999 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 97999 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 6122 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 6122 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 19591 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 13993 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 65820 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 65820 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 97999 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 97999 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 6122 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 6122 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 19591 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 13993 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 65820 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 65820 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 20029 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 43263 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0826-EWPc-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 29683 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 20029 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 20029 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
JIL0826-EWPc-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 29683 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2711 | h | 223 | 1
JIL0826-EWPc-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2711 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 38097 | h | 223 | 1
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 38097 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 24786 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32655 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 7321 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3500 | h | 223 | 1
EEE1049-EWPc-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3500 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1703 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 4112 | h | 223 | 1
EEE1049-EWPc-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 4112 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 13706 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 4112 | h | 223 | 1
EEE1049-EWPc-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 4112 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 13706 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 4112 | h | 223 | 1
EEE1049-EWPc-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 4112 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 11748 | h | 223 | 1
EWPp-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 122325 | h | 223 | 1
EWPp-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 122325 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1505417 | h | 223 | 1
C3000 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1505417 | h | 223 | 1
SUWP-AT-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3768 | h | 223 | 1
SUWP-AT-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3768 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 5620 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 5620 | h | 223 | 1
SUWP-AS-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 23472 | h | 223 | 1
SUWP-AS-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 23472 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2528 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2528 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 8994 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 8994 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 628 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 628 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1356 | h | 223 | 1
SUWP-EC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1356 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 12212 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 12212 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 6602 | h | 223 | 1
SUWP-RP-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 6602 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 606 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 606 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1547 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1547 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 9351 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 9351 | h | 223 | 1
SUWP-AT-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 486 | h | 223 | 1
SUWP-AT-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 486 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 5367 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 5367 | h | 223 | 1
SUWP-AS-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 13796 | h | 223 | 1
SUWP-AS-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 13796 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1485 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1485 | h | 223 | 1
SUWP-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 162 | h | 223 | 1
SUWP-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 162 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 745 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 745 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1937 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1937 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 353 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 353 | h | 223 | 1
SUWP-RP-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 419 | h | 223 | 1
SUWP-RP-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 419 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3688 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 9877 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 9877 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 154483 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 154483 | h | 223 | 1
SUWP-AT-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1097 | h | 223 | 1
SUWP-AT-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1097 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 7793 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 7793 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 836 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 836 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 10 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 10 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 263 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 263 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 293 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 293 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 945 | h | 223 | 1
SUWP-AT-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 945 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 532 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 532 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3248 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3248 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 4813 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 4813 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3015 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3015 | h | 223 | 1
SUWP-AT-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1509 | h | 223 | 1
SUWP-AT-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1509 | h | 223 | 1
SUWP-AT-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2324 | h | 223 | 1
SUWP-AT-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2324 | h | 223 | 1
SUWP-RP-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2236 | h | 223 | 1
SUWP-RP-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2236 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3948 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3948 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 137 | h | 223 | 1
SUWP-RP-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 137 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 3266 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 3266 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 32341 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 32341 | h | 223 | 1
SUWP-AT-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 1876 | h | 223 | 1
SUWP-AT-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 1876 | h | 223 | 1
SUWP-AS-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2152 | h | 223 | 1
SUWP-AS-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2152 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 199 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 199 | h | 223 | 1
SUWP-RP-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 27 | h | 223 | 1
SUWP-RP-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 27 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 115 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 115 | h | 223 | 1
SUWP-RP-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 309 | h | 223 | 1
SUWP-RP-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 309 | h | 223 | 1
SUWP-RP-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 8975 | h | 223 | 1
SUWP-RP-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 8975 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 2242763 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-11 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-11 | 193165 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-11 | 2353 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-11 | 2353 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-11 | 3368 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-11 | 3368 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-11 | 2262 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-11 | 2262 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-11 | 3368 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-11 | 3368 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-11 | 2262 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-11 | 2262 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-11 | 3368 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-11 | 3368 | h | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-18 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-18 | 3 | t | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 11905 | h | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 11905 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 34849 | h | 223 | 1
MEM0817-PWPp-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 34849 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 41955 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 41955 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 33564 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 334815 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 334815 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 20029 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 22748 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 22748 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-EWPc-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-EWPc-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 27298 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 51089 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 51089 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 33564 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 33564 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 51089 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-EWPc-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 41955 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 74586 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-EWPc-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2372 | h | 223 | 1
MEM0822-EWPc-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2372 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2721 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2721 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-EWPc-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 41955 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 41955 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 55940 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 22706 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 22706 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 51089 | h | 223 | 1
MMR0822-EWPc-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 51089 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 41955 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 41955 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 55940 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-EWPc-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2372 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 21767 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1224 | h | 223 | 1
MEM0822-PWPe-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1224 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 97999 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 97999 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 19591 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2449 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2449 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 13993 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 65820 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 65820 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 97999 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 97999 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2449 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2449 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1224 | h | 223 | 1
MEM0822-PWPe-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1224 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 19591 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 13993 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 65820 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 65820 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 97999 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 97999 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2449 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2449 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1224 | h | 223 | 1
MEM0822-PWPe-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1224 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 19591 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 13993 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 65820 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 65820 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 20029 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 43263 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 29683 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 20029 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 20029 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 29683 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 29683 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 29683 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 38097 | h | 223 | 1
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 38097 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 24786 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32655 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 7321 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 11748 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 819 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 819 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 662 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 662 | h | 223 | 1
SUWP-AT-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 4396 | h | 223 | 1
SUWP-AT-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 4396 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 5620 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 5620 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 416 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 416 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2528 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2528 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 8994 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 8994 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 628 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 628 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1162 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1162 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 3489 | h | 223 | 1
SUWP-RP-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 3489 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 13956 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 13956 | h | 223 | 1
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 889 | h | 223 | 1
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 889 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 87 | h | 223 | 1
SUWP-RP-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 87 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1547 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1547 | h | 223 | 1
SUWP-AT-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 9118 | h | 223 | 1
SUWP-AT-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 9118 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 9351 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 9351 | h | 223 | 1
SUWP-AT-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 3404 | h | 223 | 1
SUWP-AT-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 3404 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 5367 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 5367 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1485 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1485 | h | 223 | 1
SUWP-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 54 | h | 223 | 1
SUWP-EC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 54 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 745 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 745 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1937 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1937 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 252 | h | 223 | 1
SUWP-RP-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 252 | h | 223 | 1
SUWP-RP-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 587 | h | 223 | 1
SUWP-RP-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 587 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 3688 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 9877 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 9877 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 154483 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 154483 | h | 223 | 1
SUWP-AS-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 426667 | h | 223 | 1
SUWP-AS-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 426667 | h | 223 | 1
SUWP-AT-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1320 | h | 223 | 1
SUWP-AT-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1320 | h | 223 | 1
SUWP-AT-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1536 | h | 223 | 1
SUWP-AT-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1536 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 10910 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 10910 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 836 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 836 | h | 223 | 1
SUWP-AT-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1486 | h | 223 | 1
SUWP-AT-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1486 | h | 223 | 1
SUWP-AT-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 9076 | h | 223 | 1
SUWP-AT-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 9076 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1 | h | 223 | 1
SUWP-RP-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1 | h | 223 | 1
SUWP-AS-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 4888 | h | 223 | 1
SUWP-AS-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 4888 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 263 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 263 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 293 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 293 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1240 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1240 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 3248 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 3248 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 11230 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 11230 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 4221 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 4221 | h | 223 | 1
SUWP-RP-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 3130 | h | 223 | 1
SUWP-RP-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 3130 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 3948 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 3948 | h | 223 | 1
SUWP-AT-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 3960 | h | 223 | 1
SUWP-AT-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 3960 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1866 | h | 223 | 1
SUWP-AT-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1866 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1026 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1026 | h | 223 | 1
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 796 | h | 223 | 1
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 796 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 32341 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 32341 | h | 223 | 1
SUWP-AT-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 1876 | h | 223 | 1
SUWP-AT-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 1876 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 199 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 199 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 115 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 115 | h | 223 | 1
SUWP-AT-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 3440 | h | 223 | 1
SUWP-AT-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 3440 | h | 223 | 1
SUWP-RP-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 433 | h | 223 | 1
SUWP-RP-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 433 | h | 223 | 1
SUWP-RP-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 8975 | h | 223 | 1
SUWP-RP-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 8975 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 2242763 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-18 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-18 | 193165 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-18 | 2353 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-18 | 2353 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-18 | 3368 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-18 | 3368 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-18 | 2262 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-18 | 2262 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-18 | 3368 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-18 | 3368 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-18 | 2262 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-18 | 2262 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-18 | 3368 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-18 | 3368 | h | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-06-25 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-06-25 | 3 | t | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 26668 | h | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 26668 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 41955 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 41955 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 33564 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 334815 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 12328 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 12328 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 29885 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 29885 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 42148 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 42148 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0822-PWPe-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 20029 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 22748 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 22748 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 27298 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 29376 | h | 223 | 1
MCD0822-EWPc-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 29376 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 33564 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 33564 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 41955 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 74586 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2109 | h | 223 | 1
MEM0822-EWPc-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2109 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21713 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21713 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 24124 | h | 223 | 1
EEE0822-PWPe-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 24124 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 55940 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 22706 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 22706 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 41955 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 41955 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 55940 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 21767 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 21767 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 97999 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 97999 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 19591 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3061 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3061 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 13993 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 65820 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 65820 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 97999 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 97999 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3061 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3061 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 19591 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 13993 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 65820 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 65820 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 97999 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 97999 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3061 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3061 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 19591 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 13993 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 65820 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 65820 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 121576 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 121576 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0823-PWPe-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 20029 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 43263 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 29683 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 137573 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 137573 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0826-PWPe-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 20029 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 137573 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 137573 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0826-PWPe-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 20029 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1837 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1837 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28941 | h | 223 | 1
JIL0826-PWPp-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28941 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1837 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1837 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28941 | h | 223 | 1
JIL0826-PWPp-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28941 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2093 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 95462 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 95462 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32812 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32812 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 10205 | h | 223 | 1
ELU0827-PWPl-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 10205 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0827-PWPe-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 4338 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32655 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 7321 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 11748 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32766 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32766 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 26477 | h | 223 | 1
SUWP-AT-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 628 | h | 223 | 1
SUWP-AT-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 628 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 5620 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 5620 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 416 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 416 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 52 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 52 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2528 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2528 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 8994 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 8994 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 628 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 628 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1356 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1356 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 24424 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 24424 | h | 223 | 1
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1556 | h | 223 | 1
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1556 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1547 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1547 | h | 223 | 1
SUWP-AT-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 31912 | h | 223 | 1
SUWP-AT-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 31912 | h | 223 | 1
SUWP-AS-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 173672 | h | 223 | 1
SUWP-AS-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 173672 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 9351 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 9351 | h | 223 | 1
SUWP-AT-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2918 | h | 223 | 1
SUWP-AT-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2918 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 5367 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 5367 | h | 223 | 1
SUWP-AS-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 18334 | h | 223 | 1
SUWP-AS-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 18334 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1485 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1485 | h | 223 | 1
SUWP-AT-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 543 | h | 223 | 1
SUWP-AT-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 543 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 745 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 745 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1937 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1937 | h | 223 | 1
SUWP-RP-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 587 | h | 223 | 1
SUWP-RP-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 587 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3688 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 9877 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 9877 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 154483 | h | 223 | 1
SUWP-AC-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 154483 | h | 223 | 1
SUWP-AS-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1493333 | h | 223 | 1
SUWP-AS-PM-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1493333 | h | 223 | 1
SUWP-AT-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1320 | h | 223 | 1
SUWP-AT-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1320 | h | 223 | 1
SUWP-AT-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 439 | h | 223 | 1
SUWP-AT-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 439 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 10910 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 10910 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 119 | h | 223 | 1
SUWP-RP-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 119 | h | 223 | 1
SUWP-AT-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3468 | h | 223 | 1
SUWP-AT-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3468 | h | 223 | 1
SUWP-AT-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 9076 | h | 223 | 1
SUWP-AT-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 9076 | h | 223 | 1
SUWP-AT-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 40 | h | 223 | 1
SUWP-AT-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 40 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 263 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 263 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 293 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 293 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1240 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1240 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2784 | h | 223 | 1
SUWP-EC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2784 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 11230 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 11230 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 4221 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 4221 | h | 223 | 1
SUWP-AT-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3554 | h | 223 | 1
SUWP-AT-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3554 | h | 223 | 1
SUWP-RP-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3130 | h | 223 | 1
SUWP-RP-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3130 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3948 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3948 | h | 223 | 1
SUWP-AT-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3960 | h | 223 | 1
SUWP-AT-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3960 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2395 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2395 | h | 223 | 1
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 929 | h | 223 | 1
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 929 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 32341 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 32341 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 57 | h | 223 | 1
SUWP-RP-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 57 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 115 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 115 | h | 223 | 1
SUWP-AT-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3440 | h | 223 | 1
SUWP-AT-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3440 | h | 223 | 1
SUWP-RP-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 433 | h | 223 | 1
SUWP-RP-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 433 | h | 223 | 1
SUWP-RP-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 6411 | h | 223 | 1
SUWP-RP-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 6411 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 3629 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 3629 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 2242763 | h | 223 | 1
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 28950 | h | 223 | 1
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 28950 | h | 223 | 1
MEM1214-PWPe-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 15928 | h | 223 | 1
MEM1214-PWPe-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 15928 | h | 223 | 1
MCD0822-PWPp-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1342554 | h | 223 | 1
MCD0822-PWPp-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1342554 | h | 223 | 1
MCD0822-PWPp-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 1342554 | h | 223 | 1
MCD0822-PWPp-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 1342554 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-06-25 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-06-25 | 193165 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-25 | 2353 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-25 | 2353 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-25 | 3368 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-25 | 3368 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-25 | 2262 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-25 | 2262 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-25 | 3368 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-25 | 3368 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-25 | 2262 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-25 | 2262 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-06-25 | 3368 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-06-25 | 3368 | h | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-02 | 3 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-02 | 3 | t | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21372 | h | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21372 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21372 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21372 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21372 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21372 | h | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 26668 | h | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 26668 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32058 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32058 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 26435 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 26435 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 24240 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 24240 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 33060 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 33060 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 7342 | h | 223 | 1
SES0820-PWPe-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 7342 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 33564 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21372 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21372 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 47816 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 2165 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 2165 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 246 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 246 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1883 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1883 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 334815 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 70936 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 70936 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 620 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 620 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 334815 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 70936 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 70936 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 70936 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 70936 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 70936 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 70936 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 70936 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 70936 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 47816 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 2165 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 2165 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1883 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1883 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 51089 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 51089 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 20029 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 42148 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 42148 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 7342 | h | 223 | 1
SES0822-PWPe-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 7342 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 41955 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 22748 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 22748 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 27298 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 42148 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 42148 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 7342 | h | 223 | 1
SES0822-PWPe-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 7342 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 33564 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 42148 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 42148 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 7342 | h | 223 | 1
SES0822-PWPe-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 7342 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 33564 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 42148 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 42148 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 7342 | h | 223 | 1
SES0822-PWPe-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 7342 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 74586 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 51089 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 51089 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 55940 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 22706 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 22706 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 42148 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 42148 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 7342 | h | 223 | 1
MCD0822-PWPe-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 7342 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 55940 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21767 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 6734 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 6734 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 8163 | h | 223 | 1
JIL0822-PWPp-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 8163 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 27247 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 27247 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 27247 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 27247 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 246 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 246 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 589 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 589 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 97999 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 97999 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 19591 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3061 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3061 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 13993 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 65820 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 65820 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 97999 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 97999 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3061 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3061 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 19591 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 13993 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 65820 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 65820 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 97999 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 97999 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3061 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3061 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 19591 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 13993 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 65820 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 65820 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 78595 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 78595 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 147365 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 20029 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 246 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 246 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 589 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 589 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 29683 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 166755 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 166755 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 20029 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 166755 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 166755 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 589 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 589 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 11428 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 11428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 11428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 11428 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 246 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 246 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 21212 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 21212 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 589 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 589 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3349 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 152740 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 152740 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 39772 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 39772 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 246 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 246 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32655 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 7321 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 23268 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 23268 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 11748 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 246 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 246 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 589 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 589 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 246 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 246 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 655 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 655 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 19855 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 19855 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 58349 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 58349 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32766 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32766 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 26477 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 58349 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 58349 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 58349 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 58349 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 58349 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 58349 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 58349 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 58349 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 38900 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 38900 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 38900 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 38900 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 38900 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 38900 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 38900 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 38900 | h | 223 | 1
EWPp-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 244649 | h | 223 | 1
EWPp-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 244649 | h | 223 | 1
EWPp-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 305811 | h | 223 | 1
EWPp-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 305811 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 5620 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 5620 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 416 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 416 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 52 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 52 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 2528 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 2528 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 8994 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 8994 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 628 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 628 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1356 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1356 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 24424 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 24424 | h | 223 | 1
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1556 | h | 223 | 1
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1556 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1547 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1547 | h | 223 | 1
SUWP-AT-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 22794 | h | 223 | 1
SUWP-AT-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 22794 | h | 223 | 1
SUWP-AT-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 128 | h | 223 | 1
SUWP-AT-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 128 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 9351 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 9351 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 5367 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 5367 | h | 223 | 1
SUWP-AS-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 55002 | h | 223 | 1
SUWP-AS-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 55002 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1485 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1485 | h | 223 | 1
SUWP-AT-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1900 | h | 223 | 1
SUWP-AT-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1900 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 745 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 745 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 830 | h | 223 | 1
SUWP-RP-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 830 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3688 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 9877 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 9877 | h | 223 | 1
SUWP-AT-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 2016 | h | 223 | 1
SUWP-AT-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 2016 | h | 223 | 1
SUWP-AT-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 4580 | h | 223 | 1
SUWP-AT-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 4580 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 10910 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 10910 | h | 223 | 1
SUWP-AT-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1982 | h | 223 | 1
SUWP-AT-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1982 | h | 223 | 1
SUWP-AT-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 40 | h | 223 | 1
SUWP-AT-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 40 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 263 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 263 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 167 | h | 223 | 1
SUWP-AT-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 167 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 92 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 92 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1240 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1240 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 11230 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 11230 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 4221 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 4221 | h | 223 | 1
SUWP-AT-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 4976 | h | 223 | 1
SUWP-AT-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 4976 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3948 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3948 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3136 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3136 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 2395 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 2395 | h | 223 | 1
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 929 | h | 223 | 1
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 929 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 32341 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 32341 | h | 223 | 1
SUWP-AT-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 118 | h | 223 | 1
SUWP-AT-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 118 | h | 223 | 1
SUWP-AT-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 100 | h | 223 | 1
SUWP-AT-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 100 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 33 | h | 223 | 1
SUWP-AC-PF-1127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 33 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 3629 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 3629 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 40 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 40 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 8687 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 8687 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 8687 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 8687 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 8687 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 8687 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 19855 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 19855 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 2165 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 2165 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1883 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1883 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 2165 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 2165 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 1883 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 1883 | h | 223 | 1
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 68118 | h | 223 | 1
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 68118 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-02 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-02 | 193165 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-02 | 2353 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-02 | 2353 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-02 | 3368 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-02 | 3368 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-02 | 2262 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-02 | 2262 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-02 | 3368 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-02 | 3368 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-02 | 2262 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-02 | 2262 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-02 | 3368 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-02 | 3368 | h | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-178 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-09 | 2 | t | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-09 | 2 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-119 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-181 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-09 | 2 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-09 | 2 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-123 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-183 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-09 | 2 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-09 | 2 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-09 | 1 | t | 223 | 1
MSD0822-CWP-127 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-09 | 1 | t | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 26715 | h | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 26715 | h | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 26668 | h | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 26668 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 40073 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 40073 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 33044 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 33044 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 30300 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 30300 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 40073 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 33564 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 26715 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 26715 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 47816 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3465 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3465 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 41 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 41 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 83 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 83 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 153457 | h | 223 | 1
MEM0821-PWPe-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 153457 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 334815 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 88671 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 88671 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 24810 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 153457 | h | 223 | 1
MEM0821-PWPe-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 153457 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 334815 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 88671 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 88671 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 88671 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 88671 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 88671 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 88671 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 88671 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 88671 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 47816 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3465 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3465 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3012 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 51089 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 51089 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 20029 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 51089 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 51089 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 41955 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 22748 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 22748 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 27298 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 51089 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 51089 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 33564 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 51089 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 33564 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 51089 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 51089 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 74586 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 51089 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 51089 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 55940 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 22706 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 22706 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 51089 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 51089 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 55940 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 21767 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 11428 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 11428 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 34059 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 34059 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 23570 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 19600 | h | 223 | 1
MSD0822-CWP-178 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 19600 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 19591 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3061 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3061 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 78399 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 78399 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 4898 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 4898 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 8905 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 8905 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 13993 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 13164 | h | 223 | 1
MSD0822-CWP-119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 13164 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 19600 | h | 223 | 1
MSD0822-CWP-181 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 19600 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3061 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3061 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 19591 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 78399 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 78399 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 4898 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 4898 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 8905 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 8905 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 13993 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 13164 | h | 223 | 1
MSD0822-CWP-123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 13164 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 19600 | h | 223 | 1
MSD0822-CWP-183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 19600 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3061 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3061 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 19591 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 78399 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 78399 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 4898 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 4898 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 8905 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 8905 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 13993 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 13164 | h | 223 | 1
MSD0822-CWP-127 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 13164 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 98243 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 98243 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 147365 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 20029 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 23570 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 29683 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 166755 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 166755 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 20029 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 166755 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 166755 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 23570 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 11428 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 11428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 11428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 11428 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 9821 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 26515 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 26515 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3349 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 152740 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 152740 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 39772 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 39772 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 9821 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32655 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 7321 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 37229 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 37229 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 11748 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 26189 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 24819 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 24819 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 72937 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 72937 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 32766 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 32766 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 26477 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 72937 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 72937 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 72937 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 72937 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 72937 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 72937 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 72937 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 72937 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 48624 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 48624 | h | 223 | 1
EWPp-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 183487 | h | 223 | 1
EWPp-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 183487 | h | 223 | 1
EWPp-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 122325 | h | 223 | 1
EWPp-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 122325 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3211 | h | 223 | 1
SUWP-AC-PF-1110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3211 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 416 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 416 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 52 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 52 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 2528 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 2528 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 8994 | h | 223 | 1
SUWP-AC-PF-0504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 8994 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 628 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 628 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1356 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1356 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 24424 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 24424 | h | 223 | 1
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1334 | h | 223 | 1
SUWP-AC-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1334 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1547 | h | 223 | 1
SUWP-AC-PF-1118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1547 | h | 223 | 1
SUWP-AT-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 448 | h | 223 | 1
SUWP-AT-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 448 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 9351 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 9351 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 5367 | h | 223 | 1
SUWP-AC-PF-1106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 5367 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1485 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1485 | h | 223 | 1
SUWP-AT-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1357 | h | 223 | 1
SUWP-AT-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1357 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 106 | h | 223 | 1
SUWP-RP-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 106 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3688 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 9877 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 9877 | h | 223 | 1
SUWP-AT-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 576 | h | 223 | 1
SUWP-AT-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 576 | h | 223 | 1
SUWP-AT-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 17400 | h | 223 | 1
SUWP-AT-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 17400 | h | 223 | 1
SUWP-AT-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 4580 | h | 223 | 1
SUWP-AT-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 4580 | h | 223 | 1
SUWP-AS-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 208568 | h | 223 | 1
SUWP-AS-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 208568 | h | 223 | 1
SUWP-AS-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 151956 | h | 223 | 1
SUWP-AS-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 151956 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 10910 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 10910 | h | 223 | 1
SUWP-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 168 | h | 223 | 1
SUWP-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 168 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 263 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 263 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 215 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 215 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1240 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1240 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 11230 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 11230 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1809 | h | 223 | 1
SUWP-RP-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1809 | h | 223 | 1
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1156 | h | 223 | 1
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1156 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1950 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1950 | h | 223 | 1
SUWP-AT-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1422 | h | 223 | 1
SUWP-AT-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1422 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3948 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3948 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3136 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3136 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 2395 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 2395 | h | 223 | 1
SUWP-AS-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 1590 | h | 223 | 1
SUWP-AS-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 1590 | h | 223 | 1
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 531 | h | 223 | 1
SUWP-AC-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 531 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 23101 | h | 223 | 1
SUWP-AC-PF-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 23101 | h | 223 | 1
SUWP-AT-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 824 | h | 223 | 1
SUWP-AT-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 824 | h | 223 | 1
SUWP-AT-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 100 | h | 223 | 1
SUWP-AT-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 100 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3629 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3629 | h | 223 | 1
SUWP-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 6456 | h | 223 | 1
SUWP-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 6456 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 50 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 41 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 41 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 77 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 77 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 10858 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 10858 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 24819 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 24819 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3465 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3465 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3012 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3465 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3465 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 3012 | h | 223 | 1
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 68118 | h | 223 | 1
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 68118 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-09 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-09 | 193165 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-09 | 471 | h | 223 | 1
MSD0822-CWP-178 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-09 | 471 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-09 | 1882 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-09 | 1882 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-09 | 674 | h | 223 | 1
MSD0822-CWP-119 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-09 | 674 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-09 | 452 | h | 223 | 1
MSD0822-CWP-181 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-09 | 452 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-09 | 1810 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-09 | 1810 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-09 | 674 | h | 223 | 1
MSD0822-CWP-123 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-09 | 674 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-09 | 452 | h | 223 | 1
MSD0822-CWP-183 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-09 | 452 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-09 | 1810 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-09 | 1810 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-09 | 674 | h | 223 | 1
MSD0822-CWP-127 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-09 | 674 | h | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-16 | 3 | t | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-16 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-16 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-16 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-16 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-16 | 3 | t | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 26715 | h | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 26715 | h | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 22382 | h | 223 | 1
MEM0817-PWPl-498 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 22382 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 40073 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 40073 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 33044 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 33044 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 30300 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 30300 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 40073 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 33564 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 26715 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 26715 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 47816 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3465 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3465 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 1657 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 1657 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 334815 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 88671 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 88671 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 24810 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 334815 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 88671 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 88671 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 88671 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 47816 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3465 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3465 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3012 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 51089 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 51089 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 20029 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 51089 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 51089 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 41955 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 22748 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 22748 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 27298 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 51089 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 51089 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 33564 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 51089 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 33564 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 51089 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 51089 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 74586 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 51089 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 51089 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 55940 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 22706 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 22706 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 51089 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 51089 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 55940 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 21767 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 11428 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 11428 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 34059 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 34059 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 23570 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 19591 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3061 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3061 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 97999 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 97999 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 6122 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 6122 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 13993 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3061 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3061 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 19591 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 97999 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 97999 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 6122 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 6122 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 13993 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3061 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3061 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 19591 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 97999 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 97999 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 6122 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 6122 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 13993 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 98243 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 98243 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 147365 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 20029 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 23570 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 29683 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 29683 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 166755 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 166755 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 20029 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 166755 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 166755 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 23570 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 11428 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 11428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 11428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 11428 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 9821 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 26515 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 26515 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3349 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 152740 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 152740 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39772 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39772 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 9821 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 32655 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 7321 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 7321 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 37229 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 37229 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 11748 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 26189 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 24819 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 24819 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 72937 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 72937 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 1823 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 1823 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 31947 | h | 223 | 1
MEM1214-PWPe-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 31947 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 26477 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 72937 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 72937 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 72937 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 72937 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 72937 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 72937 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 72937 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 72937 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 48624 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 48624 | h | 223 | 1
SUWP-AS-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 7728 | h | 223 | 1
SUWP-AS-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 7728 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 416 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 416 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 52 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 52 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 2528 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 2528 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 449 | h | 223 | 1
SUWP-AC-PF-1205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 449 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 387 | h | 223 | 1
SUWP-RP-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 387 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 1548 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 1548 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 13956 | h | 223 | 1
SUWP-AT-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 13956 | h | 223 | 1
SUWP-AT-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 2512 | h | 223 | 1
SUWP-AT-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 2512 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 4599 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 4599 | h | 223 | 1
SUWP-AT-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 320 | h | 223 | 1
SUWP-AT-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 320 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 9351 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 9351 | h | 223 | 1
SUWP-AT-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3613 | h | 223 | 1
SUWP-AT-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3613 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 1485 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 1485 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 812 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 812 | h | 223 | 1
SUWP-AT-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 883 | h | 223 | 1
SUWP-AT-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 883 | h | 223 | 1
SUWP-AT-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 8020 | h | 223 | 1
SUWP-AT-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 8020 | h | 223 | 1
SUWP-AT-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 627 | h | 223 | 1
SUWP-AT-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 627 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3688 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 9877 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 9877 | h | 223 | 1
SUWP-AT-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 24360 | h | 223 | 1
SUWP-AT-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 24360 | h | 223 | 1
SUWP-AS-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 50652 | h | 223 | 1
SUWP-AS-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 50652 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 10910 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 10910 | h | 223 | 1
SUWP-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 56 | h | 223 | 1
SUWP-EC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 56 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 263 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 263 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 215 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 215 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 1240 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 1240 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 11230 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 11230 | h | 223 | 1
SUWP-AT-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 12494 | h | 223 | 1
SUWP-AT-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 12494 | h | 223 | 1
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 2023 | h | 223 | 1
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 2023 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 2274 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 2274 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 501 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 501 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3948 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3948 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 609 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 609 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3136 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3136 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 2395 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 2395 | h | 223 | 1
SUWP-AS-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 4770 | h | 223 | 1
SUWP-AS-PF-0203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 4770 | h | 223 | 1
SUWP-AS-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 10672 | h | 223 | 1
SUWP-AS-PF-0204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 10672 | h | 223 | 1
SUWP-AT-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 706 | h | 223 | 1
SUWP-AT-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 706 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3629 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3629 | h | 223 | 1
SUWP-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 6456 | h | 223 | 1
SUWP-EC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 6456 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 50 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 1657 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 1657 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3093 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 10858 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 10858 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 24819 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 24819 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3465 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3465 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3012 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3465 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3465 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 3012 | h | 223 | 1
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
MCD0822-EWPc-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
MCD0822-EWPc-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 39168 | h | 223 | 1
SES0822-EWPc-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 39168 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-16 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-16 | 193165 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-16 | 2353 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-16 | 2353 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-16 | 2262 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-16 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-16 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-16 | 2262 | h | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-23 | 3 | t | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-23 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-23 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-23 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-23 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-23 | 3 | t | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 26715 | h | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 26715 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 40073 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 40073 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 33044 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 33044 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 30300 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 30300 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 40073 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 33564 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 26715 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 26715 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 47816 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 55419 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 55419 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3465 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3465 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 1657 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 1657 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 55419 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 55419 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0824-PWPe-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0821-PWPe-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 334815 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 88671 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 88671 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 24810 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 55419 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 55419 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0821-PWPe-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 334815 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 88671 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 88671 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 88671 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 47816 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 31930 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 31930 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 31930 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 31930 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 31930 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 31930 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3465 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3465 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3012 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0822-PWPe-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0822-PWPe-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0822-PWPe-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 8941 | h | 223 | 1
MEM0822-EWPc-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 8941 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 20029 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 51089 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 51089 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 41955 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 1277 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 1277 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 22179 | h | 223 | 1
SES0822-PWPe-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 22179 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 27298 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 51089 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 51089 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 33564 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 51089 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 33564 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 51089 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 51089 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 74586 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 29376 | h | 223 | 1
EEE0822-EWPc-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 29376 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 55940 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 22706 | h | 223 | 1
MMR0822-EWPc-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 22706 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 51089 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 51089 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 55940 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 21767 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 11428 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 11428 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 34059 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 34059 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 23570 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 19591 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3061 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3061 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 97999 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 97999 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 6122 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 6122 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 13993 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3061 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3061 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 19591 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 97999 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 97999 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 6122 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 6122 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 13993 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3061 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3061 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 19591 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 97999 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 97999 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 6122 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 6122 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 13993 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 92103 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 92103 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 98243 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 98243 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0823-PWPe-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 25789 | h | 223 | 1
MEM0823-EWPc-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 25789 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 20029 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0824-PWPe-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 17667 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 17667 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 49467 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 15451 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 15451 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 23570 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 19894 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 19894 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0824-PWPe-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 82893 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 82893 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 82893 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 82893 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 1837 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 1837 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 28941 | h | 223 | 1
MCD0826-PWPp-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 28941 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 29182 | h | 223 | 1
MEM0826-EWPc-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 29182 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 20029 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 29182 | h | 223 | 1
MEM0826-EWPc-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 29182 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 23570 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 11428 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 11428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 11428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 11428 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 9821 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 26515 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 26515 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3349 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 24858 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 24858 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 57277 | h | 223 | 1
MCD0827-PWPe-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 57277 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 6960 | h | 223 | 1
MEM0827-EWPc-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 6960 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 9821 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 32655 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3501 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3501 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 1281 | h | 223 | 1
EEE1048-PWPp-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 1281 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 37229 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 37229 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 11748 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 26189 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 24819 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 24819 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 72937 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 72937 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 72937 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 72937 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 26477 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 72937 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 72937 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 72937 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 72937 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 72937 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 72937 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 72937 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 72937 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 48624 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 48624 | h | 223 | 1
EWPp-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 183487 | h | 223 | 1
EWPp-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 183487 | h | 223 | 1
EWPp-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 183487 | h | 223 | 1
EWPp-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 183487 | h | 223 | 1
EWPp-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 183487 | h | 223 | 1
EWPp-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 183487 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 416 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 416 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 7 | h | 223 | 1
SUWP-RP-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 7 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 361 | h | 223 | 1
SUWP-AC-PF-1111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 361 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 2709 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 2709 | h | 223 | 1
SUWP-AT-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 2512 | h | 223 | 1
SUWP-AT-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 2512 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 16097 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 16097 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 6873 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 6873 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 9351 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 9351 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 105 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 105 | h | 223 | 1
SUWP-AT-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 2891 | h | 223 | 1
SUWP-AT-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 2891 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 212 | h | 223 | 1
SUWP-AC-PF-1112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 212 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 947 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 947 | h | 223 | 1
SUWP-AT-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3092 | h | 223 | 1
SUWP-AT-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3092 | h | 223 | 1
SUWP-AT-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 8020 | h | 223 | 1
SUWP-AT-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 8020 | h | 223 | 1
SUWP-AT-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 1464 | h | 223 | 1
SUWP-AT-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 1464 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 1955 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3688 | h | 223 | 1
SUWP-RP-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3688 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 9877 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 9877 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 5644 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 5644 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 284 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 284 | h | 223 | 1
SUWP-RP-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 83 | h | 223 | 1
SUWP-RP-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 83 | h | 223 | 1
SUWP-AT-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 6960 | h | 223 | 1
SUWP-AT-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 6960 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 10910 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 10910 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 1955 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 1955 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 6 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 6 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 263 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 263 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 215 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 215 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 354 | h | 223 | 1
SUWP-AC-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 354 | h | 223 | 1
SUWP-AS-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 7088 | h | 223 | 1
SUWP-AS-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 7088 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 11230 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 11230 | h | 223 | 1
SUWP-AT-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 17492 | h | 223 | 1
SUWP-AT-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 17492 | h | 223 | 1
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 2023 | h | 223 | 1
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 2023 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 2274 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 2274 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 501 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 501 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 236 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 236 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3948 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3948 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 853 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 853 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3136 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3136 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 2395 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 2395 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 404 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 404 | h | 223 | 1
SUWP-RP-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 4077 | h | 223 | 1
SUWP-RP-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 4077 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3629 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3629 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 50 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 1657 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 1657 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3093 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 10858 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 10858 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 24819 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 24819 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3465 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3465 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3012 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3465 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3465 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 3012 | h | 223 | 1
MEM1214-EWPc-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-EWPc-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 206654 | h | 223 | 1
MEM1214-PWPp-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103532 | h | 223 | 1
MEM1214-PWPp-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103528 | h | 223 | 1
MEM1214-PWPp-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103528 | h | 223 | 1
MEM1214-PWPp-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103528 | h | 223 | 1
MEM1214-PWPp-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103528 | h | 223 | 1
MEM1214-PWPp-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 103528 | h | 223 | 1
MEM1214-PWPp-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 103528 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-23 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-23 | 193165 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-23 | 2353 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-23 | 2353 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-23 | 2262 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-23 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-23 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-23 | 2262 | h | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-30 | 3 | t | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-30 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-30 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-30 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-07-30 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-07-30 | 3 | t | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 26715 | h | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 26715 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 8015 | h | 223 | 1
CDC0820-EWPc-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 8015 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 6609 | h | 223 | 1
MSD0820-EWPc-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 6609 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 6060 | h | 223 | 1
ESD0820-EWPc-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 6060 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 7013 | h | 223 | 1
SES0820-EWPc-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 7013 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 33564 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 26715 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 26715 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 14248 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 14248 | h | 223 | 1
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 87084 | h | 223 | 1
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 87084 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 79168 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 47816 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 55419 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 55419 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 88671 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 88671 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1299 | h | 223 | 1
TTU0821-PWPe-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1299 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1657 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1657 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 88671 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 88671 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 88671 | h | 223 | 1
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 88671 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 334815 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 17734 | h | 223 | 1
CDC0821-EWPc-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 17734 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 24810 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 88671 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 88671 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 88671 | h | 223 | 1
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 88671 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 334815 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 17734 | h | 223 | 1
MEM0821-EWPc-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 17734 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 17734 | h | 223 | 1
MEM0821-EWPc-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 17734 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 17734 | h | 223 | 1
EEE0821-EWPc-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 17734 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 17734 | h | 223 | 1
MEM0821-EWPc-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 17734 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 47816 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 51089 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 51089 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 51089 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 51089 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 51089 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 51089 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1299 | h | 223 | 1
MEM0822-PWPe-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1299 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3012 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 21287 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 21287 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 20029 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MCD0822-PWPp-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 8941 | h | 223 | 1
SES0822-EWPc-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 8941 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 41955 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 51089 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 51089 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPp-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
TTU0822-PWPp-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
TTU0822-PWPp-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPp-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 27298 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 8941 | h | 223 | 1
SES0822-EWPc-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 8941 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 33564 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 8941 | h | 223 | 1
SES0822-EWPc-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 8941 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 33564 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
TTU0822-PWPp-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPp-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 30300 | h | 223 | 1
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 30300 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MRF0822-PWPp-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 8941 | h | 223 | 1
SES0822-EWPc-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 8941 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 74586 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MCD0822-PWPp-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MRF0822-PWPp-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MCD0822-PWPp-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MRF0822-PWPp-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
TTU0822-PWPp-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPp-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MCD0822-PWPp-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPp-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 55940 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 8941 | h | 223 | 1
MCD0822-EWPc-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 8941 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 55940 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
MEM0822-PWPp-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3469 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPp-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16870 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 7959 | h | 223 | 1
JIL0822-PWPl-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 7959 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 34059 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 34059 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 23570 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 19591 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3061 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3061 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 97999 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 97999 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 6122 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 6122 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 13993 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3061 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3061 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 19591 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 97999 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 97999 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 6122 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 6122 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 13993 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3061 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3061 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 19591 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 97999 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 97999 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 6122 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 6122 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 13993 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 147365 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 147365 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 98243 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 98243 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3684 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3684 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 20029 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 78595 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 78595 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1658 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1658 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 17225 | h | 223 | 1
MEM0824-PWPe-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 17225 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 49467 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1658 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1658 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 15065 | h | 223 | 1
MEM0824-PWPe-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 15065 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 43263 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 17667 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 17667 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 49467 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 15451 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 15451 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 43263 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 17667 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 17667 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 49467 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 15451 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 15451 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 23570 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 88419 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 132628 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 132628 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 132628 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 132628 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 11428 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 11428 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 23570 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1428 | h | 223 | 1
JIL0826-PWPl-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1428 | h | 223 | 1
JIL0826-PWPl-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1428 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9821 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 26515 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 26515 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3349 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 39772 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 39772 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9821 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 32655 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 4782 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 4782 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 13961 | h | 223 | 1
MSD1214-EWPc-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 13961 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 11748 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 30714 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 30714 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 26189 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 24819 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 24819 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 14587 | h | 223 | 1
CDC1214-EWPc-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 14587 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 72937 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 72937 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 26477 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 14587 | h | 223 | 1
MSD1214-EWPc-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 14587 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 14587 | h | 223 | 1
MSD1214-EWPc-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 14587 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 14587 | h | 223 | 1
MSD1214-EWPc-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 14587 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 14587 | h | 223 | 1
CPI1214-EWPc-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 14587 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 48624 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 48624 | h | 223 | 1
EWPp-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 305811 | h | 223 | 1
EWPp-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 305811 | h | 223 | 1
EWPp-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 244649 | h | 223 | 1
EWPp-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 244649 | h | 223 | 1
EWPp-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 244649 | h | 223 | 1
EWPp-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 244649 | h | 223 | 1
EWPp-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 244649 | h | 223 | 1
EWPp-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 244649 | h | 223 | 1
EWPp-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 305811 | h | 223 | 1
EWPp-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 305811 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 416 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 416 | h | 223 | 1
SUWP-AT-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 220 | h | 223 | 1
SUWP-AT-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 220 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 741 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 741 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 2709 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 2709 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 16097 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 16097 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 6873 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 6873 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9351 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9351 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 733 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 733 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 947 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 947 | h | 223 | 1
SUWP-AT-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 2209 | h | 223 | 1
SUWP-AT-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 2209 | h | 223 | 1
SUWP-AT-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 837 | h | 223 | 1
SUWP-AT-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 837 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1955 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9877 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9877 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9877 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9877 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 143 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 143 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 284 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 284 | h | 223 | 1
SUWP-RP-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 83 | h | 223 | 1
SUWP-RP-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 83 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 750 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 750 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 10910 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 10910 | h | 223 | 1
SUWP-AS-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 13864 | h | 223 | 1
SUWP-AS-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 13864 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1955 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1955 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 9 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 9 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 188 | h | 223 | 1
SUWP-AC-PF-1132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 188 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 215 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 215 | h | 223 | 1
SUWP-AS-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 7088 | h | 223 | 1
SUWP-AS-PE-0502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 7088 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 11230 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 11230 | h | 223 | 1
SUWP-AT-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 4998 | h | 223 | 1
SUWP-AT-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 4998 | h | 223 | 1
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1734 | h | 223 | 1
SUWP-AC-PF-1207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1734 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 2274 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 2274 | h | 223 | 1
SUWP-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1564 | h | 223 | 1
SUWP-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1564 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 501 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 501 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 331 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 331 | h | 223 | 1
SUWP-AT-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 4855 | h | 223 | 1
SUWP-AT-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 4855 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3948 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3948 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 853 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 853 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 448 | h | 223 | 1
SUWP-RP-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 448 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3021 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3021 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 2395 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 2395 | h | 223 | 1
SUWP-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 264 | h | 223 | 1
SUWP-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 264 | h | 223 | 1
SUWP-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 738 | h | 223 | 1
SUWP-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 738 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 404 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 404 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 15 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 15 | h | 223 | 1
SUWP-RP-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 4757 | h | 223 | 1
SUWP-RP-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 4757 | h | 223 | 1
SUWP-AT-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 672 | h | 223 | 1
SUWP-AT-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 672 | h | 223 | 1
SUWP-AS-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 67400 | h | 223 | 1
SUWP-AS-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 67400 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3629 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3629 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 50 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 2245 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 2245 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1657 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1657 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3093 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 10858 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 10858 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 24819 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 24819 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1299 | h | 223 | 1
MCD0622-PWPe-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1299 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3012 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 30539 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 30539 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 15270 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 15270 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 1299 | h | 223 | 1
MEM0622-PWPe-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 1299 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 3012 | h | 223 | 1
MEM1214-EWPc-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 85093 | h | 223 | 1
MEM1214-EWPc-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 85093 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-07-30 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-07-30 | 193165 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-30 | 2353 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-30 | 2353 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-30 | 2262 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-30 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-07-30 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-07-30 | 2262 | h | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-06 | 3 | t | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-06 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-06 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-06 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-06 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-06 | 3 | t | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 26715 | h | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 26715 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 26715 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 26715 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 33564 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 26715 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 26715 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 17810 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 17810 | h | 223 | 1
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 87084 | h | 223 | 1
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 87084 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 79168 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 47816 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 88671 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 88671 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 88671 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 88671 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1657 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1657 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 88671 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 88671 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 88671 | h | 223 | 1
MEM0821-EWPc-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 88671 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 24810 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 88671 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 88671 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 88671 | h | 223 | 1
MEM0821-EWPc-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 88671 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 334815 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 47816 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 51089 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 51089 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 51089 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 51089 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 51089 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 51089 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3012 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 34059 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 34059 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 20029 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 41955 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 51089 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 51089 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3484 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3484 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3097 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3097 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 33564 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 212290 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 212290 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 33564 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3484 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3484 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3097 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3097 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 30300 | h | 223 | 1
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 30300 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 74586 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 55940 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 204329 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 204329 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3484 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3484 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3097 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3097 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 55940 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 34059 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 34059 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 34059 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 23570 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 12244 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 19591 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 19591 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3061 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3061 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 97999 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 97999 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2449 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2449 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1224 | h | 223 | 1
MEM0822-PWPe-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1224 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 13993 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3061 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3061 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 12244 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 19591 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 19591 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 97999 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 97999 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 4898 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 4898 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1224 | h | 223 | 1
MEM0822-PWPe-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1224 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 13993 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3061 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3061 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 12244 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 19591 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 19591 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 97999 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 97999 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2449 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2449 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1224 | h | 223 | 1
MEM0822-PWPe-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1224 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 13993 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 147365 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 147365 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 98243 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 98243 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 147365 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 20029 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 98243 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 98243 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 66314 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 66314 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 49467 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 66314 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 66314 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 43263 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 56367 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 56367 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 10158 | h | 223 | 1
MEM0824-PWPe-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 10158 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 49467 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 56367 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 56367 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 8884 | h | 223 | 1
MEM0824-PWPe-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 8884 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 43263 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 56367 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 56367 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 10158 | h | 223 | 1
MEM0824-PWPe-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 10158 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 49467 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 56367 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 56367 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 8884 | h | 223 | 1
MEM0824-PWPe-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 8884 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 23570 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 88419 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 132628 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 132628 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 132628 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 132628 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11428 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11428 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 23570 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 9821 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 26515 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 26515 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3349 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 39772 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 39772 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 9821 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 32655 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 4782 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 4782 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11748 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 37229 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 37229 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 26189 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 24819 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 24819 | h | 223 | 1
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 7554 | h | 223 | 1
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 7554 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 13735 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 72937 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 72937 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 26477 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 48624 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 48624 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 48624 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 48624 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 48624 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 689 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 689 | h | 223 | 1
EWPp-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 122325 | h | 223 | 1
EWPp-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 122325 | h | 223 | 1
EWPp-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 305811 | h | 223 | 1
EWPp-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 305811 | h | 223 | 1
EWPp-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 305811 | h | 223 | 1
EWPp-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 305811 | h | 223 | 1
EWPp-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 305811 | h | 223 | 1
EWPp-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 305811 | h | 223 | 1
EWPp-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 305811 | h | 223 | 1
EWPp-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 305811 | h | 223 | 1
EWPp-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 122325 | h | 223 | 1
EWPp-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 122325 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 416 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 416 | h | 223 | 1
SUWP-AT-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 220 | h | 223 | 1
SUWP-AT-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 220 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 741 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 741 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2709 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2709 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 152 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 152 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 16097 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 16097 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 6873 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 6873 | h | 223 | 1
SUWP-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2796 | h | 223 | 1
SUWP-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2796 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2672 | h | 223 | 1
SUWP-AC-PF-0307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2672 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 28 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 28 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 733 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 733 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 947 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 947 | h | 223 | 1
SUWP-AT-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1140 | h | 223 | 1
SUWP-AT-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1140 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1955 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 4233 | h | 223 | 1
SUWP-AT-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 4233 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 9877 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 9877 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 268 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 268 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1000 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1000 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 284 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 284 | h | 223 | 1
SUWP-RP-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 59 | h | 223 | 1
SUWP-RP-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 59 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 5247 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 5247 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 10910 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 10910 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1955 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1955 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 9 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 9 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 215 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 215 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11230 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11230 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2274 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2274 | h | 223 | 1
SUWP-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 4692 | h | 223 | 1
SUWP-EC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 4692 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 501 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 501 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 766 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 766 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 331 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 331 | h | 223 | 1
SUWP-AT-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 8496 | h | 223 | 1
SUWP-AT-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 8496 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2256 | h | 223 | 1
SUWP-AC-PF-1105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2256 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 853 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 853 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 4230 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 4230 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2395 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2395 | h | 223 | 1
SUWP-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 792 | h | 223 | 1
SUWP-EC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 792 | h | 223 | 1
SUWP-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2214 | h | 223 | 1
SUWP-EC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2214 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 404 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 404 | h | 223 | 1
SUWP-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 594 | h | 223 | 1
SUWP-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 594 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 22 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 22 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 117 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 117 | h | 223 | 1
SUWP-RP-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 4077 | h | 223 | 1
SUWP-RP-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 4077 | h | 223 | 1
SUWP-AT-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1176 | h | 223 | 1
SUWP-AT-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1176 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3629 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3629 | h | 223 | 1
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 253263 | h | 223 | 1
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 253263 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 251608 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 50 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 11224 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 1657 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 1657 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3093 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 10858 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 10858 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 10858 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 10858 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 24819 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 24819 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3012 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 48863 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 48863 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 3012 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-06 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-06 | 193165 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-06 | 2353 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-06 | 2353 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-06 | 2262 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-06 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-06 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-06 | 2262 | h | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-13 | 3 | t | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-13 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-13 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-13 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-13 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-13 | 3 | t | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 5343 | h | 223 | 1
ESD0800-EWPc-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 5343 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 5343 | h | 223 | 1
ESD0800-EWPc-482 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 5343 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 5343 | h | 223 | 1
ESD0800-EWPc-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 5343 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 33564 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 5343 | h | 223 | 1
ESD0822-EWPc-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 5343 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 17810 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 17810 | h | 223 | 1
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 87084 | h | 223 | 1
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 87084 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 79168 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 47816 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 88671 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 88671 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 88671 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 88671 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1657 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1657 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 88671 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 88671 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 24810 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 88671 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 88671 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 334815 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 47816 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 51089 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 51089 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 51089 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 51089 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 51089 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 51089 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3012 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 34059 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 34059 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1913 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1913 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 4636 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 4636 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 20029 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 41955 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 51089 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 51089 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 4223 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 4223 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3754 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 33564 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 257322 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 33564 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 4223 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 4223 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3754 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 30300 | h | 223 | 1
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 30300 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 74586 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 55940 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 247672 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 247672 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 4223 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 4223 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3754 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 55940 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 6812 | h | 223 | 1
JSD0822-EWPc-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 6812 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 6812 | h | 223 | 1
JSD0822-EWPc-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 6812 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 23570 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1684 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1684 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 7346 | h | 223 | 1
MEM0822-PWPp-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 7346 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 612 | h | 223 | 1
MEM0822-EWPc-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 612 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 97999 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 97999 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3061 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3061 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 13993 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 612 | h | 223 | 1
MEM0822-EWPc-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 612 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1684 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1684 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 7346 | h | 223 | 1
MEM0822-PWPp-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 7346 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 97999 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 97999 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 6122 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 6122 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 13993 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 612 | h | 223 | 1
MEM0822-EWPc-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 612 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1684 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1684 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 7346 | h | 223 | 1
MEM0822-PWPp-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 7346 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 97999 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 97999 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3061 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3061 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 13993 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 580 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 580 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 147365 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 147365 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 19649 | h | 223 | 1
SSD0823-EWPc-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 19649 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 15300 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 15300 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 147365 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 20029 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 98243 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 98243 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 66314 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 66314 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 49467 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 66314 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 66314 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 43263 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 132628 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 132628 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 49467 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 132628 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 132628 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 43263 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 132628 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 132628 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 49467 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 132628 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 132628 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 23570 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 88419 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 132628 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 132628 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 132628 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 132628 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11428 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11428 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 23570 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9821 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 5303 | h | 223 | 1
MSD0827-EWPc-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 5303 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3349 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 39772 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 39772 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9821 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 32655 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 4782 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 4782 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11748 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 37229 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 37229 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 26189 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 4964 | h | 223 | 1
ESD1062-EWPc-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 4964 | h | 223 | 1
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 7554 | h | 223 | 1
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 7554 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 13735 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 71113 | h | 223 | 1
MEM1214-EWPc-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 71113 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 26477 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9725 | h | 223 | 1
ESD1214-EWPc-488 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9725 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9725 | h | 223 | 1
ESD1214-EWPc-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9725 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9725 | h | 223 | 1
TSD1214-EWPc-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9725 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9725 | h | 223 | 1
ESD1214-EWPc-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9725 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3060 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3060 | h | 223 | 1
EWPp-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 122325 | h | 223 | 1
EWPp-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 122325 | h | 223 | 1
EWPp-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 305811 | h | 223 | 1
EWPp-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 305811 | h | 223 | 1
EWPp-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 122325 | h | 223 | 1
EWPp-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 122325 | h | 223 | 1
EWPp-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 122325 | h | 223 | 1
EWPp-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 122325 | h | 223 | 1
EWPp-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 122325 | h | 223 | 1
EWPp-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 122325 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 416 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 416 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 741 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 741 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1548 | h | 223 | 1
SUWP-AT-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1548 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 576 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 576 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 177 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 177 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 16097 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 16097 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 6873 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 6873 | h | 223 | 1
SUWP-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 932 | h | 223 | 1
SUWP-EC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 932 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 96 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 96 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 733 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 733 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 947 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 947 | h | 223 | 1
SUWP-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 258 | h | 223 | 1
SUWP-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 258 | h | 223 | 1
SUWP-AT-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1596 | h | 223 | 1
SUWP-AT-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1596 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1955 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9877 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9877 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 626 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 626 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1000 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1000 | h | 223 | 1
SUWP-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 5490 | h | 223 | 1
SUWP-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 5490 | h | 223 | 1
SUWP-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 588 | h | 223 | 1
SUWP-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 588 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 284 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 284 | h | 223 | 1
SUWP-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 342 | h | 223 | 1
SUWP-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 342 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 5247 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 5247 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 6234 | h | 223 | 1
SUWP-AC-PF-1113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 6234 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1955 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1955 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 986 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 986 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 215 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 215 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 9626 | h | 223 | 1
SUWP-AC-PF-1202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 9626 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 218 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 218 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 2274 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 2274 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1079 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1079 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 509 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 509 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 501 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 501 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1072 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1072 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 331 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 331 | h | 223 | 1
SUWP-AT-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3641 | h | 223 | 1
SUWP-AT-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3641 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 853 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 853 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 4230 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 4230 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 2395 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 2395 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 404 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 404 | h | 223 | 1
SUWP-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 198 | h | 223 | 1
SUWP-EC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 198 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 22 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 22 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 409 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 409 | h | 223 | 1
SUWP-AT-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 504 | h | 223 | 1
SUWP-AT-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 504 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3629 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3629 | h | 223 | 1
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 253263 | h | 223 | 1
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 253263 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 251608 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 50 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 11224 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 1657 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 1657 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3093 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 2172 | h | 223 | 1
ESD0600-EWPc-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 2172 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 2172 | h | 223 | 1
ESD0600-EWPc-479 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 2172 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 2172 | h | 223 | 1
ESD0600-EWPc-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 2172 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 4964 | h | 223 | 1
ESD1062-EWPc-486 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 4964 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3012 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 48863 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 48863 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 3012 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-13 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-13 | 193165 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-13 | 2353 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-13 | 2353 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-13 | 2262 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-13 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-13 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-13 | 2262 | h | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-20 | 3 | t | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-20 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-20 | 3 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-20 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-20 | 3 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-20 | 3 | t | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 33564 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 17810 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 17810 | h | 223 | 1
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 87084 | h | 223 | 1
MEM0821-PWPe-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 87084 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 79168 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 47816 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 88671 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 88671 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 33251 | h | 223 | 1
MCD0821-EWPc-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 33251 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1657 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1657 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 5146 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 5146 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 7841 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 7841 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 33251 | h | 223 | 1
MCD0824-EWPc-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 33251 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 24810 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 33251 | h | 223 | 1
MCD0821-EWPc-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 33251 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 334815 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 5146 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 5146 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 7841 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 7841 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 47816 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 19158 | h | 223 | 1
MCD0822-EWPc-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 19158 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 19158 | h | 223 | 1
MCD0822-EWPc-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 19158 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 19158 | h | 223 | 1
MCD0822-EWPc-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 19158 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3012 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 34059 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 34059 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3060 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3060 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 20029 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 41955 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 49812 | h | 223 | 1
SES0822-EWPc-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 49812 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 4223 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 4223 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3754 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 33564 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 257322 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 33564 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 4223 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 4223 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3754 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 30300 | h | 223 | 1
MSD0822-EWPc-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 30300 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 74586 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 55940 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 247672 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 247672 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 4223 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 4223 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3754 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 55940 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 23570 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 2857 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 97999 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 97999 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3061 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3061 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 13993 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 2857 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 97999 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 97999 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 6122 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 6122 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 13993 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 2857 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 97999 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 97999 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3061 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3061 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 13993 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 55262 | h | 223 | 1
MCD0823-EWPc-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 55262 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 24481 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 24481 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 147365 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 20029 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 98243 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 98243 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 66314 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 66314 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 49467 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 66314 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 66314 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 43263 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 132628 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 132628 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 49467 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 132628 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 132628 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 43263 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 132628 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 132628 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 49467 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 132628 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 132628 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 23570 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 88419 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 49736 | h | 223 | 1
MCD0824-EWPc-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 49736 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 49736 | h | 223 | 1
MCD0824-EWPc-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 49736 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11428 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11428 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 23570 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 9821 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3349 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 14915 | h | 223 | 1
MCD0827-EWPc-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 14915 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 9821 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 32655 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 2647 | h | 223 | 1
EEE1048-PWPl-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 2647 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11748 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 37229 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 37229 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 26189 | h | 223 | 1
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 7554 | h | 223 | 1
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 7554 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 13735 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 26477 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3060 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3060 | h | 223 | 1
EWPp-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 122325 | h | 223 | 1
EWPp-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 122325 | h | 223 | 1
EWPp-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 305810 | h | 223 | 1
EWPp-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 305810 | h | 223 | 1
SUWP-AS-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 17576 | h | 223 | 1
SUWP-AS-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 17576 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 119 | h | 223 | 1
SUWP-AC-PF-1213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 119 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 741 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 741 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 2015 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 2015 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 177 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 177 | h | 223 | 1
SUWP-RP-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1373 | h | 223 | 1
SUWP-RP-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1373 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 16097 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 16097 | h | 223 | 1
SUWP-AS-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 127648 | h | 223 | 1
SUWP-AS-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 127648 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 6873 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 6873 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 96 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 96 | h | 223 | 1
SUWP-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 2064 | h | 223 | 1
SUWP-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 2064 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 733 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 733 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 947 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 947 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 666 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 666 | h | 223 | 1
SUWP-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 86 | h | 223 | 1
SUWP-EC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 86 | h | 223 | 1
SUWP-AT-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 456 | h | 223 | 1
SUWP-AT-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 456 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1955 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 9877 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 9877 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 626 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 626 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1000 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1000 | h | 223 | 1
SUWP-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1830 | h | 223 | 1
SUWP-EC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1830 | h | 223 | 1
SUWP-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 196 | h | 223 | 1
SUWP-EC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 196 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 284 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 284 | h | 223 | 1
SUWP-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 114 | h | 223 | 1
SUWP-EC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 114 | h | 223 | 1
SUWP-AS-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 16419 | h | 223 | 1
SUWP-AS-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 16419 | h | 223 | 1
SUWP-AT-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 163 | h | 223 | 1
SUWP-AT-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 163 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 5247 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 5247 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1955 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1955 | h | 223 | 1
SUWP-AS-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 126 | h | 223 | 1
SUWP-AS-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 126 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 9 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 9 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 986 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 986 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 215 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 215 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 255 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 255 | h | 223 | 1
SUWP-AS-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 42240 | h | 223 | 1
SUWP-AS-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 42240 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 2274 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 2274 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1510 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1510 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 713 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 713 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 501 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 501 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1072 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1072 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 331 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 331 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 853 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 853 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 4230 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 4230 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 342 | h | 223 | 1
SUWP-AC-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 342 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 2691 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 2691 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 191 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 191 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 404 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 404 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 22 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 22 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 409 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 409 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3629 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3629 | h | 223 | 1
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 253263 | h | 223 | 1
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 253263 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 251608 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 50 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 11224 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 1657 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 1657 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3093 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3012 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 48863 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 48863 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 3012 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-20 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-20 | 193165 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-20 | 2353 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-20 | 2353 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-20 | 2262 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-20 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-20 | 2262 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-20 | 2262 | h | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-27 | 1 | t | 223 | 1
MSD0822-CWP-180 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-27 | 1 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-27 | 1 | t | 223 | 1
MSD0822-CWP-186 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-27 | 1 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-08-27 | 1 | t | 223 | 1
MSD0822-CWP-188 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-08-27 | 1 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-08-27 | 56 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-08-27 | 56 | t | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 33564 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 17810 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 17810 | h | 223 | 1
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 88671 | h | 223 | 1
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 88671 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 79168 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 47816 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 33251 | h | 223 | 1
TTU0821-EWPc-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 33251 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 2217 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 2217 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1616 | h | 223 | 1
TTU0821-PWPe-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1616 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 8233 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 8233 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 12546 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 24810 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 334815 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 8233 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 8233 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 12546 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3012 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 34059 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 34059 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3060 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3060 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 20029 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MCD0822-PWPl-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 41955 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
TTU0822-PWPl-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
TTU0822-PWPl-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 4223 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 4223 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3754 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
TTU0822-PWPl-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 33564 | h | 223 | 1
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 40017 | h | 223 | 1
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 40017 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 257322 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 33564 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 4223 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 4223 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3754 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 41576 | h | 223 | 1
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 40017 | h | 223 | 1
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 40017 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 41576 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MRF0822-PWPl-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 74586 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MCD0822-PWPl-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MRF0822-PWPl-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MCD0822-PWPl-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MRF0822-PWPl-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
TTU0822-PWPl-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MCD0822-PWPl-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 55940 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 247672 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 247672 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MSD0822-CWP-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 272380 | h | 223 | 1
MSD0822-CWP-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 272380 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 4223 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 4223 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3754 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 55940 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
MEM0822-PWPl-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
JIL0822-PWPl-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 23570 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 2857 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 19600 | h | 223 | 1
MSD0822-CWP-180 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 19600 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3061 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3061 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 13993 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 2857 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 19600 | h | 223 | 1
MSD0822-CWP-186 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 19600 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 6122 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 6122 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 13993 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 2857 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 19600 | h | 223 | 1
MSD0822-CWP-188 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 19600 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3061 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3061 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 13993 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 24481 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 24481 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 143681 | h | 223 | 1
JPA0823-EWPc-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 143681 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 20029 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 98243 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 98243 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 66314 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 66314 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 49467 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 66314 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 66314 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 43263 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 132628 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 132628 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 49467 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 132628 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 132628 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 43263 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 132628 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 132628 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 49467 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 132628 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 132628 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 23570 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 88419 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1428 | h | 223 | 1
MCD0826-PWPl-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1428 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 23570 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9821 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3349 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 25398 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9821 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 32655 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 32655 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11748 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 6515 | h | 223 | 1
EEE1062-EWPc-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 6515 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 26189 | h | 223 | 1
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 7554 | h | 223 | 1
EEE1062-PWPe-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 7554 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 13735 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 26477 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3060 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3060 | h | 223 | 1
EWPp-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 183486 | h | 223 | 1
EWPp-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 183486 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 34 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 34 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 741 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 741 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 2015 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 2015 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 177 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 177 | h | 223 | 1
SUWP-RP-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1373 | h | 223 | 1
SUWP-RP-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1373 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 16097 | h | 223 | 1
SUWP-AC-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 16097 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 6873 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 6873 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 96 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 96 | h | 223 | 1
SUWP-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 688 | h | 223 | 1
SUWP-EC-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 688 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 733 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 733 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 551 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 551 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 947 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 947 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 666 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 666 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 541 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 541 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 135 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 135 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 83 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 83 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1955 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1955 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9877 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9877 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 626 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 626 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1767 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1767 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 189 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 189 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1000 | h | 223 | 1
SUWP-EC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1000 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 110 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 110 | h | 223 | 1
SUWP-AS-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 5280 | h | 223 | 1
SUWP-AS-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 5280 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 284 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 284 | h | 223 | 1
SUWP-AS-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 19156 | h | 223 | 1
SUWP-AS-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 19156 | h | 223 | 1
SUWP-AT-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 228 | h | 223 | 1
SUWP-AT-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 228 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 5247 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 5247 | h | 223 | 1
SUWP-AS-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 36304 | h | 223 | 1
SUWP-AS-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 36304 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1955 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1955 | h | 223 | 1
SUWP-AS-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 42 | h | 223 | 1
SUWP-AS-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 42 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 986 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 986 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 215 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 215 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 255 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 255 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 2274 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 2274 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1510 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1510 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 713 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 713 | h | 223 | 1
SUWP-AS-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 9288 | h | 223 | 1
SUWP-AS-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 9288 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 501 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 501 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1072 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1072 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 331 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 331 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1727 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1727 | h | 223 | 1
SUWP-AS-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 15840 | h | 223 | 1
SUWP-AS-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 15840 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 853 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 853 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 4230 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 4230 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3768 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3768 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 191 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 191 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 404 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 404 | h | 223 | 1
SUWP-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 13902 | h | 223 | 1
SUWP-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 13902 | h | 223 | 1
SUWP-AS-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 300 | h | 223 | 1
SUWP-AS-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 300 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 22 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 22 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 409 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 409 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1037 | h | 223 | 1
SUWP-AC-PF-1201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1037 | h | 223 | 1
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 202611 | h | 223 | 1
B30363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 202611 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 251608 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 50 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 2864 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 2864 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 1616 | h | 223 | 1
TTU0622-PWPe-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 1616 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3093 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3012 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 48863 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 48863 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 3012 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-08-27 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-08-27 | 193165 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-27 | 45228 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-27 | 45228 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-27 | 471 | h | 223 | 1
MSD0822-CWP-180 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-27 | 471 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-27 | 452 | h | 223 | 1
MSD0822-CWP-186 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-27 | 452 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-08-27 | 452 | h | 223 | 1
MSD0822-CWP-188 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-08-27 | 452 | h | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-09-03 | 63 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-09-03 | 63 | t | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 22105 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 22105 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 33564 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 17810 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 17810 | h | 223 | 1
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 88671 | h | 223 | 1
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 88671 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 79168 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 47816 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 88671 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 88671 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 8233 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 8233 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12546 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 24810 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 334815 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 8233 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 8233 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12546 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3012 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 34059 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 34059 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3060 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3060 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 41955 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 42148 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 42148 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 739 | h | 223 | 1
EEE1042-PWPe-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 739 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3754 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 42148 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 42148 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 33564 | h | 223 | 1
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 40017 | h | 223 | 1
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 40017 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 257322 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 33564 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 739 | h | 223 | 1
EEE1042-PWPe-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 739 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3754 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 41576 | h | 223 | 1
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 40017 | h | 223 | 1
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 40017 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 41576 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 74586 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 55940 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 42148 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 42148 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 43343 | h | 223 | 1
MEM0822-PWPe-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 43343 | h | 223 | 1
MSD0822-CWP-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 311292 | h | 223 | 1
MSD0822-CWP-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 311292 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 42148 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 42148 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 739 | h | 223 | 1
EEE1042-PWPe-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 739 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 55940 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 23570 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 2857 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3061 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3061 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 13993 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 2857 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1224 | h | 223 | 1
MEM0822-EWPc-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1224 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 13993 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 2857 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3061 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3061 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 13993 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 24481 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 24481 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 20029 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 98243 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 98243 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 22105 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 22105 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 66314 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 66314 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 49467 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 66314 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 66314 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 43263 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 76261 | h | 223 | 1
MEM0824-EWPc-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 76261 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 49467 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 76261 | h | 223 | 1
MEM0824-EWPc-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 76261 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 43263 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 76261 | h | 223 | 1
MEM0824-EWPc-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 76261 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 49467 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 76261 | h | 223 | 1
MEM0824-EWPc-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 76261 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 23570 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 68525 | h | 223 | 1
MCD0824-EWPc-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 68525 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 23570 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 9821 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
SES0827-PWPp-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 15715 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 15715 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 15715 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 15715 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 15715 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 15715 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MRF0827-PWPp-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MRF0827-PWPp-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 11905 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 11905 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 25398 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 20029 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3349 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
EEE0827-PWPp-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 25398 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 15715 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 15715 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
JIL0827-PWPp-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 9821 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
MEM0827-PWPp-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 12245 | h | 223 | 1
JIL0827-PWPp-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 12245 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 11748 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 26189 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 16546 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 16546 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 13735 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 26477 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 2372 | h | 223 | 1
TTU1215-PWPe-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 2372 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1669 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1669 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 10941 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 10941 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 58782 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 58782 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 47 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 47 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 741 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 741 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 2015 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 2015 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 177 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 177 | h | 223 | 1
SUWP-RP-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 981 | h | 223 | 1
SUWP-RP-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 981 | h | 223 | 1
SUWP-AS-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 121421 | h | 223 | 1
SUWP-AS-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 121421 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 6873 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 6873 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 96 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 96 | h | 223 | 1
SUWP-AS-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3402 | h | 223 | 1
SUWP-AS-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3402 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 733 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 733 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 772 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 772 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 947 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 947 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 666 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 666 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 541 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 541 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 315 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 315 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 83 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 83 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 664 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 664 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1397 | h | 223 | 1
SUWP-EC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1397 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 9877 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 9877 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 447 | h | 223 | 1
SUWP-AC-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 447 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1767 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1767 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 189 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 189 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 110 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 110 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 284 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 284 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 857 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 857 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 179 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 179 | h | 223 | 1
SUWP-AS-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 6144 | h | 223 | 1
SUWP-AS-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 6144 | h | 223 | 1
SUWP-AS-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 5473 | h | 223 | 1
SUWP-AS-PA-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 5473 | h | 223 | 1
SUWP-AT-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 65 | h | 223 | 1
SUWP-AT-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 65 | h | 223 | 1
SUWP-AS-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 97448 | h | 223 | 1
SUWP-AS-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 97448 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 5247 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 5247 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1955 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1955 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 9 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 9 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 986 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 986 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 31 | h | 223 | 1
SUWP-AC-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 31 | h | 223 | 1
SUWP-AS-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1472 | h | 223 | 1
SUWP-AS-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1472 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 255 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 255 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 2274 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 2274 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1510 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1510 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 713 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 713 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 501 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 501 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1072 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1072 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 331 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 331 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1830 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1830 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 1727 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 1727 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 853 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 853 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 4230 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 4230 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3768 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3768 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 191 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 191 | h | 223 | 1
SUWP-AS-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 7504 | h | 223 | 1
SUWP-AS-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 7504 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 404 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 404 | h | 223 | 1
SUWP-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 4634 | h | 223 | 1
SUWP-EC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 4634 | h | 223 | 1
SUWP-AS-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3304 | h | 223 | 1
SUWP-AS-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3304 | h | 223 | 1
SUWP-AS-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 100 | h | 223 | 1
SUWP-AS-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 100 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 22 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 22 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 409 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 409 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 145 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 145 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 251608 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 50 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 114551 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 114551 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3093 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3012 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 48863 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 48863 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 3012 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-03 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-03 | 193165 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-09-03 | 51689 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-09-03 | 51689 | h | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-09-10 | 63 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-09-10 | 63 | t | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 98243 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 98243 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 33564 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 17810 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 17810 | h | 223 | 1
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 88671 | h | 223 | 1
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 88671 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 79168 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 47816 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 88671 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 88671 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 8233 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 8233 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 12546 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 24810 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 334815 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 8233 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 8233 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 12546 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 19724 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 19724 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3012 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 12772 | h | 223 | 1
MEM0822-EWPc-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 12772 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1148 | h | 223 | 1
TTU0822-PWPe-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1148 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 31930 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 31930 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 41955 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 51089 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3754 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 51089 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 51089 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 33564 | h | 223 | 1
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 40017 | h | 223 | 1
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 40017 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 257322 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 33564 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3754 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 34044 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 34044 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 38908 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 38908 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 34044 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 34044 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 38908 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 38908 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 34044 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 34044 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 38908 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 38908 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 41576 | h | 223 | 1
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 40017 | h | 223 | 1
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 40017 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 41576 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 74586 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 55940 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 51089 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 51089 | h | 223 | 1
MSD0822-CWP-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 298321 | h | 223 | 1
MSD0822-CWP-096 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 298321 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 51089 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 51089 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 55940 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 23570 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 2857 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3061 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3061 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 13993 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 13993 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 2857 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3061 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3061 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 13993 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 92103 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 92103 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9180 | h | 223 | 1
TTU0823-PWPe-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9180 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 20029 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 19649 | h | 223 | 1
MEM0823-EWPc-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 19649 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 98243 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 98243 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 66314 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 66314 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 49467 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 66314 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 66314 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 23570 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 23570 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9821 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 4286 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 26668 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 26668 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 26668 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 26668 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 26668 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 26668 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 4286 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 19049 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 19049 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 25398 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 4286 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 20029 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3349 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 4286 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 25398 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 26668 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 26668 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9821 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 4286 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 4286 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 4286 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 4286 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 11748 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 26189 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 16546 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 16546 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 13735 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 26477 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 7418 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 48624 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 48624 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 97971 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 97971 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 47 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 47 | h | 223 | 1
SUWP-AS-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 13760 | h | 223 | 1
SUWP-AS-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 13760 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 741 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 741 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 2015 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 2015 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 177 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 177 | h | 223 | 1
SUWP-AS-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 80947 | h | 223 | 1
SUWP-AS-PF-0305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 80947 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 6873 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 6873 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 96 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 96 | h | 223 | 1
SUWP-AS-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 10206 | h | 223 | 1
SUWP-AS-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 10206 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 733 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 733 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 772 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 772 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 947 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 947 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 666 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 666 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 541 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 541 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 315 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 315 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 83 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 83 | h | 223 | 1
SUWP-AS-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 900 | h | 223 | 1
SUWP-AS-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 900 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 664 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 664 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9877 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9877 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 246 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 246 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1767 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1767 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 189 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 189 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 110 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 110 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 284 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 284 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1000 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1000 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1253 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1253 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 5247 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 5247 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1955 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1955 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 9 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 9 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 986 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 986 | h | 223 | 1
SUWP-AS-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1717 | h | 223 | 1
SUWP-AS-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1717 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 73 | h | 223 | 1
SUWP-RP-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 73 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 975 | h | 223 | 1
SUWP-AC-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 975 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 647 | h | 223 | 1
SUWP-RP-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 647 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 305 | h | 223 | 1
SUWP-RP-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 305 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 501 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 501 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1072 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1072 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 331 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 331 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1830 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1830 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1727 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1727 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 853 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 853 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1813 | h | 223 | 1
SUWP-AT-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1813 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 1321 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 1321 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3768 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3768 | h | 223 | 1
SUWP-RP-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 6829 | h | 223 | 1
SUWP-RP-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 6829 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 191 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 191 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 404 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 404 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 22 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 22 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 409 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 409 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 253 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 253 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 251608 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 50 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 114551 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 114551 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3093 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3012 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 18324 | h | 223 | 1
MCD0622-EWPc-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 18324 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 3012 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 5685 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 5685 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 13643 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 13643 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-10 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-10 | 193165 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-09-10 | 51689 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-09-10 | 51689 | h | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-09-17 | 63 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-09-17 | 63 | t | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 98243 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 98243 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 33564 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 17810 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 17810 | h | 223 | 1
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 88671 | h | 223 | 1
MEM0821-EWPc-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 88671 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 79168 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 19724 | h | 223 | 1
MEM0821-PWPe-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 19724 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 47816 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 88671 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 88671 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 55419 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 55419 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3087 | h | 223 | 1
EEE0821-PWPe-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3087 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 12546 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 9821 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 9821 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 66211 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 66211 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 55419 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 55419 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 334815 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 41382 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 41382 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3087 | h | 223 | 1
EEE0821-PWPe-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3087 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 12546 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 55419 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 55419 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 7397 | h | 223 | 1
MEM0821-PWPe-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 7397 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3012 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 51089 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 51089 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 41955 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 51089 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3754 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 51089 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 51089 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 33564 | h | 223 | 1
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 40017 | h | 223 | 1
MEM0822-PWPe-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 40017 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 257322 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 33564 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3754 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 80105 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 80105 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 91548 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 80105 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 80105 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 91548 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 80105 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 80105 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 91548 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 41576 | h | 223 | 1
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 40017 | h | 223 | 1
MEM0822-PWPe-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 40017 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 41576 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 74586 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 55940 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 17219 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 17219 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 31309 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 31309 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 51089 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 51089 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 51089 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 51089 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 55940 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 9821 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 9821 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 23570 | h | 223 | 1
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 6122 | h | 223 | 1
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 6122 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 2857 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3061 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3061 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 13993 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 13993 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 2857 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3061 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3061 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 13993 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 147365 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 20029 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 98243 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 98243 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 66314 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 66314 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 49467 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 66314 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 66314 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 9821 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 9821 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 23570 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 23570 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 9821 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 9821 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 19049 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 19049 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 25398 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 20029 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3349 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 25398 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 9821 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 9821 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26668 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26668 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 11748 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 9821 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 9821 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 23570 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 9821 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 9821 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26189 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 16546 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 16546 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 13735 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 15790 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 15790 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 37897 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 37897 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 26477 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 45 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 45 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 108 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 108 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 7418 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 48624 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 48624 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 97971 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 97971 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 47 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 47 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 741 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 741 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 2015 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 2015 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 177 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 177 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 6873 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 6873 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 96 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 96 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 733 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 733 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 772 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 772 | h | 223 | 1
SUWP-AS-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3804 | h | 223 | 1
SUWP-AS-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3804 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 406 | h | 223 | 1
SUWP-AC-PF-1204 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 406 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 666 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 666 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 541 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 541 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 315 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 315 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 83 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 83 | h | 223 | 1
SUWP-AS-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 900 | h | 223 | 1
SUWP-AS-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 900 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 664 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 664 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 8466 | h | 223 | 1
SUWP-AC-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 8466 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 344 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 344 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 1767 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 1767 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 189 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 189 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 110 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 110 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 284 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 284 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 1000 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 1000 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 1253 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 1253 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 5247 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 5247 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 1955 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 1955 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 9 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 9 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 986 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 986 | h | 223 | 1
SUWP-AS-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 491 | h | 223 | 1
SUWP-AS-PE-0501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 491 | h | 223 | 1
SUWP-AT-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 905 | h | 223 | 1
SUWP-AT-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 905 | h | 223 | 1
SUWP-AT-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 4466 | h | 223 | 1
SUWP-AT-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 4466 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 143 | h | 223 | 1
SUWP-AC-PF-1123 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 143 | h | 223 | 1
SUWP-AS-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 19912 | h | 223 | 1
SUWP-AS-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 19912 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 1072 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 1072 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 331 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 331 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 1830 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 1830 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 1727 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 1727 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 487 | h | 223 | 1
SUWP-AC-PF-1114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 487 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3083 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3083 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3768 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3768 | h | 223 | 1
SUWP-RP-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 6829 | h | 223 | 1
SUWP-RP-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 6829 | h | 223 | 1
SUWP-AT-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 2106 | h | 223 | 1
SUWP-AT-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 2106 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 27 | h | 223 | 1
SUWP-RP-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 27 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 404 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 404 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 22 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 22 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 409 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 409 | h | 223 | 1
SUWP-AT-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 11067 | h | 223 | 1
SUWP-AT-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 11067 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 253 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 253 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 251608 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 50 | h | 223 | 1
A303030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 63248 | h | 223 | 1
A303030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 63248 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 114551 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 114551 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3093 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3012 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 3012 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 15790 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 15790 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 15790 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 15790 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 25265 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 37897 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 37897 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 37897 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 37897 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 60635 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-17 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-17 | 193165 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-09-17 | 51689 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-09-17 | 51689 | h | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-09-24 | 63 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-09-24 | 63 | t | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 98243 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 98243 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 33564 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 17810 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 17810 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 79168 | h | 223 | 1
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 88671 | h | 223 | 1
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 88671 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 47816 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 86454 | h | 223 | 1
TTU0821-EWPc-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 86454 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 2217 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 2217 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 88671 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 88671 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 12546 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9575 | h | 223 | 1
JPA0821-PWPe-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9575 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 80256 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9836 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9836 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 23845 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 23845 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 88671 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 88671 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 334815 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 50160 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 50160 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 12546 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 88671 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 47816 | h | 223 | 1
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1254 | h | 223 | 1
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1254 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9836 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9836 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 23845 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 23845 | h | 223 | 1
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 11032 | h | 223 | 1
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 11032 | h | 223 | 1
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1254 | h | 223 | 1
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1254 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 16048 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3041 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 51089 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 51089 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 41955 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 108 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 108 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 260 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 260 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 51089 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3754 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 51089 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 51089 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 33564 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 257322 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 33564 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3754 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 80105 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 80105 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 91548 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 80105 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 80105 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 91548 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 80105 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 80105 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 91548 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1277 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1277 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 41576 | h | 223 | 1
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 51089 | h | 223 | 1
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 51089 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 41576 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 74586 | h | 223 | 1
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 51089 | h | 223 | 1
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 51089 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 55940 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 20872 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 20872 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 37950 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 51089 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 51089 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 51089 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 51089 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 55940 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9575 | h | 223 | 1
JPA0822-PWPe-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9575 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 23570 | h | 223 | 1
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 6122 | h | 223 | 1
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 6122 | h | 223 | 1
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 43108 | h | 223 | 1
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 43108 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 62703 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 2857 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3061 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3061 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 13993 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 13993 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 2857 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3061 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3061 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 13993 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 380 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 147365 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 147365 | h | 223 | 1
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 10034 | h | 223 | 1
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 10034 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 20029 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 98243 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 98243 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9836 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9836 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 23845 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 23845 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 64656 | h | 223 | 1
MEM0824-EWPc-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 64656 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 49467 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 64656 | h | 223 | 1
MEM0824-EWPc-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 64656 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 43263 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9575 | h | 223 | 1
JPA0824-PWPe-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9575 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 23570 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 2210 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 2210 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1326 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1326 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 4169 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 4169 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 547 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 547 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9575 | h | 223 | 1
JPA0826-PWPe-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9575 | h | 223 | 1
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1254 | h | 223 | 1
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1254 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 19049 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 19049 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 25398 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 23845 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 23845 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 20029 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3040 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3349 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 994 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 994 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 25398 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9575 | h | 223 | 1
JPA0827-PWPe-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9575 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9836 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9836 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26668 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26668 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 11748 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 931 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 931 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9575 | h | 223 | 1
JPA1062-PWPe-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9575 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 23570 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 465 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 465 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 9575 | h | 223 | 1
JPA1062-PWPe-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 9575 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26189 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 16546 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 16546 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 13735 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 25265 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 25265 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 60635 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 26477 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 198 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 198 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 479 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 7418 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 48624 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 48624 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 97971 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 97971 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 47 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 47 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 741 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 741 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 576 | h | 223 | 1
SUWP-AC-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 576 | h | 223 | 1
SUWP-AS-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 17965 | h | 223 | 1
SUWP-AS-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 17965 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 177 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 177 | h | 223 | 1
SUWP-AT-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3732 | h | 223 | 1
SUWP-AT-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3732 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1964 | h | 223 | 1
SUWP-AC-PF-0201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1964 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 96 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 96 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 733 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 733 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 772 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 772 | h | 223 | 1
SUWP-AS-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3804 | h | 223 | 1
SUWP-AS-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3804 | h | 223 | 1
SUWP-AS-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 6184 | h | 223 | 1
SUWP-AS-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 6184 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 666 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 666 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 541 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 541 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 315 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 315 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 12 | h | 223 | 1
SUWP-RP-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 12 | h | 223 | 1
SUWP-AT-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 149 | h | 223 | 1
SUWP-AT-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 149 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 664 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 664 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 14752 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 344 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 344 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 252 | h | 223 | 1
SUWP-RP-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 252 | h | 223 | 1
SUWP-AT-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3139 | h | 223 | 1
SUWP-AT-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3139 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 27 | h | 223 | 1
SUWP-RP-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 27 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 16 | h | 223 | 1
SUWP-RP-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 16 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 81 | h | 223 | 1
SUWP-AC-PF-1209 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 81 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1000 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1000 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1253 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1253 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 5247 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 5247 | h | 223 | 1
SUWP-AS-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 18320 | h | 223 | 1
SUWP-AS-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 18320 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 559 | h | 223 | 1
SUWP-AC-PF-1210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 559 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 35 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 35 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 5 | h | 223 | 1
SUWP-AC-PF-0805 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 5 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 986 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 986 | h | 223 | 1
SUWP-AT-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1056 | h | 223 | 1
SUWP-AT-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1056 | h | 223 | 1
SUWP-AT-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 6252 | h | 223 | 1
SUWP-AT-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 6252 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1072 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1072 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 189 | h | 223 | 1
SUWP-AC-PF-1208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 189 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1830 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1830 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1727 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1727 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3083 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3083 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3768 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3768 | h | 223 | 1
SUWP-RP-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 4878 | h | 223 | 1
SUWP-RP-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 4878 | h | 223 | 1
SUWP-AT-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 2948 | h | 223 | 1
SUWP-AT-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 2948 | h | 223 | 1
SUWP-AT-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 225 | h | 223 | 1
SUWP-AT-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 225 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 115 | h | 223 | 1
SUWP-AC-PF-1124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 115 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 22 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 22 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 409 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 409 | h | 223 | 1
SUWP-AT-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 12912 | h | 223 | 1
SUWP-AT-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 12912 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 253 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 253 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 32559 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 32559 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 2242763 | h | 223 | 1
B40623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 49320 | h | 223 | 1
B40623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 49320 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 50 | h | 223 | 1
A303030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 79060 | h | 223 | 1
A303030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 79060 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 114551 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 114551 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3093 | h | 223 | 1
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 1254 | h | 223 | 1
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 1254 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3041 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3012 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 3012 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 25265 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 25265 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 60635 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-09-24 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-09-24 | 193165 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-09-24 | 51689 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-09-24 | 51689 | h | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-10-01 | 11 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-10-01 | 11 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Budgeted Units | 2023-10-01 | 16 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | At Completion Units | 2023-10-01 | 16 | m | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-01 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-01 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-01 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-01 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-01 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-01 | 0 | un | 223 | 1
TTU0822-CWP-205 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2023-10-01 | 67 | t | 223 | 1
TTU0822-CWP-205 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2023-10-01 | 67 | t | 223 | 1
MSD0827-CWP-492 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 1 | t | 223 | 1
MSD0827-CWP-492 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 1 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 1 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 1 | t | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 260 | Meter | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 260 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 3363 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 3363 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 13 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 13 | Meter | 223 | 1
ESD1062-CWP-486 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 333 | Meter | 223 | 1
ESD1062-CWP-486 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 333 | Meter | 223 | 1
ESD1214-CWP-487 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 28 | Meter | 223 | 1
ESD1214-CWP-487 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 28 | Meter | 223 | 1
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 848 | Meter | 223 | 1
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 848 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-01 | 63 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-01 | 63 | Meter | 223 | 1
JSD0822-CWP-494 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2023-10-01 | 23 | unid | 223 | 1
JSD0822-CWP-494 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2023-10-01 | 23 | unid | 223 | 1
ESD1042-CWP-511 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2023-10-01 | 5 | unid | 223 | 1
ESD1042-CWP-511 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2023-10-01 | 5 | unid | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-01 | 1 | t | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-01 | 1 | t | 223 | 1
MSD0622-CWP-005 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-01 | 11 | t | 223 | 1
MSD0622-CWP-005 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-01 | 11 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-01 | 63 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-01 | 63 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-01 | 5 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-01 | 5 | t | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 27741 | h | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 27741 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26715 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26715 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 98243 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 98243 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24858 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24858 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24858 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24858 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24858 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24858 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24858 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24858 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24858 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24858 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23710 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23710 | h | 223 | 1
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 40073 | h | 223 | 1
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 40073 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 165 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 165 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 33564 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3562 | h | 223 | 1
MEM0820-EWPc-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3562 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 79168 | h | 223 | 1
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 88671 | h | 223 | 1
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 88671 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 47816 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 88671 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 88671 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 88671 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 88671 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 12546 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 80256 | h | 223 | 1
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 88671 | h | 223 | 1
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 88671 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23143 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23143 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 56105 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 88671 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 88671 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2398 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2398 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3146 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3146 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1154 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1154 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 4278 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 4278 | h | 223 | 1
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 88671 | h | 223 | 1
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 88671 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 334815 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 50160 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 50160 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 12546 | h | 223 | 1
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 88671 | h | 223 | 1
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 88671 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 88671 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 47816 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 34059 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 34059 | h | 223 | 1
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1254 | h | 223 | 1
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1254 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23143 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23143 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 56105 | h | 223 | 1
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 11032 | h | 223 | 1
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 11032 | h | 223 | 1
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1254 | h | 223 | 1
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1254 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 16048 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3041 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23279 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 20029 | h | 223 | 1
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 41955 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 478 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 478 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1158 | h | 223 | 1
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 8941 | h | 223 | 1
EEE1042-EWPc-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 8941 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3754 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 8941 | h | 223 | 1
EEE1042-EWPc-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 8941 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 33564 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 257322 | h | 223 | 1
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 33564 | h | 223 | 1
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3754 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 80105 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 80105 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 91548 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 80105 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 80105 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 91548 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 80105 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 80105 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 91548 | h | 223 | 1
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 10491 | h | 223 | 1
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 10491 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23980 | h | 223 | 1
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 41576 | h | 223 | 1
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 41576 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 74586 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 74586 | h | 223 | 1
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 4454 | h | 223 | 1
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 4454 | h | 223 | 1
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 6479 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2969 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2969 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 6479 | h | 223 | 1
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 55940 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 20872 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 20872 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 37950 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 8941 | h | 223 | 1
MEM0822-EWPc-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 8941 | h | 223 | 1
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 10491 | h | 223 | 1
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 10491 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23980 | h | 223 | 1
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 10491 | h | 223 | 1
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 10491 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23980 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 8941 | h | 223 | 1
EEE1042-EWPc-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 8941 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 55940 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 94102 | h | 223 | 1
JSD0822-CWP-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 104756 | h | 223 | 1
JSD0822-CWP-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 104756 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23570 | h | 223 | 1
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 6122 | h | 223 | 1
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 6122 | h | 223 | 1
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 51089 | h | 223 | 1
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 51089 | h | 223 | 1
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 43108 | h | 223 | 1
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 43108 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 62703 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2857 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 612 | h | 223 | 1
MEM0822-EWPc-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 612 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 11131 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 13993 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 13993 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 11131 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 13993 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 13993 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2857 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 612 | h | 223 | 1
MEM0822-EWPc-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 612 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 11131 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 13993 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 13993 | h | 223 | 1
MEM0822-CWP-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2020 | h | 223 | 1
MEM0822-CWP-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2020 | h | 223 | 1
MEM0822-CWP-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2020 | h | 223 | 1
MEM0822-CWP-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2020 | h | 223 | 1
MEM0822-CWP-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2020 | h | 223 | 1
MEM0822-CWP-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2020 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 263310 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 263310 | h | 223 | 1
MEM0822-CWP-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 8890 | h | 223 | 1
MEM0822-CWP-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 8890 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 380 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 147365 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 147365 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 368008 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 368008 | h | 223 | 1
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 10034 | h | 223 | 1
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 10034 | h | 223 | 1
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 147365 | h | 223 | 1
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 147365 | h | 223 | 1
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 147365 | h | 223 | 1
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 20029 | h | 223 | 1
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 147365 | h | 223 | 1
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 147365 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 98243 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 98243 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23143 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23143 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 56105 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23570 | h | 223 | 1
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 132628 | h | 223 | 1
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 132628 | h | 223 | 1
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 132628 | h | 223 | 1
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 132628 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1520 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1520 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3684 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3684 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 88419 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23279 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 5895 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 166755 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 166755 | h | 223 | 1
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 166755 | h | 223 | 1
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 166755 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2432 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2432 | h | 223 | 1
MSD0827-CWP-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 14131 | h | 223 | 1
MSD0827-CWP-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 14131 | h | 223 | 1
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1254 | h | 223 | 1
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1254 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26668 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 18572 | h | 223 | 1
MEM0827-PWPl-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 18572 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 18572 | h | 223 | 1
MEM0827-PWPl-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 18572 | h | 223 | 1
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 39772 | h | 223 | 1
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 39772 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 18572 | h | 223 | 1
MRF0827-PWPl-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 18572 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26668 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 19049 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 19049 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24858 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24858 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 16572 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 16572 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 25398 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24858 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24858 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1520 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1520 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26668 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 20029 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24858 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24858 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 43729 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 43729 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 16572 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 16572 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 39772 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26668 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 25398 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 18572 | h | 223 | 1
JIL0827-PWPl-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 18572 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3684 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3684 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23143 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23143 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 564 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 16457 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 16457 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26668 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24858 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24858 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26668 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26668 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2746 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3432 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3432 | h | 223 | 1
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 39772 | h | 223 | 1
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 39772 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 20200 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 20200 | h | 223 | 1
ESD1042-CWP-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 387232 | h | 223 | 1
ESD1042-CWP-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 387232 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 11748 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 37229 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 37229 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 23570 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 18614 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 18614 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26189 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1358 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1358 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 16546 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 16546 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 13735 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1666 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1666 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2665 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2665 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 25265 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 25265 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 60635 | h | 223 | 1
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 72937 | h | 223 | 1
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 72937 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 26477 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1617 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 198 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 198 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 479 | h | 223 | 1
ESD1214-CWP-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2908 | h | 223 | 1
ESD1214-CWP-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2908 | h | 223 | 1
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 90476 | h | 223 | 1
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 90476 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 7418 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 48624 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 48624 | h | 223 | 1
TTU1340-EWPc-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 208391 | h | 223 | 1
TTU1340-EWPc-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 208391 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 19594 | h | 223 | 1
EWPp-DD-PF-1206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 19594 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 47 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 47 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 212 | h | 223 | 1
SUWP-AC-PF-1128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 212 | h | 223 | 1
SUWP-AS-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 4491 | h | 223 | 1
SUWP-AS-PF-0207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 4491 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 177 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 177 | h | 223 | 1
SUWP-AT-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3732 | h | 223 | 1
SUWP-AT-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3732 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 96 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 96 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 105 | h | 223 | 1
SUWP-AC-PF-1122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 105 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 772 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 772 | h | 223 | 1
SUWP-AS-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 6184 | h | 223 | 1
SUWP-AS-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 6184 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 666 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 666 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 541 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 541 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 315 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 315 | h | 223 | 1
SUWP-AT-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 348 | h | 223 | 1
SUWP-AT-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 348 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 95 | h | 223 | 1
SUWP-RP-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 95 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 14752 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 344 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 344 | h | 223 | 1
SUWP-AT-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 7324 | h | 223 | 1
SUWP-AT-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 7324 | h | 223 | 1
SUWP-AT-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 780 | h | 223 | 1
SUWP-AT-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 780 | h | 223 | 1
SUWP-AT-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 130 | h | 223 | 1
SUWP-AT-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 130 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 286 | h | 223 | 1
SUWP-RP-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 286 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1142 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1142 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1253 | h | 223 | 1
SUWP-AS-PE-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1253 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 5247 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 5247 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 49 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 49 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 986 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 986 | h | 223 | 1
SUWP-AT-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 151 | h | 223 | 1
SUWP-AT-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 151 | h | 223 | 1
SUWP-AT-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1786 | h | 223 | 1
SUWP-AT-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1786 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1072 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1072 | h | 223 | 1
SUWP-AS-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 33984 | h | 223 | 1
SUWP-AS-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 33984 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1830 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1830 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1727 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1727 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3083 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3083 | h | 223 | 1
SUWP-AS-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 69960 | h | 223 | 1
SUWP-AS-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 69960 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3768 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3768 | h | 223 | 1
SUWP-AT-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 842 | h | 223 | 1
SUWP-AT-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 842 | h | 223 | 1
SUWP-AT-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 788 | h | 223 | 1
SUWP-AT-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 788 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 12 | h | 223 | 1
SUWP-AC-PF-1211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 12 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 409 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 409 | h | 223 | 1
SUWP-AT-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1845 | h | 223 | 1
SUWP-AT-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1845 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 253 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 253 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 52095 | h | 223 | 1
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 40000 | h | 223 | 1
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 40000 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 2242763 | h | 223 | 1
B40623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 197280 | h | 223 | 1
B40623 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 197280 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 50 | h | 223 | 1
A303030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 32612 | h | 223 | 1
A303030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 32612 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 114551 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 114551 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3093 | h | 223 | 1
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 1254 | h | 223 | 1
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 1254 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3041 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 6750 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 6750 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3012 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 3012 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 73716 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 73716 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 25265 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 25265 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 60635 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 193165 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 20905 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-01 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-01 | 20905 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 1144 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 1144 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 978 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 978 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 7 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 7 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 102 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 102 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 130 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 130 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 48 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 48 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 218 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 218 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 960 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 51689 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 51689 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 14795 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 14795 | h | 223 | 1
JSD0822-CWP-494 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 4320 | h | 223 | 1
JSD0822-CWP-494 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 4320 | h | 223 | 1
MEM0822-CWP-194 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 83 | h | 223 | 1
MEM0822-CWP-194 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 83 | h | 223 | 1
MEM0822-CWP-195 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 83 | h | 223 | 1
MEM0822-CWP-195 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 83 | h | 223 | 1
MEM0822-CWP-196 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 83 | h | 223 | 1
MEM0822-CWP-196 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 83 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 10859 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 10859 | h | 223 | 1
MEM0822-CWP-221 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 367 | h | 223 | 1
MEM0822-CWP-221 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 367 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 4031 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 4031 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 982 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 982 | h | 223 | 1
MSD0827-CWP-492 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 583 | h | 223 | 1
MSD0827-CWP-492 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 583 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 73 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 73 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 679 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 679 | h | 223 | 1
ESD1042-CWP-511 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 1138 | h | 223 | 1
ESD1042-CWP-511 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 1138 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 56 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 56 | h | 223 | 1
ESD1062-CWP-486 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 4400 | h | 223 | 1
ESD1062-CWP-486 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 4400 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 67 | h | 223 | 1
ESD1214-CWP-487 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 120 | h | 223 | 1
ESD1214-CWP-487 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 120 | h | 223 | 1
ESD1214-CWP-489 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 13432 | h | 223 | 1
ESD1214-CWP-489 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 13432 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 278 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 278 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 3040 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 3040 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 872 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-01 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-01 | 872 | h | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-10-08 | 14 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-10-08 | 14 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Budgeted Units | 2023-10-08 | 20 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | At Completion Units | 2023-10-08 | 20 | m | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-08 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-08 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-08 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-08 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-08 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-08 | 0 | un | 223 | 1
TTU0822-CWP-205 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2023-10-08 | 53 | t | 223 | 1
TTU0822-CWP-205 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2023-10-08 | 53 | t | 223 | 1
MSD0827-CWP-492 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 0 | t | 223 | 1
MSD0827-CWP-492 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 0 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 1 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 1 | t | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 260 | Meter | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 260 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 3363 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 3363 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 13 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 13 | Meter | 223 | 1
ESD1062-CWP-486 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 333 | Meter | 223 | 1
ESD1062-CWP-486 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 333 | Meter | 223 | 1
ESD1214-CWP-487 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 28 | Meter | 223 | 1
ESD1214-CWP-487 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 28 | Meter | 223 | 1
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 848 | Meter | 223 | 1
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 848 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-08 | 63 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-08 | 63 | Meter | 223 | 1
JSD0822-CWP-494 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2023-10-08 | 23 | unid | 223 | 1
JSD0822-CWP-494 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2023-10-08 | 23 | unid | 223 | 1
ESD1042-CWP-511 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2023-10-08 | 1 | unid | 223 | 1
ESD1042-CWP-511 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2023-10-08 | 1 | unid | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-08 | 1 | t | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-08 | 1 | t | 223 | 1
MSD0622-CWP-005 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-08 | 14 | t | 223 | 1
MSD0622-CWP-005 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-08 | 14 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-08 | 63 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-08 | 63 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-08 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-08 | 6 | t | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 27741 | h | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 27741 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26715 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26715 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 98243 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 98243 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23710 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23710 | h | 223 | 1
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 40073 | h | 223 | 1
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 40073 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 6583 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 6583 | h | 223 | 1
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 40073 | h | 223 | 1
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 33564 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 79168 | h | 223 | 1
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 88671 | h | 223 | 1
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 88671 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 47816 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 88671 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 88671 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 88671 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 88671 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 12546 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 334815 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 80256 | h | 223 | 1
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 88671 | h | 223 | 1
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 88671 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23143 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23143 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 56105 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 88671 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 88671 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2998 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2998 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3932 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3932 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1442 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1442 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5348 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5348 | h | 223 | 1
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 88671 | h | 223 | 1
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 88671 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 334815 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 50160 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 50160 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 12546 | h | 223 | 1
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 88671 | h | 223 | 1
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 88671 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 88671 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 47816 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 34059 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 34059 | h | 223 | 1
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1254 | h | 223 | 1
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1254 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23143 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23143 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 56105 | h | 223 | 1
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 11032 | h | 223 | 1
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 11032 | h | 223 | 1
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1254 | h | 223 | 1
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1254 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 16048 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3041 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 19158 | h | 223 | 1
TTU0822-EWPc-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 19158 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23279 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 20029 | h | 223 | 1
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 41955 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 478 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 478 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1158 | h | 223 | 1
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 33564 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 257322 | h | 223 | 1
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 33564 | h | 223 | 1
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 12878 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 12878 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3754 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 46060 | h | 223 | 1
ERE0822-PWPe-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 46060 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 91548 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 12878 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 12878 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 46060 | h | 223 | 1
ERE0822-PWPe-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 46060 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 91548 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 12878 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 12878 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 46060 | h | 223 | 1
ERE0822-PWPe-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 46060 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 91548 | h | 223 | 1
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 10491 | h | 223 | 1
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 10491 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23980 | h | 223 | 1
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 41576 | h | 223 | 1
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 41576 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 28669 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 28669 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 13053 | h | 223 | 1
SES0822-PWPp-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 13053 | h | 223 | 1
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4454 | h | 223 | 1
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4454 | h | 223 | 1
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 6479 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2969 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2969 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 6479 | h | 223 | 1
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 55940 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 20872 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 20872 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 37950 | h | 223 | 1
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 10491 | h | 223 | 1
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 10491 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23980 | h | 223 | 1
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 10491 | h | 223 | 1
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 10491 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 55940 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 94102 | h | 223 | 1
JSD0822-CWP-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 104756 | h | 223 | 1
JSD0822-CWP-494 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 104756 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23570 | h | 223 | 1
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 6122 | h | 223 | 1
JIL0822-PWPe-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 6122 | h | 223 | 1
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 51089 | h | 223 | 1
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 51089 | h | 223 | 1
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 43108 | h | 223 | 1
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 43108 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 62703 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2857 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1684 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1684 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5247 | h | 223 | 1
MEM0822-PWPp-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5247 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1684 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1684 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5247 | h | 223 | 1
MEM0822-PWPp-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5247 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2857 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1684 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1684 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5247 | h | 223 | 1
MEM0822-PWPp-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5247 | h | 223 | 1
MEM0822-CWP-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2020 | h | 223 | 1
MEM0822-CWP-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2020 | h | 223 | 1
MEM0822-CWP-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2020 | h | 223 | 1
MEM0822-CWP-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2020 | h | 223 | 1
MEM0822-CWP-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2020 | h | 223 | 1
MEM0822-CWP-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2020 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 263310 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 263310 | h | 223 | 1
MEM0822-CWP-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 8890 | h | 223 | 1
MEM0822-CWP-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 8890 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 380 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 55262 | h | 223 | 1
TTU0823-EWPc-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 55262 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 460009 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 460009 | h | 223 | 1
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 8169 | h | 223 | 1
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 8169 | h | 223 | 1
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 10034 | h | 223 | 1
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 10034 | h | 223 | 1
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 147365 | h | 223 | 1
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 147365 | h | 223 | 1
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 147365 | h | 223 | 1
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 20029 | h | 223 | 1
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 147365 | h | 223 | 1
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 147365 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 98243 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 98243 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23143 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23143 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 56105 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23570 | h | 223 | 1
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 132628 | h | 223 | 1
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 132628 | h | 223 | 1
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 132628 | h | 223 | 1
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 132628 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2432 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2432 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5895 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 88419 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23279 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5895 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 166755 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 166755 | h | 223 | 1
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 166755 | h | 223 | 1
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 166755 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2432 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2432 | h | 223 | 1
MSD0827-CWP-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5653 | h | 223 | 1
MSD0827-CWP-492 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5653 | h | 223 | 1
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 8169 | h | 223 | 1
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 8169 | h | 223 | 1
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1254 | h | 223 | 1
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1254 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26668 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26668 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26668 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 19049 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 19049 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26515 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26515 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 25398 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2432 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2432 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26668 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 69966 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 69966 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26515 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26515 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26668 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 25398 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5895 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23143 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23143 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 564 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 16457 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 16457 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26668 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26668 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26668 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4393 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5492 | h | 223 | 1
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 16164 | h | 223 | 1
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 16164 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39184 | h | 223 | 1
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 39772 | h | 223 | 1
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 39772 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 20200 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 20200 | h | 223 | 1
ESD1042-CWP-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 96808 | h | 223 | 1
ESD1042-CWP-511 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 96808 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 11748 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 37229 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 37229 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 23570 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 18614 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 18614 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26189 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1358 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1358 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 16546 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 16546 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 13735 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3920 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3920 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 6271 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 25265 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 25265 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 60635 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 24819 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 24819 | h | 223 | 1
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 72937 | h | 223 | 1
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 72937 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 26477 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1617 | h | 223 | 1
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 72937 | h | 223 | 1
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 72937 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 198 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 198 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 479 | h | 223 | 1
ESD1214-CWP-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2908 | h | 223 | 1
ESD1214-CWP-487 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2908 | h | 223 | 1
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 90476 | h | 223 | 1
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 90476 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 7418 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 48624 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 48624 | h | 223 | 1
TTU1340-EWPc-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 83356 | h | 223 | 1
TTU1340-EWPc-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 83356 | h | 223 | 1
EWPp-DD-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 93080 | h | 223 | 1
EWPp-DD-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 93080 | h | 223 | 1
SUWP-AS-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 872 | h | 223 | 1
SUWP-AS-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 872 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 47 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 47 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 76 | h | 223 | 1
SUWP-AC-PF-0303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 76 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 96 | h | 223 | 1
SUWP-AC-PF-0703 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 96 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 772 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 772 | h | 223 | 1
SUWP-AS-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3423 | h | 223 | 1
SUWP-AS-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3423 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 666 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 666 | h | 223 | 1
SUWP-AS-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 10048 | h | 223 | 1
SUWP-AS-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 10048 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 541 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 541 | h | 223 | 1
SUWP-AS-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4386 | h | 223 | 1
SUWP-AS-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4386 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 315 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 315 | h | 223 | 1
SUWP-AT-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 199 | h | 223 | 1
SUWP-AT-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 199 | h | 223 | 1
SUWP-AT-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2748 | h | 223 | 1
SUWP-AT-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2748 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 14752 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 344 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 344 | h | 223 | 1
SUWP-AT-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4185 | h | 223 | 1
SUWP-AT-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4185 | h | 223 | 1
SUWP-AT-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 780 | h | 223 | 1
SUWP-AT-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 780 | h | 223 | 1
SUWP-AT-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 456 | h | 223 | 1
SUWP-AT-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 456 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1999 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1999 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 750 | h | 223 | 1
SUWP-AC-PF-1004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 750 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 49 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 49 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 986 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 986 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 612 | h | 223 | 1
SUWP-AC-PF-1119 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 612 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1830 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1830 | h | 223 | 1
SUWP-AS-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 32088 | h | 223 | 1
SUWP-AS-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 32088 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1727 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1727 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3083 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3083 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3768 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3768 | h | 223 | 1
SUWP-AT-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 563 | h | 223 | 1
SUWP-AT-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 563 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 409 | h | 223 | 1
SUWP-AC-PF-1115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 409 | h | 223 | 1
SUWP-AS-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 4704 | h | 223 | 1
SUWP-AS-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 4704 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 253 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 253 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 52095 | h | 223 | 1
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 40000 | h | 223 | 1
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 40000 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 2242763 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 2242763 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 50 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 114551 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 114551 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3093 | h | 223 | 1
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 1254 | h | 223 | 1
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 1254 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3041 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 6750 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 6750 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3012 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 3012 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 48863 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 48863 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 92145 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 92145 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 25265 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 25265 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 60635 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 193165 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 20905 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-08 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-08 | 20905 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 1144 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 1144 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 978 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 978 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 271 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 271 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 128 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 128 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 162 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 162 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 59 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 59 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 272 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 272 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 960 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 51689 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 51689 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 14795 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 14795 | h | 223 | 1
JSD0822-CWP-494 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 4320 | h | 223 | 1
JSD0822-CWP-494 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 4320 | h | 223 | 1
MEM0822-CWP-194 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 83 | h | 223 | 1
MEM0822-CWP-194 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 83 | h | 223 | 1
MEM0822-CWP-195 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 83 | h | 223 | 1
MEM0822-CWP-195 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 83 | h | 223 | 1
MEM0822-CWP-196 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 83 | h | 223 | 1
MEM0822-CWP-196 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 83 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 10859 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 10859 | h | 223 | 1
MEM0822-CWP-221 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 367 | h | 223 | 1
MEM0822-CWP-221 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 367 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 5039 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 982 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 982 | h | 223 | 1
MSD0827-CWP-492 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 233 | h | 223 | 1
MSD0827-CWP-492 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 233 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 73 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 73 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 679 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 679 | h | 223 | 1
ESD1042-CWP-511 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 14 | h | 223 | 1
ESD1042-CWP-511 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 14 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 56 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 56 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 67 | h | 223 | 1
ESD1214-CWP-487 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 120 | h | 223 | 1
ESD1214-CWP-487 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 120 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 278 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 278 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 3800 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 3800 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 872 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-08 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-08 | 872 | h | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-10-15 | 14 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-10-15 | 14 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Budgeted Units | 2023-10-15 | 20 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | At Completion Units | 2023-10-15 | 20 | m | 223 | 1
JIL0822-CWP-199 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-10-15 | 154 | un | 223 | 1
JIL0822-CWP-199 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-10-15 | 154 | un | 223 | 1
JIL0822-CWP-224 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-10-15 | 45 | un | 223 | 1
JIL0822-CWP-224 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-10-15 | 45 | un | 223 | 1
MEM0822-CWP-220 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-10-15 | 7 | t | 223 | 1
MEM0822-CWP-220 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-10-15 | 7 | t | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-15 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-15 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-15 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-15 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-15 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-15 | 0 | un | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-15 | 1 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-15 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-15 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-15 | 1 | t | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-15 | 260 | Meter | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-15 | 260 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-15 | 3363 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-15 | 3363 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-15 | 13 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-15 | 13 | Meter | 223 | 1
ESD1062-CWP-486 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-15 | 333 | Meter | 223 | 1
ESD1062-CWP-486 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-15 | 333 | Meter | 223 | 1
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-15 | 848 | Meter | 223 | 1
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-15 | 848 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-15 | 63 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-15 | 63 | Meter | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-15 | 1 | t | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-15 | 1 | t | 223 | 1
MSD0622-CWP-005 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-15 | 3 | t | 223 | 1
MSD0622-CWP-005 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-15 | 3 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-15 | 63 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-15 | 63 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-15 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-15 | 6 | t | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 27741 | h | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 27741 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 26715 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 26715 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 76139 | h | 223 | 1
TTU0813-EWPc-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 76139 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23710 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23710 | h | 223 | 1
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 40073 | h | 223 | 1
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 40073 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 6583 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 6583 | h | 223 | 1
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 40073 | h | 223 | 1
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 33564 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 79168 | h | 223 | 1
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 88671 | h | 223 | 1
MEM0821-EWPc-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 88671 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 47816 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 88671 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 88671 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 33251 | h | 223 | 1
EEE0821-EWPc-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 33251 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 12546 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4925 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4925 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 45 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 45 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 334815 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 10946 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 10946 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 66 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 66 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 80256 | h | 223 | 1
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 88671 | h | 223 | 1
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 88671 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23143 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23143 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 56105 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 33251 | h | 223 | 1
EEE0821-EWPc-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 33251 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2998 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2998 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3932 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3932 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1442 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1442 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5348 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5348 | h | 223 | 1
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 88671 | h | 223 | 1
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 88671 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 334815 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 73153 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 73153 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 8778 | h | 223 | 1
MEM0822-PWPe-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 8778 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 12546 | h | 223 | 1
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 88671 | h | 223 | 1
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 88671 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 33251 | h | 223 | 1
MEM0821-EWPc-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 33251 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 47816 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 34059 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 34059 | h | 223 | 1
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1254 | h | 223 | 1
MCD0822-PWPe-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1254 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23143 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23143 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 56105 | h | 223 | 1
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 11032 | h | 223 | 1
MEM0822-PWPe-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 11032 | h | 223 | 1
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1254 | h | 223 | 1
TTU0822-PWPe-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1254 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 16048 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3041 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23279 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 20029 | h | 223 | 1
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 41955 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 478 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 478 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1158 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4925 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4925 | h | 223 | 1
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 11941 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 11941 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 257322 | h | 223 | 1
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 33564 | h | 223 | 1
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 30300 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 30300 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 91548 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 30300 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 30300 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 91548 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 30300 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 30300 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 91548 | h | 223 | 1
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 10491 | h | 223 | 1
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 10491 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23980 | h | 223 | 1
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4925 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4925 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 10946 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 10946 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 41576 | h | 223 | 1
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
MEM0822-EWPc-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 41576 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39158 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39158 | h | 223 | 1
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4454 | h | 223 | 1
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4454 | h | 223 | 1
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 6479 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2969 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2969 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 6479 | h | 223 | 1
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
MEM0822-EWPc-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 55940 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 42148 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 42148 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3653 | h | 223 | 1
SES0822-PWPe-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3653 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 37950 | h | 223 | 1
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 10491 | h | 223 | 1
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 10491 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23980 | h | 223 | 1
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 10491 | h | 223 | 1
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 10491 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 55940 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23570 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3061 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3061 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 21767 | h | 223 | 1
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 51089 | h | 223 | 1
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 51089 | h | 223 | 1
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 43108 | h | 223 | 1
MEM0822-PWPe-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 43108 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 62703 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2857 | h | 223 | 1
MEM0822-CWP-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 808 | h | 223 | 1
MEM0822-CWP-194 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 808 | h | 223 | 1
MEM0822-CWP-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 808 | h | 223 | 1
MEM0822-CWP-195 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 808 | h | 223 | 1
MEM0822-CWP-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 808 | h | 223 | 1
MEM0822-CWP-196 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 808 | h | 223 | 1
JIL0822-CWP-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 715826 | h | 223 | 1
JIL0822-CWP-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 715826 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 263310 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 263310 | h | 223 | 1
MEM0822-CWP-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 103688 | h | 223 | 1
MEM0822-CWP-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 103688 | h | 223 | 1
MEM0822-CWP-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3556 | h | 223 | 1
MEM0822-CWP-221 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3556 | h | 223 | 1
MEM0822-CWP-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5334 | h | 223 | 1
MEM0822-CWP-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5334 | h | 223 | 1
JIL0822-CWP-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 209510 | h | 223 | 1
JIL0822-CWP-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 209510 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 66 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 66 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 380 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 460009 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 460009 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 45 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 45 | h | 223 | 1
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 8169 | h | 223 | 1
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 8169 | h | 223 | 1
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 10034 | h | 223 | 1
TTU0823-PWPe-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 10034 | h | 223 | 1
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 147365 | h | 223 | 1
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 147365 | h | 223 | 1
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 147365 | h | 223 | 1
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 20029 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 45 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 45 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 66 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 66 | h | 223 | 1
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 147365 | h | 223 | 1
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 147365 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 76139 | h | 223 | 1
TTU0823-EWPc-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 76139 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23143 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23143 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 56105 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23570 | h | 223 | 1
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 132628 | h | 223 | 1
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 132628 | h | 223 | 1
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 132628 | h | 223 | 1
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 132628 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2432 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2432 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5895 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 88419 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23279 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5895 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 166755 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 166755 | h | 223 | 1
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 166755 | h | 223 | 1
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 166755 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2432 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2432 | h | 223 | 1
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 8169 | h | 223 | 1
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 8169 | h | 223 | 1
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1254 | h | 223 | 1
TTU0827-PWPe-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1254 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3333 | h | 223 | 1
SES0827-PWPl-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPl-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3333 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3333 | h | 223 | 1
MRF0827-PWPl-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 7143 | h | 223 | 1
MEM0827-PWPl-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 7143 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 26515 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 26515 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 25398 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPl-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2432 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2432 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPl-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3333 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 69966 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 69966 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 26515 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 26515 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3333 | h | 223 | 1
EEE0827-PWPl-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 25398 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5895 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23143 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23143 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 564 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 16457 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 16457 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPl-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPl-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3333 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3333 | h | 223 | 1
JIL0827-PWPl-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3333 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4393 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5492 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 45 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 45 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 66 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 66 | h | 223 | 1
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 16164 | h | 223 | 1
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 16164 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39184 | h | 223 | 1
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 39772 | h | 223 | 1
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 39772 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 20200 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 20200 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 11748 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 37229 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 37229 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 23570 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 18614 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 18614 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 26189 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1358 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1358 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 16546 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 16546 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 13735 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3920 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3920 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 6271 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 25265 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 25265 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 60635 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 24819 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 24819 | h | 223 | 1
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 72937 | h | 223 | 1
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 72937 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 26477 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1617 | h | 223 | 1
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 72937 | h | 223 | 1
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 72937 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 16411 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 16411 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 153 | h | 223 | 1
JIL1214-PWPe-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 153 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 479 | h | 223 | 1
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 90476 | h | 223 | 1
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 90476 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 7418 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 37684 | h | 223 | 1
TTU1215-EWPc-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 37684 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 47 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 47 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 772 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 772 | h | 223 | 1
SUWP-AS-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 4792 | h | 223 | 1
SUWP-AS-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 4792 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 26422 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 26422 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 666 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 666 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 541 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 541 | h | 223 | 1
SUWP-AS-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1462 | h | 223 | 1
SUWP-AS-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1462 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 315 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 315 | h | 223 | 1
SUWP-AT-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 2748 | h | 223 | 1
SUWP-AT-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 2748 | h | 223 | 1
SUWP-AS-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 6376 | h | 223 | 1
SUWP-AS-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 6376 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 14752 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 344 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 344 | h | 223 | 1
SUWP-AT-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 326 | h | 223 | 1
SUWP-AT-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 326 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1999 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1999 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 49 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 49 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 282 | h | 223 | 1
SUWP-AC-PF-1121 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 282 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1830 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1830 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1727 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1727 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3083 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3083 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3768 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3768 | h | 223 | 1
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 352 | h | 223 | 1
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 352 | h | 223 | 1
SUWP-AT-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 18540 | h | 223 | 1
SUWP-AT-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 18540 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 253 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 253 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 52095 | h | 223 | 1
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 40000 | h | 223 | 1
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 40000 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1794210 | h | 223 | 1
SUWP-MO-PF0402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1794210 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 50 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 50 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 114551 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 114551 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3093 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 45 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 45 | h | 223 | 1
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 1254 | h | 223 | 1
TTU0623-PWPe-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 1254 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 66 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 66 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3041 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 6750 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 6750 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3012 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 24431 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 24431 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 3012 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 48863 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 48863 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 92145 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 92145 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 25265 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 25265 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 60635 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 213861 | h | 223 | 1
MMR0822-PWPp-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 213861 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 193165 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 6238 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 6238 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 20905 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-15 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-15 | 20905 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 1144 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 1144 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 978 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 978 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 271 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 271 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 128 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 128 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 162 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 162 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 59 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 59 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 272 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 272 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 960 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 51689 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 51689 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 14795 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 14795 | h | 223 | 1
MEM0822-CWP-194 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 33 | h | 223 | 1
MEM0822-CWP-194 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 33 | h | 223 | 1
MEM0822-CWP-195 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 33 | h | 223 | 1
MEM0822-CWP-195 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 33 | h | 223 | 1
MEM0822-CWP-196 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 33 | h | 223 | 1
MEM0822-CWP-196 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 33 | h | 223 | 1
JIL0822-CWP-199 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 29520 | h | 223 | 1
JIL0822-CWP-199 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 29520 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 10859 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 10859 | h | 223 | 1
MEM0822-CWP-220 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 4276 | h | 223 | 1
MEM0822-CWP-220 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 4276 | h | 223 | 1
MEM0822-CWP-221 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 147 | h | 223 | 1
MEM0822-CWP-221 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 147 | h | 223 | 1
MEM0822-CWP-222 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 220 | h | 223 | 1
MEM0822-CWP-222 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 220 | h | 223 | 1
JIL0822-CWP-224 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 8640 | h | 223 | 1
JIL0822-CWP-224 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 8640 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 5039 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 982 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 982 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 73 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 73 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 679 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 679 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 56 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 56 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 67 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 278 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 278 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 3800 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 3800 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 872 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-15 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-15 | 872 | h | 223 | 1
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-10-22 | 2 | m | 223 | 1
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-10-22 | 2 | m | 223 | 1
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-10-22 | 0 | m | 223 | 1
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-10-22 | 0 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-10-22 | 14 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-10-22 | 14 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Budgeted Units | 2023-10-22 | 20 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | At Completion Units | 2023-10-22 | 20 | m | 223 | 1
JIL0822-CWP-199 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-10-22 | 256 | un | 223 | 1
JIL0822-CWP-199 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-10-22 | 256 | un | 223 | 1
JIL0822-CWP-224 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-10-22 | 75 | un | 223 | 1
JIL0822-CWP-224 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-10-22 | 75 | un | 223 | 1
MEM0822-CWP-220 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-10-22 | 12 | t | 223 | 1
MEM0822-CWP-220 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-10-22 | 12 | t | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-22 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-22 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-22 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-22 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-22 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-22 | 0 | un | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-22 | 4 | t | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-22 | 4 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-22 | 1 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-22 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-22 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-22 | 1 | t | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-22 | 260 | Meter | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-22 | 260 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-22 | 3363 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-22 | 3363 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-22 | 13 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-22 | 13 | Meter | 223 | 1
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-22 | 509 | Meter | 223 | 1
ESD1214-CWP-489 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-22 | 509 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-22 | 63 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-22 | 63 | Meter | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-22 | 1 | t | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-22 | 1 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-22 | 63 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-22 | 63 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-22 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-22 | 6 | t | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 27741 | h | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 27741 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 26715 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 26715 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23710 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23710 | h | 223 | 1
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 40073 | h | 223 | 1
CEC0820-EWPc-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 40073 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 6583 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 6583 | h | 223 | 1
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 40073 | h | 223 | 1
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 33564 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 47816 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 86454 | h | 223 | 1
JPA0821-EWPc-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 86454 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 12546 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 7881 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 7881 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1806 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1806 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 334815 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 71943 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 71943 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 80256 | h | 223 | 1
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 88671 | h | 223 | 1
CDC0821-EWPc-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 88671 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 37685 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 37685 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 13307 | h | 223 | 1
SES0821-PWPe-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 13307 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 56105 | h | 223 | 1
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 111006 | h | 223 | 1
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 111006 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2998 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2998 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3932 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3932 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1442 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1442 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5348 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5348 | h | 223 | 1
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 88671 | h | 223 | 1
MSD0821-EWPc-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 88671 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 334815 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 88671 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 88671 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 12546 | h | 223 | 1
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 88671 | h | 223 | 1
CEC0821-EWPc-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 47816 | h | 223 | 1
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 34059 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 34059 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 13307 | h | 223 | 1
SES0821-PWPe-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 13307 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 56105 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 34059 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 14475 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 14475 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 16048 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3041 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 20435 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23279 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 20029 | h | 223 | 1
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
MSD0822-EWPc-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
MSD0822-EWPc-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 41955 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 11495 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 11495 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 370 | h | 223 | 1
MEM0823-PWPe-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 370 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1158 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 7881 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 7881 | h | 223 | 1
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
MSD0822-EWPc-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 257322 | h | 223 | 1
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
CEC0822-EWPc-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 33564 | h | 223 | 1
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
MSD0822-EWPc-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 890 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 890 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 30300 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 30300 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 91548 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 30300 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 30300 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 91548 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 30300 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 30300 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 91548 | h | 223 | 1
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 10491 | h | 223 | 1
ERE0822-PWPe-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 10491 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23980 | h | 223 | 1
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
MSD0822-EWPc-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 7881 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 7881 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 17514 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 49812 | h | 223 | 1
JPA0822-EWPc-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 49812 | h | 223 | 1
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
MSD0822-EWPc-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 41576 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39158 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39158 | h | 223 | 1
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 21754 | h | 223 | 1
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 21754 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 31643 | h | 223 | 1
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4454 | h | 223 | 1
MEM0822-PWPe-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4454 | h | 223 | 1
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
CDC0822-EWPc-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 6479 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2969 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2969 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 6479 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 55940 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 37950 | h | 223 | 1
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 10491 | h | 223 | 1
ERE0822-PWPe-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 10491 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23980 | h | 223 | 1
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 10491 | h | 223 | 1
ERE0822-PWPe-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 10491 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 55940 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23570 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3061 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3061 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 21767 | h | 223 | 1
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 51089 | h | 223 | 1
MSD0822-EWPc-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 51089 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 62703 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 367 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 367 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2857 | h | 223 | 1
JIL0822-CWP-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1193043 | h | 223 | 1
JIL0822-CWP-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1193043 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 263310 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 263310 | h | 223 | 1
MEM0822-CWP-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 172813 | h | 223 | 1
MEM0822-CWP-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 172813 | h | 223 | 1
MEM0822-CWP-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 8890 | h | 223 | 1
MEM0822-CWP-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 8890 | h | 223 | 1
JIL0822-CWP-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 349183 | h | 223 | 1
JIL0822-CWP-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 349183 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2627 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 380 | h | 223 | 1
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 147365 | h | 223 | 1
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 147365 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 460009 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 460009 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1806 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1806 | h | 223 | 1
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 8169 | h | 223 | 1
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 8169 | h | 223 | 1
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 147365 | h | 223 | 1
CEC0823-EWPc-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 147365 | h | 223 | 1
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 147365 | h | 223 | 1
MSD0823-EWPc-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 20029 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1806 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1806 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2627 | h | 223 | 1
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 147365 | h | 223 | 1
CDC0823-EWPc-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 147365 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 301 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 301 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 13307 | h | 223 | 1
SES0823-PWPe-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 13307 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 56105 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 62630 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 62630 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23570 | h | 223 | 1
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 132628 | h | 223 | 1
CDC0824-EWPc-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 132628 | h | 223 | 1
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 132628 | h | 223 | 1
CFU0824-EWPc-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 132628 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2432 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2432 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5895 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 88419 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23279 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5895 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 162586 | h | 223 | 1
JPA0826-EWPc-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 162586 | h | 223 | 1
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 166755 | h | 223 | 1
EEE0826-EWPc-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 166755 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 37520 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 37520 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1885 | h | 223 | 1
MEM0826-PWPe-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1885 | h | 223 | 1
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 8169 | h | 223 | 1
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 8169 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
CEC0827-EWPc-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 26515 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 26515 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 25398 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 25398 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2432 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2432 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 69966 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 69966 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 26515 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 26515 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 38778 | h | 223 | 1
JPA0827-EWPc-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 38778 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 16903 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 16903 | h | 223 | 1
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 25398 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 25398 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5895 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 13307 | h | 223 | 1
SES0827-PWPe-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 13307 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 564 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 16457 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 16457 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4393 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5492 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1806 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1806 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2627 | h | 223 | 1
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 16164 | h | 223 | 1
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 16164 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39184 | h | 223 | 1
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 39772 | h | 223 | 1
MSD0827-EWPc-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 39772 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 20200 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 20200 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 11748 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 36298 | h | 223 | 1
JPA1062-EWPc-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 36298 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 23570 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 18614 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 18614 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 26189 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1358 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1358 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 16546 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 16546 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 13735 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3920 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3920 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 6271 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 25265 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 25265 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 60635 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 24819 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 24819 | h | 223 | 1
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 72937 | h | 223 | 1
CEC1214-EWPc-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 72937 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 26477 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1617 | h | 223 | 1
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 72937 | h | 223 | 1
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 72937 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 72937 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 72937 | h | 223 | 1
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 233 | h | 223 | 1
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 233 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 479 | h | 223 | 1
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 54285 | h | 223 | 1
ESD1214-CWP-489 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 54285 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 7418 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 47 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 47 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2384 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2384 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 574 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 574 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 551 | h | 223 | 1
SUWP-AC-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 551 | h | 223 | 1
SUWP-AS-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 4792 | h | 223 | 1
SUWP-AS-PF-1005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 4792 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 33027 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 190 | h | 223 | 1
SUWP-AC-PF-0309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 190 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 541 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 541 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 315 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 315 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 14752 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 344 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 344 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1999 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1999 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 49 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 49 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1830 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1830 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1727 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1727 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3083 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3083 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2153 | h | 223 | 1
SUWP-AC-PF-1101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2153 | h | 223 | 1
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 616 | h | 223 | 1
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 616 | h | 223 | 1
SUWP-AT-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 18540 | h | 223 | 1
SUWP-AT-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 18540 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 253 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 253 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 52095 | h | 223 | 1
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 40000 | h | 223 | 1
MEM1110-EWPc-465 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 40000 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 10 | h | 223 | 1
B40883 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 10 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 114551 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 114551 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3093 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 1806 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 1806 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 114551 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3041 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 6750 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 6750 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3012 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 9162 | h | 223 | 1
MEM0622-EWPc-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 9162 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 3012 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 48863 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 48863 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 92145 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 92145 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 5584 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 5584 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 25265 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 25265 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 25265 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 19580 | h | 223 | 1
EEE1061-PWPe-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 19580 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 60635 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 193165 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 43663 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 20905 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-22 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-22 | 20905 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 1144 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 1144 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 978 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 978 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 271 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 271 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 2967 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 2967 | h | 223 | 1
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 4578 | h | 223 | 1
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 4578 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 128 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 128 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 162 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 162 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 59 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 59 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 272 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 272 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 960 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 51689 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 51689 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 14795 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 14795 | h | 223 | 1
JIL0822-CWP-199 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 49200 | h | 223 | 1
JIL0822-CWP-199 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 49200 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 10859 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 10859 | h | 223 | 1
MEM0822-CWP-220 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 7127 | h | 223 | 1
MEM0822-CWP-220 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 7127 | h | 223 | 1
MEM0822-CWP-222 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 367 | h | 223 | 1
MEM0822-CWP-222 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 367 | h | 223 | 1
JIL0822-CWP-224 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 14400 | h | 223 | 1
JIL0822-CWP-224 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 14400 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 5039 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 13 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 13 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 982 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 982 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 73 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 73 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 679 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 679 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 56 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 56 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 67 | h | 223 | 1
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 10 | h | 223 | 1
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 10 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 278 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 278 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 3800 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 3800 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 872 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-22 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-22 | 872 | h | 223 | 1
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-10-29 | 7 | m | 223 | 1
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-10-29 | 7 | m | 223 | 1
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-10-29 | 2 | m | 223 | 1
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-10-29 | 2 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-10-29 | 14 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-10-29 | 14 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Budgeted Units | 2023-10-29 | 20 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | At Completion Units | 2023-10-29 | 20 | m | 223 | 1
JIL0822-CWP-199 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-10-29 | 205 | un | 223 | 1
JIL0822-CWP-199 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-10-29 | 205 | un | 223 | 1
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-10-29 | 6 | un | 223 | 1
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-10-29 | 6 | un | 223 | 1
JIL0822-CWP-224 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-10-29 | 60 | un | 223 | 1
JIL0822-CWP-224 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-10-29 | 60 | un | 223 | 1
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2023-10-29 | 3 | m | 223 | 1
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2023-10-29 | 3 | m | 223 | 1
MEM0822-CWP-220 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-10-29 | 2 | t | 223 | 1
MEM0822-CWP-220 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-10-29 | 2 | t | 223 | 1
MSD0827-CWP-367 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-29 | 4 | un | 223 | 1
MSD0827-CWP-367 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-29 | 4 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-29 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-29 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-29 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-29 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-10-29 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-10-29 | 0 | un | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-29 | 17 | t | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-29 | 17 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-29 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-29 | 12 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-29 | 1 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-29 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-29 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-29 | 1 | t | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-29 | 260 | Meter | 223 | 1
ESD0800-CWP-481 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-29 | 260 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-29 | 3363 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-29 | 3363 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-29 | 13 | Meter | 223 | 1
ESD1062-CWP-485 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-29 | 13 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-10-29 | 63 | Meter | 223 | 1
ESD0600-CWP-478 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-10-29 | 63 | Meter | 223 | 1
MSD0822-CWP-203 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2023-10-29 | 19 | unid | 223 | 1
MSD0822-CWP-203 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2023-10-29 | 19 | unid | 223 | 1
MSD0822-CWP-200 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-29 | 4 | t | 223 | 1
MSD0822-CWP-200 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-29 | 4 | t | 223 | 1
MSD0822-CWP-230 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-29 | 4 | t | 223 | 1
MSD0822-CWP-230 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-29 | 4 | t | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-10-29 | 1 | t | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-10-29 | 1 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-29 | 63 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-29 | 63 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-10-29 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-10-29 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-10-29 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-10-29 | 8 | t | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 27741 | h | 223 | 1
ESD0800-CWP-481 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 27741 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 26715 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 26715 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14915 | h | 223 | 1
SSD0817-EWPc-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14915 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14915 | h | 223 | 1
SSD0817-EWPc-028 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14915 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPe-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MCD0817-PWPe-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
STP0817-PWPe-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14915 | h | 223 | 1
MSD0817-EWPc-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14915 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPe-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPe-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPe-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPe-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MCD0817-PWPe-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14915 | h | 223 | 1
EEL0817-EWPc-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14915 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPe-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
ELU0817-PWPe-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
JIL0817-PWPe-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MMR0817-PWPe-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14915 | h | 223 | 1
CPI0817-EWPc-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14915 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPe-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23710 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23710 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 6583 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 6583 | h | 223 | 1
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 40073 | h | 223 | 1
ELU0800-EWPc-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 33564 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 47816 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 12546 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7881 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7881 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1806 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1806 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 334815 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 345326 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 345326 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 80256 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 88671 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 88671 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 56105 | h | 223 | 1
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 532829 | h | 223 | 1
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 532829 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2998 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2998 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3932 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3932 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1442 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1442 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5348 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5348 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 334815 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 88671 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 88671 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 12546 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 47816 | h | 223 | 1
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 51089 | h | 223 | 1
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 51089 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 34059 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 34059 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 56105 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 34059 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 34059 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 16048 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3041 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 20435 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23279 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 41955 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 51089 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 51089 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1158 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7881 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7881 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 257322 | h | 223 | 1
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 83078 | h | 223 | 1
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 83078 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 33564 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 35601 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 30300 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 30300 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 91548 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 30300 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 30300 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 91548 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 30300 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 30300 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23980 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7881 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7881 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 41576 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 39158 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 39158 | h | 223 | 1
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 21754 | h | 223 | 1
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 21754 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 31643 | h | 223 | 1
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 51089 | h | 223 | 1
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 51089 | h | 223 | 1
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 51089 | h | 223 | 1
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 6479 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2969 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2969 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 6479 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 55940 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 51089 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 51089 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 160509 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 55940 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23570 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3061 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3061 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 21767 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 62703 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14686 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14686 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2857 | h | 223 | 1
JIL0822-CWP-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 954435 | h | 223 | 1
JIL0822-CWP-199 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 954435 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 26319 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 26319 | h | 223 | 1
MSD0822-CWP-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 87297 | h | 223 | 1
MSD0822-CWP-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 87297 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 263310 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 263310 | h | 223 | 1
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 25607 | h | 223 | 1
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 25607 | h | 223 | 1
MEM0822-CWP-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 138251 | h | 223 | 1
MEM0822-CWP-220 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 138251 | h | 223 | 1
MEM0822-CWP-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7112 | h | 223 | 1
MEM0822-CWP-222 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7112 | h | 223 | 1
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1778 | h | 223 | 1
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1778 | h | 223 | 1
JIL0822-CWP-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 279347 | h | 223 | 1
JIL0822-CWP-224 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 279347 | h | 223 | 1
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1455 | h | 223 | 1
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1455 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2627 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 380 | h | 223 | 1
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 147365 | h | 223 | 1
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 147365 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 460009 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 460009 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1806 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1806 | h | 223 | 1
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 8169 | h | 223 | 1
MEM0823-PWPe-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 8169 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 20029 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1806 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1806 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2627 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1446 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1446 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 56105 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 147365 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 147365 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 49467 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23052 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23052 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23570 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 82893 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 82893 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 912 | h | 223 | 1
MEM0824-PWPe-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 912 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5895 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 88419 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 88419 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23279 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 20029 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5895 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 166755 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 166755 | h | 223 | 1
MSD0822-CWP-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 41143 | h | 223 | 1
MSD0822-CWP-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 41143 | h | 223 | 1
MSD0827-CWP-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 17321 | h | 223 | 1
MSD0827-CWP-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 17321 | h | 223 | 1
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 8169 | h | 223 | 1
MEM0827-PWPe-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 8169 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPe-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MCD0827-PWPe-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MMR0827-PWPe-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 43729 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 43729 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14915 | h | 223 | 1
MSD0827-EWPc-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14915 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 26515 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 26515 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPe-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MCD0827-PWPe-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 9524 | h | 223 | 1
MCD0827-PWPp-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 9524 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 15715 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 15715 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14915 | h | 223 | 1
MSD0827-EWPc-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14915 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 912 | h | 223 | 1
MEM0827-PWPe-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 912 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 43729 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 43729 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
STP0827-PWPe-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14915 | h | 223 | 1
MSD0827-EWPc-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14915 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 69966 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 69966 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPe-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
ELU0827-PWPe-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
JIL0827-PWPe-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 26515 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 26515 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 39772 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 39772 | h | 223 | 1
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 39772 | h | 223 | 1
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
STP0827-PWPe-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 9524 | h | 223 | 1
MEM0827-PWPp-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 9524 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5895 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 564 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 16457 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 16457 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14915 | h | 223 | 1
MSD0827-EWPc-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14915 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPe-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPe-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPe-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1648 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5492 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24858 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24858 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1806 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1806 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2627 | h | 223 | 1
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 16164 | h | 223 | 1
JIL0827-PWPe-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 16164 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 39184 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 20200 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 20200 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 23570 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 18614 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 18614 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 26189 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1358 | h | 223 | 1
ESD1062-CWP-485 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1358 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 16546 | h | 223 | 1
EEE1062-EWPc-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 16546 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 13735 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7032 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7032 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2254 | h | 223 | 1
EEE1062-PWPe-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2254 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 10341 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 10341 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 9474 | h | 223 | 1
EEE1062-PWPe-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 9474 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 60635 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24819 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24819 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 26477 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1617 | h | 223 | 1
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 72937 | h | 223 | 1
ELU1214-EWPc-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 72937 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 72937 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 72937 | h | 223 | 1
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1035 | h | 223 | 1
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1035 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 479 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7418 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 27 | h | 223 | 1
SUWP-AC-PF-0902 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 27 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2781 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2781 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 804 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 804 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 72 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 72 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 33027 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 155 | h | 223 | 1
SUWP-AC-PF-0803 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 155 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 270 | h | 223 | 1
SUWP-AC-PF-1130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 270 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 32 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 32 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 14752 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 344 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 344 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 676 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 676 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1142 | h | 223 | 1
SUWP-AT-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1142 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 376 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 376 | h | 223 | 1
SUWP-AS-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 904 | h | 223 | 1
SUWP-AS-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 904 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 49 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 49 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 962 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 962 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1830 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1830 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 494 | h | 223 | 1
SUWP-AC-PF-1103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 494 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3083 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3083 | h | 223 | 1
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 616 | h | 223 | 1
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 616 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 454 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 454 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 170 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 170 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 253 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 253 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 52095 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 578 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 578 | h | 223 | 1
B40893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 110571 | h | 223 | 1
B40893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 110571 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 11224 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 111687 | h | 223 | 1
TTU0622-EWPc-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 111687 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3093 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1806 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1806 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 114551 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3041 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 6750 | h | 223 | 1
ESD0600-CWP-478 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 6750 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3012 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 48863 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 48863 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 92145 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 92145 | h | 223 | 1
MEM0821-PWPe-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2080 | h | 223 | 1
MEM0821-PWPe-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2080 | h | 223 | 1
MEM0821-PWPe-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 2080 | h | 223 | 1
MEM0821-PWPe-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 2080 | h | 223 | 1
MEM0821-PWPe-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1397 | h | 223 | 1
MEM0821-PWPe-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1397 | h | 223 | 1
MEM0821-PWPe-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 1397 | h | 223 | 1
MEM0821-PWPe-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 1397 | h | 223 | 1
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 31024 | h | 223 | 1
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 31024 | h | 223 | 1
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 31024 | h | 223 | 1
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 31024 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 24819 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 24819 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 9474 | h | 223 | 1
EEE1052-PWPe-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 9474 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 9474 | h | 223 | 1
EEE1063-PWPe-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 9474 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 60635 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 193165 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 43663 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 8408 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 8408 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3153 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 3154 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 3154 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 7643 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 7643 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 20905 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-10-29 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-10-29 | 20905 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 1144 | h | 223 | 1
ESD0800-CWP-481 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 1144 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 978 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 978 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 271 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 271 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 14241 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 14241 | h | 223 | 1
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 21973 | h | 223 | 1
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 21973 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 128 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 128 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 162 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 162 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 59 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 59 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 272 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 272 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 960 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 6822 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 51689 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 51689 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 9760 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 14795 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 14795 | h | 223 | 1
JIL0822-CWP-199 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 39360 | h | 223 | 1
JIL0822-CWP-199 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 39360 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 1085 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 1085 | h | 223 | 1
MSD0822-CWP-203 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 3600 | h | 223 | 1
MSD0822-CWP-203 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 3600 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 10859 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 10859 | h | 223 | 1
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 1056 | h | 223 | 1
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 1056 | h | 223 | 1
MEM0822-CWP-220 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 5701 | h | 223 | 1
MEM0822-CWP-220 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 5701 | h | 223 | 1
MEM0822-CWP-222 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 293 | h | 223 | 1
MEM0822-CWP-222 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 293 | h | 223 | 1
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 73 | h | 223 | 1
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 73 | h | 223 | 1
JIL0822-CWP-224 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 11520 | h | 223 | 1
JIL0822-CWP-224 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 11520 | h | 223 | 1
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 60 | h | 223 | 1
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 60 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 5039 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 61 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 61 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 951 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 951 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 982 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 982 | h | 223 | 1
MSD0822-CWP-238 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 1697 | h | 223 | 1
MSD0822-CWP-238 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 1697 | h | 223 | 1
MSD0827-CWP-367 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 714 | h | 223 | 1
MSD0827-CWP-367 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 714 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 73 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 73 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 679 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 679 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 56 | h | 223 | 1
ESD1062-CWP-485 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 56 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 67 | h | 223 | 1
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 43 | h | 223 | 1
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 43 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 278 | h | 223 | 1
ESD0600-CWP-478 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 278 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 3800 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 3800 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 872 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-10-29 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-10-29 | 872 | h | 223 | 1
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-11-05 | 7 | m | 223 | 1
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-11-05 | 7 | m | 223 | 1
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-11-05 | 2 | m | 223 | 1
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-11-05 | 2 | m | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-11-05 | 4 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-11-05 | 4 | t | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-11-05 | 14 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-11-05 | 14 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Budgeted Units | 2023-11-05 | 20 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | At Completion Units | 2023-11-05 | 20 | m | 223 | 1
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-11-05 | 28 | un | 223 | 1
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-11-05 | 28 | un | 223 | 1
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2023-11-05 | 13 | m | 223 | 1
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2023-11-05 | 13 | m | 223 | 1
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-11-05 | 1 | t | 223 | 1
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-11-05 | 1 | t | 223 | 1
MSD0827-CWP-367 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-05 | 6 | un | 223 | 1
MSD0827-CWP-367 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-05 | 6 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-05 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-05 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-05 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-05 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-05 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-05 | 0 | un | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-05 | 17 | t | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-05 | 17 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-05 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-05 | 12 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-05 | 1 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-05 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-05 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-05 | 1 | t | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-05 | 3363 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-05 | 3363 | Meter | 223 | 1
MSD0822-CWP-203 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2023-11-05 | 19 | unid | 223 | 1
MSD0822-CWP-203 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2023-11-05 | 19 | unid | 223 | 1
MSD0822-CWP-200 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-11-05 | 4 | t | 223 | 1
MSD0822-CWP-200 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-11-05 | 4 | t | 223 | 1
MSD0822-CWP-230 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-11-05 | 3 | t | 223 | 1
MSD0822-CWP-230 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-11-05 | 3 | t | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2023-11-05 | 1 | t | 223 | 1
MSD0827-CWP-352 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2023-11-05 | 1 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-11-05 | 50 | t | 223 | 1
MSD0822-CWP-096 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-11-05 | 50 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-11-05 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-11-05 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-11-05 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-11-05 | 8 | t | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 26715 | h | 223 | 1
CEC0800-EWPc-475 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 26715 | h | 223 | 1
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2387 | h | 223 | 1
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2387 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5787 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23710 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23710 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6583 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6583 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 33564 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 47816 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12546 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 7881 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 7881 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1806 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1806 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 334815 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 345326 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 345326 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 80256 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 88671 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 88671 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 56105 | h | 223 | 1
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 532829 | h | 223 | 1
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 532829 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3958 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3958 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2998 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2998 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3932 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3932 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1442 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1442 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5348 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5348 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 334815 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 88671 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 88671 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12546 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 47816 | h | 223 | 1
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 51089 | h | 223 | 1
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 51089 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 34059 | h | 223 | 1
MSD0822-EWPc-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 34059 | h | 223 | 1
MSD0822-EWPc-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 34059 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 56105 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 34059 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 34059 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 16048 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 7418 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 7418 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3041 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 20435 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23279 | h | 223 | 1
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 38100 | h | 223 | 1
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 38100 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 41955 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 51089 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 51089 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1158 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 7881 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 7881 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 257322 | h | 223 | 1
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 83078 | h | 223 | 1
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 83078 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 33564 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 35601 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 17423 | h | 223 | 1
ERE0822-EWPc-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 17423 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 91548 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 17423 | h | 223 | 1
ERE0822-EWPc-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 17423 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 91548 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 17423 | h | 223 | 1
ERE0822-EWPc-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 17423 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23980 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 7881 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 7881 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 41576 | h | 223 | 1
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2387 | h | 223 | 1
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2387 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 21677 | h | 223 | 1
SES0822-PWPl-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 21677 | h | 223 | 1
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 21754 | h | 223 | 1
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 21754 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 31643 | h | 223 | 1
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 51089 | h | 223 | 1
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 51089 | h | 223 | 1
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 51089 | h | 223 | 1
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6479 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2969 | h | 223 | 1
MEM0822-PWPe-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2969 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6479 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 55940 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 55940 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 51089 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 51089 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 160509 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 55235 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 55235 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 55940 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5787 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3061 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3061 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 21767 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 62703 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 14686 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 14686 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2857 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 26319 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 26319 | h | 223 | 1
MSD0822-CWP-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 87297 | h | 223 | 1
MSD0822-CWP-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 87297 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 263310 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 263310 | h | 223 | 1
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 128033 | h | 223 | 1
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 128033 | h | 223 | 1
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 8890 | h | 223 | 1
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 8890 | h | 223 | 1
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 7273 | h | 223 | 1
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 7273 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2627 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 927 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 927 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 380 | h | 223 | 1
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 147365 | h | 223 | 1
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 147365 | h | 223 | 1
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 147365 | h | 223 | 1
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 147365 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 460009 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 460009 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1806 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1806 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 20029 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1806 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1806 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2627 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1446 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1446 | h | 223 | 1
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2387 | h | 223 | 1
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2387 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 56105 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5787 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 147365 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 147365 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 49467 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23052 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23052 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23570 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 132628 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 132628 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5895 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 86208 | h | 223 | 1
JPA0824-EWPc-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 86208 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23279 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 20029 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5895 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 166755 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 166755 | h | 223 | 1
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2387 | h | 223 | 1
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2387 | h | 223 | 1
MSD0822-CWP-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 41143 | h | 223 | 1
MSD0822-CWP-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 41143 | h | 223 | 1
MSD0827-CWP-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 21479 | h | 223 | 1
MSD0827-CWP-367 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 21479 | h | 223 | 1
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 15378 | h | 223 | 1
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 15378 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 69966 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 69966 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 26515 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 26515 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 4286 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 4286 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 26668 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 26668 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 69966 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 69966 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 69966 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 69966 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 26515 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 26515 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5895 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 564 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 16457 | h | 223 | 1
MSD0827-CWP-352 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 16457 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5492 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1806 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1806 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2627 | h | 223 | 1
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39772 | h | 223 | 1
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39772 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 39184 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 20200 | h | 223 | 1
CEC0830-EWPc-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 20200 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 23570 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 18614 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 18614 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 26189 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 13735 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 16546 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 16546 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 16546 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 16546 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 60635 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 24819 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 24819 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 26477 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1563 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1563 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3572 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3572 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1617 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 72937 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 72937 | h | 223 | 1
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1035 | h | 223 | 1
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1035 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 479 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 7418 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2781 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2781 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 804 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 804 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 423 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 423 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 168 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 168 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 33027 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 75 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 75 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 14752 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 344 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 344 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1577 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1577 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1317 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1317 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 98 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 98 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 49 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 49 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1347 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1347 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 523 | h | 223 | 1
SUWP-AC-PF-0503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 523 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3083 | h | 223 | 1
SUWP-AC-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3083 | h | 223 | 1
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 528 | h | 223 | 1
SUWP-AC-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 528 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 635 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 635 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 170 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 170 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 181 | h | 223 | 1
SUWP-AC-PF-0901 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 181 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 52095 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2891 | h | 223 | 1
B40893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 442285 | h | 223 | 1
B40893 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 442285 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3093 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 1806 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 1806 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 114551 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3041 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 3012 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 48863 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 48863 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 92145 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 92145 | h | 223 | 1
MEM0821-PWPe-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 9779 | h | 223 | 1
MEM0821-PWPe-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 9779 | h | 223 | 1
MEM0821-PWPe-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 9779 | h | 223 | 1
MEM0821-PWPe-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 9779 | h | 223 | 1
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 49639 | h | 223 | 1
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 49639 | h | 223 | 1
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 49639 | h | 223 | 1
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 49639 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 24819 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 24819 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 60635 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPp-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 193165 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 6238 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5045 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 5046 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 5046 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 12229 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 20905 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-05 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-05 | 20905 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 978 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 978 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 271 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 271 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 14241 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 14241 | h | 223 | 1
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 21973 | h | 223 | 1
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 21973 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 172 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 172 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 128 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 128 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 162 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 162 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 59 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 59 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 272 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 272 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 960 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 6822 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 40921 | h | 223 | 1
MSD0822-CWP-096 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 40921 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 2278 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 2278 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 9760 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 14795 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 14795 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 1085 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 1085 | h | 223 | 1
MSD0822-CWP-203 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 3600 | h | 223 | 1
MSD0822-CWP-203 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 3600 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 10859 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 10859 | h | 223 | 1
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 5280 | h | 223 | 1
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 5280 | h | 223 | 1
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 367 | h | 223 | 1
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 367 | h | 223 | 1
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 300 | h | 223 | 1
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 300 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 5039 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 61 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 61 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 951 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 951 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 982 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 982 | h | 223 | 1
MSD0822-CWP-238 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 1697 | h | 223 | 1
MSD0822-CWP-238 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 1697 | h | 223 | 1
MSD0827-CWP-367 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 886 | h | 223 | 1
MSD0827-CWP-367 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 886 | h | 223 | 1
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 634 | h | 223 | 1
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 634 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 73 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 73 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 679 | h | 223 | 1
MSD0827-CWP-352 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 679 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 67 | h | 223 | 1
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 43 | h | 223 | 1
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 43 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 3800 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 3800 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 872 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-05 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-05 | 872 | h | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-12 | 37 | m | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-12 | 37 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-12 | 3 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-12 | 3 | m | 223 | 1
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-12 | 0 | m | 223 | 1
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-12 | 0 | m | 223 | 1
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-11-12 | 6 | m | 223 | 1
CDC0821-CWP-069 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-11-12 | 6 | m | 223 | 1
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-11-12 | 1 | m | 223 | 1
CDC1214-CWP-391 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-11-12 | 1 | m | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-11-12 | 17 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-11-12 | 17 | t | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-11-12 | 14 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-11-12 | 14 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Budgeted Units | 2023-11-12 | 20 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | At Completion Units | 2023-11-12 | 20 | m | 223 | 1
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-11-12 | 28 | un | 223 | 1
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-11-12 | 28 | un | 223 | 1
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2023-11-12 | 13 | m | 223 | 1
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2023-11-12 | 13 | m | 223 | 1
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-11-12 | 3 | t | 223 | 1
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-11-12 | 3 | t | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-12 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-12 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-12 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-12 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-12 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-12 | 0 | un | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 17 | t | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 17 | t | 223 | 1
MSD0822-CWP-508 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 1 | t | 223 | 1
MSD0822-CWP-508 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 1 | t | 223 | 1
MSD0822-CWP-509 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 22 | t | 223 | 1
MSD0822-CWP-509 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 22 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 12 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 1 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 1 | t | 223 | 1
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 92 | Meter | 223 | 1
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 92 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 3363 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 3363 | Meter | 223 | 1
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 22 | Meter | 223 | 1
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 22 | Meter | 223 | 1
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-12 | 10 | Meter | 223 | 1
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-12 | 10 | Meter | 223 | 1
MSD0822-CWP-203 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2023-11-12 | 8 | unid | 223 | 1
MSD0822-CWP-203 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2023-11-12 | 8 | unid | 223 | 1
EEE1062-CWP-382 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2023-11-12 | 0 | unid | 223 | 1
EEE1062-CWP-382 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2023-11-12 | 0 | unid | 223 | 1
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-11-12 | 4 | t | 223 | 1
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-11-12 | 4 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-11-12 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-11-12 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-11-12 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-11-12 | 8 | t | 223 | 1
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2387 | h | 223 | 1
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2387 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5787 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23710 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23710 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 6418 | h | 223 | 1
MSD0820-CWP-055 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 6418 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 33564 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 47816 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 55419 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 55419 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2217 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2217 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12546 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2955 | h | 223 | 1
MEM0821-PWPe-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2955 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1761 | h | 223 | 1
MEM0821-PWPe-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1761 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 334815 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 345326 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 345326 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 80256 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 88671 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 88671 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 56105 | h | 223 | 1
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 421823 | h | 223 | 1
CDC0821-CWP-069 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 421823 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3972 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3972 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 9894 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 9894 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2398 | h | 223 | 1
MEM0821-CWP-077 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2398 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3932 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3932 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1442 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1442 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5348 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5348 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 334815 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 15517 | h | 223 | 1
MEM0822-EWPc-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 15517 | h | 223 | 1
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 78176 | h | 223 | 1
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 78176 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12546 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 47816 | h | 223 | 1
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 51089 | h | 223 | 1
TTU0822-EWPc-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 51089 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 56105 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 34059 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 34059 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 16048 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 4266 | h | 223 | 1
TTU0822-PWPp-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 4266 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3041 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 20435 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23279 | h | 223 | 1
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 38100 | h | 223 | 1
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 38100 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 41955 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 51089 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 51089 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1158 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 31930 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 31930 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2955 | h | 223 | 1
MEM0822-PWPe-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2955 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 257322 | h | 223 | 1
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 83078 | h | 223 | 1
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 83078 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 33564 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 35601 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23980 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 31930 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 31930 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2955 | h | 223 | 1
MEM0822-PWPe-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2955 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 67928 | h | 223 | 1
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2387 | h | 223 | 1
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2387 | h | 223 | 1
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 21754 | h | 223 | 1
MEM0822-PWPe-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 21754 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 31643 | h | 223 | 1
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 51089 | h | 223 | 1
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 51089 | h | 223 | 1
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 51089 | h | 223 | 1
MEM0822-EWPc-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 6479 | h | 223 | 1
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 51089 | h | 223 | 1
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 51089 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 6479 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 17481 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 17481 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 32165 | h | 223 | 1
EEE0822-PWPp-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 32165 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 8941 | h | 223 | 1
SES0822-EWPc-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 8941 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 160509 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 265130 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 265130 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3754 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 55940 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 55940 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5787 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3061 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3061 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 21767 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 62703 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 14686 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 14686 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2857 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 26319 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 26319 | h | 223 | 1
MSD0822-CWP-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 34919 | h | 223 | 1
MSD0822-CWP-203 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 34919 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 263310 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 263310 | h | 223 | 1
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 128033 | h | 223 | 1
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 128033 | h | 223 | 1
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 8890 | h | 223 | 1
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 8890 | h | 223 | 1
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 7273 | h | 223 | 1
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 7273 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2627 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 533 | h | 223 | 1
TTU0823-PWPp-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 533 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 380 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3684 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3684 | h | 223 | 1
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 147365 | h | 223 | 1
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 147365 | h | 223 | 1
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 147365 | h | 223 | 1
TTU0823-EWPc-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 147365 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 460009 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 460009 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1761 | h | 223 | 1
MEM0823-PWPe-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1761 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 20029 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3684 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3684 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1761 | h | 223 | 1
MEM0823-PWPe-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1761 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2627 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1578 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1578 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3825 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3825 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1446 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1446 | h | 223 | 1
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2387 | h | 223 | 1
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2387 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 56105 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5787 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 147365 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 147365 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 49467 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23052 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23052 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23570 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1578 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1578 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3825 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3825 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1578 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1578 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3825 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3825 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 132628 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 132628 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5895 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23279 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 20029 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5895 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 166755 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 166755 | h | 223 | 1
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2387 | h | 223 | 1
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2387 | h | 223 | 1
MSD0822-CWP-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 16457 | h | 223 | 1
MSD0822-CWP-238 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 16457 | h | 223 | 1
MSD0822-CWP-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 24686 | h | 223 | 1
MSD0822-CWP-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 24686 | h | 223 | 1
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 68345 | h | 223 | 1
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 68345 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 69966 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 69966 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 9943 | h | 223 | 1
SES0827-EWPc-318 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 9943 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 26668 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 26668 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 26668 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 26668 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 69966 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 69966 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 69966 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 69966 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 9943 | h | 223 | 1
MSD0827-EWPc-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 9943 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
TTU0827-EWPc-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2061 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2061 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5895 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 564 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3297 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5492 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 994 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 994 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1761 | h | 223 | 1
MEM0827-PWPe-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1761 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2627 | h | 223 | 1
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39772 | h | 223 | 1
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39772 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 39184 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 429 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 429 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 23570 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 18614 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 18614 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 26189 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 13735 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 16546 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 16546 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 16546 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 16546 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 60635 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 24819 | h | 223 | 1
ELU1062-EWPc-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 24819 | h | 223 | 1
EEE1062-CWP-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1257 | h | 223 | 1
EEE1062-CWP-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1257 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 26477 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 6946 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 6946 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 15875 | h | 223 | 1
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2037 | h | 223 | 1
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2037 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1617 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 56526 | h | 223 | 1
JIL1214-EWPc-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 56526 | h | 223 | 1
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 802 | h | 223 | 1
CDC1214-CWP-391 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 802 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 479 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 7418 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2781 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2781 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 804 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 804 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 592 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 592 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 168 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 168 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 33027 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 75 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 75 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 14752 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 196 | h | 223 | 1
SUWP-AC-PF-1135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 196 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1577 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1577 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1317 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1317 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 98 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 98 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 49 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 49 | h | 223 | 1
SUWP-AS-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 4232 | h | 223 | 1
SUWP-AS-PF-0205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 4232 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1347 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1347 | h | 223 | 1
SUWP-AS-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 51968 | h | 223 | 1
SUWP-AS-PM-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 51968 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 635 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 635 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2852 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2852 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 170 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 170 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 52095 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3093 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 1761 | h | 223 | 1
MEM0623-PWPe-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 1761 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 6443 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 6443 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 114551 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3041 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 3012 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 48863 | h | 223 | 1
ELU0600-EWPc-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 48863 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 18429 | h | 223 | 1
MSD0622-CWP-005 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 18429 | h | 223 | 1
MCD0822-PWPl-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 167819 | h | 223 | 1
MCD0822-PWPl-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 167819 | h | 223 | 1
MCD0822-PWPl-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 167819 | h | 223 | 1
MCD0822-PWPl-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 167819 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 25123 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 25123 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 25123 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 25123 | h | 223 | 1
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2956 | h | 223 | 1
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2956 | h | 223 | 1
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 2956 | h | 223 | 1
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 2956 | h | 223 | 1
MEM0821-PWPp-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 16640 | h | 223 | 1
MEM0821-PWPp-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 16640 | h | 223 | 1
MEM0821-PWPp-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 16640 | h | 223 | 1
MEM0821-PWPp-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 16640 | h | 223 | 1
MEM0821-PWPp-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 11175 | h | 223 | 1
MEM0821-PWPp-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 11175 | h | 223 | 1
MEM0821-PWPp-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 11175 | h | 223 | 1
MEM0821-PWPp-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 11175 | h | 223 | 1
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 49639 | h | 223 | 1
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 49639 | h | 223 | 1
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 49639 | h | 223 | 1
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 49639 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 24819 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 24819 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 43663 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5045 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 5046 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 5046 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 12229 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 20905 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-12 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-12 | 20905 | h | 223 | 1
ESD0800-CWP-482 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 1520 | h | 223 | 1
ESD0800-CWP-482 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 1520 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 978 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 978 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 265 | h | 223 | 1
MSD0820-CWP-055 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 265 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 14241 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 14241 | h | 223 | 1
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 17396 | h | 223 | 1
CDC0821-CWP-069 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 17396 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 164 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 164 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 429 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 429 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 77 | h | 223 | 1
MEM0821-CWP-077 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 77 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 162 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 162 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 59 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 59 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 54 | h | 223 | 1
MEM0821-CWP-080 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 54 | h | 223 | 1
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 3224 | h | 223 | 1
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 3224 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 960 | h | 223 | 1
MSD0822-CWP-508 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 80 | h | 223 | 1
MSD0822-CWP-508 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 80 | h | 223 | 1
MSD0822-CWP-509 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 17508 | h | 223 | 1
MSD0822-CWP-509 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 17508 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 6822 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 10934 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 10934 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 9760 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 14795 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 14795 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 1085 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 1085 | h | 223 | 1
MSD0822-CWP-203 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 1440 | h | 223 | 1
MSD0822-CWP-203 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 1440 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 10859 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 10859 | h | 223 | 1
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 5280 | h | 223 | 1
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 5280 | h | 223 | 1
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 367 | h | 223 | 1
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 367 | h | 223 | 1
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 300 | h | 223 | 1
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 300 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 5039 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 61 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 61 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 951 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 951 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 982 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 982 | h | 223 | 1
MSD0822-CWP-238 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 679 | h | 223 | 1
MSD0822-CWP-238 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 679 | h | 223 | 1
MSD0822-CWP-241 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 1018 | h | 223 | 1
MSD0822-CWP-241 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 1018 | h | 223 | 1
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 2818 | h | 223 | 1
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 2818 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 85 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 85 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 73 | h | 223 | 1
CDC0827-CWP-351 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 73 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 136 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 18 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 18 | h | 223 | 1
EEE1062-CWP-382 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 54 | h | 223 | 1
EEE1062-CWP-382 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 54 | h | 223 | 1
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 84 | h | 223 | 1
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 84 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 67 | h | 223 | 1
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 33 | h | 223 | 1
CDC1214-CWP-391 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 33 | h | 223 | 1
ESD1214-CWP-488 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 362 | h | 223 | 1
ESD1214-CWP-488 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 362 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 24 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 24 | h | 223 | 1
ESD0600-CWP-479 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 165 | h | 223 | 1
ESD0600-CWP-479 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 165 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 760 | h | 223 | 1
MSD0622-CWP-005 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 760 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 872 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-12 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-12 | 872 | h | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-19 | 179 | m | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-19 | 179 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-19 | 10 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-19 | 10 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-19 | 3 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-19 | 3 | m | 223 | 1
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-19 | 2 | m | 223 | 1
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-19 | 2 | m | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-11-19 | 17 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-11-19 | 17 | t | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-11-19 | 8 | m | 223 | 1
TTU0821-CWP-079 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-11-19 | 8 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | Budgeted Units | 2023-11-19 | 12 | m | 223 | 1
EEE0821-CWP-078 | CABLAGEM - WIRING | Material | At Completion Units | 2023-11-19 | 12 | m | 223 | 1
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2023-11-19 | 6 | un | 223 | 1
JIL0822-CWP-217 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2023-11-19 | 6 | un | 223 | 1
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2023-11-19 | 3 | m | 223 | 1
JIL0822-CWP-225 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2023-11-19 | 3 | m | 223 | 1
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-11-19 | 3 | t | 223 | 1
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-11-19 | 3 | t | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-19 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-19 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-19 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-19 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-19 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-19 | 0 | un | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 17 | t | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 17 | t | 223 | 1
MSD0822-CWP-508 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 1 | t | 223 | 1
MSD0822-CWP-508 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 1 | t | 223 | 1
MSD0822-CWP-509 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 22 | t | 223 | 1
MSD0822-CWP-509 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 22 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 12 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 1 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 1 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 1 | t | 223 | 1
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 3683 | Meter | 223 | 1
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 3683 | Meter | 223 | 1
ESD0800-CWP-483 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 23750 | Meter | 223 | 1
ESD0800-CWP-483 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 23750 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 3363 | Meter | 223 | 1
JSD0822-CWP-484 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 3363 | Meter | 223 | 1
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 877 | Meter | 223 | 1
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 877 | Meter | 223 | 1
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-19 | 400 | Meter | 223 | 1
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-19 | 400 | Meter | 223 | 1
EEE1062-CWP-382 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2023-11-19 | 1 | unid | 223 | 1
EEE1062-CWP-382 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2023-11-19 | 1 | unid | 223 | 1
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-11-19 | 19 | t | 223 | 1
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-11-19 | 19 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-11-19 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-11-19 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-11-19 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-11-19 | 8 | t | 223 | 1
ESD0800-CWP-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2534104 | h | 223 | 1
ESD0800-CWP-483 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2534104 | h | 223 | 1
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2387 | h | 223 | 1
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2387 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5787 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23710 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23710 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 33564 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 47816 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 88671 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 88671 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 88671 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 88671 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12546 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 334815 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 345326 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 345326 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 80256 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 50986 | h | 223 | 1
SES0821-EWPc-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 50986 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 56105 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 19066 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 19066 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 9894 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 9894 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2359 | h | 223 | 1
EEE0821-CWP-078 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2359 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 865 | h | 223 | 1
TTU0821-CWP-079 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 865 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3209 | h | 223 | 1
MEM0821-CWP-080 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3209 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 334815 | h | 223 | 1
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 375243 | h | 223 | 1
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 375243 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12546 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 56105 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 34059 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 34059 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3041 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 20435 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23279 | h | 223 | 1
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 38100 | h | 223 | 1
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 38100 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 41955 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39594 | h | 223 | 1
MEM0823-EWPc-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39594 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1158 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 51089 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 257322 | h | 223 | 1
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 83078 | h | 223 | 1
MEM0822-PWPe-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 83078 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 33564 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 35601 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23980 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 51089 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 51089 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 67928 | h | 223 | 1
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2387 | h | 223 | 1
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2387 | h | 223 | 1
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 51089 | h | 223 | 1
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 51089 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 31643 | h | 223 | 1
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 51089 | h | 223 | 1
MEM0822-EWPc-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 6479 | h | 223 | 1
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 51089 | h | 223 | 1
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 51089 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 6479 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39158 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39158 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 160509 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 265130 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 265130 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3754 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 28669 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 28669 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 9789 | h | 223 | 1
MCD0822-PWPp-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 9789 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5787 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3061 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3061 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 21767 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 62703 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1277 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1277 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 14319 | h | 223 | 1
KMT0822-PWPe-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 14319 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2857 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 26319 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 26319 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 263310 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 263310 | h | 223 | 1
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 25607 | h | 223 | 1
JIL0822-CWP-217 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 25607 | h | 223 | 1
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1778 | h | 223 | 1
MEM0822-CWP-223 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1778 | h | 223 | 1
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1455 | h | 223 | 1
JIL0822-CWP-225 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1455 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 380 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 147365 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 147365 | h | 223 | 1
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 147365 | h | 223 | 1
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 147365 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 460009 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 460009 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 20029 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 147365 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 147365 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2627 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2525 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2525 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 6120 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1446 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1446 | h | 223 | 1
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2387 | h | 223 | 1
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2387 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 56105 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5787 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 84735 | h | 223 | 1
SES0823-EWPc-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 84735 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 49467 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23052 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23052 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23570 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2525 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2525 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 6120 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2525 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2525 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 6120 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 132628 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 132628 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5895 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23279 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 20029 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5895 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 129235 | h | 223 | 1
MEM0826-EWPc-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 129235 | h | 223 | 1
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2387 | h | 223 | 1
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2387 | h | 223 | 1
MSD0822-CWP-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 41143 | h | 223 | 1
MSD0822-CWP-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 41143 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 18517 | h | 223 | 1
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 68345 | h | 223 | 1
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 68345 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 69966 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 69966 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 26668 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 26668 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 26668 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 26668 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 69966 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 69966 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 26237 | h | 223 | 1
EEL0827-EWPc-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 26237 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 22869 | h | 223 | 1
SES0827-EWPc-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 22869 | h | 223 | 1
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3297 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3297 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5895 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 564 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3297 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5492 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2627 | h | 223 | 1
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39772 | h | 223 | 1
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39772 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 39184 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 429 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 429 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 23570 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 18149 | h | 223 | 1
JPA1062-EWPc-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 18149 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 26189 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 13735 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 16546 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 16546 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 16546 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 16546 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 60635 | h | 223 | 1
EEE1062-CWP-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3399 | h | 223 | 1
EEE1062-CWP-382 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3399 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 26477 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 6946 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 6946 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 15875 | h | 223 | 1
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 9053 | h | 223 | 1
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 9053 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1617 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 479 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 7418 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2781 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2781 | h | 223 | 1
SUWP-AS-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 11190 | h | 223 | 1
SUWP-AS-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 11190 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 804 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 804 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 592 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 592 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 168 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 168 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 33027 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 75 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 75 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 14752 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1577 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1577 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1317 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1317 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 98 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 98 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 49 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 49 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 1347 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 1347 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 635 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 635 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3993 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3993 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 170 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 170 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 52095 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3093 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 257739 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 257739 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 114551 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3041 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 3012 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 59114 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 59114 | h | 223 | 1
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 118227 | h | 223 | 1
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 118227 | h | 223 | 1
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 118227 | h | 223 | 1
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 118227 | h | 223 | 1
MEM0821-PWPp-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 78222 | h | 223 | 1
MEM0821-PWPp-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 78222 | h | 223 | 1
MEM0821-PWPp-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 78222 | h | 223 | 1
MEM0821-PWPp-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 78222 | h | 223 | 1
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 18614 | h | 223 | 1
EEE1052-EWPc-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 18614 | h | 223 | 1
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 18614 | h | 223 | 1
EEE1063-EWPc-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 18614 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 24819 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 24819 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 43663 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5045 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 5046 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 5046 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 12229 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 20905 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-19 | 20905 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-19 | 20905 | h | 223 | 1
ESD0800-CWP-482 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 47105 | h | 223 | 1
ESD0800-CWP-482 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 47105 | h | 223 | 1
ESD0800-CWP-483 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 104504 | h | 223 | 1
ESD0800-CWP-483 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 104504 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 978 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 978 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 14241 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 14241 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 786 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 786 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 429 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 429 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 97 | h | 223 | 1
EEE0821-CWP-078 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 97 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 36 | h | 223 | 1
TTU0821-CWP-079 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 36 | h | 223 | 1
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 15475 | h | 223 | 1
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 15475 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 960 | h | 223 | 1
MSD0822-CWP-508 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 80 | h | 223 | 1
MSD0822-CWP-508 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 80 | h | 223 | 1
MSD0822-CWP-509 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 17508 | h | 223 | 1
MSD0822-CWP-509 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 17508 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 6822 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 10934 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 10934 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 9760 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 14795 | h | 223 | 1
JSD0822-CWP-484 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 14795 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 1085 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 1085 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 10859 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 10859 | h | 223 | 1
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 1056 | h | 223 | 1
JIL0822-CWP-217 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 1056 | h | 223 | 1
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 73 | h | 223 | 1
MEM0822-CWP-223 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 73 | h | 223 | 1
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 60 | h | 223 | 1
JIL0822-CWP-225 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 60 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 5039 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 61 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 61 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 951 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 951 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 982 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 982 | h | 223 | 1
MSD0822-CWP-241 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 1697 | h | 223 | 1
MSD0822-CWP-241 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 1697 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 2337 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 2337 | h | 223 | 1
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 2818 | h | 223 | 1
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 2818 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 136 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 136 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 18 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 18 | h | 223 | 1
EEE1062-CWP-382 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 138 | h | 223 | 1
EEE1062-CWP-382 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 138 | h | 223 | 1
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 373 | h | 223 | 1
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 373 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 67 | h | 223 | 1
ESD1214-CWP-488 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 11214 | h | 223 | 1
ESD1214-CWP-488 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 11214 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 968 | h | 223 | 1
ESD0600-CWP-479 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 5115 | h | 223 | 1
ESD0600-CWP-479 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 5115 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 872 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-19 | 872 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-19 | 872 | h | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-26 | 179 | m | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-26 | 179 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-26 | 10 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-26 | 10 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-26 | 3 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-26 | 3 | m | 223 | 1
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-11-26 | 2 | m | 223 | 1
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-11-26 | 2 | m | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-11-26 | 17 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-11-26 | 17 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-11-26 | 0 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-11-26 | 0 | t | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | Budgeted Units | 2023-11-26 |  |  | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | At Completion Units | 2023-11-26 |  |  | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-11-26 | 1 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-11-26 | 1 | t | 223 | 1
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-11-26 | 1 | t | 223 | 1
MEM0827-CWP-368 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-11-26 | 1 | t | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-26 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-26 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-26 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-26 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-11-26 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-11-26 | 0 | un | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-26 | 17 | t | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-26 | 17 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-26 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-26 | 12 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-26 | 0 | t | 223 | 1
MSD0823-CWP-586 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-26 | 0 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-26 | 0 | t | 223 | 1
MSD0824-CWP-587 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-26 | 0 | t | 223 | 1
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-26 | 3683 | Meter | 223 | 1
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-26 | 3683 | Meter | 223 | 1
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-26 | 877 | Meter | 223 | 1
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-26 | 877 | Meter | 223 | 1
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-11-26 | 400 | Meter | 223 | 1
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-11-26 | 400 | Meter | 223 | 1
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-11-26 | 19 | t | 223 | 1
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-11-26 | 19 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-11-26 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-11-26 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-11-26 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-11-26 | 8 | t | 223 | 1
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2387 | h | 223 | 1
EEE0800-PWPe-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2387 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5787 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-EWPc-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MCD0817-EWPc-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
STP0817-EWPc-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MMR0817-EWPc-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-EWPc-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-EWPc-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-EWPc-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-EWPc-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MCD0817-EWPc-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MMR0817-EWPc-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-EWPc-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
ELU0817-EWPc-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
JIL0817-EWPc-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MMR0817-EWPc-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0817-EWPc-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23710 | h | 223 | 1
ESD0820-CWP-057 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23710 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 11321 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 11321 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 47816 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 88671 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 88671 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 88671 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 88671 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12546 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 334815 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 345326 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 345326 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 80256 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 56105 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 19066 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 19066 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 9894 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 9894 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 334815 | h | 223 | 1
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 375243 | h | 223 | 1
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 375243 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12546 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 55419 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 55419 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 56105 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 34059 | h | 223 | 1
MCD0822-EWPc-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 34059 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 34059 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2091 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2091 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3041 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 20435 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 31930 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 31930 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23279 | h | 223 | 1
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 38100 | h | 223 | 1
MEM0822-PWPe-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 38100 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 41955 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1158 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 257322 | h | 223 | 1
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 33564 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 35601 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23980 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 67928 | h | 223 | 1
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2387 | h | 223 | 1
EEE0822-PWPe-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2387 | h | 223 | 1
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 31643 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 6479 | h | 223 | 1
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 6479 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 39158 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 39158 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 160509 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 265130 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 265130 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3754 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 39158 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 39158 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5787 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3061 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3061 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 21767 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 62703 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 51089 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 51089 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2857 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 26319 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 26319 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 263310 | h | 223 | 1
TTU0822-CWP-205 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 263310 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 380 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 92103 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 92103 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 147365 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 147365 | h | 223 | 1
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 147365 | h | 223 | 1
MEM0823-EWPc-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 147365 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 322007 | h | 223 | 1
SSD0823-CWP-477 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 322007 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2091 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2091 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 20029 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 92103 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 92103 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 147365 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 147365 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2627 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2525 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2525 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 6120 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1446 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1446 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3971 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3971 | h | 223 | 1
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2387 | h | 223 | 1
EEE0823-PWPe-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2387 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 56105 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5787 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 49467 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23052 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23052 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23570 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 82893 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 82893 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2525 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2525 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 6120 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2525 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2525 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 6120 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 49736 | h | 223 | 1
MEM0824-EWPc-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 49736 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5895 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 82893 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 82893 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23279 | h | 223 | 1
MSD0826-CWP-288 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 20029 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5895 | h | 223 | 1
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2387 | h | 223 | 1
EEE0826-PWPe-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2387 | h | 223 | 1
MSD0822-CWP-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 32915 | h | 223 | 1
MSD0822-CWP-241 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 32915 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 18517 | h | 223 | 1
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 25629 | h | 223 | 1
MEM0827-CWP-368 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 25629 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1746 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1746 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MCD0827-EWPc-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MMR0827-EWPc-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MMR0827-EWPc-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 69966 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 69966 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0827-EWPc-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MCD0827-EWPc-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 26668 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 26668 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 18572 | h | 223 | 1
MEM0827-PWPl-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 18572 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 69966 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 69966 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
STP0827-EWPc-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0827-EWPc-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
ELU0827-EWPc-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
JIL0827-EWPc-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 39772 | h | 223 | 1
MEM0827-EWPc-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 39772 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 24858 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 24858 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MMR0827-EWPc-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
STP0827-EWPc-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3297 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3297 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5895 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 564 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3297 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0827-EWPc-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0827-EWPc-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5492 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14915 | h | 223 | 1
SES0827-EWPc-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14915 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 39772 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 39772 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2627 | h | 223 | 1
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 39772 | h | 223 | 1
JIL0827-EWPc-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 39772 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 39184 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 429 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 429 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 26189 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 13735 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 13735 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 16546 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 16546 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 16546 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 16546 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 60635 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 26477 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 6946 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 6946 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 15875 | h | 223 | 1
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 9053 | h | 223 | 1
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 9053 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1617 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 479 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 7418 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 7418 | h | 223 | 1
SUWP-AS-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 51640 | h | 223 | 1
SUWP-AS-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 51640 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2781 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2781 | h | 223 | 1
SUWP-AS-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3730 | h | 223 | 1
SUWP-AS-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3730 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 804 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 804 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 592 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 592 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 168 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 168 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 33027 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 75 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 75 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 14752 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1577 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1577 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1317 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1317 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 98 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 98 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 28 | h | 223 | 1
SUWP-AC-PF-0604 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 28 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1347 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1347 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 635 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 635 | h | 223 | 1
SUWP-AS-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3160 | h | 223 | 1
SUWP-AS-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3160 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3993 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3993 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 170 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 170 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2817 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2817 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 52095 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3093 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 257739 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 257739 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 114551 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3041 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 3012 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 30539 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 30539 | h | 223 | 1
SES0822-PWPl-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 167819 | h | 223 | 1
SES0822-PWPl-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 167819 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 59114 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 59114 | h | 223 | 1
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 118227 | h | 223 | 1
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 118227 | h | 223 | 1
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 118227 | h | 223 | 1
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 118227 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 24819 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 24819 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 43663 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0821-PWPe-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0823-PWPe-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0824-PWPe-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0827-PWPe-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0822-PWPe-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0823-PWPe-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0824-PWPe-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0622-PWPe-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 1892 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 12229 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 10453 | h | 223 | 1
MSD0823-CWP-586 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 10453 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-11-26 | 10453 | h | 223 | 1
MSD0824-CWP-587 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-11-26 | 10453 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 978 | h | 223 | 1
ESD0820-CWP-057 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 978 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 467 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 467 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 14241 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 14241 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 786 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 786 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 429 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 429 | h | 223 | 1
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 15475 | h | 223 | 1
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 15475 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 960 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 6822 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 10934 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 10934 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 9760 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 1085 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 1085 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 10859 | h | 223 | 1
TTU0822-CWP-205 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 10859 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 5039 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 61 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 61 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 166 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 166 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 951 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 951 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 785 | h | 223 | 1
MSD0826-CWP-288 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 785 | h | 223 | 1
MSD0822-CWP-241 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 1357 | h | 223 | 1
MSD0822-CWP-241 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 1357 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 2337 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 2337 | h | 223 | 1
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 1057 | h | 223 | 1
MEM0827-CWP-368 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 1057 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 72 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 72 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 136 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 136 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 18 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 18 | h | 223 | 1
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 373 | h | 223 | 1
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 373 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 67 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 968 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 349 | h | 223 | 1
MSD0823-CWP-586 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 349 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-11-26 | 349 | h | 223 | 1
MSD0824-CWP-587 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-11-26 | 349 | h | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-03 | 179 | m | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-03 | 179 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-03 | 10 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-03 | 10 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-03 | 3 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-03 | 3 | m | 223 | 1
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-03 | 1 | m | 223 | 1
CPI1214-CWP-405 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-03 | 1 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-03 | 0 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-03 | 0 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-12-03 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-12-03 | 13 | m | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-03 | 17 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-03 | 17 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-03 | 1 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-03 | 1 | t | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | Budgeted Units | 2023-12-03 |  |  | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | At Completion Units | 2023-12-03 |  |  | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-03 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-03 | 3 | t | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-12-03 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-12-03 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-12-03 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-12-03 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-12-03 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-12-03 | 0 | un | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-03 | 11 | t | 223 | 1
MSD0821-CWP-065 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-03 | 11 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-03 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-03 | 12 | t | 223 | 1
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-03 | 3591 | Meter | 223 | 1
ESD0800-CWP-482 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-03 | 3591 | Meter | 223 | 1
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-03 | 855 | Meter | 223 | 1
ESD1214-CWP-488 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-03 | 855 | Meter | 223 | 1
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-03 | 390 | Meter | 223 | 1
ESD0600-CWP-479 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-03 | 390 | Meter | 223 | 1
ESD0600-CWP-480 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-03 | 60 | Meter | 223 | 1
ESD0600-CWP-480 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-03 | 60 | Meter | 223 | 1
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-12-03 | 15 | t | 223 | 1
CDC0821-CWP-468 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-12-03 | 15 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-12-03 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-12-03 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-12-03 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-12-03 | 8 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5787 | h | 223 | 1
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 40073 | h | 223 | 1
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 40073 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5463 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 56606 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 47816 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 88671 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 88671 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 88671 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 88671 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12546 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 334815 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 215829 | h | 223 | 1
MSD0821-CWP-065 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 215829 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 80256 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 56105 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 19066 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 19066 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5936 | h | 223 | 1
MEM0821-CWP-076 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5936 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 334815 | h | 223 | 1
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 297067 | h | 223 | 1
CDC0821-CWP-468 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 297067 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12546 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 88671 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 56105 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 19584 | h | 223 | 1
SES0821-EWPc-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 19584 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2856 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2856 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3041 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 20435 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 51089 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 51089 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23279 | h | 223 | 1
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 41955 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 1158 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 257322 | h | 223 | 1
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 33564 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 35601 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23980 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 67928 | h | 223 | 1
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 51089 | h | 223 | 1
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 31643 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 6479 | h | 223 | 1
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-EWPc-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 6479 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 39158 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 39158 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 160509 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 265130 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 265130 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3754 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 39158 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 39158 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5787 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3061 | h | 223 | 1
JIL0822-EWPc-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3061 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 21767 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 62703 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 51089 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 51089 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2857 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 26319 | h | 223 | 1
MSD0822-CWP-200 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 26319 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 380 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 147365 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 147365 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 147365 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 147365 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2856 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2856 | h | 223 | 1
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 147365 | h | 223 | 1
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 20029 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 147365 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 147365 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 147365 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 147365 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2627 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2525 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2525 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 6120 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 1386 | h | 223 | 1
CDC0823-CWP-262 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 1386 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 19856 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 19856 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 56105 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5787 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 49467 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23052 | h | 223 | 1
MSD0822-CWP-230 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23052 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23570 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 132628 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 132628 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2525 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2525 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 6120 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2525 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2525 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 6120 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5895 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 132628 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 132628 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23279 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 20029 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5895 | h | 223 | 1
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 166755 | h | 223 | 1
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 166755 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 18517 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 7760 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 7760 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 69966 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 69966 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 26668 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 26668 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 69966 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 69966 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 39772 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3297 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3297 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5895 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 564 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3297 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5492 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 39772 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 39772 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2627 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 39184 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 429 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 429 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 26189 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 8241 | h | 223 | 1
EEE1062-PWPp-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 8241 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 16546 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 16546 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 16546 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 16546 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 60635 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 4145 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 4145 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 6141 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 6141 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 26477 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 16411 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 16411 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5383 | h | 223 | 1
MEM1214-PWPe-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5383 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 15875 | h | 223 | 1
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 7016 | h | 223 | 1
CPI1214-CWP-405 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 7016 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 1617 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2689 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2689 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 479 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 459 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 459 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 7233 | h | 223 | 1
TTU1215-PWPp-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 7233 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2781 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2781 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 804 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 804 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 592 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 592 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 168 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 168 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 33027 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 75 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 75 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 14752 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 14752 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 1577 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 1577 | h | 223 | 1
SUWP-AS-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 1832 | h | 223 | 1
SUWP-AS-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 1832 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 1317 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 1317 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 98 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 98 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 1347 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 1347 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 635 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 635 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3993 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3993 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 170 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 170 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 4508 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 4508 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 52095 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3093 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 257739 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 257739 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 114551 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3041 | h | 223 | 1
ESD0600-CWP-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 6402 | h | 223 | 1
ESD0600-CWP-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 6402 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 3012 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 48863 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 48863 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 59114 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 59114 | h | 223 | 1
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 115272 | h | 223 | 1
MEM0821-EWPc-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 115272 | h | 223 | 1
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 115272 | h | 223 | 1
MEM0821-EWPc-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 115272 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 19235 | h | 223 | 1
EEE1061-EWPc-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 19235 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 43663 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-03 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-03 | 12229 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 2334 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 8901 | h | 223 | 1
MSD0821-CWP-065 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 8901 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 786 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 786 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 172 | h | 223 | 1
MEM0821-CWP-076 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 172 | h | 223 | 1
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 12251 | h | 223 | 1
CDC0821-CWP-468 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 12251 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 960 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 6822 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 10934 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 10934 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 9760 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 1085 | h | 223 | 1
MSD0822-CWP-200 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 1085 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 5039 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 49 | h | 223 | 1
CDC0823-CWP-262 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 49 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 829 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 829 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 951 | h | 223 | 1
MSD0822-CWP-230 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 951 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 982 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 982 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 2337 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 2337 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 320 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 320 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 136 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 136 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 18 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 18 | h | 223 | 1
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 289 | h | 223 | 1
CPI1214-CWP-405 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 289 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 67 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 111 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 111 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 968 | h | 223 | 1
ESD0600-CWP-480 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-03 | 1320 | h | 223 | 1
ESD0600-CWP-480 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-03 | 1320 | h | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-10 | 179 | m | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-10 | 179 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-10 | 10 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-10 | 10 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-10 | 3 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-10 | 3 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-10 | 2 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-10 | 2 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-12-10 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-12-10 | 13 | m | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-10 | 4 | t | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-10 | 4 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-10 | 17 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-10 | 17 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-10 | 1 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-10 | 1 | t | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | Budgeted Units | 2023-12-10 |  |  | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | At Completion Units | 2023-12-10 |  |  | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-10 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-10 | 3 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-10 | 2 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-10 | 2 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-10 | 2 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-10 | 2 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-10 | 2 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-10 | 2 | t | 223 | 1
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-10 | 35 | t | 223 | 1
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-10 | 35 | t | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-12-10 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-12-10 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-12-10 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-12-10 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-12-10 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-12-10 | 0 | un | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-10 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-10 | 12 | t | 223 | 1
ESD0600-CWP-480 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-10 | 2340 | Meter | 223 | 1
ESD0600-CWP-480 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-10 | 2340 | Meter | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-12-10 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-12-10 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-12-10 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-12-10 | 8 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5787 | h | 223 | 1
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 40073 | h | 223 | 1
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 40073 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5463 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 56606 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 47816 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 33251 | h | 223 | 1
MEM0821-EWPc-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 33251 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 86454 | h | 223 | 1
MEM0821-EWPc-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 86454 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12546 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 334815 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 80256 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 56105 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 19066 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 19066 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 334815 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12546 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 88671 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 56105 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2856 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2856 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3041 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 20435 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 51089 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 51089 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23279 | h | 223 | 1
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 51089 | h | 223 | 1
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 51089 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 41955 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1158 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 19158 | h | 223 | 1
MEM0822-EWPc-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 19158 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 257322 | h | 223 | 1
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 51089 | h | 223 | 1
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 51089 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 33564 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 59400 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 59400 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 35601 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23980 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 19158 | h | 223 | 1
MEM0822-EWPc-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 19158 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 67928 | h | 223 | 1
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 51089 | h | 223 | 1
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 51089 | h | 223 | 1
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 51089 | h | 223 | 1
MEM0822-EWPc-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 51089 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 31643 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 6479 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 32865 | h | 223 | 1
EEE0822-PWPl-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 32865 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 160509 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 265130 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 265130 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3754 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 39158 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 39158 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5787 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 21767 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 62703 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 51089 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 51089 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12244 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1582 | h | 223 | 1
MEM0822-PWPl-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1582 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 56159 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 56159 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12244 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1582 | h | 223 | 1
MEM0822-PWPl-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1582 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 56159 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 56159 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12244 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1582 | h | 223 | 1
MEM0822-PWPl-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1582 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 45942 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 45942 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2857 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 380 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 147365 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 147365 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 143681 | h | 223 | 1
MEM0823-EWPc-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 143681 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2856 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2856 | h | 223 | 1
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 147365 | h | 223 | 1
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 20029 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 147365 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 147365 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 143681 | h | 223 | 1
MEM0823-EWPc-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 143681 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2627 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 92103 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 92103 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 947 | h | 223 | 1
MCD0823-PWPe-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 947 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 6120 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 19856 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 19856 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 56105 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5787 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23570 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 132628 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 132628 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 82893 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 82893 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 947 | h | 223 | 1
MCD0824-PWPe-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 947 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 6120 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 82893 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 82893 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 947 | h | 223 | 1
MCD0824-PWPe-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 947 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 6120 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5895 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 132628 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 132628 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23279 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 20029 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5895 | h | 223 | 1
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 166755 | h | 223 | 1
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 166755 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 18517 | h | 223 | 1
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 696136 | h | 223 | 1
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 696136 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 7760 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 7760 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 69966 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 69966 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3333 | h | 223 | 1
MCD0827-PWPl-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3333 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 69966 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 69966 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 39772 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3297 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3297 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5895 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 564 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3297 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5492 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 38778 | h | 223 | 1
MEM0827-EWPc-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 38778 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2627 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 39184 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 429 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 429 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 26189 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 16546 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 16546 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 16546 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 16546 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 60635 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5024 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5024 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 7444 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 26477 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 72937 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 72937 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 15875 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 15901 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 15901 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 4850 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 4850 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1617 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1617 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 11950 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 11950 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 479 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 479 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2856 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2856 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2781 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2781 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 804 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 804 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 592 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 592 | h | 223 | 1
SUWP-AS-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2346 | h | 223 | 1
SUWP-AS-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2346 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 168 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 168 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 33027 | h | 223 | 1
SUWP-AS-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1038 | h | 223 | 1
SUWP-AS-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1038 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 75 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 75 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 4215 | h | 223 | 1
SUWP-AS-PF-2001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 4215 | h | 223 | 1
SUWP-AS-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 21972 | h | 223 | 1
SUWP-AS-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 21972 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1577 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1577 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1317 | h | 223 | 1
SUWP-AC-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1317 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 98 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 98 | h | 223 | 1
SUWP-AS-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 25008 | h | 223 | 1
SUWP-AS-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 25008 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 1347 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 1347 | h | 223 | 1
SUWP-AS-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 11792 | h | 223 | 1
SUWP-AS-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 11792 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 635 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 635 | h | 223 | 1
SUWP-AS-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 55614 | h | 223 | 1
SUWP-AS-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 55614 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3993 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3993 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 170 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 170 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 4508 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 4508 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 52095 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3093 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 251296 | h | 223 | 1
MEM0623-EWPc-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 251296 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 114551 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3041 | h | 223 | 1
ESD0600-CWP-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 249670 | h | 223 | 1
ESD0600-CWP-480 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 249670 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 3012 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 48863 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 48863 | h | 223 | 1
SES0822-PWPl-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 167819 | h | 223 | 1
SES0822-PWPl-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 167819 | h | 223 | 1
SES0822-PWPl-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 167819 | h | 223 | 1
SES0822-PWPl-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 167819 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 59114 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 59114 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 43663 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-10 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-10 | 12229 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 2334 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 786 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 786 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 960 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 2450 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 2450 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 6822 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 10934 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 10934 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 9760 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 2316 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 2316 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 2316 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 2316 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 1895 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 1895 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 5039 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 829 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 829 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 982 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 982 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 2337 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 2337 | h | 223 | 1
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 28708 | h | 223 | 1
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 28708 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 320 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 320 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 136 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 136 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 18 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 18 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 667 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 667 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 200 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 200 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 67 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 67 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 493 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 493 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 968 | h | 223 | 1
ESD0600-CWP-480 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-10 | 9240 | h | 223 | 1
ESD0600-CWP-480 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-10 | 9240 | h | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-17 | 149 | m | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-17 | 149 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-17 | 10 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-17 | 10 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-17 | 3 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-17 | 3 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-17 | 2 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-17 | 2 | m | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-17 | 14 | t | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-17 | 14 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-17 | 14 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-17 | 14 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-17 | 9 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-17 | 9 | t | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | Budgeted Units | 2023-12-17 |  |  | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | At Completion Units | 2023-12-17 |  |  | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-17 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-17 | 3 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-17 | 4 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-17 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-17 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-17 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-17 | 3 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-17 | 3 | t | 223 | 1
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-17 | 35 | t | 223 | 1
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-17 | 35 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-17 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-17 | 12 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-12-17 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-12-17 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-12-17 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-12-17 | 8 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5787 | h | 223 | 1
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 40073 | h | 223 | 1
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 40073 | h | 223 | 1
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 40073 | h | 223 | 1
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 40073 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 56606 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 47816 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12546 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 334815 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 24810 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 80256 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 56105 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 56105 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 15889 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 15889 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 334815 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12546 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 88671 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3041 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3041 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 56105 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 56105 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2856 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2856 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3041 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3041 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 20435 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 51089 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 51089 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23279 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 21713 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 21713 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 21713 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 21713 | h | 223 | 1
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 51089 | h | 223 | 1
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 51089 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 41955 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 1158 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 1158 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 257322 | h | 223 | 1
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 51089 | h | 223 | 1
MEM0822-EWPc-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 51089 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 86314 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 21713 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 21713 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 21713 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 21713 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 33564 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 220001 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 220001 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 35601 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23980 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 67928 | h | 223 | 1
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 51089 | h | 223 | 1
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 51089 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 31643 | h | 223 | 1
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 51089 | h | 223 | 1
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 6479 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 160509 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 220942 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 220942 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3754 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 21677 | h | 223 | 1
MCD0822-PWPl-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 21677 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5787 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 21767 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 62703 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 49812 | h | 223 | 1
KMT0822-EWPc-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 49812 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 136732 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 136732 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12244 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 83820 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 83820 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12244 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 83820 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 83820 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12244 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 68570 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 68570 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2857 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 380 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 380 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 147365 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 147365 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2856 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2856 | h | 223 | 1
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 147365 | h | 223 | 1
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 20029 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 147365 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 147365 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2627 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 147365 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 147365 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 6120 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 56105 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 56105 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5787 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23570 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 132628 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 132628 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 132628 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 132628 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 6120 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 132628 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 132628 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 6120 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5895 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 132628 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 132628 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23279 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 20029 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5895 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5895 | h | 223 | 1
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 166755 | h | 223 | 1
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 166755 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 18517 | h | 223 | 1
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 696136 | h | 223 | 1
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 696136 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 7760 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 7760 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 26237 | h | 223 | 1
MEM0827-EWPc-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 26237 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 69966 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 69966 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 56105 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 56105 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3040 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3040 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 26237 | h | 223 | 1
MEM0827-EWPc-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 26237 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 39772 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 39772 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3297 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3297 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5895 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 564 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3297 | h | 223 | 1
MSD0827-CWP-353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2627 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 39184 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 429 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 429 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 26189 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5036 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5036 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 16546 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 16546 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 16546 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 16546 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 60635 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5024 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5024 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 7444 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 8377 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 8377 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 30998 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 30998 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 30998 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 30998 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 48624 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 48624 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 26477 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 72937 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 72937 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 15875 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 48624 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 48624 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 121 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 121 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 9959 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 9959 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 292 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 292 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 467 | h | 223 | 1
JIL1214-PWPp-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 467 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2856 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2856 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2781 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2781 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 804 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 804 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 592 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 592 | h | 223 | 1
SUWP-AS-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 782 | h | 223 | 1
SUWP-AS-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 782 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 168 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 168 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 33027 | h | 223 | 1
SUWP-AS-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 10992 | h | 223 | 1
SUWP-AS-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 10992 | h | 223 | 1
SUWP-AS-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 346 | h | 223 | 1
SUWP-AS-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 346 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 75 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 75 | h | 223 | 1
SUWP-AS-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 7324 | h | 223 | 1
SUWP-AS-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 7324 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 1577 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 1577 | h | 223 | 1
SUWP-AS-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 7643 | h | 223 | 1
SUWP-AS-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 7643 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 98 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 98 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 1347 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 1347 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 635 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 635 | h | 223 | 1
SUWP-AS-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 18538 | h | 223 | 1
SUWP-AS-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 18538 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3993 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3993 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 170 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 170 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 4508 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 4508 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 11040 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 11040 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 52095 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 52095 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3093 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 114551 | h | 223 | 1
TTU0623-EWPc-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 114551 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 48684 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 48684 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3041 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3041 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 3012 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 48863 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 48863 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 59114 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 59114 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 59114 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 43663 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-17 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-17 | 12229 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 2334 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 655 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 655 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 960 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 9073 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 9073 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 6822 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 9111 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 9111 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 9760 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 5451 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 5451 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 3457 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 3457 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 3457 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 3457 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 2828 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 2828 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 5039 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 982 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 982 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 2337 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 2337 | h | 223 | 1
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 28708 | h | 223 | 1
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 28708 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 320 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 320 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 136 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 136 | h | 223 | 1
MSD0827-CWP-353 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 136 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 18 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 18 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 411 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 411 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-17 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-17 | 968 | h | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-24 | 10 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-24 | 10 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-24 | 3 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-24 | 3 | m | 223 | 1
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-12-24 | 41 | m | 223 | 1
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-12-24 | 41 | m | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | Budgeted Units | 2023-12-24 |  |  | 223 | 1
MEM0827-CWP-360 | CALDEIRARIA (t) | Material | At Completion Units | 2023-12-24 |  |  | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-24 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-24 | 3 | t | 223 | 1
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-24 | 6 | t | 223 | 1
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-24 | 6 | t | 223 | 1
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-24 | 35 | t | 223 | 1
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-24 | 35 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-24 | 1 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-24 | 1 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-24 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-24 | 12 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-12-24 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-12-24 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-12-24 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-12-24 | 8 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5787 | h | 223 | 1
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 40073 | h | 223 | 1
EEE0800-EWPc-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 40073 | h | 223 | 1
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 40073 | h | 223 | 1
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 40073 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 56606 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 47816 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12546 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 335 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 335 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 334815 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 812 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 812 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 80256 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43481 | h | 223 | 1
SES0821-PWPp-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43481 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 334815 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12546 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 33251 | h | 223 | 1
MMR0821-EWPc-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 33251 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 47816 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 6557 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 6557 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3012 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 608 | h | 223 | 1
MCD0822-PWPp-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 608 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43481 | h | 223 | 1
SES0821-PWPp-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43481 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 1581 | h | 223 | 1
TTU0822-PWPl-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 1581 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 608 | h | 223 | 1
TTU0822-PWPp-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 608 | h | 223 | 1
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 4342 | h | 223 | 1
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 4342 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 20435 | h | 223 | 1
MEM0822-EWPc-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 20435 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 19158 | h | 223 | 1
MMR0822-EWPc-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 19158 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23279 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 51089 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 51089 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 51089 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 51089 | h | 223 | 1
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 51089 | h | 223 | 1
MEM0822-EWPc-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 51089 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 20029 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 41955 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 1129 | h | 223 | 1
MEM0823-PWPp-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 1129 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 86314 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 51089 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 51089 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 51089 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 33564 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 35601 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23980 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 67928 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 335 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 335 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 812 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 812 | h | 223 | 1
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 51089 | h | 223 | 1
EEE0822-EWPc-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 51089 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 31643 | h | 223 | 1
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 51089 | h | 223 | 1
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 6479 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 160509 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3754 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5787 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 21767 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 62703 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12244 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12244 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2857 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12244 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12244 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2857 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12244 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12244 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2857 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 19802 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 76 | h | 223 | 1
TTU0823-PWPp-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 76 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 55262 | h | 223 | 1
MMR0823-EWPc-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 55262 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 1581 | h | 223 | 1
TTU0823-PWPl-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 1581 | h | 223 | 1
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 147365 | h | 223 | 1
EEE0823-EWPc-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 147365 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 20029 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 55262 | h | 223 | 1
MMR0823-EWPc-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 55262 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2627 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 147365 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 147365 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 6120 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 335 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 335 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43481 | h | 223 | 1
SES0823-PWPp-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43481 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 812 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 812 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5787 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23570 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 49736 | h | 223 | 1
MMR0824-EWPc-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 49736 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 132628 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 132628 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 6120 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 132628 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 132628 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 6120 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5895 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5895 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 49736 | h | 223 | 1
MMR0824-EWPc-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 49736 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23279 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 20029 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 812 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 812 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23570 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5748 | h | 223 | 1
MEM0826-PWPp-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5748 | h | 223 | 1
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 166755 | h | 223 | 1
EEE0826-EWPc-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 166755 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 335 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 335 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 18517 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 335 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 335 | h | 223 | 1
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 113534 | h | 223 | 1
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 113534 | h | 223 | 1
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 696136 | h | 223 | 1
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 696136 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 6014 | h | 223 | 1
MEM0827-CWP-360 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 6014 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 69966 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 69966 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23570 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43481 | h | 223 | 1
SES0827-PWPp-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43481 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 19802 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 608 | h | 223 | 1
TTU0827-PWPp-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 608 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 812 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 812 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 14915 | h | 223 | 1
MMR0827-EWPc-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 14915 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 1237 | h | 223 | 1
MSD0827-CWP-302 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 1237 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5895 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5895 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 7659 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 7659 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 564 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3297 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2627 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 39184 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 429 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 429 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 26189 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 7050 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 7050 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 16546 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 16546 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 16546 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 16546 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 60635 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5024 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5024 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 7444 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 37229 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 37229 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 72937 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 72937 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 72937 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 72937 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 48624 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 48624 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 26477 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 72937 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 72937 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 15875 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 48624 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 48624 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 536 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 536 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 1299 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2856 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2856 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 1192 | h | 223 | 1
SUWP-AC-PF-0602 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 1192 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 459 | h | 223 | 1
SUWP-AC-PF-0702 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 459 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 592 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 592 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 168 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 168 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 33027 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 75 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 75 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 1577 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 1577 | h | 223 | 1
SUWP-AS-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 8917 | h | 223 | 1
SUWP-AS-PF-1138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 8917 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 98 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 98 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 1347 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 1347 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 635 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 635 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3993 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3993 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 170 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 170 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 140103 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 140103 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 4508 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 4508 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 49068 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 251608 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 19536 | h | 223 | 1
B29713 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 19536 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 7838 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 7838 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3093 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 114551 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 2627 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 608 | h | 223 | 1
TTU0623-PWPp-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 608 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 3012 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 48863 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 48863 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 33990 | h | 223 | 1
MEM0821-EWPc-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 33990 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 33990 | h | 223 | 1
MEM0821-EWPc-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 33990 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 43663 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-24 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-24 | 12229 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 2334 | h | 223 | 1
TTU0822-CWP-428 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 537 | h | 223 | 1
TTU0822-CWP-428 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 537 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 960 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 6822 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 9760 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 5039 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 982 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 982 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 2337 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 2337 | h | 223 | 1
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 4682 | h | 223 | 1
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 4682 | h | 223 | 1
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 28708 | h | 223 | 1
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 28708 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 248 | h | 223 | 1
MEM0827-CWP-360 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 248 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 51 | h | 223 | 1
MSD0827-CWP-302 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 51 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 954 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 954 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 136 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 136 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 18 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 18 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-24 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-24 | 968 | h | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-31 | 179 | m | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-31 | 179 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-31 | 10 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-31 | 10 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-31 | 3 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-31 | 3 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2023-12-31 | 2 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2023-12-31 | 2 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2023-12-31 | 10 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2023-12-31 | 10 | m | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-31 | 17 | t | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-31 | 17 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-31 | 17 | t | 223 | 1
SES0822-CWP-098 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-31 | 17 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-31 | 22 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-31 | 22 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2023-12-31 | 1 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2023-12-31 | 1 | t | 223 | 1
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2023-12-31 | 96 | m | 223 | 1
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2023-12-31 | 96 | m | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-31 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-31 | 3 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-31 | 4 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-31 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-31 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-31 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-31 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-31 | 4 | t | 223 | 1
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-31 | 6 | t | 223 | 1
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-31 | 6 | t | 223 | 1
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-31 | 35 | t | 223 | 1
MCD0827-CWP-359 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-31 | 35 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2023-12-31 | 2 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2023-12-31 | 2 | t | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-12-31 | 1 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-12-31 | 1 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-12-31 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-12-31 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2023-12-31 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2023-12-31 | 0 | un | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2023-12-31 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2023-12-31 | 12 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2023-12-31 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2023-12-31 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2023-12-31 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2023-12-31 | 8 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5787 | h | 223 | 1
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 40073 | h | 223 | 1
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 40073 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 4370 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 4370 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 56606 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 47816 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12546 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 536 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 536 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 334815 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1299 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 80256 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 19066 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 19066 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 334815 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12546 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 47816 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 335 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 335 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 21600 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 21600 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3012 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 335 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 335 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 10216 | h | 223 | 1
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 10216 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23279 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 51089 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 51089 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 51089 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 51089 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 20029 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 4898 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 4898 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 41955 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 72 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 72 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 19106 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 86314 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 51089 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 51089 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 51089 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 33564 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 264001 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 264001 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 35601 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 91548 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23980 | h | 223 | 1
ERE0822-PWPp-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23980 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 302 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 302 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1097 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1097 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 453 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 453 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1097 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1097 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 453 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 453 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1097 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1097 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 17514 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 67928 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 536 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 536 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 31643 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 955 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 955 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2314 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2314 | h | 223 | 1
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 51089 | h | 223 | 1
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 6479 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 37950 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 160509 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 254083 | h | 223 | 1
SES0822-CWP-098 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 254083 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23980 | h | 223 | 1
ERE0822-PWPp-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23980 | h | 223 | 1
ERE0822-PWPp-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23980 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3754 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5787 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 21767 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1377 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1377 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1377 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1377 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 62703 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 349104 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 349104 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 8163 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 8163 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2449 | h | 223 | 1
MEM0822-PWPp-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2449 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 100584 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 100584 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2857 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 8163 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 8163 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2449 | h | 223 | 1
MEM0822-PWPp-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2449 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 100584 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 100584 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2857 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 8163 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 8163 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2449 | h | 223 | 1
MEM0822-PWPp-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2449 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 82284 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 82284 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2857 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 335 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 335 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 19802 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 19802 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 20029 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2627 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 147365 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 147365 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 6120 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 15885 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 15885 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 536 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 536 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1299 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5787 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23570 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 132628 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 132628 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 6120 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 132628 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 132628 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 6120 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3390 | h | 223 | 1
MEM0824-PWPp-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3390 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23279 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 20029 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1299 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23570 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 536 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 536 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 18517 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 536 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 536 | h | 223 | 1
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 113534 | h | 223 | 1
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 113534 | h | 223 | 1
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 696136 | h | 223 | 1
MCD0827-CWP-359 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 696136 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 335 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 335 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 69966 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 69966 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 19802 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 19802 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3390 | h | 223 | 1
MEM0827-PWPp-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3390 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12255 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 564 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3297 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2627 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 39184 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 39184 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 429 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 429 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 7321 | h | 223 | 1
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3416 | h | 223 | 1
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3416 | h | 223 | 1
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3986 | h | 223 | 1
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3986 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 26189 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 7050 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 7050 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 9514 | h | 223 | 1
EEE1062-EWPc-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 9514 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 6271 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 6205 | h | 223 | 1
EEE1062-EWPc-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 6205 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 60635 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 17551 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 17551 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 879 | h | 223 | 1
EEE1062-PWPe-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 879 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 7444 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 37229 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 37229 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 72937 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 72937 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 72937 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 72937 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 48624 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 48624 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 26477 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 56526 | h | 223 | 1
MEM1214-EWPc-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 56526 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 15875 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 48624 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 48624 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12721 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12721 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3880 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3880 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1293 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1293 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 536 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 536 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 11950 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 11950 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1299 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 83 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 83 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2856 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2856 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 592 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 592 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 144 | h | 223 | 1
SUWP-AC-PF-0704 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 144 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 33027 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 64 | h | 223 | 1
SUWP-AC-PF-0308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 64 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 1352 | h | 223 | 1
SUWP-AC-PF-0301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 1352 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 98 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 98 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 769 | h | 223 | 1
SUWP-AC-PF-0801 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 769 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 363 | h | 223 | 1
SUWP-AC-PF-1001 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 363 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3993 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3993 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 48 | h | 223 | 1
SUWP-AC-PF-0802 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 48 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 169822 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 4508 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 4508 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 49068 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 5914 | h | 223 | 1
B22013 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 5914 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 251608 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 17558 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 17558 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3093 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 335 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 335 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 114551 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 2627 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 3012 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 48863 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 48863 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 43663 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2023-12-31 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2023-12-31 | 12229 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 179 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 179 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 2334 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 786 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 786 | h | 223 | 1
TTU0822-CWP-428 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 727 | h | 223 | 1
TTU0822-CWP-428 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 727 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 960 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 10887 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 10887 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 6822 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 10478 | h | 223 | 1
SES0822-CWP-098 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 10478 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 9760 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 13917 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 13917 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 4148 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 4148 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 3393 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 3393 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 5039 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 663 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 663 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 982 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 982 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 2337 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 2337 | h | 223 | 1
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 4682 | h | 223 | 1
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 4682 | h | 223 | 1
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 28708 | h | 223 | 1
MCD0827-CWP-359 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 28708 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 1527 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 1527 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 136 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 136 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 18 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 18 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 533 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 533 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 160 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 160 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 53 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 53 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 493 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 493 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2023-12-31 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2023-12-31 | 968 | h | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-01-07 | 171 | m | 223 | 1
CEC0821-CWP-075 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-01-07 | 171 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-01-07 | 2 | m | 223 | 1
CEC0827-CWP-311 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-01-07 | 2 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-01-07 | 2 | m | 223 | 1
CEC0830-CWP-490 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-01-07 | 2 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-01-07 | 2 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-01-07 | 2 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-01-07 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-01-07 | 13 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-01-07 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-01-07 | 41 | m | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-07 | 17 | t | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-07 | 17 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-07 | 22 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-07 | 22 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-07 | 1 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-07 | 1 | t | 223 | 1
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-01-07 | 96 | m | 223 | 1
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-01-07 | 96 | m | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-07 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-07 | 3 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-07 | 4 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-07 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-07 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-07 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-07 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-07 | 4 | t | 223 | 1
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-07 | 6 | t | 223 | 1
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-07 | 6 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-07 | 2 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-07 | 2 | t | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-01-07 | 0 | un | 223 | 1
MSD1214-CWP-402 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-01-07 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-01-07 | 0 | un | 223 | 1
MSD1214-CWP-403 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-01-07 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-01-07 | 0 | un | 223 | 1
MSD1214-CWP-404 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-01-07 | 0 | un | 223 | 1
MCD0822-CWP-242 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-07 | 3 | t | 223 | 1
MCD0822-CWP-242 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-07 | 3 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-07 | 9 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-07 | 9 | t | 223 | 1
MEM0830-CWP-503 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-07 | 37 | t | 223 | 1
MEM0830-CWP-503 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-07 | 37 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-01-07 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-01-07 | 12 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-01-07 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-01-07 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-01-07 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-01-07 | 8 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5787 | h | 223 | 1
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 40073 | h | 223 | 1
EBD0800-EWPc-417 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 40073 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2938 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2938 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 7121 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 7121 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2609 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2609 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 10436 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 10436 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5463 | h | 223 | 1
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 824 | h | 223 | 1
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 824 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3714 | h | 223 | 1
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 40073 | h | 223 | 1
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 56606 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2652 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2652 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6429 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6429 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 47816 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12546 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12546 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 536 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 536 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 334815 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1299 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 80256 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12729 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12729 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2609 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2609 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 10436 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 10436 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 18272 | h | 223 | 1
CEC0821-CWP-075 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 18272 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 334815 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12546 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12546 | h | 223 | 1
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 88671 | h | 223 | 1
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 47816 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1171 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1171 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 21600 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 21600 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3012 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1171 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1171 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 10216 | h | 223 | 1
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 10216 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 23279 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 4378 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 4378 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 10612 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 10612 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 20029 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 21767 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 41955 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 41955 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 446 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 446 | h | 223 | 1
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 19106 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 19106 | h | 223 | 1
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 86314 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 33564 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 264001 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 264001 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 127879 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 35601 | h | 223 | 1
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 91548 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1399 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1399 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 483 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 483 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1756 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 724 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 724 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1756 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 724 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 724 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1756 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 418 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 418 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1013 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1013 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 17514 | h | 223 | 1
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 67928 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 536 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 536 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 31643 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 4243 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 4243 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 10286 | h | 223 | 1
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
EBD0822-EWPc-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6479 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 37950 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 37950 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2652 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2652 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6429 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6429 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 160509 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1399 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1399 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1399 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1399 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3754 | h | 223 | 1
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5787 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 21767 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6122 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6122 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6122 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6122 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 62703 | h | 223 | 1
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 51089 | h | 223 | 1
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 51089 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 349104 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 349104 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 11428 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 11428 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 100584 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 100584 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2857 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 11428 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 11428 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 100584 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 100584 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2857 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 11428 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 11428 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 82284 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 82284 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2857 | h | 223 | 1
MCD0822-CWP-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 32980 | h | 223 | 1
MCD0822-CWP-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 32980 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1171 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1171 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3960 | h | 223 | 1
MEM0823-PWPp-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3960 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 20029 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2627 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 55262 | h | 223 | 1
MCD0823-EWPc-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 55262 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6120 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 19856 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 19856 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 536 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 536 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12729 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12729 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1299 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5787 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 23570 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 49736 | h | 223 | 1
MCD0824-EWPc-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 49736 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6120 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 49736 | h | 223 | 1
MCD0824-EWPc-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 49736 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6120 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 23279 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 20029 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1299 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 23570 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1013 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1013 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 536 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 536 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 18517 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 536 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 536 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 168493 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 168493 | h | 223 | 1
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 113534 | h | 223 | 1
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 113534 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12729 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12729 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1171 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1171 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 69966 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 69966 | h | 223 | 1
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 39772 | h | 223 | 1
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 39772 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 20029 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3960 | h | 223 | 1
MEM0827-PWPp-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3960 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2652 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2652 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6429 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6429 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12255 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 564 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3297 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2627 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 7837 | h | 223 | 1
JIL0827-PWPp-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 7837 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6402 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6402 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 257 | h | 223 | 1
CEC0830-CWP-490 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 257 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 7321 | h | 223 | 1
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3416 | h | 223 | 1
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3416 | h | 223 | 1
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3986 | h | 223 | 1
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3986 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 26189 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 7050 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 7050 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6271 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 60635 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 21274 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 21274 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1013 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1013 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 37229 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 37229 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 418 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 418 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 72937 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 72937 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 72937 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 72937 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 48624 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 48624 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2652 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2652 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6429 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6429 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 26477 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 15875 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 48624 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 48624 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6360 | h | 223 | 1
MSD1214-CWP-402 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6360 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 970 | h | 223 | 1
MSD1214-CWP-403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 970 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 323 | h | 223 | 1
MSD1214-CWP-404 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 323 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 536 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 536 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 11950 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 11950 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1299 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 185 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 185 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 357 | h | 223 | 1
TTU1215-PWPl-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 357 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 338 | h | 223 | 1
SUWP-OU-PF-0304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 338 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 33027 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 28 | h | 223 | 1
SUWP-AC-PF-0206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 28 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3993 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3993 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 169822 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 4508 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 4508 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 49068 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1424 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1424 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 251608 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 17558 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 17558 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3093 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 1171 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 1171 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 114551 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2627 | h | 223 | 1
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 16288 | h | 223 | 1
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 16288 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3012 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 10612 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 10612 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 3012 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2652 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2652 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 6429 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 6429 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 2609 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 2609 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 10436 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 10436 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 18324 | h | 223 | 1
MMR0622-EWPc-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 18324 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 4378 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 4378 | h | 223 | 1
ECB1214-EWPc-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 145873 | h | 223 | 1
ECB1214-EWPc-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 145873 | h | 223 | 1
ECB1214-EWPc-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 291747 | h | 223 | 1
ECB1214-EWPc-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 291747 | h | 223 | 1
ECB0817-EWPc-550 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0817-EWPc-550 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0817-EWPc-551 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0817-EWPc-551 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0817-EWPc-552 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0817-EWPc-552 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0821-EWPc-553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 177341 | h | 223 | 1
ECB0821-EWPc-553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 177341 | h | 223 | 1
ECB0821-EWPc-554 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 177341 | h | 223 | 1
ECB0821-EWPc-554 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 177341 | h | 223 | 1
ECB0823-EWPc-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 294730 | h | 223 | 1
ECB0823-EWPc-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 294730 | h | 223 | 1
ECB0823-EWPc-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 294730 | h | 223 | 1
ECB0823-EWPc-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 294730 | h | 223 | 1
ECB0823-EWPc-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 294730 | h | 223 | 1
ECB0823-EWPc-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 294730 | h | 223 | 1
ECB0824-EWPc-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 265256 | h | 223 | 1
ECB0824-EWPc-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 265256 | h | 223 | 1
ECB0824-EWPc-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 265256 | h | 223 | 1
ECB0824-EWPc-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 265256 | h | 223 | 1
ECB0824-EWPc-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 265256 | h | 223 | 1
ECB0824-EWPc-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 265256 | h | 223 | 1
ECB0826-EWPc-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 333510 | h | 223 | 1
ECB0826-EWPc-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 333510 | h | 223 | 1
ECB0826-EWPc-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 333510 | h | 223 | 1
ECB0826-EWPc-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 333510 | h | 223 | 1
ECB0826-EWPc-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 333510 | h | 223 | 1
ECB0826-EWPc-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 333510 | h | 223 | 1
ECB0827-EWPc-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0827-EWPc-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0827-EWPc-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0827-EWPc-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0827-EWPc-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 79545 | h | 223 | 1
ECB0827-EWPc-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 79545 | h | 223 | 1
ECB1049-EWPc-570 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 60600 | h | 223 | 1
ECB1049-EWPc-570 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 60600 | h | 223 | 1
ECB1049-EWPc-571 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 60600 | h | 223 | 1
ECB1049-EWPc-571 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 60600 | h | 223 | 1
ECB1049-EWPc-572 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 60600 | h | 223 | 1
ECB1049-EWPc-572 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 60600 | h | 223 | 1
ECB1062-EWPc-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 74458 | h | 223 | 1
ECB1062-EWPc-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 74458 | h | 223 | 1
ECB1062-EWPc-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 74458 | h | 223 | 1
ECB1062-EWPc-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 74458 | h | 223 | 1
ECB1062-EWPc-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 74458 | h | 223 | 1
ECB1062-EWPc-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 74458 | h | 223 | 1
ECB1214-EWPc-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 145873 | h | 223 | 1
ECB1214-EWPc-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 145873 | h | 223 | 1
ECB1214-EWPc-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 145873 | h | 223 | 1
ECB1214-EWPc-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 145873 | h | 223 | 1
SES0822-PWPl-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 167819 | h | 223 | 1
SES0822-PWPl-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 167819 | h | 223 | 1
SES0822-PWPl-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 167819 | h | 223 | 1
SES0822-PWPl-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 167819 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 43663 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-07 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-07 | 12229 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 2334 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 754 | h | 223 | 1
CEC0821-CWP-075 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 754 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 960 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 10887 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 10887 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 6822 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 9760 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 13917 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 13917 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 4148 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 4148 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 3393 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 3393 | h | 223 | 1
MCD0822-CWP-242 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 1360 | h | 223 | 1
MCD0822-CWP-242 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 1360 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 5039 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 829 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 829 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 982 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 982 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 438 | h | 223 | 1
CEC0827-CWP-311 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 438 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 6949 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 6949 | h | 223 | 1
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 4682 | h | 223 | 1
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 4682 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 1527 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 1527 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 136 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 136 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 264 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 264 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 11 | h | 223 | 1
CEC0830-CWP-490 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 11 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 133 | h | 223 | 1
MSD1214-CWP-402 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 133 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 40 | h | 223 | 1
MSD1214-CWP-403 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 40 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 13 | h | 223 | 1
MSD1214-CWP-404 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 13 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 493 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 493 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-07 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-07 | 968 | h | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-01-14 | 2 | m | 223 | 1
CEC1214-CWP-393 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-01-14 | 2 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-01-14 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-01-14 | 13 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-01-14 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-01-14 | 41 | m | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-14 | 17 | t | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-14 | 17 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-14 | 22 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-14 | 22 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-14 | 1 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-14 | 1 | t | 223 | 1
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-14 | 7 | t | 223 | 1
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-14 | 7 | t | 223 | 1
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-01-14 | 55 | m | 223 | 1
TTU0822-CWP-428 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-01-14 | 55 | m | 223 | 1
EEE1062-CWP-381 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-01-14 | 0 | un | 223 | 1
EEE1062-CWP-381 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-01-14 | 0 | un | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-14 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-14 | 3 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-14 | 4 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-14 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-14 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-14 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-14 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-14 | 4 | t | 223 | 1
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-14 | 6 | t | 223 | 1
MEM0827-CWP-358 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-14 | 6 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-14 | 2 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-14 | 2 | t | 223 | 1
MCD0822-CWP-242 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-14 | 2 | t | 223 | 1
MCD0822-CWP-242 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-14 | 2 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-14 | 11 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-14 | 11 | t | 223 | 1
MEM0830-CWP-503 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-14 | 92 | t | 223 | 1
MEM0830-CWP-503 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-14 | 92 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-01-14 | 12 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-01-14 | 12 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-01-14 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-01-14 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-01-14 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-01-14 | 8 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5787 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 13056 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 13056 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 31651 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11596 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11596 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 46384 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 46384 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5463 | h | 223 | 1
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 824 | h | 223 | 1
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 824 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3714 | h | 223 | 1
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 40073 | h | 223 | 1
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 56606 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 10286 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 47816 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4705 | h | 223 | 1
EEE0821-PWPp-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4705 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 536 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 536 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3314 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3314 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 334815 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 17514 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 17514 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1299 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 80256 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 21600 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 21600 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11596 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11596 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 46384 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 46384 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 334815 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4705 | h | 223 | 1
EEE0821-PWPp-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4705 | h | 223 | 1
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 88671 | h | 223 | 1
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 47816 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1171 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1171 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 21600 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 21600 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3012 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1171 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1171 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5874 | h | 223 | 1
TTU0822-CWP-428 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5874 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 23279 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 29376 | h | 223 | 1
TTU0822-EWPc-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 29376 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 29376 | h | 223 | 1
TTU0822-EWPc-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 29376 | h | 223 | 1
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 7004 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 7004 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 16979 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 20029 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 21767 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 28669 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 28669 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 7342 | h | 223 | 1
SES0822-PWPp-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 7342 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 446 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 446 | h | 223 | 1
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 33564 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 10986 | h | 223 | 1
MEM0822-PWPp-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 10986 | h | 223 | 1
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 86314 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 29376 | h | 223 | 1
TTU0822-EWPc-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 29376 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 29376 | h | 223 | 1
TTU0822-EWPc-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 29376 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 33564 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 264001 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 264001 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 127879 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 35601 | h | 223 | 1
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 91548 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 9792 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 9792 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 483 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 483 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1756 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 724 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 724 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1756 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 724 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 724 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1756 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1856 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1856 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4500 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 17514 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 17514 | h | 223 | 1
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 67928 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 536 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 536 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 31643 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 10286 | h | 223 | 1
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 6479 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 29412 | h | 223 | 1
SES0822-PWPp-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 29412 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 10286 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 160509 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 9792 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 9792 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 9792 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 9792 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3754 | h | 223 | 1
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 238563 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 238563 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5787 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 21767 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 6122 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 6122 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 6122 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 6122 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 62703 | h | 223 | 1
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 51089 | h | 223 | 1
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 51089 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 349104 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 349104 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11428 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11428 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 100584 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 100584 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2857 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11428 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11428 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 100584 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 100584 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2857 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11428 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11428 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 82284 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 82284 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2857 | h | 223 | 1
MCD0822-CWP-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 32980 | h | 223 | 1
MCD0822-CWP-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 32980 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2178 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2178 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1171 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1171 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 20029 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2627 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 6120 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 19856 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 19856 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 536 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 536 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 21600 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 21600 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1299 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5787 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 23570 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 6120 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1662 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1662 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 23279 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 20029 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1299 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 23570 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2270 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2270 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 536 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 536 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 18517 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 536 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 536 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 207376 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 207376 | h | 223 | 1
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 113534 | h | 223 | 1
MEM0827-CWP-358 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 113534 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 21600 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 21600 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2178 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2178 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1171 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1171 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 69966 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 69966 | h | 223 | 1
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 39772 | h | 223 | 1
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 39772 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 20029 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 10286 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1662 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1662 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 12255 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 564 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3297 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2627 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4310 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4310 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 16004 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 16004 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 7321 | h | 223 | 1
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3416 | h | 223 | 1
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3416 | h | 223 | 1
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3986 | h | 223 | 1
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3986 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 26189 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4029 | h | 223 | 1
EEE1062-PWPl-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4029 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 6271 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 60635 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 21274 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 21274 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4500 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 28852 | h | 223 | 1
EBD1062-EWPc-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 28852 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1856 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1856 | h | 223 | 1
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1490 | h | 223 | 1
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1490 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 41939 | h | 223 | 1
TTU1214-EWPc-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 41939 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 41939 | h | 223 | 1
TST1214-EWPc-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 41939 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 48624 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 48624 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4243 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4243 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 26477 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 15875 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 48624 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 48624 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 16411 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 16411 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 415 | h | 223 | 1
EEE1214-PWPe-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 415 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11253 | h | 223 | 1
CEC1214-CWP-393 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11253 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 71940 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 71940 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1299 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 185 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 185 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 33027 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2282 | h | 223 | 1
SUWP-AC-PF-0701 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2282 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 169822 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4508 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4508 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 49068 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1994 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1994 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 251608 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 17558 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 17558 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3093 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 1171 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 1171 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 114551 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 2627 | h | 223 | 1
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 16288 | h | 223 | 1
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 16288 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3012 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 3012 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 4243 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 10286 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 11596 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 11596 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 46384 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 46384 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 7004 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 7004 | h | 223 | 1
ECB1214-EWPc-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 145873 | h | 223 | 1
ECB1214-EWPc-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 145873 | h | 223 | 1
ECB0817-EWPc-550 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0817-EWPc-550 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0817-EWPc-551 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0817-EWPc-551 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0817-EWPc-552 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0817-EWPc-552 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0821-EWPc-553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 177341 | h | 223 | 1
ECB0821-EWPc-553 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 177341 | h | 223 | 1
ECB0821-EWPc-554 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 177341 | h | 223 | 1
ECB0821-EWPc-554 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 177341 | h | 223 | 1
ECB0823-EWPc-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 294730 | h | 223 | 1
ECB0823-EWPc-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 294730 | h | 223 | 1
ECB0823-EWPc-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 294730 | h | 223 | 1
ECB0823-EWPc-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 294730 | h | 223 | 1
ECB0823-EWPc-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 294730 | h | 223 | 1
ECB0823-EWPc-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 294730 | h | 223 | 1
ECB0824-EWPc-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 265256 | h | 223 | 1
ECB0824-EWPc-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 265256 | h | 223 | 1
ECB0824-EWPc-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 265256 | h | 223 | 1
ECB0824-EWPc-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 265256 | h | 223 | 1
ECB0824-EWPc-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 265256 | h | 223 | 1
ECB0824-EWPc-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 265256 | h | 223 | 1
ECB0826-EWPc-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 333510 | h | 223 | 1
ECB0826-EWPc-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 333510 | h | 223 | 1
ECB0826-EWPc-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 333510 | h | 223 | 1
ECB0826-EWPc-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 333510 | h | 223 | 1
ECB0826-EWPc-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 333510 | h | 223 | 1
ECB0826-EWPc-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 333510 | h | 223 | 1
ECB0827-EWPc-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0827-EWPc-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0827-EWPc-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0827-EWPc-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0827-EWPc-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 79545 | h | 223 | 1
ECB0827-EWPc-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 79545 | h | 223 | 1
ECB1049-EWPc-570 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 60600 | h | 223 | 1
ECB1049-EWPc-570 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 60600 | h | 223 | 1
ECB1049-EWPc-571 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 60600 | h | 223 | 1
ECB1049-EWPc-571 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 60600 | h | 223 | 1
ECB1049-EWPc-572 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 60600 | h | 223 | 1
ECB1049-EWPc-572 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 60600 | h | 223 | 1
ECB1062-EWPc-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 74458 | h | 223 | 1
ECB1062-EWPc-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 74458 | h | 223 | 1
ECB1062-EWPc-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 74458 | h | 223 | 1
ECB1062-EWPc-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 74458 | h | 223 | 1
ECB1062-EWPc-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 74458 | h | 223 | 1
ECB1062-EWPc-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 74458 | h | 223 | 1
ECB1214-EWPc-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 145873 | h | 223 | 1
ECB1214-EWPc-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 145873 | h | 223 | 1
ECB1214-EWPc-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 145873 | h | 223 | 1
ECB1214-EWPc-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 145873 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 43663 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 13452 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 13452 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-14 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-14 | 12229 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 2334 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 960 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 10887 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 10887 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 6822 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 9760 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 9760 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 13917 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 13917 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 4148 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 4148 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 3393 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 3393 | h | 223 | 1
MCD0822-CWP-242 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 1360 | h | 223 | 1
MCD0822-CWP-242 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 1360 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 5039 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 829 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 829 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 982 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 982 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 8552 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 8552 | h | 223 | 1
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 4682 | h | 223 | 1
MEM0827-CWP-358 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 4682 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 1527 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 1527 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 136 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 136 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 660 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 660 | h | 223 | 1
EEE1062-CWP-381 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 64 | h | 223 | 1
EEE1062-CWP-381 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 64 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 464 | h | 223 | 1
CEC1214-CWP-393 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 464 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 2967 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 2967 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-14 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-14 | 968 | h | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-01-21 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-01-21 | 13 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-01-21 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-01-21 | 41 | m | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-21 | 17 | t | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-21 | 17 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-21 | 22 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-21 | 22 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-21 | 1 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-21 | 1 | t | 223 | 1
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-21 | 13 | t | 223 | 1
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-21 | 13 | t | 223 | 1
EEE1062-CWP-381 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-01-21 | 1 | un | 223 | 1
EEE1062-CWP-381 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-01-21 | 1 | un | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-21 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-21 | 3 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-21 | 4 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-21 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-21 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-21 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-21 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-21 | 4 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-21 | 2 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-21 | 2 | t | 223 | 1
MRF0822-CWP-243 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-21 | 1 | t | 223 | 1
MRF0822-CWP-243 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-21 | 1 | t | 223 | 1
MCD0822-CWP-244 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-21 | 2 | t | 223 | 1
MCD0822-CWP-244 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-21 | 2 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-21 | 11 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-21 | 11 | t | 223 | 1
MEM0830-CWP-503 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-21 | 37 | t | 223 | 1
MEM0830-CWP-503 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-21 | 37 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-01-21 | 7 | t | 223 | 1
MSD0822-CWP-116 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-01-21 | 7 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-01-21 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-01-21 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-01-21 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-01-21 | 8 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5787 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 13056 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 13056 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 31651 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11596 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11596 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 46384 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 46384 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5463 | h | 223 | 1
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 824 | h | 223 | 1
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 824 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3714 | h | 223 | 1
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 40073 | h | 223 | 1
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 56606 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 10286 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 47816 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1235 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1235 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 201 | h | 223 | 1
EEE0821-PWPe-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 201 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3012 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3231 | h | 223 | 1
TTU0821-PWPp-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3231 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 334815 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 55419 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 55419 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 13573 | h | 223 | 1
MEM0821-PWPp-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 13573 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1299 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 80256 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 21600 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 21600 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11596 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11596 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 46384 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 46384 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 334815 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1235 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1235 | h | 223 | 1
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 88671 | h | 223 | 1
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 47816 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1171 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1171 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 21215 | h | 223 | 1
SES0821-PWPl-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 21215 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3012 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1171 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1171 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 23279 | h | 223 | 1
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 7004 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 7004 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 16979 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 20029 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 21767 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 39158 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 39158 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 446 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 446 | h | 223 | 1
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 33564 | h | 223 | 1
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 33564 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 264001 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 264001 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 127879 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 35601 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 35601 | h | 223 | 1
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 91548 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 9792 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 9792 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 483 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 483 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1756 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 724 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 724 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1756 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 724 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 724 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1756 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1856 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1856 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 4500 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 13573 | h | 223 | 1
MEM0822-PWPp-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 13573 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 31930 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 31930 | h | 223 | 1
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 67928 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 201 | h | 223 | 1
EEE0822-PWPe-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 201 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 31643 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 10286 | h | 223 | 1
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 6479 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 10286 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 160509 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 9792 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 9792 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 9792 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 9792 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3754 | h | 223 | 1
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 119281 | h | 223 | 1
MSD0822-CWP-116 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 119281 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5787 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 21767 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 6122 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 6122 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 6122 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 6122 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 62703 | h | 223 | 1
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 51089 | h | 223 | 1
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 51089 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 349104 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 349104 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11428 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11428 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 100584 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 100584 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2857 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11428 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11428 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 100584 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 100584 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2857 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11428 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11428 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 82284 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 82284 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2857 | h | 223 | 1
MCD0822-CWP-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 13192 | h | 223 | 1
MCD0822-CWP-242 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 13192 | h | 223 | 1
MRF0822-CWP-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 9894 | h | 223 | 1
MRF0822-CWP-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 9894 | h | 223 | 1
MCD0822-CWP-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 19788 | h | 223 | 1
MCD0822-CWP-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 19788 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 7624 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 7624 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1171 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1171 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 20029 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2627 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 6120 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 19856 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 19856 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 201 | h | 223 | 1
EEE0823-PWPe-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 201 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 21600 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 21600 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1299 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5787 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 92103 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 92103 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 23570 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 6120 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2270 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2270 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 23279 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 20029 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1299 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 23570 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 104222 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 104222 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2270 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2270 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 201 | h | 223 | 1
EEE0826-PWPe-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 201 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 18517 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 201 | h | 223 | 1
EEE0827-PWPe-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 201 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 207376 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 207376 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 21600 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 21600 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 7624 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 7624 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1171 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1171 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 69966 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 69966 | h | 223 | 1
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 39772 | h | 223 | 1
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 39772 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 20029 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3349 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3349 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 10286 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2270 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2270 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 24858 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 24858 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 12255 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 564 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3297 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2627 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 15085 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 15085 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 16004 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 16004 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 7321 | h | 223 | 1
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3416 | h | 223 | 1
EEE1048-PWPe-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3416 | h | 223 | 1
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3986 | h | 223 | 1
EEE1049-PWPe-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3986 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 26189 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 6271 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 60635 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 21274 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 21274 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 4500 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1856 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1856 | h | 223 | 1
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3725 | h | 223 | 1
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3725 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 48624 | h | 223 | 1
EBD1214-EWPc-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 48624 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 4243 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 4243 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 26477 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 15875 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 48624 | h | 223 | 1
EBD1214-EWPc-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 48624 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 72937 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 72937 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 128848 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 128848 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1299 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 185 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 185 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 169822 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 4395 | h | 223 | 1
B30153 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 4395 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 49068 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1994 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1994 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 251608 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 14736 | h | 223 | 1
B29743 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 14736 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3093 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 1171 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 1171 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 114551 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 2627 | h | 223 | 1
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 16288 | h | 223 | 1
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 16288 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3012 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 3012 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 4243 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 10286 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 11596 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 11596 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 46384 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 46384 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 7004 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 7004 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 60635 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 43663 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 5045 | h | 223 | 1
MMR0821-PWPp-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 5045 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-21 | 12229 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-21 | 12229 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 2334 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 960 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 10887 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 10887 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 6822 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 5856 | h | 223 | 1
MSD0822-CWP-116 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 5856 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 13917 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 13917 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 4148 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 4148 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 3393 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 3393 | h | 223 | 1
MCD0822-CWP-242 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 544 | h | 223 | 1
MCD0822-CWP-242 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 544 | h | 223 | 1
MRF0822-CWP-243 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 408 | h | 223 | 1
MRF0822-CWP-243 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 408 | h | 223 | 1
MCD0822-CWP-244 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 816 | h | 223 | 1
MCD0822-CWP-244 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 816 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 5039 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 829 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 829 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 982 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 982 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 8552 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 8552 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 1527 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 1527 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 136 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 136 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 660 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 660 | h | 223 | 1
EEE1062-CWP-381 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 160 | h | 223 | 1
EEE1062-CWP-381 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 160 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 5314 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 5314 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-21 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-21 | 968 | h | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-01-28 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-01-28 | 13 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-01-28 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-01-28 | 41 | m | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-28 | 5 | t | 223 | 1
EEE0822-CWP-105 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-28 | 5 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-28 | 13 | t | 223 | 1
MCD0822-CWP-151 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-28 | 13 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-28 | 1 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-28 | 1 | t | 223 | 1
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-28 | 13 | t | 223 | 1
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-28 | 13 | t | 223 | 1
MCD0822-CWP-540 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-01-28 | 23 | t | 223 | 1
MCD0822-CWP-540 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-01-28 | 23 | t | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-01-28 | 0 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-01-28 | 0 | un | 223 | 1
EEE1062-CWP-381 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-01-28 | 1 | un | 223 | 1
EEE1062-CWP-381 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-01-28 | 1 | un | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-28 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-28 | 3 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-28 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-28 | 1 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-28 | 4 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-28 | 4 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-28 | 1 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-28 | 1 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-28 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-28 | 4 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-28 | 1 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-28 | 1 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-28 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-28 | 4 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-01-28 | 0 | t | 223 | 1
MEM0827-CWP-304 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-01-28 | 0 | t | 223 | 1
MRF0822-CWP-243 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-28 | 1 | t | 223 | 1
MRF0822-CWP-243 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-28 | 1 | t | 223 | 1
MCD0822-CWP-244 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-28 | 3 | t | 223 | 1
MCD0822-CWP-244 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-28 | 3 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-01-28 | 11 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-01-28 | 11 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-01-28 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-01-28 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-01-28 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-01-28 | 8 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-01-28 | 0 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-01-28 | 0 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5787 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5787 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 13056 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 13056 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 31651 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11596 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11596 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 46384 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 46384 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5463 | h | 223 | 1
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 824 | h | 223 | 1
JIL0800-PWPe-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 824 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3714 | h | 223 | 1
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 40073 | h | 223 | 1
ECB0800-EWPc-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 40073 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 56606 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4243 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4243 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 10286 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 47816 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7684 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7684 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3012 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0824-PWPp-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 334815 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 88671 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 88671 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2627 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0821-PWPp-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1299 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 80256 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 80256 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 21600 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 21600 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11596 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11596 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 46384 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 46384 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0821-PWPp-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 334815 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7684 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7684 | h | 223 | 1
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 88671 | h | 223 | 1
ECB0821-EWPc-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 47816 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1171 | h | 223 | 1
MCD0822-PWPl-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1171 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3012 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1171 | h | 223 | 1
TTU0822-PWPl-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1171 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 16048 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0822-PWPp-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0822-PWPp-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0822-PWPp-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 23279 | h | 223 | 1
MRF0822-CWP-177 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 23279 | h | 223 | 1
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7004 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7004 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 16979 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 92364 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 92364 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 20029 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 21767 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 39158 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 39158 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 446 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 446 | h | 223 | 1
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 33564 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5385 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5385 | h | 223 | 1
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 33564 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 72600 | h | 223 | 1
EEE0822-CWP-105 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 72600 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 127879 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6230 | h | 223 | 1
KMT0822-PWPp-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6230 | h | 223 | 1
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 91548 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 9792 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 9792 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 483 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 483 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1756 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 31930 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 31930 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 272 | h | 223 | 1
EEE0820-PWPe-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 272 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1756 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 31930 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 31930 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 272 | h | 223 | 1
EEE0820-PWPe-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 272 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1756 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1856 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1856 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4500 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
JCI0822-EWPc-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 310 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 310 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 67928 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 67928 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 31643 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11495 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11495 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3288 | h | 223 | 1
JIL0822-PWPe-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3288 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 10286 | h | 223 | 1
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6479 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3827 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3827 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4243 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4243 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 10286 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 160509 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 9792 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 9792 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 9792 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 9792 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3754 | h | 223 | 1
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5787 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5787 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 21767 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 689 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 689 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4745 | h | 223 | 1
JIL0822-PWPe-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4745 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 689 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 689 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4745 | h | 223 | 1
JIL0822-PWPe-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4745 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 62703 | h | 223 | 1
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 51089 | h | 223 | 1
ECB0822-EWPc-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 51089 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 154188 | h | 223 | 1
MCD0822-CWP-151 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 154188 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4898 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4898 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 18106 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 18106 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6530 | h | 223 | 1
MEM0822-PWPl-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6530 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 100584 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 100584 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2857 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2857 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 18106 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 18106 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6530 | h | 223 | 1
MEM0822-PWPl-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6530 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 100584 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 100584 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2857 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2857 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 18106 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 18106 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6530 | h | 223 | 1
MEM0822-PWPl-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6530 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 82284 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 82284 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2857 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2857 | h | 223 | 1
MRF0822-CWP-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 16490 | h | 223 | 1
MRF0822-CWP-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 16490 | h | 223 | 1
MCD0822-CWP-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 32980 | h | 223 | 1
MCD0822-CWP-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 32980 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7624 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7624 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1171 | h | 223 | 1
TTU0823-PWPl-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1171 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2627 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0823-PWPp-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 20029 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2627 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6120 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 19856 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 19856 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 21600 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 21600 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1299 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5787 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5787 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 147365 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 147365 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 23570 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6120 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2270 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2270 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0824-PWPp-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0824-PWPp-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 23279 | h | 223 | 1
MRF0826-CWP-289 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 23279 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 20029 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1299 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5787 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5787 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 23570 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 166755 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 166755 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2270 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2270 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 18517 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 207376 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 207376 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 21600 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 21600 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7624 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7624 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1171 | h | 223 | 1
TTU0827-PWPl-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1171 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 69966 | h | 223 | 1
EBD0827-EWPc-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 69966 | h | 223 | 1
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 39772 | h | 223 | 1
ECB0827-EWPc-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 39772 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 23570 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 20029 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 586 | h | 223 | 1
MCD0827-PWPp-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 586 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4243 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4243 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 10286 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2270 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2270 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 39772 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 39772 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 12255 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 564 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3297 | h | 223 | 1
MSD0827-CWP-354 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3297 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2627 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 15085 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 15085 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 16004 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 16004 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7321 | h | 223 | 1
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 30300 | h | 223 | 1
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 30300 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 26189 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 6271 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 60635 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 60635 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 21274 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 21274 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4500 | h | 223 | 1
SWP-029-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11941 | h | 223 | 1
SWP-029-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11941 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1856 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1856 | h | 223 | 1
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3725 | h | 223 | 1
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3725 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4243 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4243 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 26477 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 15875 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 181 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 181 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 72937 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 72937 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 128848 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 128848 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1299 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 155 | h | 223 | 1
JIL1214-PWPl-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 155 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2633 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2633 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 169822 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 735 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 735 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 49068 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1994 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1994 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 251608 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11224 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3093 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3093 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 1171 | h | 223 | 1
TTU0623-PWPl-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 1171 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 114551 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2627 | h | 223 | 1
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 16288 | h | 223 | 1
ECB0600-EWPc-408 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 16288 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3012 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 3012 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 4243 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 4243 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 10286 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 11596 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 11596 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 46384 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 46384 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7004 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7004 | h | 223 | 1
MCD0822-CWP-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 347581 | h | 223 | 1
MCD0822-CWP-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 347581 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 60635 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 60635 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 60635 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 46992 | h | 223 | 1
EEE1061-PWPp-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 46992 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 10737 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 10737 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 43663 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0823-PWPp-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0824-PWPp-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 757 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 757 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 2102 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 2102 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0827-PWPp-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0822-PWPp-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0823-PWPp-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0824-PWPp-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-01-28 | 7032 | h | 223 | 1
MMR0622-PWPp-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-01-28 | 7032 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 2334 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 960 | h | 223 | 1
MRF0822-CWP-177 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 960 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 2994 | h | 223 | 1
EEE0822-CWP-105 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 2994 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 6822 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 8466 | h | 223 | 1
MCD0822-CWP-151 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 8466 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 679 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 679 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 4148 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 4148 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 679 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 679 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 4148 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 679 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 679 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 3393 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 3393 | h | 223 | 1
MRF0822-CWP-243 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 680 | h | 223 | 1
MRF0822-CWP-243 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 680 | h | 223 | 1
MCD0822-CWP-244 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 1360 | h | 223 | 1
MCD0822-CWP-244 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 1360 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 5039 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 829 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 829 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 785 | h | 223 | 1
MRF0826-CWP-289 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 785 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 8552 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 8552 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 267 | h | 223 | 1
MEM0827-CWP-304 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 267 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 136 | h | 223 | 1
MSD0827-CWP-354 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 136 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 660 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 660 | h | 223 | 1
SWP-029-1062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 2567 | h | 223 | 1
SWP-029-1062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 2567 | h | 223 | 1
EEE1062-CWP-381 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 160 | h | 223 | 1
EEE1062-CWP-381 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 160 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 7 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 7 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 5314 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 5314 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 109 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 109 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 968 | h | 223 | 1
MCD0822-CWP-540 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-01-28 | 14335 | h | 223 | 1
MCD0822-CWP-540 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-01-28 | 14335 | h | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-02-04 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-02-04 | 13 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-02-04 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-02-04 | 41 | m | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-04 | 10 | t | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-04 | 10 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-04 | 1 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-04 | 1 | t | 223 | 1
SES0827-CWP-452 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-04 | 4 | t | 223 | 1
SES0827-CWP-452 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-04 | 4 | t | 223 | 1
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-04 | 9 | t | 223 | 1
TST1214-CWP-394 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-04 | 9 | t | 223 | 1
MCD0822-CWP-540 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-04 | 58 | t | 223 | 1
MCD0822-CWP-540 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-04 | 58 | t | 223 | 1
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-02-04 | 188 | m | 223 | 1
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-02-04 | 188 | m | 223 | 1
EEE0827-CWP-345 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-02-04 | 7 | un | 223 | 1
EEE0827-CWP-345 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-02-04 | 7 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-02-04 | 2 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-02-04 | 2 | un | 223 | 1
MEM0823-CWP-248 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-02-04 | 7 | un | 223 | 1
MEM0823-CWP-248 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-02-04 | 7 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-02-04 | 14 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-02-04 | 14 | un | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 3 | t | 223 | 1
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 1 | t | 223 | 1
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 2 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 4 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 4 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 2 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 4 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 4 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 2 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 4 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 4 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 0 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 0 | t | 223 | 1
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 1 | t | 223 | 1
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 1 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-04 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-04 | 13 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-04 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-04 | 0 | t | 223 | 1
MRF0822-CWP-243 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-04 | 0 | t | 223 | 1
MRF0822-CWP-243 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-04 | 0 | t | 223 | 1
MRF0822-CWP-245 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-04 | 0 | t | 223 | 1
MRF0822-CWP-245 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-04 | 0 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-04 | 2 | t | 223 | 1
MRF0827-CWP-357 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-04 | 2 | t | 223 | 1
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-04 | 0 | t | 223 | 1
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-04 | 0 | t | 223 | 1
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-04 | 0 | t | 223 | 1
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-04 | 0 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-02-04 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-02-04 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-02-04 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-02-04 | 8 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-02-04 | 2 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-02-04 | 2 | t | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1157 | h | 223 | 1
EEE0800-PWPp-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1157 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 9016 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 9016 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 63319 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 63319 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 9016 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 9016 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 10118 | h | 223 | 1
RIN0800-PWPe-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 10118 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 31651 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 8987 | h | 223 | 1
KMT0800-PWPe-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 8987 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 46384 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 46384 | h | 223 | 1
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 20022 | h | 223 | 1
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 20022 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 40073 | h | 223 | 1
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 40073 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5463 | h | 223 | 1
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 40073 | h | 223 | 1
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 40073 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3714 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 56606 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1591 | h | 223 | 1
JIL0820-PWPe-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1591 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 10286 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 25046 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 25046 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 47816 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 7684 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 7684 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 403 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 403 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 4334 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 4334 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3012 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 334815 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 88671 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 88671 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2627 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1299 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 14045 | h | 223 | 1
MEM0822-PWPp-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 14045 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 15043 | h | 223 | 1
SES0821-PWPl-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 15043 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 19951 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 19951 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 8987 | h | 223 | 1
KMT0821-PWPe-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 8987 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 46384 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 46384 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 149186 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 149186 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 334815 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 7684 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 7684 | h | 223 | 1
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 88671 | h | 223 | 1
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3012 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2589 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 16048 | h | 223 | 1
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 14792 | h | 223 | 1
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 14792 | h | 223 | 1
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 51089 | h | 223 | 1
EBD0822-EWPc-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 51089 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2627 | h | 223 | 1
JIL0822-PWPe-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2627 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 16979 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 18473 | h | 223 | 1
MEM0822-PWPp-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 18473 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 20029 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 21767 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 39158 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 39158 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 56 | h | 223 | 1
MEM0823-PWPl-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 56 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1023 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1023 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 33564 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 7355 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 7355 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 33564 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 127879 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 91548 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 9792 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 9792 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 483 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 483 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1756 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 51089 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 51089 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1756 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 51089 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 51089 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1756 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 11495 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 11495 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1438 | h | 223 | 1
EEE0822-PWPe-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1438 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 4500 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 4335 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 4335 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 51089 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 41576 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 155 | h | 223 | 1
MSD0822-CWP-508 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 155 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 33964 | h | 223 | 1
MSD0822-CWP-509 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 33964 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 31643 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 51089 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 51089 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 10286 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 6479 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 6494 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 31930 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 31930 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1591 | h | 223 | 1
JIL0822-PWPe-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1591 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 10286 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 160509 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 9792 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 9792 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 9792 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 9792 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3754 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 23570 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1157 | h | 223 | 1
EEE0822-PWPp-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1157 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 21767 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3061 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3061 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 62703 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 21767 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 31930 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 31930 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 45265 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 100584 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 100584 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 11131 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1582 | h | 223 | 1
MEM0822-PWPl-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1582 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 45265 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 100584 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 100584 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 11131 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1582 | h | 223 | 1
MEM0822-PWPl-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1582 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 45265 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 82284 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 82284 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 11131 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1582 | h | 223 | 1
MEM0822-PWPl-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1582 | h | 223 | 1
MRF0822-CWP-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 13192 | h | 223 | 1
MRF0822-CWP-243 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 13192 | h | 223 | 1
MCD0822-CWP-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 26384 | h | 223 | 1
MCD0822-CWP-244 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 26384 | h | 223 | 1
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1649 | h | 223 | 1
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1649 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 7624 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 7624 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2627 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 20029 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2627 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 6120 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 6120 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 19856 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 19856 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 15043 | h | 223 | 1
SES0823-PWPl-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 15043 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1299 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1157 | h | 223 | 1
EEE0823-PWPp-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1157 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 147365 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 147365 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 23570 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 6120 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 6120 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 6120 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2270 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2270 | h | 223 | 1
MRF0826-CWP-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 23280 | h | 223 | 1
MRF0826-CWP-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 23280 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 20029 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1299 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1157 | h | 223 | 1
EEE0826-PWPp-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1157 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 23570 | h | 223 | 1
MEM0826-CWP-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 825 | h | 223 | 1
MEM0826-CWP-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 825 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 166755 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 166755 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1905 | h | 223 | 1
MEM0826-PWPl-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1905 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 18517 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 38883 | h | 223 | 1
MRF0827-CWP-357 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 38883 | h | 223 | 1
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 290 | h | 223 | 1
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 290 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 15043 | h | 223 | 1
SES0827-PWPl-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 15043 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 9894 | h | 223 | 1
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 9894 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 7624 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 7624 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 23570 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 16268 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 16268 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 20029 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
EEE0827-CWP-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 32592 | h | 223 | 1
EEE0827-CWP-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 32592 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5620 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5620 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 24858 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 24858 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1591 | h | 223 | 1
JIL0827-PWPe-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1591 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 10286 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2270 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2270 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 39772 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 39772 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 16893 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 16893 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 12255 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3297 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3297 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 259962 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 564 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2627 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 15085 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 15085 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 16004 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 16004 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 7321 | h | 223 | 1
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 30300 | h | 223 | 1
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 30300 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 11748 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 8377 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 8377 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 26189 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 6271 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 22738 | h | 223 | 1
EEE1062-PWPp-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 22738 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 21274 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 21274 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 4500 | h | 223 | 1
SWP-029-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 52358 | h | 223 | 1
SWP-029-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 52358 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3723 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3723 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1438 | h | 223 | 1
EEE1062-PWPe-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1438 | h | 223 | 1
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 372 | h | 223 | 1
EEE1062-CWP-381 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 372 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 45585 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 45585 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1591 | h | 223 | 1
JIL1214-PWPe-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1591 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 26477 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 15875 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 15875 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 7243 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 7243 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 72937 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 72937 | h | 223 | 1
MEM0823-CWP-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 32592 | h | 223 | 1
MEM0823-CWP-248 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 32592 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 128848 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 128848 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1299 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 45144 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 45144 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 169822 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1004 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1004 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 49068 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1139 | h | 223 | 1
B22043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1139 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 251608 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 11224 | h | 223 | 1
TTU0623-CWP-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 384 | h | 223 | 1
TTU0623-CWP-411 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 384 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3016 | h | 223 | 1
TTU0622-PWPp-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3016 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 114551 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2627 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3012 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 15270 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 15270 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 3012 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 30539 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 30539 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 1591 | h | 223 | 1
JIL0622-PWPe-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 1591 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 10286 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 10994 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 10994 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 8987 | h | 223 | 1
KMT0622-PWPe-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 8987 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 46384 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 46384 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 2627 | h | 223 | 1
JIL0622-PWPe-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 2627 | h | 223 | 1
MCD0822-CWP-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 887440 | h | 223 | 1
MCD0822-CWP-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 887440 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 22738 | h | 223 | 1
EEE1052-PWPp-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 22738 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 22738 | h | 223 | 1
EEE1063-PWPp-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 22738 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 20843 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 20843 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 20843 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 20843 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 35370 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 35370 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 43663 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 4708 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 4708 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-04 | 4708 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-04 | 4708 | h | 223 | 1
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 7834 | h | 223 | 1
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 7834 | h | 223 | 1
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 826 | h | 223 | 1
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 826 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 2334 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 6152 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 6152 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 258 | h | 223 | 1
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 610 | h | 223 | 1
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 610 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 6822 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 1697 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 4148 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 4148 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 1697 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 4148 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 4148 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 1697 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 3393 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 3393 | h | 223 | 1
MRF0822-CWP-243 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 544 | h | 223 | 1
MRF0822-CWP-243 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 544 | h | 223 | 1
MCD0822-CWP-244 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 1088 | h | 223 | 1
MCD0822-CWP-244 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 1088 | h | 223 | 1
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 68 | h | 223 | 1
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 68 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 5039 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 829 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 829 | h | 223 | 1
MRF0826-CWP-291 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 1067 | h | 223 | 1
MRF0826-CWP-291 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 1067 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 10 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 10 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 1603 | h | 223 | 1
MRF0827-CWP-357 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 1603 | h | 223 | 1
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 12 | h | 223 | 1
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 12 | h | 223 | 1
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 408 | h | 223 | 1
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 408 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 671 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 671 | h | 223 | 1
EEE0827-CWP-345 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 1344 | h | 223 | 1
EEE0827-CWP-345 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 1344 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 697 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 697 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 136 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 136 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 10721 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 660 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 660 | h | 223 | 1
SWP-029-1062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 11257 | h | 223 | 1
SWP-029-1062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 11257 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 299 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 299 | h | 223 | 1
MEM0823-CWP-248 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 1344 | h | 223 | 1
MEM0823-CWP-248 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 1344 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 5314 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 5314 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 1862 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 1862 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 968 | h | 223 | 1
TTU0623-CWP-411 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 11 | h | 223 | 1
TTU0623-CWP-411 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 11 | h | 223 | 1
MCD0822-CWP-540 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-04 | 36600 | h | 223 | 1
MCD0822-CWP-540 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-04 | 36600 | h | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-02-11 | 0 | m | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-02-11 | 0 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-02-11 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-02-11 | 13 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-02-11 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-02-11 | 41 | m | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-11 | 25 | t | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-11 | 25 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-11 | 1 | t | 223 | 1
MEM0823-CWP-495 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-11 | 1 | t | 223 | 1
SES0827-CWP-452 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-11 | 19 | t | 223 | 1
SES0827-CWP-452 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-11 | 19 | t | 223 | 1
MCD0822-CWP-540 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-11 | 0 | t | 223 | 1
MCD0822-CWP-540 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-11 | 0 | t | 223 | 1
MCD0822-CWP-541 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-11 | 57 | t | 223 | 1
MCD0822-CWP-541 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-11 | 57 | t | 223 | 1
SES0822-CWP-546 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-11 | 10 | t | 223 | 1
SES0822-CWP-546 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-11 | 10 | t | 223 | 1
SES0822-CWP-549 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-11 | 12 | t | 223 | 1
SES0822-CWP-549 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-11 | 12 | t | 223 | 1
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-02-11 | 196 | m | 223 | 1
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-02-11 | 196 | m | 223 | 1
EEE0827-CWP-345 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-02-11 | 7 | un | 223 | 1
EEE0827-CWP-345 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-02-11 | 7 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-02-11 | 2 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-02-11 | 2 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-02-11 | 34 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-02-11 | 34 | un | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 3 | t | 223 | 1
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 1 | t | 223 | 1
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 3 | t | 223 | 1
MEM0822-CWP-118 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 3 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 3 | t | 223 | 1
MEM0822-CWP-122 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 3 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 3 | t | 223 | 1
MEM0822-CWP-126 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 3 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 2 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 2 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 1 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 1 | t | 223 | 1
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 1 | t | 223 | 1
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 1 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-11 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-11 | 13 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-11 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-11 | 0 | t | 223 | 1
MRF0822-CWP-245 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-11 | 1 | t | 223 | 1
MRF0822-CWP-245 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-11 | 1 | t | 223 | 1
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-11 | 0 | t | 223 | 1
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-11 | 0 | t | 223 | 1
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-11 | 0 | t | 223 | 1
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-11 | 0 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-02-11 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-02-11 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-02-11 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-02-11 | 8 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-02-11 | 2 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-02-11 | 2 | t | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 637 | h | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 637 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 40073 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 40073 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 158297 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 158297 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 40073 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 40073 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 31651 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 46384 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 46384 | h | 223 | 1
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 20892 | h | 223 | 1
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 20892 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 40073 | h | 223 | 1
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 40073 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5463 | h | 223 | 1
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 40073 | h | 223 | 1
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 40073 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3714 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 56606 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 10286 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 40073 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 40073 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 47816 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7684 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7684 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 902 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7355 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7355 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3012 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 334815 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 88671 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 88671 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 2627 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1299 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 88671 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 88671 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 46384 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 46384 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 380901 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 380901 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 334815 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 14212 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 14212 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7684 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7684 | h | 223 | 1
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 88671 | h | 223 | 1
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3012 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 2589 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 16048 | h | 223 | 1
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 14792 | h | 223 | 1
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 14792 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 33083 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 33083 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 16979 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 10160 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 10160 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 20029 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 21767 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 21677 | h | 223 | 1
SES0822-PWPl-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 21677 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 33564 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7355 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7355 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 33564 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 127879 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 91548 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1399 | h | 223 | 1
ERE0822-PWPl-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1399 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 31930 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 31930 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 181 | h | 223 | 1
EEE0820-PWPe-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 181 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1756 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 51089 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 51089 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1756 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 51089 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 51089 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1756 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 51089 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 51089 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 4500 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7357 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7357 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 51089 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 51089 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 41576 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 31643 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 51089 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 51089 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 10286 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 6479 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 6494 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 51089 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 51089 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 10286 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 160509 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1399 | h | 223 | 1
ERE0822-PWPl-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1399 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1399 | h | 223 | 1
ERE0822-PWPl-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1399 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3754 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 23570 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 637 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 637 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1633 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1633 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 21767 | h | 223 | 1
JIL0822-PWPp-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 21767 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3061 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3061 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 62703 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 21767 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 51089 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 51089 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 45265 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 61189 | h | 223 | 1
MEM0822-CWP-118 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 61189 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 11131 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 39395 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 39395 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 45265 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 61189 | h | 223 | 1
MEM0822-CWP-122 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 61189 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 11131 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 32228 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 32228 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 45265 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 50056 | h | 223 | 1
MEM0822-CWP-126 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 50056 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 11131 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 39395 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 39395 | h | 223 | 1
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 8243 | h | 223 | 1
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 8243 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7624 | h | 223 | 1
MEM0823-PWPl-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7624 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 2627 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 20029 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 2627 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 637 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 637 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3519 | h | 223 | 1
MCD0823-PWPp-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3519 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 45 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 45 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 9928 | h | 223 | 1
MEM0823-CWP-495 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 9928 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1299 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 147365 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 147365 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 23570 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3519 | h | 223 | 1
MCD0824-PWPp-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3519 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3519 | h | 223 | 1
MCD0824-PWPp-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3519 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1257 | h | 223 | 1
MEM0824-PWPl-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1257 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 637 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 637 | h | 223 | 1
MRF0826-CWP-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 23280 | h | 223 | 1
MRF0826-CWP-291 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 23280 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 20029 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1299 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 23570 | h | 223 | 1
MEM0826-CWP-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 32980 | h | 223 | 1
MEM0826-CWP-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 32980 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 166755 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 166755 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18517 | h | 223 | 1
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 290 | h | 223 | 1
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 290 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 9894 | h | 223 | 1
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 9894 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7624 | h | 223 | 1
MEM0827-PWPl-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7624 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 23570 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 72303 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 72303 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 20029 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
EEE0827-CWP-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 32592 | h | 223 | 1
EEE0827-CWP-345 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 32592 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 18514 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 18514 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 39772 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 39772 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 10286 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1257 | h | 223 | 1
MEM0827-PWPl-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1257 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 39772 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 39772 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 16893 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 16893 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 12255 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3297 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3297 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 259962 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 564 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 2627 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 15085 | h | 223 | 1
JIL0827-PWPl-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 15085 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 16004 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 16004 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7321 | h | 223 | 1
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 30300 | h | 223 | 1
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 30300 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 11748 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 37229 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 37229 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 26189 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 6271 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 6271 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 5684 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 5684 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 21274 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 21274 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 4500 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 16546 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 16546 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 72937 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 72937 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 26477 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 12303 | h | 223 | 1
MEM1214-PWPp-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 12303 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7243 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7243 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 56526 | h | 223 | 1
EEE1214-EWPc-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 56526 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 128848 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 128848 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1299 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 45144 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 45144 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 169822 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 1004 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 1004 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 49068 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 251608 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 11224 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 114551 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 114551 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 2627 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3012 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 24431 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3012 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 48863 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 48863 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 10286 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 48863 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 48863 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 46384 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 46384 | h | 223 | 1
MCD0822-CWP-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 7395 | h | 223 | 1
MCD0822-CWP-540 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 7395 | h | 223 | 1
MCD0822-CWP-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 880045 | h | 223 | 1
MCD0822-CWP-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 880045 | h | 223 | 1
SES0822-CWP-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 161459 | h | 223 | 1
SES0822-CWP-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 161459 | h | 223 | 1
SES0822-CWP-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 187880 | h | 223 | 1
SES0822-CWP-549 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 187880 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 35370 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 35370 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 35370 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 35370 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 35370 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 35370 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 43663 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 4708 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 4708 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 4708 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 4708 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-11 | 3447 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-11 | 3447 | h | 223 | 1
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 19584 | h | 223 | 1
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 19584 | h | 223 | 1
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 862 | h | 223 | 1
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 862 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 2334 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 15708 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 15708 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 258 | h | 223 | 1
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 610 | h | 223 | 1
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 610 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 1364 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 1364 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 6822 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 1697 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 2523 | h | 223 | 1
MEM0822-CWP-118 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 2523 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 1329 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 1329 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 1697 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 2523 | h | 223 | 1
MEM0822-CWP-122 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 2523 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 1329 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 1329 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 1697 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 2064 | h | 223 | 1
MEM0822-CWP-126 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 2064 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 1329 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 1329 | h | 223 | 1
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 340 | h | 223 | 1
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 340 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 5039 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 2 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 2 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 331 | h | 223 | 1
MEM0823-CWP-495 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 331 | h | 223 | 1
MRF0826-CWP-291 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 853 | h | 223 | 1
MRF0826-CWP-291 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 853 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 408 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 408 | h | 223 | 1
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 12 | h | 223 | 1
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 12 | h | 223 | 1
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 408 | h | 223 | 1
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 408 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 2982 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 2982 | h | 223 | 1
EEE0827-CWP-345 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 1344 | h | 223 | 1
EEE0827-CWP-345 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 1344 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 697 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 697 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 136 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 136 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 10721 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 660 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 660 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 299 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 299 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 5314 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 5314 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 1862 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 1862 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 968 | h | 223 | 1
TTU0623-CWP-411 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 5 | h | 223 | 1
TTU0623-CWP-411 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 5 | h | 223 | 1
MCD0822-CWP-540 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 305 | h | 223 | 1
MCD0822-CWP-540 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 305 | h | 223 | 1
MCD0822-CWP-541 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 36295 | h | 223 | 1
MCD0822-CWP-541 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 36295 | h | 223 | 1
SES0822-CWP-546 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 6662 | h | 223 | 1
SES0822-CWP-546 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 6662 | h | 223 | 1
SES0822-CWP-549 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-11 | 7752 | h | 223 | 1
SES0822-CWP-549 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-11 | 7752 | h | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-02-18 | 1 | m | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-02-18 | 1 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-02-18 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-02-18 | 13 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-02-18 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-02-18 | 41 | m | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-18 | 25 | t | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-18 | 25 | t | 223 | 1
SES0827-CWP-452 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-18 | 9 | t | 223 | 1
SES0827-CWP-452 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-18 | 9 | t | 223 | 1
MCD0822-CWP-541 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-18 | 24 | t | 223 | 1
MCD0822-CWP-541 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-18 | 24 | t | 223 | 1
SES0822-CWP-546 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-18 | 2 | t | 223 | 1
SES0822-CWP-546 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-18 | 2 | t | 223 | 1
SES0822-CWP-547 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-18 | 12 | t | 223 | 1
SES0822-CWP-547 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-18 | 12 | t | 223 | 1
SES0822-CWP-548 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-18 | 9 | t | 223 | 1
SES0822-CWP-548 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-18 | 9 | t | 223 | 1
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-02-18 | 196 | m | 223 | 1
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-02-18 | 196 | m | 223 | 1
JIL0827-CWP-349 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-02-18 | 7 | un | 223 | 1
JIL0827-CWP-349 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-02-18 | 7 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-02-18 | 2 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-02-18 | 2 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-02-18 | 34 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-02-18 | 34 | un | 223 | 1
EEE1048-CWP-472 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 22 | un | 223 | 1
EEE1048-CWP-472 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 22 | un | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 3 | t | 223 | 1
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 1 | t | 223 | 1
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 2 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 4 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 4 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 2 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 4 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 4 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 2 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 4 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 4 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 1 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 1 | t | 223 | 1
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 0 | t | 223 | 1
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 0 | t | 223 | 1
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 1 | t | 223 | 1
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 1 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-18 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-18 | 13 | t | 223 | 1
MSD0817-CWP-033 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-02-18 | 1 | un | 223 | 1
MSD0817-CWP-033 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-02-18 | 1 | un | 223 | 1
MSD0827-CWP-323 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-02-18 | 1 | un | 223 | 1
MSD0827-CWP-323 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-02-18 | 1 | un | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-18 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-18 | 0 | t | 223 | 1
MRF0822-CWP-245 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-18 | 0 | t | 223 | 1
MRF0822-CWP-245 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-18 | 0 | t | 223 | 1
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-18 | 0 | t | 223 | 1
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-18 | 0 | t | 223 | 1
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-18 | 0 | t | 223 | 1
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-18 | 0 | t | 223 | 1
ESD1048-CWP-470 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-02-18 | 3 | unid | 223 | 1
ESD1048-CWP-470 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-02-18 | 3 | unid | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-02-18 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-02-18 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-02-18 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-02-18 | 8 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-02-18 | 2 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-02-18 | 2 | t | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2228 | h | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2228 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 40073 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 40073 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 158297 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 158297 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 40073 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 40073 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 31651 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 46384 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 46384 | h | 223 | 1
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 20892 | h | 223 | 1
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 20892 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MSD0817-CWP-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 9700 | h | 223 | 1
MSD0817-CWP-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 9700 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 40073 | h | 223 | 1
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 40073 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5463 | h | 223 | 1
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 40073 | h | 223 | 1
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 40073 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3714 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 56606 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 10286 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 40073 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 40073 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 47816 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 7684 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 7684 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 902 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 7355 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 7355 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3012 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 13811 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 13811 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 334815 | h | 223 | 1
MEM0821-PWPp-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 334815 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 33251 | h | 223 | 1
EEE0821-EWPc-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 33251 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2627 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1299 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 88671 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 88671 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 46384 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 46384 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 380901 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 380901 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 13811 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 13811 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 334815 | h | 223 | 1
MEM0821-PWPp-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 334815 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 46816 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 46816 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 7684 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 7684 | h | 223 | 1
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 88671 | h | 223 | 1
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3012 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2589 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 16048 | h | 223 | 1
MEM0822-PWPp-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 16048 | h | 223 | 1
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 14792 | h | 223 | 1
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 14792 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 59252 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 59252 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 16979 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 35560 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 35560 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 20029 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 20029 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 33564 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 7355 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 7355 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 33564 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 127879 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 91548 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 51089 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 51089 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1756 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 51089 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 51089 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1756 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 51089 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 51089 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1756 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 51089 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 51089 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4500 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 7357 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 7357 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 19158 | h | 223 | 1
EEE0822-EWPc-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 19158 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 41576 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 31643 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 51089 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 51089 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 10286 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 6479 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 6494 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 51089 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 51089 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 10286 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 160509 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3754 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 23570 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2228 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2228 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 11428 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 11428 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3061 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3061 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 62703 | h | 223 | 1
MEM0822-PWPp-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 62703 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 21767 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 51089 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 51089 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 45265 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 11131 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 100584 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 100584 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 45265 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 11131 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 82284 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 82284 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 45265 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 11131 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 100584 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 100584 | h | 223 | 1
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 8243 | h | 223 | 1
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 8243 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2627 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 20029 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 20029 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2627 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2228 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2228 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 62 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 62 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1299 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 55262 | h | 223 | 1
EEE0823-EWPc-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 55262 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 23570 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2228 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2228 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 20029 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 20029 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 20029 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1299 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 23570 | h | 223 | 1
MEM0826-CWP-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5772 | h | 223 | 1
MEM0826-CWP-301 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5772 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 62533 | h | 223 | 1
EEE0826-EWPc-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 62533 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18517 | h | 223 | 1
MSD0827-CWP-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 19400 | h | 223 | 1
MSD0827-CWP-323 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 19400 | h | 223 | 1
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 290 | h | 223 | 1
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 290 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 728 | h | 223 | 1
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 728 | h | 223 | 1
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 9894 | h | 223 | 1
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 9894 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 23570 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 72303 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 72303 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 20029 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 20029 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 8465 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 8465 | h | 223 | 1
JIL0827-CWP-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 32592 | h | 223 | 1
JIL0827-CWP-349 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 32592 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 18514 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 18514 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 39772 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 39772 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 10286 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 14915 | h | 223 | 1
EEE0827-EWPc-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 14915 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 16893 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 16893 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 12255 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3297 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3297 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 259962 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 564 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2627 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 9602 | h | 223 | 1
MEM0830-CWP-503 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 9602 | h | 223 | 1
EEE1048-CWP-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 62888 | h | 223 | 1
EEE1048-CWP-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 62888 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 7321 | h | 223 | 1
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 30300 | h | 223 | 1
EEE1049-EWPc-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 30300 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 11748 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 37229 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 37229 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 26189 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3606 | h | 223 | 1
EEE1062-PWPp-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3606 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 35370 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 35370 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3723 | h | 223 | 1
EEE1062-EWPc-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3723 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4500 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 16546 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 16546 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 72937 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 72937 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 26477 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 7243 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 7243 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 56908 | h | 223 | 1
TST1214-CWP-394 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 56908 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1299 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 45144 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 45144 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 169822 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 1004 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 1004 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 49068 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 251608 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 403 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 403 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 65867 | h | 223 | 1
TTU0623-EWPc-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 65867 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 2627 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3012 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 24431 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 3012 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 48863 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 48863 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 10286 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 48863 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 48863 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 46384 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 46384 | h | 223 | 1
MCD0822-CWP-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 362371 | h | 223 | 1
MCD0822-CWP-541 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 362371 | h | 223 | 1
SES0822-CWP-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 26421 | h | 223 | 1
SES0822-CWP-546 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 26421 | h | 223 | 1
SES0822-CWP-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 187880 | h | 223 | 1
SES0822-CWP-547 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 187880 | h | 223 | 1
SES0822-CWP-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 137974 | h | 223 | 1
SES0822-CWP-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 137974 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 35370 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 35370 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 35370 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 35370 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 35370 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 35370 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 43663 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-18 | 4708 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-18 | 4708 | h | 223 | 1
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 19584 | h | 223 | 1
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 19584 | h | 223 | 1
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 862 | h | 223 | 1
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 862 | h | 223 | 1
MSD0817-CWP-033 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 800 | h | 223 | 1
MSD0817-CWP-033 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 800 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 2334 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 15708 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 15708 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 258 | h | 223 | 1
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 610 | h | 223 | 1
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 610 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 2444 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 2444 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 6822 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 1697 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 3394 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 3394 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 1697 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 3393 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 3393 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 1697 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 3394 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 3394 | h | 223 | 1
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 340 | h | 223 | 1
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 340 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 5039 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 3 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 3 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 408 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 408 | h | 223 | 1
MSD0827-CWP-323 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 800 | h | 223 | 1
MSD0827-CWP-323 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 800 | h | 223 | 1
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 12 | h | 223 | 1
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 12 | h | 223 | 1
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 30 | h | 223 | 1
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 30 | h | 223 | 1
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 408 | h | 223 | 1
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 408 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 2982 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 2982 | h | 223 | 1
ELU0827-CWP-346 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 1067 | h | 223 | 1
ELU0827-CWP-346 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 1067 | h | 223 | 1
JIL0827-CWP-349 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 1344 | h | 223 | 1
JIL0827-CWP-349 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 1344 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 697 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 697 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 136 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 136 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 10721 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 396 | h | 223 | 1
MEM0830-CWP-503 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 396 | h | 223 | 1
ESD1048-CWP-470 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 576 | h | 223 | 1
ESD1048-CWP-470 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 576 | h | 223 | 1
EEE1048-CWP-472 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 4416 | h | 223 | 1
EEE1048-CWP-472 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 4416 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 299 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 299 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 2347 | h | 223 | 1
TST1214-CWP-394 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 2347 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 1862 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 1862 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 968 | h | 223 | 1
MCD0822-CWP-541 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 14945 | h | 223 | 1
MCD0822-CWP-541 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 14945 | h | 223 | 1
SES0822-CWP-546 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 1090 | h | 223 | 1
SES0822-CWP-546 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 1090 | h | 223 | 1
SES0822-CWP-547 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 7752 | h | 223 | 1
SES0822-CWP-547 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 7752 | h | 223 | 1
SES0822-CWP-548 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-18 | 5693 | h | 223 | 1
SES0822-CWP-548 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-18 | 5693 | h | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-02-25 | 1 | m | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-02-25 | 1 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-02-25 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-02-25 | 13 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-02-25 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-02-25 | 41 | m | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-25 | 26 | t | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-25 | 26 | t | 223 | 1
SES0822-CWP-545 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-25 | 30 | t | 223 | 1
SES0822-CWP-545 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-25 | 30 | t | 223 | 1
SES0822-CWP-548 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-02-25 | 3 | t | 223 | 1
SES0822-CWP-548 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-02-25 | 3 | t | 223 | 1
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-02-25 | 73 | m | 223 | 1
TTU0813-CWP-504 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-02-25 | 73 | m | 223 | 1
TTU0823-CWP-505 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-02-25 | 83 | m | 223 | 1
TTU0823-CWP-505 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-02-25 | 83 | m | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-02-25 | 2 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-02-25 | 2 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-02-25 | 34 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-02-25 | 34 | un | 223 | 1
EEE1048-CWP-472 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 17 | un | 223 | 1
EEE1048-CWP-472 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 17 | un | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 3 | t | 223 | 1
MEM0820-CWP-496 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 3 | t | 223 | 1
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 1 | t | 223 | 1
TTU0822-CWP-432 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 2 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 5 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 5 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 2 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 4 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 4 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 2 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 5 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 5 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 1 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 1 | t | 223 | 1
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 0 | t | 223 | 1
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 0 | t | 223 | 1
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 0 | t | 223 | 1
TTU0827-CWP-455 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 0 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 1 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-02-25 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-02-25 | 13 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-25 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-25 | 0 | t | 223 | 1
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-25 | 0 | t | 223 | 1
MEM0827-CWP-466 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-25 | 0 | t | 223 | 1
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-02-25 | 0 | t | 223 | 1
TTU0623-CWP-411 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-02-25 | 0 | t | 223 | 1
ESD1048-CWP-470 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-02-25 | 0 | unid | 223 | 1
ESD1048-CWP-470 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-02-25 | 0 | unid | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-02-25 | 43 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-02-25 | 43 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-02-25 | 0 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-02-25 | 0 | tons | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-02-25 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-02-25 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-02-25 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-02-25 | 8 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-02-25 | 2 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-02-25 | 2 | t | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2228 | h | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2228 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 40073 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 40073 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 158297 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 158297 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 40073 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 40073 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 31651 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 46384 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 46384 | h | 223 | 1
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 7835 | h | 223 | 1
TTU0813-CWP-504 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 7835 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MSD0817-CWP-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 9700 | h | 223 | 1
MSD0817-CWP-033 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 9700 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 40073 | h | 223 | 1
EBD0800-EWPc-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 40073 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5463 | h | 223 | 1
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 40073 | h | 223 | 1
JIL0800-EWPc-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 40073 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3714 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 56606 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 10286 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 40073 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 40073 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 47816 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 961 | h | 223 | 1
EEE0821-PWPl-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 961 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 902 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 7355 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 7355 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3012 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 96678 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2627 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1299 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 88671 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 88671 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 46384 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 46384 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 406295 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 406295 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 96678 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 46816 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 46816 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 961 | h | 223 | 1
EEE0821-PWPl-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 961 | h | 223 | 1
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 88671 | h | 223 | 1
EBD0821-EWPc-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 88671 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3012 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2589 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 14792 | h | 223 | 1
TTU0822-CWP-432 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 14792 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 63202 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 63202 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 168016 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 168016 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 16979 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 35560 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 35560 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 15523 | h | 223 | 1
MEM0822-PWPp-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 15523 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 33564 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4072 | h | 223 | 1
MEM0822-PWPl-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4072 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 257322 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 257322 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 33564 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 127879 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 91548 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 51089 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 51089 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1756 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 19158 | h | 223 | 1
EEE0820-EWPc-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 19158 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1756 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 19158 | h | 223 | 1
EEE0820-EWPc-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 19158 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1756 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 51089 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 51089 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4500 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 7357 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 7357 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 41576 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 31643 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 39594 | h | 223 | 1
JIL0822-EWPc-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 39594 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 10286 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 6479 | h | 223 | 1
MEM0822-PWPp-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 6479 | h | 223 | 1
MEM0822-PWPp-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 6479 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 6494 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 51089 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 51089 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 10286 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 160509 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3754 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 23570 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2228 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2228 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 11428 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 11428 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3061 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3061 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 21767 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 51089 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 51089 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 45265 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 11131 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 107290 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 107290 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 45265 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 11131 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 87770 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 87770 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 45265 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 11131 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 107290 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 107290 | h | 223 | 1
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1649 | h | 223 | 1
MRF0822-CWP-245 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1649 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2627 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 15523 | h | 223 | 1
MEM0823-PWPp-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 15523 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2627 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2228 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2228 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1725 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1725 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 66 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 66 | h | 223 | 1
TTU0823-CWP-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 8854 | h | 223 | 1
TTU0823-CWP-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 8854 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1299 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 897 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 897 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 23570 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1725 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1725 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1725 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1725 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2228 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2228 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 15523 | h | 223 | 1
MEM0826-PWPp-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 15523 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 15523 | h | 223 | 1
MEM0826-PWPp-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 15523 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1299 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 23570 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18517 | h | 223 | 1
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 290 | h | 223 | 1
MEM0827-CWP-466 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 290 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 728 | h | 223 | 1
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 728 | h | 223 | 1
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 9894 | h | 223 | 1
TTU0827-CWP-455 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 9894 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 23570 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 72303 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 72303 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 15523 | h | 223 | 1
MEM0827-PWPp-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 15523 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 8465 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 8465 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 18514 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 18514 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 39772 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 39772 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 10286 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 16893 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 16893 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 12255 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3297 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3297 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 259962 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 564 | h | 223 | 1
CDC0827-CWP-351 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 564 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2627 | h | 223 | 1
EEE1048-CWP-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 48913 | h | 223 | 1
EEE1048-CWP-472 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 48913 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 7321 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 11748 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 37229 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 37229 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 26189 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 35370 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 35370 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4500 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 16546 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 16546 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 72937 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 72937 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 26477 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3820 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3820 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 7243 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 7243 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 1299 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 48154 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 48154 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 169822 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 556 | h | 223 | 1
B30183 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 556 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 49068 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 251608 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 251608 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 902 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 2627 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3012 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 24431 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3012 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 48863 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 48863 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 10286 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 48863 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 48863 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 46384 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 46384 | h | 223 | 1
SES0822-CWP-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 463978 | h | 223 | 1
SES0822-CWP-545 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 463978 | h | 223 | 1
SES0822-CWP-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 49906 | h | 223 | 1
SES0822-CWP-548 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 49906 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 35370 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 35370 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 35370 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 35370 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 34738 | h | 223 | 1
EEE1061-PWPl-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 34738 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 43663 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 3952 | h | 223 | 1
MMR0824-PWPl-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 3952 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-02-25 | 4708 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-02-25 | 4708 | h | 223 | 1
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 11750 | h | 223 | 1
ELU0800-CWP-062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 11750 | h | 223 | 1
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 323 | h | 223 | 1
TTU0813-CWP-504 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 323 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 2334 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 16755 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 16755 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 258 | h | 223 | 1
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 610 | h | 223 | 1
TTU0822-CWP-432 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 610 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 2606 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 2606 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 6929 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 6929 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 6822 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 1697 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 3620 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 3620 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 1697 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 3620 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 3620 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 1697 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 3620 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 3620 | h | 223 | 1
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 68 | h | 223 | 1
MRF0822-CWP-245 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 68 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 5039 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 3 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 3 | h | 223 | 1
TTU0823-CWP-505 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 365 | h | 223 | 1
TTU0823-CWP-505 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 365 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 37 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 37 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 408 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 408 | h | 223 | 1
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 12 | h | 223 | 1
MEM0827-CWP-466 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 12 | h | 223 | 1
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 30 | h | 223 | 1
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 30 | h | 223 | 1
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 408 | h | 223 | 1
TTU0827-CWP-455 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 408 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 2982 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 2982 | h | 223 | 1
ELU0827-CWP-346 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 853 | h | 223 | 1
ELU0827-CWP-346 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 853 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 697 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 697 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 136 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 136 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 10721 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 299 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 299 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 1986 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 1986 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 968 | h | 223 | 1
SES0822-CWP-545 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 19136 | h | 223 | 1
SES0822-CWP-545 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 19136 | h | 223 | 1
SES0822-CWP-548 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-02-25 | 2059 | h | 223 | 1
SES0822-CWP-548 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-02-25 | 2059 | h | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-03 | 1 | m | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-03 | 1 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-03-03 | 13 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-03-03 | 13 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-03-03 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-03-03 | 41 | m | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-03-03 | 30 | t | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-03-03 | 30 | t | 223 | 1
TTU0823-CWP-505 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-03-03 | 117 | m | 223 | 1
TTU0823-CWP-505 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-03-03 | 117 | m | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-03 | 2 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-03 | 2 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-03 | 34 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-03 | 34 | un | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 2 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 5 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 5 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 2 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 5 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 5 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 2 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 5 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 5 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 0 | t | 223 | 1
MEM0826-CWP-301 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 0 | t | 223 | 1
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 0 | t | 223 | 1
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 0 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 1 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-03 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-03 | 13 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-03 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-03 | 0 | t | 223 | 1
ESD0822-CWP-493 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-03-03 | 2 | unid | 223 | 1
ESD0822-CWP-493 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-03-03 | 2 | unid | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-03 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-03 | 6 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-03 | 201 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-03 | 201 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-03 | 9 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-03 | 9 | tons | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-03-03 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-03-03 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-03-03 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-03-03 | 8 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-03-03 | 3 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-03-03 | 3 | t | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2228 | h | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2228 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 31056 | h | 223 | 1
KMT0800-EWPc-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 31056 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 158297 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 158297 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 31056 | h | 223 | 1
RIN0800-EWPc-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 31056 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 31651 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 35947 | h | 223 | 1
KMT0800-PWPp-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 35947 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5463 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5463 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3714 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 33564 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 33564 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 56606 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 56606 | h | 223 | 1
ESD0822-CWP-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 7275 | h | 223 | 1
ESD0822-CWP-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 7275 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 10286 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15027 | h | 223 | 1
JIL0820-EWPc-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15027 | h | 223 | 1
SWP-004-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 14765 | h | 223 | 1
SWP-004-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 14765 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 47816 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0824-PWPl-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 902 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5122 | h | 223 | 1
MEM0821-PWPl-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5122 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0821-PWPl-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3012 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 96678 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2627 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1299 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 68720 | h | 223 | 1
KMT0821-EWPc-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 68720 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 35947 | h | 223 | 1
KMT0821-PWPp-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 35947 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 457082 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 457082 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 22171 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0821-PWPl-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 96678 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 46816 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 46816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3012 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2589 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 4414 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 4414 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0822-PWPl-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0822-PWPl-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0822-PWPl-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 71103 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 71103 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 780461 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 780461 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 16979 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 35560 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 35560 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 27298 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 33564 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 33564 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 250889 | h | 223 | 1
MEM0822-PWPp-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 250889 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 86314 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 33564 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 33564 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 127879 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 91548 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 51089 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 51089 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1756 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 39594 | h | 223 | 1
EEE0822-EWPc-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 39594 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 4500 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5124 | h | 223 | 1
MEM0822-PWPl-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5124 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 41576 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 31643 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 10286 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2969 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2969 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 6494 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 19158 | h | 223 | 1
JIL0822-EWPc-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 19158 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 10286 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 160509 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3754 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 23570 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2228 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2228 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 11428 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 11428 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3061 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3061 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 17243 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 17243 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 21767 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 19158 | h | 223 | 1
JIL0822-EWPc-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 19158 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 45265 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 11131 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 11131 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 120701 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 120701 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 45265 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 11131 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 11131 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 98741 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 98741 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 45265 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 11131 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 11131 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 120701 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 120701 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2627 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0823-PWPl-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2627 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2228 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2228 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2356 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2356 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 75 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 75 | h | 223 | 1
TTU0823-CWP-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 12482 | h | 223 | 1
TTU0823-CWP-505 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 12482 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1299 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 35888 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 35888 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0824-PWPl-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0824-PWPl-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 23570 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2356 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2356 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2356 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2356 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2228 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2228 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1299 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 23570 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18517 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 728 | h | 223 | 1
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 728 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 23570 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 72303 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 72303 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1299 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 8465 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 8465 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18183 | h | 223 | 1
MCD0827-PWPl-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18183 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 14915 | h | 223 | 1
JIL0827-EWPc-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 14915 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 10286 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 16893 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 16893 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 12255 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3297 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3297 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 259962 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2627 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 7321 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 11748 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 28852 | h | 223 | 1
RIN1110-EWPc-387 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 28852 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 26189 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 26189 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2679 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2679 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 35370 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 35370 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 4500 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 16546 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 16546 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 27351 | h | 223 | 1
JIL1214-EWPc-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 27351 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 26477 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 6483 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 6483 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 7243 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 7243 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 1299 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 54173 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 54173 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 169822 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 49068 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 64160 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 64160 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 150965 | h | 223 | 1
B30373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 150965 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 902 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 2627 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3012 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 24431 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 3012 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 48863 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 48863 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 10286 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 48863 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 48863 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 35947 | h | 223 | 1
KMT0622-PWPp-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 35947 | h | 223 | 1
MEM1214-PWPl-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 15928 | h | 223 | 1
MEM1214-PWPl-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 15928 | h | 223 | 1
SES0822-PWPl-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 167819 | h | 223 | 1
SES0822-PWPl-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 167819 | h | 223 | 1
SES0822-PWPl-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 167819 | h | 223 | 1
SES0822-PWPl-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 167819 | h | 223 | 1
SES0822-PWPl-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 167819 | h | 223 | 1
SES0822-PWPl-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 167819 | h | 223 | 1
EEE1063-CWP-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 18000 | h | 223 | 1
EEE1063-CWP-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 18000 | h | 223 | 1
EEE1061-CWP-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 26696 | h | 223 | 1
EEE1061-CWP-585 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 26696 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 24633 | h | 223 | 1
EEE1052-PWPl-583 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 24633 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 24633 | h | 223 | 1
EEE1063-PWPl-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 24633 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0822-PWPl-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 43663 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 589 | h | 223 | 1
MMR0821-PWPl-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 589 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-03 | 4708 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-03 | 4708 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 223 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 223 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 2334 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 2334 | h | 223 | 1
ESD0822-CWP-493 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 300 | h | 223 | 1
ESD0822-CWP-493 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 300 | h | 223 | 1
SWP-004-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 3174 | h | 223 | 1
SWP-004-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 3174 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 18850 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 18850 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 914 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 258 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 2932 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 2932 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 32185 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 32185 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 6822 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 1697 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 4073 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 4073 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 1697 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 4072 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 4072 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 1697 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 4073 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 4073 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 5039 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 3 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 3 | h | 223 | 1
TTU0823-CWP-505 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 515 | h | 223 | 1
TTU0823-CWP-505 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 515 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 1480 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 1480 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 398 | h | 223 | 1
MEM0826-CWP-301 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 398 | h | 223 | 1
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 30 | h | 223 | 1
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 30 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 2982 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 2982 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 697 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 697 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 136 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 136 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 10721 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 299 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 299 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 2234 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 2234 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-03 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-03 | 968 | h | 223 | 1
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-10 | 20 | m | 223 | 1
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-10 | 20 | m | 223 | 1
CEC0820-CWP-054 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-10 | 13 | m | 223 | 1
CEC0820-CWP-054 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-10 | 13 | m | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-10 | 1 | m | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-10 | 1 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-03-10 | 10 | m | 223 | 1
CDC0820-CWP-053 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-03-10 | 10 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-03-10 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-03-10 | 41 | m | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-03-10 | 30 | t | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-03-10 | 30 | t | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-03-10 | 124 | m | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-03-10 | 124 | m | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-10 | 2 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-10 | 2 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-10 | 34 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-10 | 34 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MCD0827-CWP-342 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-10 |  |  | 223 | 1
MCD0827-CWP-342 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-10 |  |  | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-10 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-10 | 2 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-10 | 5 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-10 | 5 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-10 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-10 | 2 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-10 | 5 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-10 | 5 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-10 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-10 | 2 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-10 | 5 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-10 | 5 | t | 223 | 1
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-10 | 0 | t | 223 | 1
MEM0827-CWP-454 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-10 | 0 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-10 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-10 | 1 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-10 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-10 | 13 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-10 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-10 | 0 | t | 223 | 1
ESD0822-CWP-493 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-03-10 | 3 | unid | 223 | 1
ESD0822-CWP-493 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-03-10 | 3 | unid | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-10 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-10 | 6 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-10 | 201 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-10 | 201 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-10 | 9 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-10 | 9 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-10 | 1 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-10 | 1 | tons | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-03-10 | 6 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-03-10 | 6 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-03-10 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-03-10 | 8 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-03-10 | 3 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-03-10 | 3 | t | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2228 | h | 223 | 1
EEE0800-PWPl-416 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2228 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 158297 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 158297 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 31651 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3824 | h | 223 | 1
CDC0820-CWP-053 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3824 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 468 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 468 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3714 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 28669 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 28669 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5874 | h | 223 | 1
SES0820-PWPp-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5874 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 45285 | h | 223 | 1
MEM0820-CWP-496 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 45285 | h | 223 | 1
ESD0822-CWP-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 11640 | h | 223 | 1
ESD0822-CWP-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 11640 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 10286 | h | 223 | 1
SWP-004-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 13813 | h | 223 | 1
SWP-004-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 13813 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 47816 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 307 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 902 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3012 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3012 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 96678 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 134 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2627 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2627 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1299 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 457082 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 457082 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 22171 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 96678 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 45980 | h | 223 | 1
MEM0822-PWPl-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 45980 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3012 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3012 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2589 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 10298 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 10298 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 71103 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 71103 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 780461 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 780461 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 16979 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 35560 | h | 223 | 1
MEM0822-PWPl-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 35560 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 13633 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 13633 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 27298 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 27298 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 28669 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 28669 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5874 | h | 223 | 1
SES0822-PWPp-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5874 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 86314 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 28669 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 28669 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5874 | h | 223 | 1
SES0822-PWPp-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5874 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 127879 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 91548 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 19158 | h | 223 | 1
EEE0820-EWPc-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 19158 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1756 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 4500 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 41576 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 31643 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 10286 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1782 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1782 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2969 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2969 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 6494 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 10286 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 160509 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3754 | h | 223 | 1
MCD0822-CWP-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 279347 | h | 223 | 1
MCD0822-CWP-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 279347 | h | 223 | 1
MCD0822-CWP-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 38800 | h | 223 | 1
MCD0822-CWP-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 38800 | h | 223 | 1
MCD0822-CWP-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 562573 | h | 223 | 1
MCD0822-CWP-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 562573 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 23570 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2228 | h | 223 | 1
EEE0822-PWPl-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2228 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 11428 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 11428 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3061 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3061 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 40234 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 40234 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 21767 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 45265 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 6530 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 6530 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 4452 | h | 223 | 1
MEM0822-PWPp-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 4452 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 120701 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 120701 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 45265 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 6530 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 6530 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 4452 | h | 223 | 1
MEM0822-PWPp-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 4452 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 98741 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 98741 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 45265 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 6530 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 6530 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 4452 | h | 223 | 1
MEM0822-PWPp-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 4452 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 120701 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 120701 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2627 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2627 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1275 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 13633 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 13633 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2627 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2627 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2228 | h | 223 | 1
EEE0823-PWPl-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2228 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2356 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2356 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 75 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 75 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1299 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 35888 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 35888 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 23570 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2356 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2356 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2356 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2356 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3298 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3298 | h | 223 | 1
MCD0824-CWP-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1453 | h | 223 | 1
MCD0824-CWP-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1453 | h | 223 | 1
MCD0824-CWP-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 9053 | h | 223 | 1
MCD0824-CWP-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 9053 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2228 | h | 223 | 1
EEE0826-PWPl-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2228 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 13633 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 13633 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 13633 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 13633 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1299 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 23570 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 18517 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 728 | h | 223 | 1
MEM0827-CWP-454 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 728 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 10328 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 10328 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 23570 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 72303 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 72303 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1299 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 16037 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 16037 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 8465 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 8465 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 10286 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 16893 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 16893 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 12255 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3297 | h | 223 | 1
MSD0827-CWP-305 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3297 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 259962 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2627 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2627 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 7321 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 8541 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1703 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1703 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 13706 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 13706 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 13706 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 23570 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 25534 | h | 223 | 1
JPA1062-PWPp-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 25534 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3659 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3659 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 35370 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 35370 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 4500 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 16546 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 16546 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 26477 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 6483 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 6483 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 7243 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 7243 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 1299 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 1299 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 54173 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 54173 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 13192 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 13192 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 169822 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 49068 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 49068 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 224560 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 224560 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 902 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2627 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2627 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3012 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3012 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 24431 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 3012 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 3012 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 48863 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 48863 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 10286 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 48863 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 48863 | h | 223 | 1
SWP-036-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 28578 | h | 223 | 1
SWP-036-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 28578 | h | 223 | 1
EEE1063-CWP-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 62000 | h | 223 | 1
EEE1063-CWP-584 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 62000 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0823-PWPl-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0827-PWPl-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0822-PWPl-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0823-PWPl-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0824-PWPl-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-10 | 2606 | h | 223 | 1
MMR0622-PWPl-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-10 | 2606 | h | 223 | 1
CEC0800-CWP-475 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 38 | h | 223 | 1
CEC0800-CWP-475 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 38 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 179 | h | 223 | 1
CDC0820-CWP-053 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 179 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 19 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 19 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 1868 | h | 223 | 1
MEM0820-CWP-496 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 1868 | h | 223 | 1
ESD0822-CWP-493 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 480 | h | 223 | 1
ESD0822-CWP-493 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 480 | h | 223 | 1
SWP-004-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 2970 | h | 223 | 1
SWP-004-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 2970 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 13 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 2 | h | 223 | 1
MCD0821-CWP-066 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 27 | h | 223 | 1
MCD0821-CWP-066 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 27 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 18850 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 18850 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 914 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 258 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 2932 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 2932 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 32185 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 32185 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 5232 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 6822 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 2304 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 2304 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 320 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 320 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 4640 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 4640 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 1697 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 4073 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 4073 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 1697 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 4072 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 4072 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 1697 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 4073 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 4073 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 53 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 5039 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 5039 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 3 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 3 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 1480 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 1480 | h | 223 | 1
MMR0824-CWP-445 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 453 | h | 223 | 1
MMR0824-CWP-445 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 453 | h | 223 | 1
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 21 | h | 223 | 1
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 21 | h | 223 | 1
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 133 | h | 223 | 1
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 133 | h | 223 | 1
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 30 | h | 223 | 1
MEM0827-CWP-454 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 30 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 2982 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 2982 | h | 223 | 1
MCD0827-CWP-342 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 1875 | h | 223 | 1
MCD0827-CWP-342 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 1875 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 697 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 697 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 136 | h | 223 | 1
MSD0827-CWP-305 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 136 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 10721 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 299 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 299 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 2234 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 2234 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 544 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 544 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 968 | h | 223 | 1
SWP-036-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-10 | 6144 | h | 223 | 1
SWP-036-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-10 | 6144 | h | 223 | 1
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-17 | 99 | m | 223 | 1
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-17 | 99 | m | 223 | 1
CEC0820-CWP-054 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-17 | 35 | m | 223 | 1
CEC0820-CWP-054 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-17 | 35 | m | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-17 | 1 | m | 223 | 1
CEC0823-CWP-253 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-17 | 1 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-03-17 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-03-17 | 41 | m | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-03-17 | 4 | t | 223 | 1
SES0821-CWP-070 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-03-17 | 4 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-03-17 | 13 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-03-17 | 13 | t | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-03-17 | 124 | m | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-03-17 | 124 | m | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-17 | 0 | un | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-17 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-17 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-17 | 0 | un | 223 | 1
JIL0822-CWP-164 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-17 | 15 | un | 223 | 1
JIL0822-CWP-164 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-17 | 15 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-17 | 2 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-17 | 2 | un | 223 | 1
EEE0800-CWP-416 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-17 | 0 | un | 223 | 1
EEE0800-CWP-416 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-17 | 0 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-17 | 34 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-17 | 34 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-17 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-17 | 0 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MCD0827-CWP-342 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-17 |  |  | 223 | 1
MCD0827-CWP-342 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-17 |  |  | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 10 | t | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 10 | t | 223 | 1
MEM0822-CWP-168 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 1 | t | 223 | 1
MEM0822-CWP-168 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 2 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 5 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 5 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 2 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 5 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 5 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 2 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 5 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 5 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 1 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-17 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-17 | 13 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-17 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-17 | 0 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-17 | 4 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-17 | 4 | t | 223 | 1
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-17 | 1 | t | 223 | 1
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-17 | 1 | t | 223 | 1
ESD0822-CWP-493 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-03-17 | 1 | unid | 223 | 1
ESD0822-CWP-493 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-03-17 | 1 | unid | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-17 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-17 | 6 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-17 | 201 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-17 | 201 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-17 | 56 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-17 | 56 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-17 | 9 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-17 | 9 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-17 | 2 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-17 | 2 | tons | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2024-03-17 | 2 | t | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2024-03-17 | 2 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | Budgeted Units | 2024-03-17 | 1 | t | 223 | 1
SSD0823-CWP-477 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY ESTRUT METÁLICA | Material | At Completion Units | 2024-03-17 | 1 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-03-17 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-03-17 | 8 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-03-17 | 1 | t | 223 | 1
TSD1214-CWP-491 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-03-17 | 1 | t | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 158297 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 158297 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 31651 | h | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 6378 | h | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 6378 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1226 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1226 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 3714 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 39158 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 39158 | h | 223 | 1
ESD0822-CWP-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 4365 | h | 223 | 1
ESD0822-CWP-493 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 4365 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 10286 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 47816 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 307 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 902 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 527 | h | 223 | 1
TTU0821-PWPp-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 527 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 96678 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 931 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 931 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 134 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2562 | h | 223 | 1
MEM0821-PWPp-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2562 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 24810 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 24810 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1299 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1299 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 6378 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 6378 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 184334 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 184334 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 53961 | h | 223 | 1
SES0821-CWP-070 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 53961 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 22171 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 931 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 931 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 96678 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 47816 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 47816 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 527 | h | 223 | 1
MEM0822-PWPp-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 527 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 30836 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 30836 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 10298 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 10298 | h | 223 | 1
MEM0822-CWP-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 19723 | h | 223 | 1
MEM0822-CWP-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 19723 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 71103 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 71103 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 780461 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 780461 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 16979 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23134 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23134 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 3754 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 26616 | h | 223 | 1
SES0822-PWPp-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 26616 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 39158 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 39158 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 86314 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 39158 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 39158 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 127879 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 3754 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 91548 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 91548 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 91548 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 91548 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1756 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 4500 | h | 223 | 1
JIL0822-CWP-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 69836 | h | 223 | 1
JIL0822-CWP-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 69836 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 41576 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 41576 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 41576 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1299 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1299 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 31643 | h | 223 | 1
MEM0822-PWPp-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 31643 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 10286 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 4157 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 4157 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2969 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2969 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 6494 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 10286 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 103197 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 103197 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 160509 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 3754 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 215714 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 215714 | h | 223 | 1
MCD0822-CWP-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 55869 | h | 223 | 1
MCD0822-CWP-429 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 55869 | h | 223 | 1
MCD0822-CWP-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 7760 | h | 223 | 1
MCD0822-CWP-431 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 7760 | h | 223 | 1
MCD0822-CWP-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 112515 | h | 223 | 1
MCD0822-CWP-430 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 112515 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23570 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1633 | h | 223 | 1
JIL0822-PWPl-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1633 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 3061 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 3061 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 3061 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 40234 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 40234 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 21767 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 45265 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 11428 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 11428 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 120701 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 120701 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 45265 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 11428 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 11428 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 98741 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 98741 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 45265 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 11428 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 11428 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 120701 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 120701 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2562 | h | 223 | 1
MEM0823-PWPp-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2562 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1275 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23134 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23134 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 271 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 271 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2562 | h | 223 | 1
MEM0823-PWPp-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2562 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2356 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2356 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 61 | h | 223 | 1
CEC0823-CWP-253 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 61 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1299 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1299 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 206309 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 206309 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 35888 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 35888 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 49467 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 49467 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 43263 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 43263 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 49467 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 49467 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 43263 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 43263 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 49467 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 49467 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 43263 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 43263 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23570 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2356 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2356 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2356 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2356 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 7760 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 7760 | h | 223 | 1
MCD0824-CWP-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 291 | h | 223 | 1
MCD0824-CWP-446 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 291 | h | 223 | 1
MCD0824-CWP-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1811 | h | 223 | 1
MCD0824-CWP-447 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1811 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23134 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23134 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23134 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23134 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1299 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1299 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23570 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 776 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 18517 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23134 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23134 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23570 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 72303 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 72303 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1299 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1299 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 16037 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 16037 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 8465 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 8465 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 10286 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 16893 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 16893 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 12255 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 259962 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 5492 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 5492 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2562 | h | 223 | 1
MEM0827-PWPp-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2562 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 42775 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 42775 | h | 223 | 1
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 24686 | h | 223 | 1
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 24686 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 7321 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 8541 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1745 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1745 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 298 | h | 223 | 1
EEE1049-PWPp-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 298 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 16056 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 16056 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2399 | h | 223 | 1
EEE1049-PWPp-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2399 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 16056 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 16056 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2399 | h | 223 | 1
EEE1049-PWPp-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2399 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 23570 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 7365 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 7365 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 3659 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 3659 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 4421 | h | 223 | 1
EEE1062-PWPl-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 4421 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 4500 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 16546 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 16546 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 10286 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 26477 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 26477 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 6483 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 6483 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 7243 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 7243 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 1266 | h | 223 | 1
EEE1214-PWPp-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 1266 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 21443 | h | 223 | 1
TSD1214-CWP-491 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 21443 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 13192 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 13192 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 169822 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 169822 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 243847 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 38028 | h | 223 | 1
B21793 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 38028 | h | 223 | 1
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 3797 | h | 223 | 1
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 3797 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 224560 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 224560 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 902 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2562 | h | 223 | 1
MEM0623-PWPp-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2562 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 527 | h | 223 | 1
MCD0622-PWPp-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 527 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 24431 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 16979 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 527 | h | 223 | 1
MEM0622-PWPp-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 527 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 18324 | h | 223 | 1
JIL0622-EWPc-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 18324 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 10286 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 37869 | h | 223 | 1
KMT0622-EWPc-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 37869 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 6378 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 6378 | h | 223 | 1
MEM0821-PWPl-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2080 | h | 223 | 1
MEM0821-PWPl-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2080 | h | 223 | 1
MEM0821-PWPl-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 2080 | h | 223 | 1
MEM0821-PWPl-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 2080 | h | 223 | 1
MEM0821-PWPl-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 11176 | h | 223 | 1
MEM0821-PWPl-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 11176 | h | 223 | 1
MEM0821-PWPl-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-17 | 11176 | h | 223 | 1
MEM0821-PWPl-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-17 | 11176 | h | 223 | 1
CEC0800-CWP-475 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 114 | h | 223 | 1
CEC0800-CWP-475 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 114 | h | 223 | 1
EEE0800-CWP-416 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 192 | h | 223 | 1
EEE0800-CWP-416 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 192 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 50 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 50 | h | 223 | 1
ESD0822-CWP-493 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 180 | h | 223 | 1
ESD0822-CWP-493 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 180 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 13 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 38 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 38 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 2 | h | 223 | 1
MCD0821-CWP-066 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 27 | h | 223 | 1
MCD0821-CWP-066 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 27 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 8145 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 8145 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 2225 | h | 223 | 1
SES0821-CWP-070 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 2225 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 914 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 38 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 38 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 258 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 3078 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 3078 | h | 223 | 1
MEM0822-CWP-168 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 813 | h | 223 | 1
MEM0822-CWP-168 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 813 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 2932 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 2932 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 32185 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 32185 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 5232 | h | 223 | 1
JIL0822-CWP-164 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 2880 | h | 223 | 1
JIL0822-CWP-164 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 2880 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 6822 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 8896 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 8896 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 2304 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 2304 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 320 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 320 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 4640 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 4640 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 1697 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 4073 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 4073 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 1697 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 4072 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 4072 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 1697 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 4073 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 4073 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 53 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 1008 | h | 223 | 1
SSD0823-CWP-477 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 1008 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 2 | h | 223 | 1
CEC0823-CWP-253 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 2 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 8508 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 8508 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 1480 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 1480 | h | 223 | 1
MMR0824-CWP-445 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 827 | h | 223 | 1
MMR0824-CWP-445 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 827 | h | 223 | 1
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 21 | h | 223 | 1
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 21 | h | 223 | 1
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 133 | h | 223 | 1
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 133 | h | 223 | 1
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 96 | h | 223 | 1
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 96 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 2982 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 2982 | h | 223 | 1
MCD0827-CWP-342 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 1101 | h | 223 | 1
MCD0827-CWP-342 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 1101 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 697 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 697 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 10721 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 1764 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 1764 | h | 223 | 1
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 1018 | h | 223 | 1
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 1018 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 299 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 299 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 884 | h | 223 | 1
TSD1214-CWP-491 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 884 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 544 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 544 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-17 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-17 | 968 | h | 223 | 1
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-24 | 99 | m | 223 | 1
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-24 | 99 | m | 223 | 1
CEC0820-CWP-054 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-24 | 31 | m | 223 | 1
CEC0820-CWP-054 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-24 | 31 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-03-24 | 41 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-03-24 | 41 | m | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-03-24 | 69 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-03-24 | 69 | t | 223 | 1
SES0827-CWP-307 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-03-24 | 2 | t | 223 | 1
SES0827-CWP-307 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-03-24 | 2 | t | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-03-24 | 124 | m | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-03-24 | 124 | m | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-24 | 0 | un | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-24 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-24 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-24 | 0 | un | 223 | 1
JIL0822-CWP-164 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-24 | 15 | un | 223 | 1
JIL0822-CWP-164 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-24 | 15 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-24 | 2 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-24 | 2 | un | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-24 | 21 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-24 | 21 | m | 223 | 1
EEE0800-CWP-416 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-24 | 0 | un | 223 | 1
EEE0800-CWP-416 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-24 | 0 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-24 | 34 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-24 | 34 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-24 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-24 | 0 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-24 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-24 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-24 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-24 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-24 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-24 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-24 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-24 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-24 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-24 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-24 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-24 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-24 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-24 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-24 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-24 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-24 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-24 |  |  | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 10 | t | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 10 | t | 223 | 1
MEM0822-CWP-168 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 1 | t | 223 | 1
MEM0822-CWP-168 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 2 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 5 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 5 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 2 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 5 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 5 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 2 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 5 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 5 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 1 | t | 223 | 1
MEM0827-CWP-303 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 1 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 13 | t | 223 | 1
MEM1214-CWP-400 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-24 | 8 | t | 223 | 1
MEM1214-CWP-400 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-24 | 8 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-24 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-24 | 0 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-24 | 4 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-24 | 4 | t | 223 | 1
MCD0823-CWP-264 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-24 | 4 | t | 223 | 1
MCD0823-CWP-264 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-24 | 4 | t | 223 | 1
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-24 | 1 | t | 223 | 1
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-24 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-03-24 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-03-24 | 1 | t | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-24 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-24 | 6 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-24 | 201 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-24 | 201 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-24 | 78 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-24 | 78 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-24 | 9 | tons | 223 | 1
MMR0824-CWP-274 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-24 | 9 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-24 | 2 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-24 | 2 | tons | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2024-03-24 | 2 | t | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2024-03-24 | 2 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-03-24 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-03-24 | 8 | t | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 158297 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 158297 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 31651 | h | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10823 | h | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10823 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPp-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MCD0817-PWPp-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
STP0817-PWPp-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPp-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPp-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPp-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPp-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MCD0817-PWPp-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0817-PWPp-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
ELU0817-PWPp-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
JIL0817-PWPp-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MMR0817-PWPp-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0817-PWPp-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1226 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1226 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 3714 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 39158 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 39158 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10286 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 79168 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 79168 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 47816 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 47816 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 307 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 982 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 982 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 902 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 96678 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1164 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1164 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 134 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 24190 | h | 223 | 1
JPA0821-PWPp-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 24190 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 747 | h | 223 | 1
EEE0821-PWPp-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 747 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10823 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10823 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 184334 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 184334 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 11989 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 11989 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 22171 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1164 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1164 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 96678 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 46621 | h | 223 | 1
MEM0821-PWPp-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 46621 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 982 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 982 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 34964 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 34964 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10298 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10298 | h | 223 | 1
MEM0822-CWP-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 19723 | h | 223 | 1
MEM0822-CWP-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 19723 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 71103 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 71103 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 780461 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 780461 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 16979 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23134 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23134 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 3754 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 39158 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 39158 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 86314 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 39158 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 39158 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 127879 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 127879 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 3754 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 33377 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 33377 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 52640 | h | 223 | 1
ERE0822-PWPp-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 52640 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 33377 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 33377 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 52640 | h | 223 | 1
ERE0822-PWPp-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 52640 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 33377 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 33377 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 52640 | h | 223 | 1
ERE0822-PWPp-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 52640 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1756 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1756 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1756 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1756 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 4500 | h | 223 | 1
JIL0822-CWP-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 69836 | h | 223 | 1
JIL0822-CWP-164 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 69836 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 33261 | h | 223 | 1
MEM0822-PWPp-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 33261 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 33261 | h | 223 | 1
MEM0822-PWPp-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 33261 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 747 | h | 223 | 1
EEE0822-PWPp-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 747 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10286 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10286 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 4157 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 4157 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 2969 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 2969 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 6494 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10286 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 231161 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 231161 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 160509 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 3754 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 301581 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 301581 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23570 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 2372 | h | 223 | 1
JIL0822-EWPc-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 2372 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 2372 | h | 223 | 1
JIL0822-EWPc-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 2372 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 40234 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 40234 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 21767 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 45265 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 11428 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 11428 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 120701 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 120701 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 45265 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 11428 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 11428 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 98741 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 98741 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 45265 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 11428 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 11428 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 120701 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 120701 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1275 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23134 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23134 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1686 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1686 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1304 | h | 223 | 1
MCD0823-PWPl-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1304 | h | 223 | 1
MCD0823-CWP-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 71078 | h | 223 | 1
MCD0823-CWP-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 71078 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 747 | h | 223 | 1
EEE0823-PWPp-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 747 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1061019 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1061019 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 34991 | h | 223 | 1
MMR0824-CWP-274 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 34991 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 13581 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 13581 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 13250 | h | 223 | 1
MEM0824-PWPp-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 13250 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 12023 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 12023 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 11202 | h | 223 | 1
MEM0824-PWPp-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 11202 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 48142 | h | 223 | 1
MEM0824-PWPp-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 48142 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 606 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 606 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 42105 | h | 223 | 1
MEM0824-PWPp-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 42105 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 48142 | h | 223 | 1
MEM0824-PWPp-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 48142 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 606 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 606 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 42105 | h | 223 | 1
MEM0824-PWPp-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 42105 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23570 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1304 | h | 223 | 1
MCD0824-PWPl-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1304 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 1304 | h | 223 | 1
MCD0824-PWPl-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 1304 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 7760 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 7760 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23134 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23134 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23134 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23134 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 747 | h | 223 | 1
EEE0826-PWPp-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 747 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23570 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 776 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 18517 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0827-PWPp-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MMR0827-PWPp-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MCD0827-PWPp-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23134 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23134 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0827-PWPp-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23570 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 56035 | h | 223 | 1
SES0827-CWP-452 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 56035 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 747 | h | 223 | 1
EEE0827-PWPp-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 747 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 16037 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 16037 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MCD0827-PWPp-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
STP0827-PWPp-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0827-PWPp-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
ELU0827-PWPp-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
JIL0827-PWPp-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 4233 | h | 223 | 1
ELU0827-CWP-346 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 4233 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10286 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 16893 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 16893 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 12255 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 12255 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 7888 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 7888 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 259962 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
STP0827-PWPp-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
MEM0827-PWPp-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0827-PWPp-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 659 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 5355 | h | 223 | 1
SES0827-PWPp-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 5355 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 42775 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 42775 | h | 223 | 1
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 24686 | h | 223 | 1
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 24686 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 7321 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 8541 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 2384 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 2384 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 21930 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 21930 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 21930 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 21930 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23570 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 45830 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 45830 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 3659 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 3659 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 4500 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 16546 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 16546 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10286 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 13653 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 13653 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 15224 | h | 223 | 1
MEM1214-PWPp-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 15224 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 4515 | h | 223 | 1
MEM1214-PWPl-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 4515 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 7243 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 7243 | h | 223 | 1
MEM1214-CWP-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 156707 | h | 223 | 1
MEM1214-CWP-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 156707 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 13192 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 13192 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 33027 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 29719 | h | 223 | 1
B29933 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 29719 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 33728 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 33728 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 243847 | h | 223 | 1
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 23624 | h | 223 | 1
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 23624 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 224560 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 224560 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 902 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 982 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 982 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 24431 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 16979 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 982 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 982 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10286 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 10823 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 10823 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-24 | 17247 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-24 | 17247 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 50 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 50 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 13 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 48 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 48 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 2 | h | 223 | 1
MCD0821-CWP-066 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 11 | h | 223 | 1
MCD0821-CWP-066 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 11 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 8145 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 8145 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 494 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 494 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 914 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 48 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 48 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 258 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 3490 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 3490 | h | 223 | 1
MEM0822-CWP-168 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 813 | h | 223 | 1
MEM0822-CWP-168 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 813 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 2932 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 2932 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 32185 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 32185 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 5232 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 5232 | h | 223 | 1
JIL0822-CWP-164 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 2880 | h | 223 | 1
JIL0822-CWP-164 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 2880 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 6822 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 6822 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 12437 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 12437 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 2304 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 2304 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 320 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 320 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 4640 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 4640 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 1697 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 4073 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 4073 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 1697 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 4072 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 4072 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 1697 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 4073 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 4073 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 53 | h | 223 | 1
MCD0823-CWP-264 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 2931 | h | 223 | 1
MCD0823-CWP-264 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 2931 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 43755 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 43755 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 1443 | h | 223 | 1
MMR0824-CWP-274 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 1443 | h | 223 | 1
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 21 | h | 223 | 1
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 21 | h | 223 | 1
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 133 | h | 223 | 1
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 133 | h | 223 | 1
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 96 | h | 223 | 1
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 96 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 2311 | h | 223 | 1
SES0827-CWP-452 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 2311 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 697 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 697 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 325 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 325 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 10721 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 1764 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 1764 | h | 223 | 1
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 1018 | h | 223 | 1
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 1018 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 299 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 299 | h | 223 | 1
MEM1214-CWP-400 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 6462 | h | 223 | 1
MEM1214-CWP-400 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 6462 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 544 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 544 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 968 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-24 | 720 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-24 | 720 | h | 223 | 1
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-31 | 79 | m | 223 | 1
CEC0800-CWP-475 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-31 | 79 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-03-31 | 0 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-03-31 | 0 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | Budgeted Units | 2024-03-31 | 25 | m | 223 | 1
CDC0822-CWP-246 | DEMOLIÇÃO POR VOLUME - DEMOLITION PER VOLUME | Material | At Completion Units | 2024-03-31 | 25 | m | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-03-31 | 46 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-03-31 | 46 | t | 223 | 1
SES0827-CWP-307 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-03-31 | 9 | t | 223 | 1
SES0827-CWP-307 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-03-31 | 9 | t | 223 | 1
SES0822-CWP-542 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-03-31 | 9 | t | 223 | 1
SES0822-CWP-542 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-03-31 | 9 | t | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-03-31 | 63 | m | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-03-31 | 63 | m | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-03-31 | 124 | m | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-03-31 | 124 | m | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-31 | 0 | un | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-31 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-31 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-31 | 0 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-03-31 | 2 | un | 223 | 1
JIL1214-CWP-464 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-03-31 | 2 | un | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-31 | 19 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-31 | 19 | m | 223 | 1
EEE0800-CWP-416 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-31 | 0 | un | 223 | 1
EEE0800-CWP-416 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-31 | 0 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-31 | 34 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-31 | 34 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-03-31 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-03-31 | 0 | un | 223 | 1
EEE1062-CWP-383 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 0 | un | 223 | 1
EEE1062-CWP-383 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 0 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-31 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-31 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-31 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-31 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-31 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-31 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-31 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-31 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-31 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-31 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-31 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-31 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-31 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-31 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-31 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-31 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-03-31 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-03-31 |  |  | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 10 | t | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 10 | t | 223 | 1
MEM0822-CWP-168 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 1 | t | 223 | 1
MEM0822-CWP-168 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 2 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 3 | t | 223 | 1
MEM0822-CWP-120 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 3 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 2 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 3 | t | 223 | 1
MEM0822-CWP-124 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 3 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 2 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 3 | t | 223 | 1
MEM0822-CWP-128 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 3 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 13 | t | 223 | 1
MEM1214-CWP-400 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-03-31 | 9 | t | 223 | 1
MEM1214-CWP-400 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-03-31 | 9 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-31 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-31 | 0 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-31 | 3 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-31 | 3 | t | 223 | 1
MCD0823-CWP-264 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-31 | 4 | t | 223 | 1
MCD0823-CWP-264 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-31 | 4 | t | 223 | 1
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-03-31 | 1 | t | 223 | 1
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-03-31 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-03-31 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-03-31 | 1 | t | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-31 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-31 | 6 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-31 | 134 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-31 | 134 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-31 | 52 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-31 | 52 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-03-31 | 2 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-03-31 | 2 | tons | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2024-03-31 | 2 | t | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2024-03-31 | 2 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-03-31 | 8 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-03-31 | 8 | t | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 158297 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 158297 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 31651 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 31651 | h | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10823 | h | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10823 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 817 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 817 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3714 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 39158 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 39158 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10286 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10286 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 58056 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 58056 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 15834 | h | 223 | 1
MEM0821-PWPp-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 15834 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 28690 | h | 223 | 1
MEM0821-PWPp-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 28690 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 307 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3234 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3234 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 902 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 753 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 753 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4419 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4419 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 96678 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 1164 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 1164 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 134 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10823 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10823 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 184334 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 184334 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 11174 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 11174 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 22171 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 1164 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 1164 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 96678 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3234 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3234 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23309 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23309 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 8827 | h | 223 | 1
MEM0822-PWPl-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 8827 | h | 223 | 1
MEM0822-CWP-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 19723 | h | 223 | 1
MEM0822-CWP-168 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 19723 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 47402 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 47402 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 520307 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 520307 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 16979 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 16979 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23134 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23134 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3754 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3555 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3555 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 39158 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 39158 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 86314 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 39158 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 39158 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 44 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 44 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 63940 | h | 223 | 1
CDC0822-CWP-246 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 63940 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 6669 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 6669 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3754 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 74764 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 74764 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 74764 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 74764 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 74764 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 74764 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 1010 | h | 223 | 1
EEE0820-PWPp-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 1010 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 1010 | h | 223 | 1
EEE0820-PWPp-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 1010 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 1010 | h | 223 | 1
EEE0820-PWPp-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 1010 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4500 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4500 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 8702 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 8702 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 636 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 636 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10029 | h | 223 | 1
JIL0822-PWPp-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10029 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4157 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4157 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 2969 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 2969 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 6494 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10286 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10286 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 231161 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 231161 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 160509 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 160509 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3754 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 201054 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 201054 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23570 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23570 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 34486 | h | 223 | 1
MEM0822-PWPl-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 34486 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 21767 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 45265 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 11428 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 11428 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 74600 | h | 223 | 1
MEM0822-CWP-120 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 74600 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 45265 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 11428 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 11428 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 61027 | h | 223 | 1
MEM0822-CWP-124 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 61027 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 45265 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 11428 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 11428 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 74600 | h | 223 | 1
MEM0822-CWP-128 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 74600 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 1275 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 753 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 753 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23134 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23134 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 1686 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 1686 | h | 223 | 1
MCD0823-CWP-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 85294 | h | 223 | 1
MCD0823-CWP-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 85294 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 707346 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 707346 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 16224 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 22638 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23570 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23570 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 7760 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 7760 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23134 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23134 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23134 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23134 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23570 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23570 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 776 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 18517 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23134 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23134 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23570 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23570 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 16037 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 16037 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10286 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10286 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3167 | h | 223 | 1
MEM0827-CWP-303 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3167 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10723 | h | 223 | 1
MEM0827-CWP-304 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10723 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 35057 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 35057 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 259962 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4101 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4101 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 753 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 753 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 42775 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 42775 | h | 223 | 1
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 24686 | h | 223 | 1
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 24686 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 683 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 683 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 7321 | h | 223 | 1
EEE1048-PWPp-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 7321 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 8541 | h | 223 | 1
EEE1049-PWPp-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 8541 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 2384 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 2384 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 21930 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 21930 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 21930 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 21930 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23570 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23570 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 45830 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 45830 | h | 223 | 1
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 792 | h | 223 | 1
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 792 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 2025 | h | 223 | 1
EEE1062-PWPl-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 2025 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 4500 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 4500 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 16546 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 16546 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10286 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10286 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 30582 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 30582 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 7062 | h | 223 | 1
JIL1214-CWP-464 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 7062 | h | 223 | 1
MEM1214-CWP-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 179093 | h | 223 | 1
MEM1214-CWP-400 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 179093 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 223 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 223 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 13192 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 13192 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 33027 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 57236 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 57236 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 243847 | h | 223 | 1
B21353 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 243847 | h | 223 | 1
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 23624 | h | 223 | 1
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 23624 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 224560 | h | 223 | 1
B30403 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 224560 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 2891 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 2891 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 902 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 753 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 753 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3234 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3234 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 24431 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 16979 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 16979 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 3234 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 3234 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10286 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10286 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 10823 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 10823 | h | 223 | 1
SES0822-CWP-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 137084 | h | 223 | 1
SES0822-CWP-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 137084 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-03-31 | 20905 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-03-31 | 20905 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 34 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 34 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 13 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 48 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 48 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 2 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 8145 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 8145 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 461 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 461 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 914 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 48 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 48 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 258 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 2327 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 2327 | h | 223 | 1
MEM0822-CWP-168 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 813 | h | 223 | 1
MEM0822-CWP-168 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 813 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 1955 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 1955 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 21457 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 21457 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 2 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 2 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 3139 | h | 223 | 1
CDC0822-CWP-246 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 3139 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 275 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 275 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 5458 | h | 223 | 1
MSD0822-CWP-095 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 5458 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 8291 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 8291 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 2304 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 2304 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 320 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 320 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 4640 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 4640 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 1697 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 2517 | h | 223 | 1
MEM0822-CWP-120 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 2517 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 1697 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 2517 | h | 223 | 1
MEM0822-CWP-124 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 2517 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 1697 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 2517 | h | 223 | 1
MEM0822-CWP-128 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 2517 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 53 | h | 223 | 1
MCD0823-CWP-264 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 3517 | h | 223 | 1
MCD0823-CWP-264 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 3517 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 29170 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 29170 | h | 223 | 1
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 8 | h | 223 | 1
MCD0824-CWP-446 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 8 | h | 223 | 1
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 50 | h | 223 | 1
MCD0824-CWP-447 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 50 | h | 223 | 1
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 96 | h | 223 | 1
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 96 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 131 | h | 223 | 1
MEM0827-CWP-303 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 131 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 1446 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 1446 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 10721 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 1764 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 1764 | h | 223 | 1
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 1018 | h | 223 | 1
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 1018 | h | 223 | 1
EEE1062-CWP-383 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 51 | h | 223 | 1
EEE1062-CWP-383 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 51 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 291 | h | 223 | 1
JIL1214-CWP-464 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 291 | h | 223 | 1
MEM1214-CWP-400 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 7386 | h | 223 | 1
MEM1214-CWP-400 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 7386 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 544 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 544 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 968 | h | 223 | 1
SES0822-CWP-542 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 5654 | h | 223 | 1
SES0822-CWP-542 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 5654 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-03-31 | 872 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-03-31 | 872 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-04-07 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-04-07 | 1 | m | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-07 | 2 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-07 | 2 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-07 | 58 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-07 | 58 | t | 223 | 1
SES0827-CWP-307 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-07 | 4 | t | 223 | 1
SES0827-CWP-307 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-07 | 4 | t | 223 | 1
SES0822-CWP-542 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-07 | 21 | t | 223 | 1
SES0822-CWP-542 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-07 | 21 | t | 223 | 1
SES0822-CWP-543 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-07 | 20 | t | 223 | 1
SES0822-CWP-543 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-07 | 20 | t | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-07 | 300 | m | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-07 | 300 | m | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-07 | 124 | m | 223 | 1
TTU1215-CWP-506 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-07 | 124 | m | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-07 | 0 | un | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-07 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-07 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-07 | 0 | un | 223 | 1
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 46 | m | 223 | 1
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 46 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 24 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 24 | m | 223 | 1
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 50 | m | 223 | 1
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 50 | m | 223 | 1
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 2 | m | 223 | 1
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 2 | m | 223 | 1
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 1 | m | 223 | 1
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 1 | m | 223 | 1
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 1 | m | 223 | 1
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 1 | m | 223 | 1
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 1 | m | 223 | 1
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 1 | m | 223 | 1
EBD1062-CWP-459 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 69 | m | 223 | 1
EBD1062-CWP-459 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 69 | m | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 20 | un | 223 | 1
ELU0800-CWP-062 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 20 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 0 | un | 223 | 1
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-07 | 0 | un | 223 | 1
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-07 | 0 | un | 223 | 1
EEE1062-CWP-383 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 1 | un | 223 | 1
EEE1062-CWP-383 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 1 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-07 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-07 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-07 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-07 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-07 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-07 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-07 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-07 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-07 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-07 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-07 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-07 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-07 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-07 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-07 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-07 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-07 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-07 |  |  | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 10 | t | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 10 | t | 223 | 1
MEM0822-CWP-169 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 2 | t | 223 | 1
MEM0822-CWP-169 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 2 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 1 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 2 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 0 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 0 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 0 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 0 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 0 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 0 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-07 | 13 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-07 | 13 | t | 223 | 1
MEM1214-CWP-520 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-07 | 1 | un | 223 | 1
MEM1214-CWP-520 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-07 | 1 | un | 223 | 1
MEM1214-CWP-521 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-07 | 1 | un | 223 | 1
MEM1214-CWP-521 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-07 | 1 | un | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-07 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-07 | 0 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-07 | 4 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-07 | 4 | t | 223 | 1
MCD0823-CWP-264 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-07 | 1 | t | 223 | 1
MCD0823-CWP-264 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-07 | 1 | t | 223 | 1
MCD0824-CWP-502 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-07 | 0 | t | 223 | 1
MCD0824-CWP-502 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-07 | 0 | t | 223 | 1
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-07 | 1 | t | 223 | 1
MRF0827-CWP-356 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-07 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-04-07 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-04-07 | 1 | t | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-07 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-07 | 6 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-07 | 168 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-07 | 168 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-07 | 65 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-07 | 65 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-07 | 1 | tons | 223 | 1
MMR0824-CWP-445 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-07 | 1 | tons | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2024-04-07 | 2 | t | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2024-04-07 | 2 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | Budgeted Units | 2024-04-07 | 4 | t | 223 | 1
MSD0822-CWP-095 | DESMONTAGEM TUBULAÇÃO | Material | At Completion Units | 2024-04-07 | 4 | t | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 94978 | h | 223 | 1
ELU0800-CWP-062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 94978 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 30860 | h | 223 | 1
RIN0800-PWPp-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 30860 | h | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 10823 | h | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 10823 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1022 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1022 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3714 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3714 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21677 | h | 223 | 1
SES0820-PWPl-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21677 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 5914 | h | 223 | 1
JIL0820-PWPp-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 5914 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 81278 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 81278 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 307 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3234 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3234 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 902 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1686 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1686 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 27498 | h | 223 | 1
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 523 | h | 223 | 1
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 523 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 96678 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1164 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1164 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 134 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 10823 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 10823 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 184334 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 184334 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 13968 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 13968 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 22171 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1164 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1164 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 96678 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 24655 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 24655 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3234 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3234 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 29137 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 29137 | h | 223 | 1
MEM0822-CWP-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 42207 | h | 223 | 1
MEM0822-CWP-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 42207 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 59252 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 59252 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 650384 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 650384 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 9763 | h | 223 | 1
JIL0822-PWPp-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 9763 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 16111 | h | 223 | 1
MEM0822-PWPl-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 16111 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3754 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3754 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 7962 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21677 | h | 223 | 1
SES0822-PWPl-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21677 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 86314 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21677 | h | 223 | 1
SES0822-PWPl-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21677 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 37549 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 37549 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 109 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 32009 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 32009 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3754 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3754 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 74764 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 74764 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 74764 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 74764 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 74764 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 74764 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4388 | h | 223 | 1
EEE0822-PWPp-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4388 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21342 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21342 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21342 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21342 | h | 223 | 1
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 523 | h | 223 | 1
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 523 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 20304 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 20304 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3960 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3960 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3563 | h | 223 | 1
MEM0822-PWPl-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3563 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 2969 | h | 223 | 1
MEM0822-PWPl-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 2969 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 6494 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 5914 | h | 223 | 1
JIL0822-PWPp-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 5914 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 231161 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 231161 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 80254 | h | 223 | 1
MSD0822-CWP-095 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 80254 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3754 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3754 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 251317 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 251317 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 17545 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 17545 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 94102 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 22980 | h | 223 | 1
JPA0822-PWPp-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 22980 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 119 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 119 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21767 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 45265 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 8163 | h | 223 | 1
MEM0822-PWPl-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 8163 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 45265 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 8163 | h | 223 | 1
MEM0822-PWPl-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 8163 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 45265 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 8163 | h | 223 | 1
MEM0822-PWPl-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 8163 | h | 223 | 1
MEM0822-CWP-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 2020 | h | 223 | 1
MEM0822-CWP-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 2020 | h | 223 | 1
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 29099 | h | 223 | 1
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 29099 | h | 223 | 1
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1212 | h | 223 | 1
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1212 | h | 223 | 1
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 606 | h | 223 | 1
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 606 | h | 223 | 1
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 606 | h | 223 | 1
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 606 | h | 223 | 1
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 364 | h | 223 | 1
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 364 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1275 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1686 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1686 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 16111 | h | 223 | 1
MEM0823-PWPl-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 16111 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1686 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1686 | h | 223 | 1
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 523 | h | 223 | 1
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 523 | h | 223 | 1
MCD0823-CWP-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21324 | h | 223 | 1
MCD0823-CWP-264 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21324 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 884182 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 884182 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 16231 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 16231 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 22638 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 16231 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 16231 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 22638 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 22980 | h | 223 | 1
JPA0824-PWPp-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 22980 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 658 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 658 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4462 | h | 223 | 1
MMR0824-CWP-445 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4462 | h | 223 | 1
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 523 | h | 223 | 1
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 523 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3328 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3328 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 582 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 582 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 16111 | h | 223 | 1
MEM0826-PWPl-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 16111 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 16111 | h | 223 | 1
MEM0826-PWPl-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 16111 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 22980 | h | 223 | 1
JPA0826-PWPp-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 22980 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 2958 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 2958 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 582 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 582 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 776 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 18517 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1851 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1851 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 19416 | h | 223 | 1
MEM0827-PWPl-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 19416 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 523 | h | 223 | 1
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 523 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 22980 | h | 223 | 1
JPA0827-PWPp-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 22980 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 8019 | h | 223 | 1
MCD0827-CWP-342 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 8019 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 5914 | h | 223 | 1
JIL0827-PWPp-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 5914 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 35057 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 35057 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 259962 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 259962 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4101 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4101 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1686 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1686 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 42775 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 42775 | h | 223 | 1
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 24686 | h | 223 | 1
MRF0827-CWP-356 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 24686 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 191 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 191 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4782 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4782 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 2384 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 2384 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21930 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21930 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 21930 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 21930 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 11748 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 22980 | h | 223 | 1
JPA1062-PWPp-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 22980 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 45830 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 45830 | h | 223 | 1
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1862 | h | 223 | 1
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1862 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 7444 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 4388 | h | 223 | 1
EEE1062-PWPp-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 4388 | h | 223 | 1
EBD1062-CWP-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 27620 | h | 223 | 1
EBD1062-CWP-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 27620 | h | 223 | 1
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 559 | h | 223 | 1
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 559 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 12823 | h | 223 | 1
EEE1062-EWPc-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 12823 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 5914 | h | 223 | 1
JIL1214-PWPp-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 5914 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 30582 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 30582 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 500 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 500 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 13192 | h | 223 | 1
TTU1215-CWP-506 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 13192 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 33027 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 57236 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 57236 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 58704 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 58704 | h | 223 | 1
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 19827 | h | 223 | 1
B21823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 19827 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 867 | h | 223 | 1
B40673 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 867 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 902 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 1686 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 1686 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3234 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3234 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 24431 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 9763 | h | 223 | 1
JIL0622-PWPp-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 9763 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 3234 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 3234 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 5914 | h | 223 | 1
JIL0622-PWPp-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 5914 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 10823 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 10823 | h | 223 | 1
MEM1214-CWP-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 23892 | h | 223 | 1
MEM1214-CWP-520 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 23892 | h | 223 | 1
MEM1214-CWP-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 20906 | h | 223 | 1
MEM1214-CWP-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 20906 | h | 223 | 1
SES0822-CWP-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 326894 | h | 223 | 1
SES0822-CWP-542 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 326894 | h | 223 | 1
SES0822-CWP-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 305804 | h | 223 | 1
SES0822-CWP-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 305804 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-07 | 20905 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-07 | 20905 | h | 223 | 1
EBD0800-CWP-417 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 4125 | h | 223 | 1
EBD0800-CWP-417 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 4125 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 42 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 42 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 13 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 48 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 48 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 2 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 8145 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 8145 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 576 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 576 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 914 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 48 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 48 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 258 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 2909 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 2909 | h | 223 | 1
MEM0822-CWP-169 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1741 | h | 223 | 1
MEM0822-CWP-169 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1741 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 2444 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 2444 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 26821 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 26821 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1536 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1536 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 4 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1320 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1320 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 10364 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 10364 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 775 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 775 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 2304 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 2304 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 320 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 320 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 4640 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 4640 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 18 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 18 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1697 | h | 223 | 1
MEM0822-CWP-191 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 83 | h | 223 | 1
MEM0822-CWP-191 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 83 | h | 223 | 1
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1200 | h | 223 | 1
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1200 | h | 223 | 1
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 50 | h | 223 | 1
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 50 | h | 223 | 1
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 25 | h | 223 | 1
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 25 | h | 223 | 1
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 25 | h | 223 | 1
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 25 | h | 223 | 1
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 15 | h | 223 | 1
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 15 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 53 | h | 223 | 1
MCD0823-CWP-264 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 879 | h | 223 | 1
MCD0823-CWP-264 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 879 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 36463 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 36463 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 27 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 27 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 137 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 137 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 25 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 25 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 92 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 92 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 24 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 24 | h | 223 | 1
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 96 | h | 223 | 1
EEE0826-CWP-449 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 96 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 76 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 76 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1446 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1446 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 10721 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 10721 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1764 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1764 | h | 223 | 1
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1018 | h | 223 | 1
MRF0827-CWP-356 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1018 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 46 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 46 | h | 223 | 1
EEE1062-CWP-383 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 120 | h | 223 | 1
EEE1062-CWP-383 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 120 | h | 223 | 1
EBD1062-CWP-459 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 1664 | h | 223 | 1
EBD1062-CWP-459 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 1664 | h | 223 | 1
ELU1062-CWP-461 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 36 | h | 223 | 1
ELU1062-CWP-461 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 36 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 544 | h | 223 | 1
TTU1215-CWP-506 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 544 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 968 | h | 223 | 1
MEM1214-CWP-520 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 192 | h | 223 | 1
MEM1214-CWP-520 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 192 | h | 223 | 1
MEM1214-CWP-521 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 168 | h | 223 | 1
MEM1214-CWP-521 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 168 | h | 223 | 1
SES0822-CWP-542 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 13482 | h | 223 | 1
SES0822-CWP-542 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 13482 | h | 223 | 1
SES0822-CWP-543 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 12612 | h | 223 | 1
SES0822-CWP-543 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 12612 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-07 | 872 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-07 | 872 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-04-14 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-04-14 | 1 | m | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-14 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-14 | 6 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-14 | 58 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-14 | 58 | t | 223 | 1
SES0822-CWP-543 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-14 | 10 | t | 223 | 1
SES0822-CWP-543 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-14 | 10 | t | 223 | 1
SES0822-CWP-544 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-14 | 30 | t | 223 | 1
SES0822-CWP-544 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-14 | 30 | t | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-14 | 300 | m | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-14 | 300 | m | 223 | 1
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-14 | 0 | un | 223 | 1
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-14 | 0 | un | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-14 | 0 | un | 223 | 1
MEM0822-CWP-160 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-14 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-14 | 0 | un | 223 | 1
MEM0822-CWP-250 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-14 | 0 | un | 223 | 1
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 1833 | m | 223 | 1
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 1833 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 24 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 24 | m | 223 | 1
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 2000 | m | 223 | 1
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 2000 | m | 223 | 1
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 83 | m | 223 | 1
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 83 | m | 223 | 1
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 42 | m | 223 | 1
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 42 | m | 223 | 1
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 42 | m | 223 | 1
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 42 | m | 223 | 1
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 25 | m | 223 | 1
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 25 | m | 223 | 1
EBD1062-CWP-459 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 251 | m | 223 | 1
EBD1062-CWP-459 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 251 | m | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 0 | un | 223 | 1
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-14 | 5 | un | 223 | 1
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-14 | 5 | un | 223 | 1
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 1 | un | 223 | 1
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 1 | un | 223 | 1
EEE1049-CWP-471 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 2 | un | 223 | 1
EEE1049-CWP-471 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 2 | un | 223 | 1
EEE1049-CWP-376 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 2 | un | 223 | 1
EEE1049-CWP-376 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 2 | un | 223 | 1
EEE1062-CWP-383 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 0 | un | 223 | 1
EEE1062-CWP-383 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 0 | un | 223 | 1
EEE1062-CWP-384 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 2 | un | 223 | 1
EEE1062-CWP-384 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 2 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-14 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-14 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-14 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-14 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-14 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-14 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-14 |  |  | 223 | 1
MCD0822-CWP-429 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-14 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-14 |  |  | 223 | 1
MCD0822-CWP-431 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-14 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-14 |  |  | 223 | 1
MCD0822-CWP-430 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-14 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-14 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-14 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-14 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-14 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-14 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-14 |  |  | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 2 | t | 223 | 1
MEM0822-CWP-068 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 2 | t | 223 | 1
MEM0822-CWP-169 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 10 | t | 223 | 1
MEM0822-CWP-169 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 10 | t | 223 | 1
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 0 | t | 223 | 1
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 0 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 1 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 2 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 2 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 2 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 2 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 1 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 1 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 4 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 4 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 10 | t | 223 | 1
MEM0827-CWP-309 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 10 | t | 223 | 1
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 1 | t | 223 | 1
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 1 | t | 223 | 1
MEM0821-CWP-579 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-14 | 0 | t | 223 | 1
MEM0821-CWP-579 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-14 | 0 | t | 223 | 1
MSD1214-CWP-374 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-14 | 1 | un | 223 | 1
MSD1214-CWP-374 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-14 | 1 | un | 223 | 1
MEM1214-CWP-521 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-14 | 0 | un | 223 | 1
MEM1214-CWP-521 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-14 | 0 | un | 223 | 1
MEM1214-CWP-522 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-14 | 1 | un | 223 | 1
MEM1214-CWP-522 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-14 | 1 | un | 223 | 1
MEM1214-CWP-523 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-14 | 1 | un | 223 | 1
MEM1214-CWP-523 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-14 | 1 | un | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-14 | 0 | t | 223 | 1
MCD0822-CWP-500 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-14 | 0 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-14 | 1 | t | 223 | 1
SES0821-CWP-501 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-14 | 1 | t | 223 | 1
MCD0824-CWP-502 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-14 | 4 | t | 223 | 1
MCD0824-CWP-502 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-14 | 4 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-04-14 | 1 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-04-14 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-04-14 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-04-14 | 1 | t | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-14 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-14 | 6 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-14 | 168 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-14 | 168 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-14 | 65 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-14 | 65 | tons | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2024-04-14 | 2 | t | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2024-04-14 | 2 | t | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 7537 | h | 223 | 1
KMT0800-PWPl-415 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 7537 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1022 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1022 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 743 | h | 223 | 1
JIL0800-PWPp-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 743 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 81278 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 81278 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 39449 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 39449 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 307 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 3234 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 3234 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 902 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1686 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1686 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 27498 | h | 223 | 1
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 714 | h | 223 | 1
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 714 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 96678 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 233 | h | 223 | 1
MEM0822-CWP-160 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 233 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 134 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 7537 | h | 223 | 1
KMT0821-PWPl-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 7537 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 92167 | h | 223 | 1
MEM0822-CWP-068 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 92167 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 13968 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 13968 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 22171 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 233 | h | 223 | 1
MEM0822-CWP-250 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 233 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 96678 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 55228 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 55228 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 3234 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 3234 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 29137 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 29137 | h | 223 | 1
MEM0822-CWP-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 187588 | h | 223 | 1
MEM0822-CWP-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 187588 | h | 223 | 1
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1385 | h | 223 | 1
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1385 | h | 223 | 1
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 3991 | h | 223 | 1
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 3991 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 59252 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 59252 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 650384 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 650384 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 3371 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 657 | h | 223 | 1
EEE1042-PWPp-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 657 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 7962 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 86314 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 88351 | h | 223 | 1