SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 88351 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 109 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 32009 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 32009 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 657 | h | 223 | 1
EEE1042-PWPp-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 657 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 74764 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 74764 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 74764 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 74764 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 74764 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 74764 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 353 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 353 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 353 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 353 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 353 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 353 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 37349 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 37349 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 37349 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 37349 | h | 223 | 1
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 714 | h | 223 | 1
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 714 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 20304 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 20304 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 3960 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 3960 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 6494 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 194010 | h | 223 | 1
MEM0822-PWPl-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 194010 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 657 | h | 223 | 1
EEE1042-PWPp-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 657 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 251317 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 251317 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 17545 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 17545 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 94102 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4419 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4419 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4770 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 21767 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 45265 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 45265 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 45265 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 45265 | h | 223 | 1
MEM0822-CWP-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 2020 | h | 223 | 1
MEM0822-CWP-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 2020 | h | 223 | 1
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1163947 | h | 223 | 1
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1163947 | h | 223 | 1
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 48497 | h | 223 | 1
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 48497 | h | 223 | 1
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 24250 | h | 223 | 1
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 24250 | h | 223 | 1
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 24250 | h | 223 | 1
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 24250 | h | 223 | 1
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 14550 | h | 223 | 1
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 14550 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1275 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1686 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1686 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1686 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1686 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 20905 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 20905 | h | 223 | 1
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 714 | h | 223 | 1
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 714 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 884182 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 884182 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 22638 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4419 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4419 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 26319 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 26319 | h | 223 | 1
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 714 | h | 223 | 1
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 714 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 14792 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 14792 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 23279 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 23279 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 13148 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 13148 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 23279 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 776 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 18517 | h | 223 | 1
CEC0827-CWP-311 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 18517 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4419 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4419 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 74056 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 74056 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 714 | h | 223 | 1
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 714 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 35057 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 35057 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 204720 | h | 223 | 1
MEM0827-CWP-309 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 204720 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 5036 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 5036 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4101 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4101 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1686 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1686 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 42775 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 42775 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 7633 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 7633 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 4782 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 4782 | h | 223 | 1
MSD1214-CWP-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 182476 | h | 223 | 1
MSD1214-CWP-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 182476 | h | 223 | 1
EEE1049-CWP-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 114047 | h | 223 | 1
EEE1049-CWP-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 114047 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1320 | h | 223 | 1
EEE1049-PWPl-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1320 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 12140 | h | 223 | 1
EEE1049-PWPl-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 12140 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 12140 | h | 223 | 1
EEE1049-PWPl-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 12140 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 11748 | h | 223 | 1
JPA1062-PWPl-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 66289 | h | 223 | 1
JPA1062-PWPl-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 66289 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 45830 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 45830 | h | 223 | 1
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1862 | h | 223 | 1
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1862 | h | 223 | 1
EEE1062-CWP-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 10942 | h | 223 | 1
EEE1062-CWP-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 10942 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 7444 | h | 223 | 1
EBD1062-CWP-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 78612 | h | 223 | 1
EBD1062-CWP-459 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 78612 | h | 223 | 1
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 22349 | h | 223 | 1
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 22349 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 30582 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 30582 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 500 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 500 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 33027 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 57236 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 57236 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 82186 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 82186 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 902 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 1686 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 1686 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 3234 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 3234 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 24431 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 3234 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 3234 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 7537 | h | 223 | 1
KMT0622-PWPl-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 7537 | h | 223 | 1
MEM1214-CWP-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 2987 | h | 223 | 1
MEM1214-CWP-521 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 2987 | h | 223 | 1
MEM1214-CWP-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 23892 | h | 223 | 1
MEM1214-CWP-522 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 23892 | h | 223 | 1
MEM1214-CWP-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 17916 | h | 223 | 1
MEM1214-CWP-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 17916 | h | 223 | 1
SES0822-CWP-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 158174 | h | 223 | 1
SES0822-CWP-543 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 158174 | h | 223 | 1
SES0822-CWP-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 463978 | h | 223 | 1
SES0822-CWP-544 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 463978 | h | 223 | 1
MEM0821-CWP-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 8 | h | 223 | 1
MEM0821-CWP-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 8 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-14 | 20905 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-14 | 20905 | h | 223 | 1
KMT0800-CWP-415 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 162 | h | 223 | 1
KMT0800-CWP-415 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 162 | h | 223 | 1
EBD0800-CWP-417 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 127875 | h | 223 | 1
EBD0800-CWP-417 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 127875 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 42 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 42 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 13 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 10 | h | 223 | 1
MEM0822-CWP-160 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 10 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 2 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1629 | h | 223 | 1
MEM0822-CWP-068 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1629 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 576 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 576 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 914 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 10 | h | 223 | 1
MEM0822-CWP-250 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 10 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 258 | h | 223 | 1
MCD0822-CWP-500 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 258 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 412 | h | 223 | 1
SES0821-CWP-501 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 412 | h | 223 | 1
MEM0822-CWP-169 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 7736 | h | 223 | 1
MEM0822-CWP-169 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 7736 | h | 223 | 1
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 50 | h | 223 | 1
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 50 | h | 223 | 1
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 144 | h | 223 | 1
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 144 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 2444 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 2444 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 26821 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 26821 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 3615 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 4 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1320 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1320 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 10364 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 10364 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 775 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 775 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 2304 | h | 223 | 1
MCD0822-CWP-429 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 2304 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 320 | h | 223 | 1
MCD0822-CWP-431 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 320 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 4640 | h | 223 | 1
MCD0822-CWP-430 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 4640 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 714 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 714 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1697 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1697 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1697 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1697 | h | 223 | 1
MEM0822-CWP-191 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 83 | h | 223 | 1
MEM0822-CWP-191 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 83 | h | 223 | 1
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 48000 | h | 223 | 1
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 48000 | h | 223 | 1
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 2000 | h | 223 | 1
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 2000 | h | 223 | 1
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1000 | h | 223 | 1
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1000 | h | 223 | 1
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1000 | h | 223 | 1
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1000 | h | 223 | 1
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 600 | h | 223 | 1
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 600 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 53 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 872 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 872 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 36463 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 36463 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1085 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1085 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 610 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 610 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 993 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 993 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 407 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 407 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 976 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 3054 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 3054 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1446 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1446 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 8442 | h | 223 | 1
MEM0827-CWP-309 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 8442 | h | 223 | 1
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 865 | h | 223 | 1
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 865 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1764 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1764 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1846 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1846 | h | 223 | 1
EEE1049-CWP-471 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1152 | h | 223 | 1
EEE1049-CWP-471 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1152 | h | 223 | 1
MSD1214-CWP-374 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 453 | h | 223 | 1
MSD1214-CWP-374 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 453 | h | 223 | 1
EEE1049-CWP-376 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 816 | h | 223 | 1
EEE1049-CWP-376 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 816 | h | 223 | 1
EEE1062-CWP-383 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 21 | h | 223 | 1
EEE1062-CWP-383 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 21 | h | 223 | 1
EEE1062-CWP-384 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 470 | h | 223 | 1
EEE1062-CWP-384 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 470 | h | 223 | 1
EBD1062-CWP-459 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 6016 | h | 223 | 1
EBD1062-CWP-459 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 6016 | h | 223 | 1
ELU1062-CWP-461 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 1440 | h | 223 | 1
ELU1062-CWP-461 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 1440 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 968 | h | 223 | 1
MEM1214-CWP-521 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 24 | h | 223 | 1
MEM1214-CWP-521 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 24 | h | 223 | 1
MEM1214-CWP-522 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 192 | h | 223 | 1
MEM1214-CWP-522 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 192 | h | 223 | 1
MEM1214-CWP-523 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 144 | h | 223 | 1
MEM1214-CWP-523 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 144 | h | 223 | 1
SES0822-CWP-543 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 6524 | h | 223 | 1
SES0822-CWP-543 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 6524 | h | 223 | 1
SES0822-CWP-544 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 19136 | h | 223 | 1
SES0822-CWP-544 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 19136 | h | 223 | 1
MEM0821-CWP-579 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 17 | h | 223 | 1
MEM0821-CWP-579 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 17 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-14 | 872 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-14 | 872 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-04-21 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-04-21 | 1 | m | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-21 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-21 | 6 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-21 | 25 | t | 223 | 1
SES0823-CWP-441 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-21 | 25 | t | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-21 | 155 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-21 | 155 | m | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-21 | 300 | m | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-21 | 300 | m | 223 | 1
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-21 | 46 | m | 223 | 1
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-21 | 46 | m | 223 | 1
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-21 | 28 | m | 223 | 1
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-21 | 28 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-21 | 32 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-21 | 32 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-21 | 15 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-21 | 15 | m | 223 | 1
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-21 | 1 | un | 223 | 1
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-21 | 1 | un | 223 | 1
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-21 | 1833 | m | 223 | 1
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-21 | 1833 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-21 | 24 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-21 | 24 | m | 223 | 1
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-21 | 2000 | m | 223 | 1
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-21 | 2000 | m | 223 | 1
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-21 | 83 | m | 223 | 1
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-21 | 83 | m | 223 | 1
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-21 | 42 | m | 223 | 1
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-21 | 42 | m | 223 | 1
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-21 | 42 | m | 223 | 1
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-21 | 42 | m | 223 | 1
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-21 | 25 | m | 223 | 1
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-21 | 25 | m | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-21 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-21 | 0 | un | 223 | 1
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-21 | 5 | un | 223 | 1
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-21 | 5 | un | 223 | 1
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | un | 223 | 1
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | un | 223 | 1
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | un | 223 | 1
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | un | 223 | 1
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | un | 223 | 1
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | un | 223 | 1
EEE1049-CWP-471 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 5 | un | 223 | 1
EEE1049-CWP-471 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 5 | un | 223 | 1
EEE1049-CWP-376 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 5 | un | 223 | 1
EEE1049-CWP-376 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 5 | un | 223 | 1
EEE1062-CWP-384 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 6 | un | 223 | 1
EEE1062-CWP-384 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 6 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-21 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-21 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-21 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-21 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-21 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-21 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-21 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-21 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-21 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-21 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-21 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-21 |  |  | 223 | 1
TTU0821-CWP-419 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 0 | t | 223 | 1
TTU0821-CWP-419 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 0 | t | 223 | 1
MEM0822-CWP-169 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 7 | t | 223 | 1
MEM0822-CWP-169 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 7 | t | 223 | 1
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 0 | t | 223 | 1
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 0 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-179 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-182 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-184 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 0 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 0 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 4 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 4 | t | 223 | 1
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 5 | t | 223 | 1
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 5 | t | 223 | 1
EEE1049-CWP-375 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
EEE1049-CWP-375 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0821-CWP-579 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0821-CWP-579 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0821-CWP-580 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MEM0821-CWP-580 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MEM0821-CWP-581 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 13 | t | 223 | 1
MEM0821-CWP-581 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 13 | t | 223 | 1
MEM0821-CWP-582 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-21 | 9 | t | 223 | 1
MEM0821-CWP-582 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-21 | 9 | t | 223 | 1
MSD1214-CWP-374 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-21 | 0 | un | 223 | 1
MSD1214-CWP-374 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-21 | 0 | un | 223 | 1
MEM1214-CWP-398 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-21 | 1 | un | 223 | 1
MEM1214-CWP-398 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-21 | 1 | un | 223 | 1
MEM1214-CWP-523 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-21 | 0 | un | 223 | 1
MEM1214-CWP-523 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-21 | 0 | un | 223 | 1
MCD0824-CWP-502 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-21 | 3 | t | 223 | 1
MCD0824-CWP-502 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-21 | 3 | t | 223 | 1
MCD0622-CWP-497 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-21 | 8 | t | 223 | 1
MCD0622-CWP-497 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-21 | 8 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-04-21 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-04-21 | 1 | t | 223 | 1
ESD1049-CWP-372 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-04-21 | 2 | unid | 223 | 1
ESD1049-CWP-372 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-04-21 | 2 | unid | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-21 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-21 | 6 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-21 | 52 | tons | 223 | 1
MMR0822-CWP-108 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-21 | 52 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-21 | 65 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-21 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-21 | 12 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-21 | 12 | tons | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | Budgeted Units | 2024-04-21 | 2 | t | 223 | 1
MSD0827-CWP-355 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY CALDEIRARIA | Material | At Completion Units | 2024-04-21 | 2 | t | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 5440 | h | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 5440 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1022 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1022 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 879 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 879 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 2899 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 2899 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 81278 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 81278 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 55228 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 55228 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 307 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3176 | h | 223 | 1
TTU0821-PWPl-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3176 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 902 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1686 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1686 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 27498 | h | 223 | 1
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 714 | h | 223 | 1
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 714 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 96678 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 134 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 13968 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 13968 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 22171 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 96678 | h | 223 | 1
TTU0821-CWP-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 2698 | h | 223 | 1
TTU0821-CWP-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 2698 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 55228 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 55228 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3176 | h | 223 | 1
MEM0822-PWPl-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3176 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 29137 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 29137 | h | 223 | 1
MEM0822-CWP-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 145381 | h | 223 | 1
MEM0822-CWP-169 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 145381 | h | 223 | 1
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1385 | h | 223 | 1
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1385 | h | 223 | 1
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3991 | h | 223 | 1
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3991 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 26170 | h | 223 | 1
SES0822-CWP-101 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 26170 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 200535 | h | 223 | 1
MMR0822-CWP-108 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 200535 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1117 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1117 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4786 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4786 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3371 | h | 223 | 1
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1709 | h | 223 | 1
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1709 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 7962 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 86314 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 88351 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 16516 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 16516 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 109 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 32009 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 32009 | h | 223 | 1
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1709 | h | 223 | 1
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1709 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 62749 | h | 223 | 1
ERE0822-PWPl-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 62749 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 62749 | h | 223 | 1
ERE0822-PWPl-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 62749 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 62749 | h | 223 | 1
ERE0822-PWPl-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 62749 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 483 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 483 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 773 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 773 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 37349 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 37349 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 37349 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 37349 | h | 223 | 1
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 714 | h | 223 | 1
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 714 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 20304 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 20304 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3960 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3960 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 6494 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 6494 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 2899 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 2899 | h | 223 | 1
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1709 | h | 223 | 1
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1709 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 251317 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 48169 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 48169 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 17545 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 17545 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 94102 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 94102 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 27498 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1117 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1117 | h | 223 | 1
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4952 | h | 223 | 1
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4952 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4770 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 21767 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 27159 | h | 223 | 1
MEM0822-CWP-179 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 27159 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 18106 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 18106 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 27159 | h | 223 | 1
MEM0822-CWP-182 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 27159 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 16457 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 16457 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 27159 | h | 223 | 1
MEM0822-CWP-184 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 27159 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 18377 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 18377 | h | 223 | 1
TTU0822-CWP-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 7502 | h | 223 | 1
TTU0822-CWP-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 7502 | h | 223 | 1
MEM0822-CWP-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 404 | h | 223 | 1
MEM0822-CWP-191 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 404 | h | 223 | 1
MEM0822-CWP-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1616 | h | 223 | 1
MEM0822-CWP-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1616 | h | 223 | 1
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1163947 | h | 223 | 1
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1163947 | h | 223 | 1
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 48497 | h | 223 | 1
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 48497 | h | 223 | 1
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3038 | h | 223 | 1
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3038 | h | 223 | 1
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 2000 | h | 223 | 1
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 2000 | h | 223 | 1
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 24250 | h | 223 | 1
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 24250 | h | 223 | 1
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4001 | h | 223 | 1
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4001 | h | 223 | 1
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 24250 | h | 223 | 1
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 24250 | h | 223 | 1
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3001 | h | 223 | 1
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3001 | h | 223 | 1
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 14550 | h | 223 | 1
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 14550 | h | 223 | 1
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1510 | h | 223 | 1
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1510 | h | 223 | 1
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1001 | h | 223 | 1
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1001 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1275 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 5588 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 5588 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1686 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1686 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 211 | h | 223 | 1
MEM0823-PWPl-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 211 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 20905 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 20905 | h | 223 | 1
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 714 | h | 223 | 1
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 714 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 383146 | h | 223 | 1
SES0823-CWP-441 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 383146 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 22638 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 27498 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 26319 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 26319 | h | 223 | 1
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 714 | h | 223 | 1
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 714 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 12276 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 12276 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 14792 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 14792 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 23279 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 23279 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 13148 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 13148 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 23279 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 776 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 27498 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 74056 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 74056 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 714 | h | 223 | 1
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 714 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 2899 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 2899 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 35057 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 35057 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 23698 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4101 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4101 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1686 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1686 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 42775 | h | 223 | 1
MSD0827-CWP-355 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 42775 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 7633 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 7633 | h | 223 | 1
JPA1062-CWP-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 38412 | h | 223 | 1
JPA1062-CWP-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 38412 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4782 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4782 | h | 223 | 1
MSD1214-CWP-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 139540 | h | 223 | 1
MSD1214-CWP-374 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 139540 | h | 223 | 1
EEE1049-CWP-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 217814 | h | 223 | 1
EEE1049-CWP-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 217814 | h | 223 | 1
EEE1049-CWP-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 268347 | h | 223 | 1
EEE1049-CWP-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 268347 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 11748 | h | 223 | 1
JPA1062-PWPl-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 228330 | h | 223 | 1
JPA1062-PWPl-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 228330 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 45830 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 45830 | h | 223 | 1
ESD1049-CWP-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 130689 | h | 223 | 1
ESD1049-CWP-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 130689 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 773 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 773 | h | 223 | 1
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 140 | h | 223 | 1
EEE1062-CWP-383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 140 | h | 223 | 1
EEE1062-CWP-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 12338 | h | 223 | 1
EEE1062-CWP-384 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 12338 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 7444 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 7444 | h | 223 | 1
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 22349 | h | 223 | 1
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 22349 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 2899 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 2899 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 25667 | h | 223 | 1
MEM1214-PWPl-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 25667 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3442 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3442 | h | 223 | 1
MEM1214-CWP-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 12610 | h | 223 | 1
MEM1214-CWP-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 12610 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 500 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 500 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1589 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1589 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 33027 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 39861 | h | 223 | 1
B29963 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 39861 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 82186 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 82186 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 902 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 2667 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 2667 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 1686 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 1686 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3176 | h | 223 | 1
MCD0622-PWPl-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3176 | h | 223 | 1
MCD0622-CWP-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 51345 | h | 223 | 1
MCD0622-CWP-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 51345 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 24431 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 24431 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 3176 | h | 223 | 1
MEM0622-PWPl-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 3176 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 2899 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 2899 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 4786 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 4786 | h | 223 | 1
MEM1214-CWP-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 5972 | h | 223 | 1
MEM1214-CWP-523 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 5972 | h | 223 | 1
MEM0821-CWP-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 184 | h | 223 | 1
MEM0821-CWP-579 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 184 | h | 223 | 1
MEM0821-CWP-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 7007 | h | 223 | 1
MEM0821-CWP-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 7007 | h | 223 | 1
MEM0821-CWP-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 246852 | h | 223 | 1
MEM0821-CWP-581 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 246852 | h | 223 | 1
MEM0821-CWP-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 164568 | h | 223 | 1
MEM0821-CWP-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 164568 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-21 | 20905 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-21 | 20905 | h | 223 | 1
KMT0800-CWP-415 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 414 | h | 223 | 1
KMT0800-CWP-415 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 414 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 42 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 42 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 13 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 2 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 576 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 576 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 914 | h | 223 | 1
TTU0821-CWP-419 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 51 | h | 223 | 1
TTU0821-CWP-419 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 51 | h | 223 | 1
MEM0822-CWP-169 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 5995 | h | 223 | 1
MEM0822-CWP-169 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 5995 | h | 223 | 1
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 50 | h | 223 | 1
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 50 | h | 223 | 1
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 144 | h | 223 | 1
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 144 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1079 | h | 223 | 1
SES0822-CWP-101 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1079 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 8270 | h | 223 | 1
MMR0822-CWP-108 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 8270 | h | 223 | 1
ERE0822-CWP-135 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 576 | h | 223 | 1
ERE0822-CWP-135 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 576 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 3615 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 681 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 681 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 4 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1320 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1320 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 10364 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1986 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1986 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 775 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 775 | h | 223 | 1
ERE0822-CWP-132 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 576 | h | 223 | 1
ERE0822-CWP-132 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 576 | h | 223 | 1
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 204 | h | 223 | 1
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 204 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 714 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 714 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1018 | h | 223 | 1
MEM0822-CWP-179 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1018 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 679 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 679 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1018 | h | 223 | 1
MEM0822-CWP-182 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1018 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 679 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 679 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1018 | h | 223 | 1
MEM0822-CWP-184 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1018 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 679 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 679 | h | 223 | 1
TTU0822-CWP-190 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 309 | h | 223 | 1
TTU0822-CWP-190 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 309 | h | 223 | 1
MEM0822-CWP-191 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 17 | h | 223 | 1
MEM0822-CWP-191 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 17 | h | 223 | 1
MEM0822-CWP-192 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 67 | h | 223 | 1
MEM0822-CWP-192 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 67 | h | 223 | 1
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 48000 | h | 223 | 1
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 48000 | h | 223 | 1
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 2000 | h | 223 | 1
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 2000 | h | 223 | 1
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 125 | h | 223 | 1
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 125 | h | 223 | 1
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 83 | h | 223 | 1
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 83 | h | 223 | 1
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1000 | h | 223 | 1
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1000 | h | 223 | 1
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 165 | h | 223 | 1
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 165 | h | 223 | 1
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1000 | h | 223 | 1
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1000 | h | 223 | 1
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 124 | h | 223 | 1
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 124 | h | 223 | 1
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 600 | h | 223 | 1
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 600 | h | 223 | 1
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 62 | h | 223 | 1
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 62 | h | 223 | 1
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 41 | h | 223 | 1
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 41 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 53 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 230 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 230 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 872 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 872 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 15801 | h | 223 | 1
SES0823-CWP-441 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 15801 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1085 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1085 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 610 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 610 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 993 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 993 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 407 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 407 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 976 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 3054 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 3054 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1446 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1446 | h | 223 | 1
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 4072 | h | 223 | 1
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 4072 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1764 | h | 223 | 1
MSD0827-CWP-355 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1764 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1846 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1846 | h | 223 | 1
JPA1062-CWP-388 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1584 | h | 223 | 1
JPA1062-CWP-388 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1584 | h | 223 | 1
MSD1214-CWP-374 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 347 | h | 223 | 1
MSD1214-CWP-374 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 347 | h | 223 | 1
EEE1049-CWP-375 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 734 | h | 223 | 1
EEE1049-CWP-375 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 734 | h | 223 | 1
EEE1049-CWP-376 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 336 | h | 223 | 1
EEE1049-CWP-376 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 336 | h | 223 | 1
ESD1049-CWP-372 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 311 | h | 223 | 1
ESD1049-CWP-372 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 311 | h | 223 | 1
EEE1062-CWP-384 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 1200 | h | 223 | 1
EEE1062-CWP-384 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 1200 | h | 223 | 1
ELU1062-CWP-461 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 828 | h | 223 | 1
ELU1062-CWP-461 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 828 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 142 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 142 | h | 223 | 1
MEM1214-CWP-398 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 520 | h | 223 | 1
MEM1214-CWP-398 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 520 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 66 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 66 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 968 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 968 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 110 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 110 | h | 223 | 1
MCD0622-CWP-497 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 2117 | h | 223 | 1
MCD0622-CWP-497 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 2117 | h | 223 | 1
MEM1214-CWP-523 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 48 | h | 223 | 1
MEM1214-CWP-523 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 48 | h | 223 | 1
MEM0821-CWP-579 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 391 | h | 223 | 1
MEM0821-CWP-579 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 391 | h | 223 | 1
MEM0821-CWP-580 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 289 | h | 223 | 1
MEM0821-CWP-580 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 289 | h | 223 | 1
MEM0821-CWP-581 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 10184 | h | 223 | 1
MEM0821-CWP-581 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 10184 | h | 223 | 1
MEM0821-CWP-582 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 6789 | h | 223 | 1
MEM0821-CWP-582 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 6789 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-21 | 872 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-21 | 872 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-04-28 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-04-28 | 1 | m | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-28 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-28 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-04-28 | 5 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-04-28 | 5 | t | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-28 | 318 | m | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-28 | 318 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-28 | 404 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-28 | 404 | m | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-28 | 38 | m | 223 | 1
MEM0822-CWP-247 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-28 | 38 | m | 223 | 1
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-28 | 121 | m | 223 | 1
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-28 | 121 | m | 223 | 1
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-28 | 126 | m | 223 | 1
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-28 | 126 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-28 | 84 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-28 | 84 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-04-28 | 66 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-04-28 | 66 | m | 223 | 1
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-28 | 1 | un | 223 | 1
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-28 | 1 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-28 | 4 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-28 | 4 | un | 223 | 1
EEE0827-CWP-457 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-28 | 2 | un | 223 | 1
EEE0827-CWP-457 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-28 | 2 | un | 223 | 1
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-04-28 | 1 | un | 223 | 1
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-04-28 | 1 | un | 223 | 1
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 1788 | m | 223 | 1
EBD0800-CWP-417 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 1788 | m | 223 | 1
EEE0821-CWP-089 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 40 | m | 223 | 1
EEE0821-CWP-089 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 40 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 8 | m | 223 | 1
EEE0821-CWP-073 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 8 | m | 223 | 1
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 1950 | m | 223 | 1
EBD0822-CWP-197 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 1950 | m | 223 | 1
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 81 | m | 223 | 1
EBD0822-CWP-207 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 81 | m | 223 | 1
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 16 | m | 223 | 1
EBD0822-CWP-218 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 16 | m | 223 | 1
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 41 | m | 223 | 1
EBD0822-CWP-229 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 41 | m | 223 | 1
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 24 | m | 223 | 1
EBD0822-CWP-234 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 24 | m | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 2 | m | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 2 | m | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 0 | un | 223 | 1
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 2 | un | 223 | 1
ELU1062-CWP-461 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 2 | un | 223 | 1
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-04-28 | 1 | un | 223 | 1
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-04-28 | 1 | un | 223 | 1
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 1 | un | 223 | 1
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 1 | un | 223 | 1
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 40 | un | 223 | 1
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 40 | un | 223 | 1
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 40 | un | 223 | 1
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 40 | un | 223 | 1
EEE1049-CWP-471 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 3 | un | 223 | 1
EEE1049-CWP-471 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 3 | un | 223 | 1
EEE1049-CWP-376 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 3 | un | 223 | 1
EEE1049-CWP-376 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 3 | un | 223 | 1
EEE1049-CWP-377 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 8 | un | 223 | 1
EEE1049-CWP-377 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 8 | un | 223 | 1
EEE1062-CWP-384 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 4 | un | 223 | 1
EEE1062-CWP-384 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 4 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-28 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-28 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-28 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-28 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-28 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-28 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-28 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-28 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-28 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-28 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-04-28 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-04-28 |  |  | 223 | 1
MEM0817-CWP-034 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 1 | t | 223 | 1
MEM0817-CWP-034 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 1 | t | 223 | 1
MEM0821-CWP-084 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 33 | t | 223 | 1
MEM0821-CWP-084 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 33 | t | 223 | 1
TTU0821-CWP-419 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 1 | t | 223 | 1
TTU0821-CWP-419 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 1 | t | 223 | 1
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 0 | t | 223 | 1
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 0 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 1 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 1 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 2 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 1 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 1 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 1 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 1 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 4 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 4 | t | 223 | 1
MEM0827-CWP-348 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 0 | t | 223 | 1
MEM0827-CWP-348 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 0 | t | 223 | 1
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 5 | t | 223 | 1
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 5 | t | 223 | 1
EEE1049-CWP-375 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 0 | t | 223 | 1
EEE1049-CWP-375 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 0 | t | 223 | 1
MEM0623-CWP-410 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 0 | t | 223 | 1
MEM0623-CWP-410 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 0 | t | 223 | 1
MEM0821-CWP-580 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 0 | t | 223 | 1
MEM0821-CWP-580 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 0 | t | 223 | 1
MEM0821-CWP-582 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-04-28 | 4 | t | 223 | 1
MEM0821-CWP-582 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-04-28 | 4 | t | 223 | 1
MEM1214-CWP-398 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-04-28 | 2 | un | 223 | 1
MEM1214-CWP-398 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-04-28 | 2 | un | 223 | 1
MCD0622-CWP-497 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-04-28 | 96 | t | 223 | 1
MCD0622-CWP-497 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-04-28 | 96 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-04-28 | 1 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-04-28 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-04-28 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-04-28 | 1 | t | 223 | 1
ESD1049-CWP-372 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-04-28 | 1 | unid | 223 | 1
ESD1049-CWP-372 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-04-28 | 1 | unid | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-28 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-28 | 6 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-28 | 65 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-28 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-28 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-28 | 65 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-28 | 0 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-28 | 0 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-04-28 | 1 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-04-28 | 1 | tons | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 12186 | h | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 12186 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MCD0817-PWPl-030 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
STP0817-PWPl-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-035 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-038 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-043 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MCD0817-PWPl-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0817-PWPl-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
ELU0817-PWPl-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
JIL0817-PWPl-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MMR0817-CWP-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 139672 | h | 223 | 1
MMR0817-CWP-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 139672 | h | 223 | 1
MEM0817-CWP-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 139672 | h | 223 | 1
MEM0817-CWP-026 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 139672 | h | 223 | 1
MEM0817-CWP-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 4656 | h | 223 | 1
MEM0817-CWP-034 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 4656 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MMR0817-PWPl-022 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0817-PWPl-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1022 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1022 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 143 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 143 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1538 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1538 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 3960 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 3960 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 46445 | h | 223 | 1
MEM0821-PWPl-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 46445 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 55228 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 55228 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 307 | h | 223 | 1
MEM0821-CWP-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 608233 | h | 223 | 1
MEM0821-CWP-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 608233 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 902 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 902 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1415 | h | 223 | 1
MEM0821-PWPl-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1415 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 27498 | h | 223 | 1
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 191 | h | 223 | 1
EEE0821-PWPl-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 191 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 5653 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 5653 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 96678 | h | 223 | 1
EEE0821-CWP-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 22989 | h | 223 | 1
EEE0821-CWP-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 22989 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 134 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 4772 | h | 223 | 1
EEE0821-CWP-073 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 4772 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 22171 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 96678 | h | 223 | 1
TTU0821-CWP-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 17086 | h | 223 | 1
TTU0821-CWP-419 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 17086 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 55228 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 55228 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 29137 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 29137 | h | 223 | 1
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1385 | h | 223 | 1
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1385 | h | 223 | 1
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 3991 | h | 223 | 1
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 3991 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 44696 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 6537 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 6537 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 21767 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 21767 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 3371 | h | 223 | 1
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 5631 | h | 223 | 1
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 5631 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 7962 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 86314 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 84725 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 84725 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 33915 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 33915 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 43086 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 43086 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 109 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 4001 | h | 223 | 1
MEM0822-CWP-247 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 4001 | h | 223 | 1
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 5631 | h | 223 | 1
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 5631 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 483 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 483 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1732 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1732 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 18436 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 18436 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 37349 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 37349 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 37349 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 37349 | h | 223 | 1
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 191 | h | 223 | 1
EEE0822-PWPl-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 191 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 17403 | h | 223 | 1
MEM0822-PWPl-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 17403 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 3960 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 3960 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1739 | h | 223 | 1
SES0822-PWPl-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1739 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 3960 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 3960 | h | 223 | 1
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 5631 | h | 223 | 1
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 5631 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 251317 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 251317 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 17545 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 17545 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 47051 | h | 223 | 1
JSD0822-CWP-484 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 47051 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 27498 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 44696 | h | 223 | 1
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 12919 | h | 223 | 1
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 12919 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 4770 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 21767 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 45943 | h | 223 | 1
TTU0822-CWP-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 33340 | h | 223 | 1
TTU0822-CWP-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 33340 | h | 223 | 1
MEM0822-CWP-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 2020 | h | 223 | 1
MEM0822-CWP-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 2020 | h | 223 | 1
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1134848 | h | 223 | 1
EBD0822-CWP-197 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1134848 | h | 223 | 1
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 47284 | h | 223 | 1
EBD0822-CWP-207 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 47284 | h | 223 | 1
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 13500 | h | 223 | 1
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 13500 | h | 223 | 1
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 8890 | h | 223 | 1
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 8890 | h | 223 | 1
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 9094 | h | 223 | 1
EBD0822-CWP-218 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 9094 | h | 223 | 1
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 17783 | h | 223 | 1
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 17783 | h | 223 | 1
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 23644 | h | 223 | 1
EBD0822-CWP-229 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 23644 | h | 223 | 1
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 13337 | h | 223 | 1
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 13337 | h | 223 | 1
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 14186 | h | 223 | 1
EBD0822-CWP-234 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 14186 | h | 223 | 1
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 6710 | h | 223 | 1
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 6710 | h | 223 | 1
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 4447 | h | 223 | 1
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 4447 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 450 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 450 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1275 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 9861 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 9861 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 2979 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 2979 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1415 | h | 223 | 1
MEM0823-PWPl-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1415 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 20905 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 20905 | h | 223 | 1
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 191 | h | 223 | 1
EEE0823-PWPl-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 191 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 22638 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 27498 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 26319 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 26319 | h | 223 | 1
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 191 | h | 223 | 1
EEE0826-PWPl-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 191 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 27498 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 14792 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 14792 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 23279 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 23279 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 13148 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 13148 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 23279 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 776 | h | 223 | 1
MEM0827-CWP-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 65956 | h | 223 | 1
MEM0827-CWP-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 65956 | h | 223 | 1
MEM0827-CWP-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 23280 | h | 223 | 1
MEM0827-CWP-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 23280 | h | 223 | 1
MMR0827-CWP-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 139672 | h | 223 | 1
MMR0827-CWP-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 139672 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0827-PWPl-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-333 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MCD0827-PWPl-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 27498 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MMR0827-PWPl-312 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 74056 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 74056 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0827-PWPl-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MCD0827-PWPl-320 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 191 | h | 223 | 1
EEE0827-PWPl-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 191 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
STP0827-PWPl-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0827-PWPl-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
ELU0827-PWPl-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
JIL0827-PWPl-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 153 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 2794 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 2794 | h | 223 | 1
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 37 | h | 223 | 1
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 37 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-324 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-325 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
STP0827-PWPl-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 3960 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 3960 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 35057 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 35057 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 23698 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-328 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0827-PWPl-330 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 513 | h | 223 | 1
SES0827-PWPl-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 513 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1415 | h | 223 | 1
MEM0827-PWPl-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1415 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 7633 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 7633 | h | 223 | 1
JPA1062-CWP-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 31428 | h | 223 | 1
JPA1062-CWP-388 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 31428 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 4782 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 4782 | h | 223 | 1
EEE1049-CWP-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 24202 | h | 223 | 1
EEE1049-CWP-375 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 24202 | h | 223 | 1
EEE1049-CWP-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 154299 | h | 223 | 1
EEE1049-CWP-376 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 154299 | h | 223 | 1
EEE1049-CWP-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 114047 | h | 223 | 1
EEE1049-CWP-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 114047 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 11748 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 45830 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 45830 | h | 223 | 1
ESD1049-CWP-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 111327 | h | 223 | 1
ESD1049-CWP-372 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 111327 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1732 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1732 | h | 223 | 1
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 2034 | h | 223 | 1
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 2034 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 5769 | h | 223 | 1
EEE1062-PWPp-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 5769 | h | 223 | 1
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 10616 | h | 223 | 1
ELU1062-CWP-461 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 10616 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 3960 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 3960 | h | 223 | 1
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 5380 | h | 223 | 1
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 5380 | h | 223 | 1
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 2444 | h | 223 | 1
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 2444 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 8979 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 8979 | h | 223 | 1
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 12609 | h | 223 | 1
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 12609 | h | 223 | 1
MEM1214-CWP-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 45590 | h | 223 | 1
MEM1214-CWP-398 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 45590 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 420 | h | 223 | 1
EEE1214-PWPl-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 420 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 7061 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 7061 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 33027 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 82186 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 82186 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 11224 | h | 223 | 1
MEM0623-CWP-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 989 | h | 223 | 1
MEM0623-CWP-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 989 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 902 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 11855 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 11855 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1415 | h | 223 | 1
MEM0623-PWPl-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1415 | h | 223 | 1
MCD0622-CWP-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 1026892 | h | 223 | 1
MCD0622-CWP-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 1026892 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 9162 | h | 223 | 1
JIL0622-EWPc-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 9162 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 3960 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 3960 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 6537 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 6537 | h | 223 | 1
MEM0821-CWP-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 2885 | h | 223 | 1
MEM0821-CWP-580 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 2885 | h | 223 | 1
MEM0821-CWP-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 82284 | h | 223 | 1
MEM0821-CWP-582 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 82284 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-04-28 | 20905 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-04-28 | 20905 | h | 223 | 1
MMR0817-CWP-022 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 5400 | h | 223 | 1
MMR0817-CWP-022 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 5400 | h | 223 | 1
MEM0817-CWP-026 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 5760 | h | 223 | 1
MEM0817-CWP-026 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 5760 | h | 223 | 1
MEM0817-CWP-034 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 192 | h | 223 | 1
MEM0817-CWP-034 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 192 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 42 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 42 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 15 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 15 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 13 | h | 223 | 1
MEM0821-CWP-084 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 26875 | h | 223 | 1
MEM0821-CWP-084 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 26875 | h | 223 | 1
EBD0821-CWP-081 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 2370 | h | 223 | 1
EBD0821-CWP-081 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 2370 | h | 223 | 1
EEE0821-CWP-089 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 948 | h | 223 | 1
EEE0821-CWP-089 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 948 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 2 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 197 | h | 223 | 1
EEE0821-CWP-073 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 197 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 914 | h | 223 | 1
TTU0821-CWP-419 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 765 | h | 223 | 1
TTU0821-CWP-419 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 765 | h | 223 | 1
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 50 | h | 223 | 1
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 50 | h | 223 | 1
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 144 | h | 223 | 1
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 144 | h | 223 | 1
ERE0822-CWP-135 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 22464 | h | 223 | 1
ERE0822-CWP-135 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 22464 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 3348 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 3348 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1399 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1399 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1777 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1777 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 4 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 165 | h | 223 | 1
MEM0822-CWP-247 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 165 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 760 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 760 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 10364 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 10364 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 775 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 775 | h | 223 | 1
ERE0822-CWP-132 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 22464 | h | 223 | 1
ERE0822-CWP-132 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 22464 | h | 223 | 1
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 533 | h | 223 | 1
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 533 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 714 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 714 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1697 | h | 223 | 1
TTU0822-CWP-190 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1375 | h | 223 | 1
TTU0822-CWP-190 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1375 | h | 223 | 1
MEM0822-CWP-192 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 83 | h | 223 | 1
MEM0822-CWP-192 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 83 | h | 223 | 1
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 46800 | h | 223 | 1
EBD0822-CWP-197 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 46800 | h | 223 | 1
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1950 | h | 223 | 1
EBD0822-CWP-207 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1950 | h | 223 | 1
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 557 | h | 223 | 1
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 557 | h | 223 | 1
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 367 | h | 223 | 1
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 367 | h | 223 | 1
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 375 | h | 223 | 1
EBD0822-CWP-218 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 375 | h | 223 | 1
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 733 | h | 223 | 1
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 733 | h | 223 | 1
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 975 | h | 223 | 1
EBD0822-CWP-229 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 975 | h | 223 | 1
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 550 | h | 223 | 1
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 550 | h | 223 | 1
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 585 | h | 223 | 1
EBD0822-CWP-234 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 585 | h | 223 | 1
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 277 | h | 223 | 1
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 277 | h | 223 | 1
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 183 | h | 223 | 1
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 183 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 19 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 19 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 53 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 407 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 407 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 123 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 123 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 872 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 872 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1085 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1085 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 610 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 610 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 993 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 993 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 407 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 407 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 976 | h | 223 | 1
MEM0827-CWP-316 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 3400 | h | 223 | 1
MEM0827-CWP-316 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 3400 | h | 223 | 1
MEM0827-CWP-324 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 960 | h | 223 | 1
MEM0827-CWP-324 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 960 | h | 223 | 1
MMR0827-CWP-312 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 5760 | h | 223 | 1
MMR0827-CWP-312 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 5760 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 3054 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 3054 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 48 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 48 | h | 223 | 1
EEE0827-CWP-457 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 317 | h | 223 | 1
EEE0827-CWP-457 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 317 | h | 223 | 1
MEM0827-CWP-348 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 3 | h | 223 | 1
MEM0827-CWP-348 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 3 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1446 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1446 | h | 223 | 1
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 4072 | h | 223 | 1
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 4072 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1846 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1846 | h | 223 | 1
JPA1062-CWP-388 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1296 | h | 223 | 1
JPA1062-CWP-388 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1296 | h | 223 | 1
EEE1049-CWP-375 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 82 | h | 223 | 1
EEE1049-CWP-375 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 82 | h | 223 | 1
EEE1049-CWP-377 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 4416 | h | 223 | 1
EEE1049-CWP-377 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 4416 | h | 223 | 1
ESD1049-CWP-372 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 265 | h | 223 | 1
ESD1049-CWP-372 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 265 | h | 223 | 1
EEE1062-CWP-384 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 730 | h | 223 | 1
EEE1062-CWP-384 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 730 | h | 223 | 1
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 222 | h | 223 | 1
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 222 | h | 223 | 1
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 101 | h | 223 | 1
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 101 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 370 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 370 | h | 223 | 1
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 520 | h | 223 | 1
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 520 | h | 223 | 1
MEM1214-CWP-398 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 1880 | h | 223 | 1
MEM1214-CWP-398 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 1880 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 291 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 291 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 750 | h | 223 | 1
MEM1110-CWP-465 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 750 | h | 223 | 1
MEM0623-CWP-410 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 16 | h | 223 | 1
MEM0623-CWP-410 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 16 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 489 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 489 | h | 223 | 1
MCD0622-CWP-497 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 42348 | h | 223 | 1
MCD0622-CWP-497 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 42348 | h | 223 | 1
MEM0821-CWP-580 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 119 | h | 223 | 1
MEM0821-CWP-580 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 119 | h | 223 | 1
MEM0821-CWP-582 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 3395 | h | 223 | 1
MEM0821-CWP-582 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 3395 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-04-28 | 872 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-04-28 | 872 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-05-05 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-05-05 | 1 | m | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-05 | 3 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-05 | 3 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-05 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-05 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-05 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-05 | 6 | t | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-05 | 363 | m | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-05 | 363 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-05 | 404 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-05 | 404 | m | 223 | 1
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-05 | 121 | m | 223 | 1
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-05 | 121 | m | 223 | 1
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-05 | 126 | m | 223 | 1
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-05 | 126 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-05 | 84 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-05 | 84 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-05 | 66 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-05 | 66 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 195 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 195 | m | 223 | 1
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 390 | m | 223 | 1
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 390 | m | 223 | 1
ECB0822-CWP-198 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-198 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-214 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-214 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-219 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-219 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-226 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-226 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-251 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-251 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-252 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 488 | m | 223 | 1
ECB0822-CWP-252 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 488 | m | 223 | 1
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 760 | m | 223 | 1
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 760 | m | 223 | 1
ECB0817-CWP-551 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 130 | m | 223 | 1
ECB0817-CWP-551 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 130 | m | 223 | 1
ECB0823-CWP-557 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 488 | m | 223 | 1
ECB0823-CWP-557 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 488 | m | 223 | 1
ECB0824-CWP-560 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-05 | 488 | m | 223 | 1
ECB0824-CWP-560 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-05 | 488 | m | 223 | 1
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-05 | 1 | un | 223 | 1
KMT0800-CWP-415 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-05 | 1 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-05 | 5 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-05 | 5 | un | 223 | 1
EEE0827-CWP-457 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-05 | 2 | un | 223 | 1
EEE0827-CWP-457 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-05 | 2 | un | 223 | 1
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-05 | 2 | un | 223 | 1
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-05 | 2 | un | 223 | 1
EEE0821-CWP-089 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-05 | 60 | m | 223 | 1
EEE0821-CWP-089 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-05 | 60 | m | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-05 | 2 | m | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-05 | 2 | m | 223 | 1
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-05 | 103 | m | 223 | 1
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-05 | 103 | m | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-05 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-05 | 0 | un | 223 | 1
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-05 | 5 | un | 223 | 1
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-05 | 5 | un | 223 | 1
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 1 | un | 223 | 1
MEM0822-CWP-173 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 1 | un | 223 | 1
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 40 | un | 223 | 1
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 40 | un | 223 | 1
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 1 | un | 223 | 1
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 1 | un | 223 | 1
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 40 | un | 223 | 1
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 40 | un | 223 | 1
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 1 | un | 223 | 1
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 1 | un | 223 | 1
EEE1048-CWP-473 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 2 | un | 223 | 1
EEE1048-CWP-473 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 2 | un | 223 | 1
EEE1049-CWP-377 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 19 | un | 223 | 1
EEE1049-CWP-377 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 19 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-05 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-05 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-05 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-05 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-05 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-05 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-05 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-05 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-05 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-05 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-05 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-05 |  |  | 223 | 1
MEM0821-CWP-421 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 1 | t | 223 | 1
MEM0821-CWP-421 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 1 | t | 223 | 1
MEM0821-CWP-084 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 51 | t | 223 | 1
MEM0821-CWP-084 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 51 | t | 223 | 1
TTU0821-CWP-420 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 0 | t | 223 | 1
TTU0821-CWP-420 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 0 | t | 223 | 1
MEM0822-CWP-170 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 7 | t | 223 | 1
MEM0822-CWP-170 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 7 | t | 223 | 1
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 0 | t | 223 | 1
MEM0822-CWP-171 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 0 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 0 | t | 223 | 1
MEM0822-CWP-426 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 0 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 2 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 1 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 1 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 1 | t | 223 | 1
MEM0826-CWP-290 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 1 | t | 223 | 1
MEM0827-CWP-321 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 16 | t | 223 | 1
MEM0827-CWP-321 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 16 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 4 | t | 223 | 1
MEM0827-CWP-453 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 4 | t | 223 | 1
MEM0827-CWP-348 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 1 | t | 223 | 1
MEM0827-CWP-348 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 1 | t | 223 | 1
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 4 | t | 223 | 1
MEM0827-CWP-310 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 4 | t | 223 | 1
MEM0623-CWP-410 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-05 | 1 | t | 223 | 1
MEM0623-CWP-410 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-05 | 1 | t | 223 | 1
MEM0817-CWP-031 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-05-05 | 1 | un | 223 | 1
MEM0817-CWP-031 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-05-05 | 1 | un | 223 | 1
MEM0822-CWP-174 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-05-05 | 0 | un | 223 | 1
MEM0822-CWP-174 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-05-05 | 0 | un | 223 | 1
MEM0822-CWP-175 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-05-05 | 1 | un | 223 | 1
MEM0822-CWP-175 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-05-05 | 1 | un | 223 | 1
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-05-05 | 11 | t | 223 | 1
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-05-05 | 11 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-05-05 | 1 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-05-05 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-05-05 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-05-05 | 1 | t | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-05 | 6 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-05 | 6 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-05 | 65 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-05 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-05 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-05 | 65 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-05 | 3 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-05 | 3 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-05 | 18 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-05 | 18 | tons | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 12186 | h | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 12186 | h | 223 | 1
MEM0817-CWP-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 23280 | h | 223 | 1
MEM0817-CWP-023 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 23280 | h | 223 | 1
MEM0817-CWP-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 19400 | h | 223 | 1
MEM0817-CWP-031 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 19400 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 37220 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 37220 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 519 | h | 223 | 1
CEC0820-CWP-054 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 519 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 5706 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1538 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1538 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 3960 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 3960 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 37828 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 37828 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 55228 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 55228 | h | 223 | 1
MEM0821-CWP-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 27644 | h | 223 | 1
MEM0821-CWP-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 27644 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 307 | h | 223 | 1
MEM0821-CWP-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1050583 | h | 223 | 1
MEM0821-CWP-084 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1050583 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 371 | h | 223 | 1
TTU0821-PWPl-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 371 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 27498 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 8586 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 8586 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 96678 | h | 223 | 1
EEE0821-CWP-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 34920 | h | 223 | 1
EEE0821-CWP-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 34920 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 161 | h | 223 | 1
TTU0821-CWP-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 19784 | h | 223 | 1
TTU0821-CWP-420 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 19784 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 134 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 22171 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 22171 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 96678 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 46352 | h | 223 | 1
MEM0821-PWPl-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 46352 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 29137 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 29137 | h | 223 | 1
MEM0822-CWP-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 138220 | h | 223 | 1
MEM0822-CWP-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 138220 | h | 223 | 1
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 693 | h | 223 | 1
MEM0822-CWP-171 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 693 | h | 223 | 1
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1995 | h | 223 | 1
MEM0822-CWP-173 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1995 | h | 223 | 1
MEM0822-CWP-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 6467 | h | 223 | 1
MEM0822-CWP-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 6467 | h | 223 | 1
MEM0822-CWP-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 12933 | h | 223 | 1
MEM0822-CWP-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 12933 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1117 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1117 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 6537 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 6537 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 16870 | h | 223 | 1
JIL0822-PWPp-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 16870 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 3371 | h | 223 | 1
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 5631 | h | 223 | 1
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 5631 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 7962 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 86314 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 102697 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 38760 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 38760 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 43086 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 43086 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 109 | h | 223 | 1
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 5631 | h | 223 | 1
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 5631 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 483 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 483 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1732 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1732 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 22347 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 22347 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 26678 | h | 223 | 1
MEM0822-PWPl-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 26678 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 26678 | h | 223 | 1
MEM0822-PWPl-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 26678 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 495 | h | 223 | 1
JIL0822-PWPl-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 495 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 3960 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 3960 | h | 223 | 1
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 5631 | h | 223 | 1
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 5631 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 251317 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 251317 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 8772 | h | 223 | 1
MEM0822-CWP-426 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 8772 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 27498 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 7442 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 7442 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1117 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1117 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 3469 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 3469 | h | 223 | 1
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 12919 | h | 223 | 1
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 12919 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 4770 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 21767 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 45943 | h | 223 | 1
TTU0822-CWP-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 12503 | h | 223 | 1
TTU0822-CWP-190 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 12503 | h | 223 | 1
MEM0822-CWP-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1212 | h | 223 | 1
MEM0822-CWP-192 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1212 | h | 223 | 1
MEM0822-CWP-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 808 | h | 223 | 1
MEM0822-CWP-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 808 | h | 223 | 1
ECB0822-CWP-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0822-CWP-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 94571 | h | 223 | 1
JIL0822-CWP-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 96997 | h | 223 | 1
JIL0822-CWP-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 96997 | h | 223 | 1
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 40584 | h | 223 | 1
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 40584 | h | 223 | 1
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 13500 | h | 223 | 1
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 13500 | h | 223 | 1
ECB0822-CWP-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0822-CWP-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 94571 | h | 223 | 1
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 8890 | h | 223 | 1
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 8890 | h | 223 | 1
ECB0822-CWP-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0822-CWP-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0822-CWP-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0822-CWP-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 94571 | h | 223 | 1
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 17783 | h | 223 | 1
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 17783 | h | 223 | 1
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 13337 | h | 223 | 1
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 13337 | h | 223 | 1
ECB0822-CWP-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0822-CWP-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0822-CWP-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0822-CWP-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 94571 | h | 223 | 1
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 6710 | h | 223 | 1
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 6710 | h | 223 | 1
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 4447 | h | 223 | 1
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 4447 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 10809 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 10809 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1275 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 9861 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 9861 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 71499 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 71499 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 20905 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 20905 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 22638 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 27498 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 26319 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 26319 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 27498 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 11464 | h | 223 | 1
MEM0826-CWP-290 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 11464 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 23279 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 23279 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 20844 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 20844 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1561 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1561 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 13148 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 13148 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 23279 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 776 | h | 223 | 1
MEM0827-CWP-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 65956 | h | 223 | 1
MEM0827-CWP-316 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 65956 | h | 223 | 1
MEM0827-CWP-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 316008 | h | 223 | 1
MEM0827-CWP-321 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 316008 | h | 223 | 1
MEM0827-CWP-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 23280 | h | 223 | 1
MEM0827-CWP-313 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 23280 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 27498 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 72205 | h | 223 | 1
MEM0827-CWP-453 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 72205 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 153 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 3386 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 3386 | h | 223 | 1
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1475 | h | 223 | 1
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1475 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 3960 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 3960 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 35057 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 35057 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 23698 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 7633 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 7633 | h | 223 | 1
JPA1062-CWP-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 23280 | h | 223 | 1
JPA1062-CWP-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 23280 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 683 | h | 223 | 1
EEE1048-PWPl-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 683 | h | 223 | 1
EEE1048-CWP-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 37267 | h | 223 | 1
EEE1048-CWP-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 37267 | h | 223 | 1
EEE1049-CWP-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 268347 | h | 223 | 1
EEE1049-CWP-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 268347 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 11748 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 11748 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 12276 | h | 223 | 1
JPA1062-PWPl-389 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 12276 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 1732 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 1732 | h | 223 | 1
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 6699 | h | 223 | 1
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 6699 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 3960 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 3960 | h | 223 | 1
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 24832 | h | 223 | 1
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 24832 | h | 223 | 1
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 10864 | h | 223 | 1
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 10864 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 8979 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 8979 | h | 223 | 1
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 58196 | h | 223 | 1
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 58196 | h | 223 | 1
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 59975 | h | 223 | 1
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 59975 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 7061 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 7061 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 33027 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 46963 | h | 223 | 1
B21383 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 46963 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 11224 | h | 223 | 1
MEM0623-CWP-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 18795 | h | 223 | 1
MEM0623-CWP-410 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 18795 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 902 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 11855 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 11855 | h | 223 | 1
MCD0622-CWP-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 975547 | h | 223 | 1
MCD0622-CWP-497 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 975547 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 3960 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 3960 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 6537 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 6537 | h | 223 | 1
ECB0823-CWP-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0823-CWP-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0824-CWP-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 94571 | h | 223 | 1
ECB0824-CWP-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 94571 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-05 | 20905 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-05 | 20905 | h | 223 | 1
MMR0817-CWP-022 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 360 | h | 223 | 1
MMR0817-CWP-022 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 360 | h | 223 | 1
MEM0817-CWP-023 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 960 | h | 223 | 1
MEM0817-CWP-023 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 960 | h | 223 | 1
MEM0817-CWP-031 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 800 | h | 223 | 1
MEM0817-CWP-031 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 800 | h | 223 | 1
MEM0817-CWP-035 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 960 | h | 223 | 1
MEM0817-CWP-035 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 960 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1535 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1535 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 23 | h | 223 | 1
CEC0820-CWP-054 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 23 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 600 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 600 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1560 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1560 | h | 223 | 1
MEM0821-CWP-421 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1221 | h | 223 | 1
MEM0821-CWP-421 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1221 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 13 | h | 223 | 1
MEM0821-CWP-084 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 41533 | h | 223 | 1
MEM0821-CWP-084 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 41533 | h | 223 | 1
EBD0821-CWP-081 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1230 | h | 223 | 1
EBD0821-CWP-081 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1230 | h | 223 | 1
EEE0821-CWP-089 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1440 | h | 223 | 1
EEE0821-CWP-089 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1440 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 2 | h | 223 | 1
TTU0821-CWP-420 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 213 | h | 223 | 1
TTU0821-CWP-420 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 213 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 914 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 914 | h | 223 | 1
MEM0822-CWP-170 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 5700 | h | 223 | 1
MEM0822-CWP-170 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 5700 | h | 223 | 1
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 50 | h | 223 | 1
MEM0822-CWP-171 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 50 | h | 223 | 1
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 144 | h | 223 | 1
MEM0822-CWP-173 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 144 | h | 223 | 1
MEM0822-CWP-174 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 320 | h | 223 | 1
MEM0822-CWP-174 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 320 | h | 223 | 1
MEM0822-CWP-175 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 640 | h | 223 | 1
MEM0822-CWP-175 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 640 | h | 223 | 1
ERE0822-CWP-136 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 576 | h | 223 | 1
ERE0822-CWP-136 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 576 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 4059 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1598 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1598 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1777 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1777 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 4 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 922 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 922 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 10364 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 10364 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 155 | h | 223 | 1
MEM0822-CWP-426 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 155 | h | 223 | 1
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3120 | h | 223 | 1
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3120 | h | 223 | 1
ERE0822-CWP-133 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 576 | h | 223 | 1
ERE0822-CWP-133 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 576 | h | 223 | 1
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 533 | h | 223 | 1
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 533 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 714 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 714 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1697 | h | 223 | 1
TTU0822-CWP-190 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 516 | h | 223 | 1
TTU0822-CWP-190 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 516 | h | 223 | 1
MEM0822-CWP-192 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 50 | h | 223 | 1
MEM0822-CWP-192 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 50 | h | 223 | 1
MEM0822-CWP-193 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 33 | h | 223 | 1
MEM0822-CWP-193 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 33 | h | 223 | 1
ECB0822-CWP-198 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0822-CWP-198 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3900 | h | 223 | 1
JIL0822-CWP-206 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 4000 | h | 223 | 1
JIL0822-CWP-206 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 4000 | h | 223 | 1
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3900 | h | 223 | 1
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 557 | h | 223 | 1
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 557 | h | 223 | 1
ECB0822-CWP-214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0822-CWP-214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3900 | h | 223 | 1
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 367 | h | 223 | 1
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 367 | h | 223 | 1
ECB0822-CWP-219 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0822-CWP-219 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0822-CWP-226 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0822-CWP-226 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3900 | h | 223 | 1
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 733 | h | 223 | 1
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 733 | h | 223 | 1
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 550 | h | 223 | 1
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 550 | h | 223 | 1
ECB0822-CWP-251 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0822-CWP-251 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0822-CWP-252 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0822-CWP-252 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3900 | h | 223 | 1
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 277 | h | 223 | 1
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 277 | h | 223 | 1
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 183 | h | 223 | 1
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 183 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 446 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 446 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 53 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 407 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 407 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 2949 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 2949 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 872 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 872 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1085 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1085 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 473 | h | 223 | 1
MEM0826-CWP-290 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 473 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 993 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 993 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 64 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 64 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 407 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 407 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 976 | h | 223 | 1
MEM0827-CWP-316 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 2040 | h | 223 | 1
MEM0827-CWP-316 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 2040 | h | 223 | 1
MEM0827-CWP-321 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 13032 | h | 223 | 1
MEM0827-CWP-321 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 13032 | h | 223 | 1
MEM0827-CWP-325 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 960 | h | 223 | 1
MEM0827-CWP-325 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 960 | h | 223 | 1
MEM0827-CWP-313 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 960 | h | 223 | 1
MEM0827-CWP-313 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 960 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 2978 | h | 223 | 1
MEM0827-CWP-453 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 2978 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 48 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 48 | h | 223 | 1
EEE0827-CWP-457 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 384 | h | 223 | 1
EEE0827-CWP-457 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 384 | h | 223 | 1
MEM0827-CWP-348 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 127 | h | 223 | 1
MEM0827-CWP-348 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 127 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1446 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1446 | h | 223 | 1
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3207 | h | 223 | 1
MEM0827-CWP-310 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3207 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1846 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1846 | h | 223 | 1
JPA1062-CWP-389 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 960 | h | 223 | 1
JPA1062-CWP-389 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 960 | h | 223 | 1
EEE1048-CWP-473 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 698 | h | 223 | 1
EEE1048-CWP-473 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 698 | h | 223 | 1
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1024 | h | 223 | 1
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1024 | h | 223 | 1
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 448 | h | 223 | 1
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 448 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 370 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 370 | h | 223 | 1
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 2400 | h | 223 | 1
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 2400 | h | 223 | 1
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 2473 | h | 223 | 1
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 2473 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 291 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 291 | h | 223 | 1
MEM0623-CWP-410 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 628 | h | 223 | 1
MEM0623-CWP-410 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 628 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 489 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 489 | h | 223 | 1
ECB0600-CWP-408 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 22800 | h | 223 | 1
ECB0600-CWP-408 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 22800 | h | 223 | 1
MCD0622-CWP-497 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 40231 | h | 223 | 1
MCD0622-CWP-497 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 40231 | h | 223 | 1
ECB0817-CWP-551 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 1043 | h | 223 | 1
ECB0817-CWP-551 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 1043 | h | 223 | 1
ECB0823-CWP-557 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0823-CWP-557 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0824-CWP-560 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 3900 | h | 223 | 1
ECB0824-CWP-560 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 3900 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-05 | 872 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-05 | 872 | h | 223 | 1
CPI0817-CWP-024 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-05-12 | 2 | m | 223 | 1
CPI0817-CWP-024 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-05-12 | 2 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-05-12 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-05-12 | 1 | m | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-12 | 7 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-12 | 7 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-12 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-12 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-12 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-12 | 6 | t | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-12 | 363 | m | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-12 | 363 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-12 | 404 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-12 | 404 | m | 223 | 1
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-12 | 115 | m | 223 | 1
TTU0822-CWP-155 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-12 | 115 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-12 | 27 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-12 | 27 | m | 223 | 1
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-12 | 22 | m | 223 | 1
TTU0822-CWP-212 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-12 | 22 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-12 | 84 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-12 | 84 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-12 | 66 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-12 | 66 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 488 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 488 | m | 223 | 1
ECB0821-CWP-082 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 2901 | m | 223 | 1
ECB0821-CWP-082 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 2901 | m | 223 | 1
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 975 | m | 223 | 1
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 975 | m | 223 | 1
ECB0822-CWP-198 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-198 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-214 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-214 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-219 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-219 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-226 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-226 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-251 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-251 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-252 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0822-CWP-252 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 1219 | m | 223 | 1
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 1900 | m | 223 | 1
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 1900 | m | 223 | 1
ECB0817-CWP-550 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 130 | m | 223 | 1
ECB0817-CWP-550 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 130 | m | 223 | 1
ECB0817-CWP-551 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 195 | m | 223 | 1
ECB0817-CWP-551 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 195 | m | 223 | 1
ECB0823-CWP-556 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 731 | m | 223 | 1
ECB0823-CWP-556 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 731 | m | 223 | 1
ECB0823-CWP-557 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 488 | m | 223 | 1
ECB0823-CWP-557 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 488 | m | 223 | 1
ECB0824-CWP-559 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 731 | m | 223 | 1
ECB0824-CWP-559 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 731 | m | 223 | 1
ECB0824-CWP-560 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-12 | 488 | m | 223 | 1
ECB0824-CWP-560 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-12 | 488 | m | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-12 | 5 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-12 | 5 | un | 223 | 1
JIL0822-CWP-213 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-12 | 2 | un | 223 | 1
JIL0822-CWP-213 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-12 | 2 | un | 223 | 1
JIL0822-CWP-228 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-12 | 6 | un | 223 | 1
JIL0822-CWP-228 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-12 | 6 | un | 223 | 1
JIL0822-CWP-233 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-12 | 11 | un | 223 | 1
JIL0822-CWP-233 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-12 | 11 | un | 223 | 1
EEE0827-CWP-457 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-12 | 0 | un | 223 | 1
EEE0827-CWP-457 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-12 | 0 | un | 223 | 1
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-12 | 2 | un | 223 | 1
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-12 | 2 | un | 223 | 1
EEE0821-CWP-089 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-12 | 21 | m | 223 | 1
EEE0821-CWP-089 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-12 | 21 | m | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-12 | 2 | m | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-12 | 2 | m | 223 | 1
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-12 | 117 | m | 223 | 1
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-12 | 117 | m | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-12 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-12 | 0 | un | 223 | 1
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-12 | 5 | un | 223 | 1
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-12 | 5 | un | 223 | 1
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 39 | un | 223 | 1
ERE0822-CWP-135 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 39 | un | 223 | 1
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 40 | un | 223 | 1
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 40 | un | 223 | 1
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 9 | un | 223 | 1
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 9 | un | 223 | 1
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 9 | un | 223 | 1
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 9 | un | 223 | 1
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 9 | un | 223 | 1
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 9 | un | 223 | 1
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 39 | un | 223 | 1
ERE0822-CWP-132 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 39 | un | 223 | 1
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 40 | un | 223 | 1
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 40 | un | 223 | 1
EEE1048-CWP-473 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 2 | un | 223 | 1
EEE1048-CWP-473 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 2 | un | 223 | 1
EEE1049-CWP-377 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 11 | un | 223 | 1
EEE1049-CWP-377 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 11 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-12 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-12 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-12 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-12 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-12 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-12 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-12 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-12 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-12 |  |  | 223 | 1
MCD0824-CWP-446 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-12 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-12 |  |  | 223 | 1
MCD0824-CWP-447 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-12 |  |  | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-12 |  |  | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-12 |  |  | 223 | 1
MEM0821-CWP-421 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 10 | t | 223 | 1
MEM0821-CWP-421 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 10 | t | 223 | 1
MEM0821-CWP-087 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 21 | t | 223 | 1
MEM0821-CWP-087 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 21 | t | 223 | 1
TTU0821-CWP-420 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 0 | t | 223 | 1
TTU0821-CWP-420 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 0 | t | 223 | 1
MEM0822-CWP-170 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 7 | t | 223 | 1
MEM0822-CWP-170 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 7 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 0 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 0 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 2 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 1 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 1 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 0 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 0 | t | 223 | 1
MEM0827-CWP-348 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 0 | t | 223 | 1
MEM0827-CWP-348 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 0 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 0 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 0 | t | 223 | 1
MEM0623-CWP-410 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-12 | 0 | t | 223 | 1
MEM0623-CWP-410 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-12 | 0 | t | 223 | 1
MEM0822-CWP-174 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-05-12 | 2 | un | 223 | 1
MEM0822-CWP-174 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-05-12 | 2 | un | 223 | 1
MEM0822-CWP-175 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-05-12 | 3 | un | 223 | 1
MEM0822-CWP-175 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-05-12 | 3 | un | 223 | 1
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-05-12 | 47 | t | 223 | 1
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-05-12 | 47 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-05-12 | 1 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-05-12 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-05-12 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-05-12 | 1 | t | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-12 | 3 | tons | 223 | 1
MMR0821-CWP-074 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-12 | 3 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-12 | 20 | tons | 223 | 1
MMR0822-CWP-144 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-12 | 20 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-12 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-12 | 65 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-12 | 3 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-12 | 3 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-12 | 18 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-12 | 18 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-12 | 1 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-12 | 1 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-12 | 3 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-12 | 3 | tons | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 12186 | h | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 12186 | h | 223 | 1
CPI0817-CWP-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 10864 | h | 223 | 1
CPI0817-CWP-024 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 10864 | h | 223 | 1
MEM0817-CWP-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3880 | h | 223 | 1
MEM0817-CWP-047 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3880 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 93051 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 93051 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 5706 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 1538 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 1538 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3960 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3960 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 94571 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 94571 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 31559 | h | 223 | 1
MEM0821-PWPl-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 31559 | h | 223 | 1
MEM0821-CWP-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 184293 | h | 223 | 1
MEM0821-CWP-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 184293 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 307 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 27498 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 8586 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 8586 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 96678 | h | 223 | 1
MEM0821-CWP-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 493704 | h | 223 | 1
MEM0821-CWP-087 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 493704 | h | 223 | 1
EEE0821-CWP-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 11931 | h | 223 | 1
EEE0821-CWP-089 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 11931 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 134 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 55347 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 55347 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 11085 | h | 223 | 1
MMR0821-CWP-074 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 11085 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 96678 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 29137 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 29137 | h | 223 | 1
MEM0822-CWP-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 138220 | h | 223 | 1
MEM0822-CWP-170 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 138220 | h | 223 | 1
MEM0822-CWP-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 32333 | h | 223 | 1
MEM0822-CWP-174 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 32333 | h | 223 | 1
MEM0822-CWP-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 64667 | h | 223 | 1
MEM0822-CWP-175 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 64667 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 44696 | h | 223 | 1
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 40226 | h | 223 | 1
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 40226 | h | 223 | 1
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 40226 | h | 223 | 1
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 40226 | h | 223 | 1
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 40226 | h | 223 | 1
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 40226 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 6537 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 6537 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3371 | h | 223 | 1
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3922 | h | 223 | 1
EEE1042-PWPl-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3922 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 5475 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 5475 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 7962 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 86314 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 102697 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 38760 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 38760 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 43086 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 43086 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 109 | h | 223 | 1
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3922 | h | 223 | 1
EEE1042-PWPl-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3922 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 483 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 483 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 1732 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 1732 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 22347 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 22347 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3960 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3960 | h | 223 | 1
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3922 | h | 223 | 1
EEE1042-PWPl-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3922 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 77489 | h | 223 | 1
MMR0822-CWP-144 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 77489 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 251317 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 27498 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 18604 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 44696 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 11428 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 11428 | h | 223 | 1
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 12273 | h | 223 | 1
TTU0822-CWP-155 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 12273 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 2907 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 2907 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 4770 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 21767 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 45943 | h | 223 | 1
MEM0822-CWP-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 2020 | h | 223 | 1
MEM0822-CWP-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 2020 | h | 223 | 1
ECB0822-CWP-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 236427 | h | 223 | 1
ECB0822-CWP-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 236427 | h | 223 | 1
JIL0822-CWP-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 96997 | h | 223 | 1
JIL0822-CWP-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 96997 | h | 223 | 1
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 101459 | h | 223 | 1
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 101459 | h | 223 | 1
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 2363 | h | 223 | 1
TTU0822-CWP-212 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 2363 | h | 223 | 1
JIL0822-CWP-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 8003 | h | 223 | 1
JIL0822-CWP-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 8003 | h | 223 | 1
ECB0822-CWP-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 236427 | h | 223 | 1
ECB0822-CWP-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 236427 | h | 223 | 1
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 1556 | h | 223 | 1
TTU0822-CWP-216 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 1556 | h | 223 | 1
ECB0822-CWP-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 236427 | h | 223 | 1
ECB0822-CWP-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 236427 | h | 223 | 1
ECB0822-CWP-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 236427 | h | 223 | 1
ECB0822-CWP-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 236427 | h | 223 | 1
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3112 | h | 223 | 1
TTU0822-CWP-227 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3112 | h | 223 | 1
JIL0822-CWP-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 25608 | h | 223 | 1
JIL0822-CWP-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 25608 | h | 223 | 1
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 2334 | h | 223 | 1
TTU0822-CWP-232 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 2334 | h | 223 | 1
JIL0822-CWP-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 51213 | h | 223 | 1
JIL0822-CWP-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 51213 | h | 223 | 1
ECB0822-CWP-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 236427 | h | 223 | 1
ECB0822-CWP-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 236427 | h | 223 | 1
ECB0822-CWP-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 236427 | h | 223 | 1
ECB0822-CWP-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 236427 | h | 223 | 1
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 1174 | h | 223 | 1
TTU0822-CWP-236 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 1174 | h | 223 | 1
JIL0822-CWP-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3201 | h | 223 | 1
JIL0822-CWP-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3201 | h | 223 | 1
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 778 | h | 223 | 1
TTU0822-CWP-239 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 778 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 10809 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 10809 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 1275 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 9861 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 9861 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 71499 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 71499 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 20905 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 20905 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 22638 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 27498 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 26319 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 26319 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 27498 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 23279 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 23279 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 166755 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 166755 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 6936 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 6936 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3616 | h | 223 | 1
MEM0826-CWP-284 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3616 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 23279 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 776 | h | 223 | 1
MMR0827-CWP-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 23280 | h | 223 | 1
MMR0827-CWP-326 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 23280 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 27498 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3982 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3982 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 29 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 29 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 1084 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 1084 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3386 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3386 | h | 223 | 1
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 1475 | h | 223 | 1
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 1475 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3960 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3960 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 27169 | h | 223 | 1
SES0827-CWP-307 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 27169 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 307 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 307 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 23698 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 7633 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 7633 | h | 223 | 1
EEE1048-CWP-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 37267 | h | 223 | 1
EEE1048-CWP-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 37267 | h | 223 | 1
EEE1049-CWP-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 154299 | h | 223 | 1
EEE1049-CWP-377 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 154299 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 531 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 531 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 16056 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 16056 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 2056 | h | 223 | 1
EEE1049-PWPp-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 2056 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 1732 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 1732 | h | 223 | 1
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 6699 | h | 223 | 1
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 6699 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3960 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3960 | h | 223 | 1
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 24832 | h | 223 | 1
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 24832 | h | 223 | 1
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 10864 | h | 223 | 1
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 10864 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 8979 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 8979 | h | 223 | 1
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 58196 | h | 223 | 1
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 58196 | h | 223 | 1
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 67896 | h | 223 | 1
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 67896 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 7061 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 7061 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 11224 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 902 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 902 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 11855 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 11855 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 3960 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 3960 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 6537 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 6537 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 10217 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 10217 | h | 223 | 1
SWP-039-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 11610 | h | 223 | 1
SWP-039-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 11610 | h | 223 | 1
ECB0823-CWP-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 141856 | h | 223 | 1
ECB0823-CWP-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 141856 | h | 223 | 1
ECB0823-CWP-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 94571 | h | 223 | 1
ECB0823-CWP-557 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 94571 | h | 223 | 1
ECB0824-CWP-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 141856 | h | 223 | 1
ECB0824-CWP-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 141856 | h | 223 | 1
ECB0824-CWP-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 94571 | h | 223 | 1
ECB0824-CWP-560 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 94571 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-12 | 20905 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-12 | 20905 | h | 223 | 1
CPI0817-CWP-024 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 448 | h | 223 | 1
CPI0817-CWP-024 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 448 | h | 223 | 1
MEM0817-CWP-047 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 160 | h | 223 | 1
MEM0817-CWP-047 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 160 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 3837 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 3837 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 600 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 600 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 3900 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 3900 | h | 223 | 1
MEM0821-CWP-421 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 8143 | h | 223 | 1
MEM0821-CWP-421 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 8143 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 13 | h | 223 | 1
MEM0821-CWP-087 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 20360 | h | 223 | 1
MEM0821-CWP-087 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 20360 | h | 223 | 1
EEE0821-CWP-089 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 492 | h | 223 | 1
EEE0821-CWP-089 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 492 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 2 | h | 223 | 1
TTU0821-CWP-420 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 340 | h | 223 | 1
TTU0821-CWP-420 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 340 | h | 223 | 1
ECB0821-CWP-082 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 23205 | h | 223 | 1
ECB0821-CWP-082 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 23205 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 457 | h | 223 | 1
MMR0821-CWP-074 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 457 | h | 223 | 1
MEM0822-CWP-170 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 5700 | h | 223 | 1
MEM0822-CWP-170 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 5700 | h | 223 | 1
MEM0822-CWP-174 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1280 | h | 223 | 1
MEM0822-CWP-174 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1280 | h | 223 | 1
MEM0822-CWP-175 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 2560 | h | 223 | 1
MEM0822-CWP-175 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 2560 | h | 223 | 1
ERE0822-CWP-136 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 22464 | h | 223 | 1
ERE0822-CWP-136 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 22464 | h | 223 | 1
EEE1042-CWP-138 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 5925 | h | 223 | 1
EEE1042-CWP-138 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 5925 | h | 223 | 1
EEE1042-CWP-139 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 5925 | h | 223 | 1
EEE1042-CWP-139 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 5925 | h | 223 | 1
EEE1042-CWP-140 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 5925 | h | 223 | 1
EEE1042-CWP-140 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 5925 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 226 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 226 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 4059 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1598 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1598 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1777 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1777 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 4 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 922 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 922 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 3196 | h | 223 | 1
MMR0822-CWP-144 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 3196 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 10364 | h | 223 | 1
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 7800 | h | 223 | 1
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 7800 | h | 223 | 1
ERE0822-CWP-133 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 22464 | h | 223 | 1
ERE0822-CWP-133 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 22464 | h | 223 | 1
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 506 | h | 223 | 1
TTU0822-CWP-155 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 506 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 120 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 120 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 714 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 714 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1697 | h | 223 | 1
MEM0822-CWP-193 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 83 | h | 223 | 1
MEM0822-CWP-193 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 83 | h | 223 | 1
ECB0822-CWP-198 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 9750 | h | 223 | 1
ECB0822-CWP-198 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 9750 | h | 223 | 1
JIL0822-CWP-206 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 4000 | h | 223 | 1
JIL0822-CWP-206 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 4000 | h | 223 | 1
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 9750 | h | 223 | 1
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 9750 | h | 223 | 1
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 97 | h | 223 | 1
TTU0822-CWP-212 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 97 | h | 223 | 1
JIL0822-CWP-213 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 330 | h | 223 | 1
JIL0822-CWP-213 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 330 | h | 223 | 1
ECB0822-CWP-214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 9750 | h | 223 | 1
ECB0822-CWP-214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 9750 | h | 223 | 1
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 64 | h | 223 | 1
TTU0822-CWP-216 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 64 | h | 223 | 1
ECB0822-CWP-219 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 9750 | h | 223 | 1
ECB0822-CWP-219 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 9750 | h | 223 | 1
ECB0822-CWP-226 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 9750 | h | 223 | 1
ECB0822-CWP-226 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 9750 | h | 223 | 1
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 128 | h | 223 | 1
TTU0822-CWP-227 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 128 | h | 223 | 1
JIL0822-CWP-228 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1056 | h | 223 | 1
JIL0822-CWP-228 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1056 | h | 223 | 1
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 96 | h | 223 | 1
TTU0822-CWP-232 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 96 | h | 223 | 1
JIL0822-CWP-233 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 2112 | h | 223 | 1
JIL0822-CWP-233 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 2112 | h | 223 | 1
ECB0822-CWP-251 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 9750 | h | 223 | 1
ECB0822-CWP-251 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 9750 | h | 223 | 1
ECB0822-CWP-252 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 9750 | h | 223 | 1
ECB0822-CWP-252 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 9750 | h | 223 | 1
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 48 | h | 223 | 1
TTU0822-CWP-236 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 48 | h | 223 | 1
JIL0822-CWP-237 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 132 | h | 223 | 1
JIL0822-CWP-237 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 132 | h | 223 | 1
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 32 | h | 223 | 1
TTU0822-CWP-239 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 32 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 446 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 446 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 53 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 407 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 407 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 2949 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 2949 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 872 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 872 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1085 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1085 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 993 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 993 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 286 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 286 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 407 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 407 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 976 | h | 223 | 1
MMR0827-CWP-326 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 960 | h | 223 | 1
MMR0827-CWP-326 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 960 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 340 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 340 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 48 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 48 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 93 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 93 | h | 223 | 1
EEE0827-CWP-457 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 67 | h | 223 | 1
EEE0827-CWP-457 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 67 | h | 223 | 1
MEM0827-CWP-348 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 22 | h | 223 | 1
MEM0827-CWP-348 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 22 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1120 | h | 223 | 1
SES0827-CWP-307 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1120 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 38 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 38 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1846 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1846 | h | 223 | 1
EEE1048-CWP-473 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 70 | h | 223 | 1
EEE1048-CWP-473 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 70 | h | 223 | 1
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1024 | h | 223 | 1
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1024 | h | 223 | 1
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 448 | h | 223 | 1
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 448 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 370 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 370 | h | 223 | 1
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 2400 | h | 223 | 1
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 2400 | h | 223 | 1
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 2800 | h | 223 | 1
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 2800 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 291 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 291 | h | 223 | 1
MEM0623-CWP-410 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 173 | h | 223 | 1
MEM0623-CWP-410 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 173 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 489 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 489 | h | 223 | 1
ECB0600-CWP-408 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 22800 | h | 223 | 1
ECB0600-CWP-408 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 22800 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1090 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1090 | h | 223 | 1
SWP-039-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 2567 | h | 223 | 1
SWP-039-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 2567 | h | 223 | 1
ECB0817-CWP-550 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1043 | h | 223 | 1
ECB0817-CWP-550 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1043 | h | 223 | 1
ECB0817-CWP-551 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 1565 | h | 223 | 1
ECB0817-CWP-551 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 1565 | h | 223 | 1
ECB0823-CWP-556 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 5850 | h | 223 | 1
ECB0823-CWP-556 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 5850 | h | 223 | 1
ECB0823-CWP-557 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 3900 | h | 223 | 1
ECB0823-CWP-557 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 3900 | h | 223 | 1
ECB0824-CWP-559 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 5850 | h | 223 | 1
ECB0824-CWP-559 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 5850 | h | 223 | 1
ECB0824-CWP-560 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 3900 | h | 223 | 1
ECB0824-CWP-560 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 3900 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-12 | 872 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-12 | 872 | h | 223 | 1
MEM0817-CWP-025 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-05-19 | 1 | m | 223 | 1
MEM0817-CWP-025 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-05-19 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-05-19 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-05-19 | 1 | m | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-19 | 7 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-19 | 7 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-19 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-19 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-19 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-19 | 6 | t | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-19 | 363 | m | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-19 | 363 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-19 | 404 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-19 | 404 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-19 | 545 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-19 | 545 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-19 | 84 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-19 | 84 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-19 | 66 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-19 | 66 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 488 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 488 | m | 223 | 1
ECB0821-CWP-082 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 24 | m | 223 | 1
ECB0821-CWP-082 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 24 | m | 223 | 1
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 975 | m | 223 | 1
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 975 | m | 223 | 1
ECB0822-CWP-198 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-198 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-214 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-214 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-219 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-219 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-226 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-226 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-251 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-251 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-252 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0822-CWP-252 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 1219 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 603 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 603 | m | 223 | 1
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 1900 | m | 223 | 1
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 1900 | m | 223 | 1
ECB0817-CWP-550 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 195 | m | 223 | 1
ECB0817-CWP-550 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 195 | m | 223 | 1
ECB0823-CWP-555 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 975 | m | 223 | 1
ECB0823-CWP-555 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 975 | m | 223 | 1
ECB0823-CWP-556 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 244 | m | 223 | 1
ECB0823-CWP-556 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 244 | m | 223 | 1
ECB0824-CWP-558 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 975 | m | 223 | 1
ECB0824-CWP-558 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 975 | m | 223 | 1
ECB0824-CWP-559 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-19 | 244 | m | 223 | 1
ECB0824-CWP-559 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-19 | 244 | m | 223 | 1
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 0 | un | 223 | 1
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 0 | un | 223 | 1
JIL0800-CWP-058 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 7 | un | 223 | 1
JIL0800-CWP-058 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 7 | un | 223 | 1
JIL0820-CWP-418 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 3 | un | 223 | 1
JIL0820-CWP-418 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 3 | un | 223 | 1
EEE0822-CWP-158 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 0 | un | 223 | 1
EEE0822-CWP-158 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 0 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 5 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 5 | un | 223 | 1
JIL0822-CWP-166 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 104 | un | 223 | 1
JIL0822-CWP-166 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 104 | un | 223 | 1
JIL0822-CWP-213 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 2 | un | 223 | 1
JIL0822-CWP-213 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 2 | un | 223 | 1
JIL0822-CWP-228 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 7 | un | 223 | 1
JIL0822-CWP-228 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 7 | un | 223 | 1
JIL0822-CWP-233 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 13 | un | 223 | 1
JIL0822-CWP-233 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 13 | un | 223 | 1
JIL0827-CWP-363 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 2 | un | 223 | 1
JIL0827-CWP-363 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 2 | un | 223 | 1
JIL0827-CWP-365 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 30 | un | 223 | 1
JIL0827-CWP-365 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 30 | un | 223 | 1
EEE1062-CWP-460 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 1 | un | 223 | 1
EEE1062-CWP-460 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 1 | un | 223 | 1
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 2 | un | 223 | 1
EEE1214-CWP-463 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 2 | un | 223 | 1
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-19 | 5 | un | 223 | 1
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-19 | 5 | un | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-19 | 2 | m | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-19 | 2 | m | 223 | 1
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-19 | 117 | m | 223 | 1
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-19 | 117 | m | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-19 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-19 | 0 | un | 223 | 1
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-19 | 4 | un | 223 | 1
ELU1214-CWP-462 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-19 | 4 | un | 223 | 1
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 1 | un | 223 | 1
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 1 | un | 223 | 1
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 40 | un | 223 | 1
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 40 | un | 223 | 1
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 1 | un | 223 | 1
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 1 | un | 223 | 1
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 40 | un | 223 | 1
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 40 | un | 223 | 1
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 40 | un | 223 | 1
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 40 | un | 223 | 1
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 40 | un | 223 | 1
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 40 | un | 223 | 1
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 40 | un | 223 | 1
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 40 | un | 223 | 1
EEE1048-CWP-473 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 2 | un | 223 | 1
EEE1048-CWP-473 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 2 | un | 223 | 1
EEE1062-CWP-386 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 0 | un | 223 | 1
EEE1062-CWP-386 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 0 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-19 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-19 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-19 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-19 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-19 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-19 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-19 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-19 |  |  | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-19 |  |  | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-19 |  |  | 223 | 1
MEM0821-CWP-421 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 3 | t | 223 | 1
MEM0821-CWP-421 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 3 | t | 223 | 1
MEM0821-CWP-083 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 7 | t | 223 | 1
MEM0821-CWP-083 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 7 | t | 223 | 1
MEM0821-CWP-087 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 4 | t | 223 | 1
MEM0821-CWP-087 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 4 | t | 223 | 1
TTU0821-CWP-420 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 0 | t | 223 | 1
TTU0821-CWP-420 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 0 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 0 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 0 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 2 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 1 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 1 | t | 223 | 1
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 0 | t | 223 | 1
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 0 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 1 | t | 223 | 1
MEM0826-CWP-284 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 1 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 2 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 2 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 0 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 0 | t | 223 | 1
TTU0622-CWP-019 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 1 | t | 223 | 1
TTU0622-CWP-019 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 1 | t | 223 | 1
MEM0622-CWP-003 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-19 | 3 | t | 223 | 1
MEM0622-CWP-003 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-19 | 3 | t | 223 | 1
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-05-19 | 47 | t | 223 | 1
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-05-19 | 47 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-05-19 | 1 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-05-19 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-05-19 | 1 | t | 223 | 1
MSD0824-CWP-588 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-05-19 | 1 | t | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-19 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-19 | 65 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-19 | 3 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-19 | 3 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-19 | 18 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-19 | 18 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-19 | 3 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-19 | 3 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-19 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-19 | 5 | tons | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 10227 | h | 223 | 1
RIN0800-PWPl-021 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 10227 | h | 223 | 1
MEM0817-CWP-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 5432 | h | 223 | 1
MEM0817-CWP-025 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 5432 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 93051 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 93051 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 5706 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 1099 | h | 223 | 1
JIL0800-PWPl-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 1099 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 2192 | h | 223 | 1
JIL0820-PWPl-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 2192 | h | 223 | 1
JIL0800-CWP-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 31659 | h | 223 | 1
JIL0800-CWP-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 31659 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 94571 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 94571 | h | 223 | 1
JIL0820-CWP-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 11873 | h | 223 | 1
JIL0820-CWP-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 11873 | h | 223 | 1
MEM0821-CWP-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 64503 | h | 223 | 1
MEM0821-CWP-421 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 64503 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 307 | h | 223 | 1
MEM0821-CWP-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 128912 | h | 223 | 1
MEM0821-CWP-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 128912 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 27498 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 8586 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 8586 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 96678 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 134 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 134 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 55812 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 55812 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 96678 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 29137 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 29137 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 1117 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 1117 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 1117 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 1117 | h | 223 | 1
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 178781 | h | 223 | 1
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 178781 | h | 223 | 1
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 178781 | h | 223 | 1
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 178781 | h | 223 | 1
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 178781 | h | 223 | 1
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 178781 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 3619 | h | 223 | 1
JIL0822-PWPl-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 3619 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 3371 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 7915 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 7915 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 7962 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 86314 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 86314 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 102697 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 38760 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 38760 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 43086 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 43086 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 109 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 483 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 483 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 483 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 483 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 1454 | h | 223 | 1
EEE0822-PWPl-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 1454 | h | 223 | 1
EEE0822-CWP-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 116 | h | 223 | 1
EEE0822-CWP-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 116 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 22347 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 22347 | h | 223 | 1
JIL0822-CWP-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 680677 | h | 223 | 1
JIL0822-CWP-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 680677 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 2192 | h | 223 | 1
JIL0822-PWPl-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 2192 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 251317 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 27498 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 18604 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 44696 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 11428 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 11428 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 58140 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 58140 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 4770 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 21767 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 45943 | h | 223 | 1
MEM0822-CWP-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 2020 | h | 223 | 1
MEM0822-CWP-193 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 2020 | h | 223 | 1
ECB0822-CWP-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 236427 | h | 223 | 1
ECB0822-CWP-198 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 236427 | h | 223 | 1
JIL0822-CWP-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 38799 | h | 223 | 1
JIL0822-CWP-206 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 38799 | h | 223 | 1
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 101459 | h | 223 | 1
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 101459 | h | 223 | 1
JIL0822-CWP-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 9700 | h | 223 | 1
JIL0822-CWP-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 9700 | h | 223 | 1
ECB0822-CWP-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 236427 | h | 223 | 1
ECB0822-CWP-214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 236427 | h | 223 | 1
ECB0822-CWP-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 236427 | h | 223 | 1
ECB0822-CWP-219 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 236427 | h | 223 | 1
ECB0822-CWP-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 236427 | h | 223 | 1
ECB0822-CWP-226 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 236427 | h | 223 | 1
JIL0822-CWP-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 31040 | h | 223 | 1
JIL0822-CWP-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 31040 | h | 223 | 1
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 206 | h | 223 | 1
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 206 | h | 223 | 1
JIL0822-CWP-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 62077 | h | 223 | 1
JIL0822-CWP-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 62077 | h | 223 | 1
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 412 | h | 223 | 1
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 412 | h | 223 | 1
ECB0822-CWP-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 236427 | h | 223 | 1
ECB0822-CWP-251 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 236427 | h | 223 | 1
ECB0822-CWP-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 236427 | h | 223 | 1
ECB0822-CWP-252 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 236427 | h | 223 | 1
JIL0822-CWP-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 3880 | h | 223 | 1
JIL0822-CWP-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 3880 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 10809 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 10809 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 1275 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 9861 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 9861 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 71499 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 71499 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 20905 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 20905 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 22638 | h | 223 | 1
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 48502 | h | 223 | 1
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 48502 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 27498 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 25661 | h | 223 | 1
MCD0824-CWP-502 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 25661 | h | 223 | 1
MEM0824-CWP-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 19301 | h | 223 | 1
MEM0824-CWP-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 19301 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 27498 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 22697 | h | 223 | 1
EBD0826-CWP-294 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 22697 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 166755 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 166755 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 6936 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 6936 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 23279 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 776 | h | 223 | 1
JIL0827-CWP-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 11873 | h | 223 | 1
JIL0827-CWP-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 11873 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 27498 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 17700 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 581 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 581 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 4817 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 3386 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 3386 | h | 223 | 1
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 701 | h | 223 | 1
MEM0827-CWP-348 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 701 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 2192 | h | 223 | 1
JIL0827-PWPl-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 2192 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 1364 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 23698 | h | 223 | 1
JIL0827-CWP-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 139672 | h | 223 | 1
JIL0827-CWP-365 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 139672 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 1336 | h | 223 | 1
EBD0827-CWP-366 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 1336 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 17650 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 17650 | h | 223 | 1
EEE1048-CWP-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 37267 | h | 223 | 1
EEE1048-CWP-473 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 37267 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 3720 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 3720 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 21930 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 21930 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 1454 | h | 223 | 1
EEE1062-PWPl-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 1454 | h | 223 | 1
EEE1062-CWP-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 2188 | h | 223 | 1
EEE1062-CWP-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 2188 | h | 223 | 1
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 4665 | h | 223 | 1
EEE1062-PWPl-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 4665 | h | 223 | 1
EEE1062-CWP-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 2514 | h | 223 | 1
EEE1062-CWP-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 2514 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 2192 | h | 223 | 1
JIL1214-PWPl-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 2192 | h | 223 | 1
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 19452 | h | 223 | 1
ELU1214-CWP-462 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 19452 | h | 223 | 1
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 8420 | h | 223 | 1
EEE1214-CWP-463 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 8420 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 8979 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 8979 | h | 223 | 1
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 45587 | h | 223 | 1
EBD1214-CWP-395 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 45587 | h | 223 | 1
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 25128 | h | 223 | 1
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 25128 | h | 223 | 1
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 67896 | h | 223 | 1
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 67896 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 7061 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 7061 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 11224 | h | 223 | 1
TTU0622-CWP-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 19784 | h | 223 | 1
TTU0622-CWP-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 19784 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 371 | h | 223 | 1
TTU0622-PWPl-019 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 371 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 11855 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 11855 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 2192 | h | 223 | 1
JIL0622-PWPl-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 2192 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 3619 | h | 223 | 1
JIL0622-PWPl-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 3619 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 20434 | h | 223 | 1
MEM0622-CWP-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 61885 | h | 223 | 1
MEM0622-CWP-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 61885 | h | 223 | 1
SWP-039-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 6251 | h | 223 | 1
SWP-039-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 6251 | h | 223 | 1
ECB0823-CWP-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 189141 | h | 223 | 1
ECB0823-CWP-555 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 189141 | h | 223 | 1
ECB0823-CWP-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 47285 | h | 223 | 1
ECB0823-CWP-556 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 47285 | h | 223 | 1
ECB0824-CWP-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 189141 | h | 223 | 1
ECB0824-CWP-558 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 189141 | h | 223 | 1
ECB0824-CWP-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 47285 | h | 223 | 1
ECB0824-CWP-559 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 47285 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-19 | 14111 | h | 223 | 1
MSD0824-CWP-588 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-19 | 14111 | h | 223 | 1
RIN0800-CWP-021 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 6 | h | 223 | 1
RIN0800-CWP-021 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 6 | h | 223 | 1
MEM0817-CWP-025 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 224 | h | 223 | 1
MEM0817-CWP-025 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 224 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 3837 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 3837 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 600 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 600 | h | 223 | 1
JIL0800-CWP-058 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1306 | h | 223 | 1
JIL0800-CWP-058 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1306 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 3900 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 3900 | h | 223 | 1
JIL0820-CWP-418 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 490 | h | 223 | 1
JIL0820-CWP-418 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 490 | h | 223 | 1
MEM0821-CWP-421 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 2036 | h | 223 | 1
MEM0821-CWP-421 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 2036 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 13 | h | 223 | 1
MEM0821-CWP-083 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 5696 | h | 223 | 1
MEM0821-CWP-083 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 5696 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 2 | h | 223 | 1
TTU0821-CWP-420 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 264 | h | 223 | 1
TTU0821-CWP-420 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 264 | h | 223 | 1
ECB0821-CWP-082 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 195 | h | 223 | 1
ECB0821-CWP-082 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 195 | h | 223 | 1
ERE0822-CWP-134 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 576 | h | 223 | 1
ERE0822-CWP-134 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 576 | h | 223 | 1
ERE0822-CWP-137 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 576 | h | 223 | 1
ERE0822-CWP-137 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 576 | h | 223 | 1
EEE1042-CWP-138 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 26331 | h | 223 | 1
EEE1042-CWP-138 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 26331 | h | 223 | 1
EEE1042-CWP-139 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 26331 | h | 223 | 1
EEE1042-CWP-139 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 26331 | h | 223 | 1
EEE1042-CWP-140 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 26331 | h | 223 | 1
EEE1042-CWP-140 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 26331 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 326 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 326 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 4059 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1598 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1598 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1777 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1777 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 4 | h | 223 | 1
EEE0822-CWP-158 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 5 | h | 223 | 1
EEE0822-CWP-158 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 5 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 922 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 922 | h | 223 | 1
JIL0822-CWP-166 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 19910 | h | 223 | 1
JIL0822-CWP-166 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 19910 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 10364 | h | 223 | 1
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 7800 | h | 223 | 1
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 7800 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 2398 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 2398 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 714 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 714 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1697 | h | 223 | 1
MEM0822-CWP-193 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 83 | h | 223 | 1
MEM0822-CWP-193 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 83 | h | 223 | 1
ECB0822-CWP-198 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-198 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 9750 | h | 223 | 1
JIL0822-CWP-206 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1600 | h | 223 | 1
JIL0822-CWP-206 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1600 | h | 223 | 1
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 9750 | h | 223 | 1
JIL0822-CWP-213 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 400 | h | 223 | 1
JIL0822-CWP-213 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 400 | h | 223 | 1
ECB0822-CWP-214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-219 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-219 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-226 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-226 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 9750 | h | 223 | 1
JIL0822-CWP-228 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1280 | h | 223 | 1
JIL0822-CWP-228 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1280 | h | 223 | 1
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 9 | h | 223 | 1
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 9 | h | 223 | 1
JIL0822-CWP-233 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 2560 | h | 223 | 1
JIL0822-CWP-233 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 2560 | h | 223 | 1
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 17 | h | 223 | 1
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 17 | h | 223 | 1
ECB0822-CWP-251 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-251 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-252 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 9750 | h | 223 | 1
ECB0822-CWP-252 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 9750 | h | 223 | 1
JIL0822-CWP-237 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 160 | h | 223 | 1
JIL0822-CWP-237 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 160 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 446 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 446 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 53 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 407 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 407 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 2949 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 2949 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 872 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 872 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1058 | h | 223 | 1
MCD0824-CWP-502 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1058 | h | 223 | 1
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 204 | h | 223 | 1
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 204 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 770 | h | 223 | 1
EBD0826-CWP-294 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 770 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 286 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 286 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 315 | h | 223 | 1
MEM0826-CWP-284 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 315 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 976 | h | 223 | 1
JIL0827-CWP-363 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 367 | h | 223 | 1
JIL0827-CWP-363 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 367 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1512 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1512 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 24 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 24 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 48 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 48 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 411 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 411 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 170 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 170 | h | 223 | 1
JIL0827-CWP-365 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 5760 | h | 223 | 1
JIL0827-CWP-365 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 5760 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 323 | h | 223 | 1
EBD0827-CWP-366 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 323 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 4826 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 4826 | h | 223 | 1
EEE1062-CWP-386 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 94 | h | 223 | 1
EEE1062-CWP-386 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 94 | h | 223 | 1
EEE1062-CWP-460 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 108 | h | 223 | 1
EEE1062-CWP-460 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 108 | h | 223 | 1
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 802 | h | 223 | 1
ELU1214-CWP-462 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 802 | h | 223 | 1
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 347 | h | 223 | 1
EEE1214-CWP-463 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 347 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 370 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 370 | h | 223 | 1
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1880 | h | 223 | 1
EBD1214-CWP-395 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1880 | h | 223 | 1
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1036 | h | 223 | 1
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1036 | h | 223 | 1
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 2800 | h | 223 | 1
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 2800 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 291 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 291 | h | 223 | 1
TTU0622-CWP-019 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 816 | h | 223 | 1
TTU0622-CWP-019 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 816 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 489 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 489 | h | 223 | 1
RIN1110-CWP-387 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 90 | h | 223 | 1
RIN1110-CWP-387 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 90 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 2179 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 2179 | h | 223 | 1
MEM0622-CWP-003 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 2552 | h | 223 | 1
MEM0622-CWP-003 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 2552 | h | 223 | 1
SWP-039-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1382 | h | 223 | 1
SWP-039-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1382 | h | 223 | 1
ECB0817-CWP-550 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1565 | h | 223 | 1
ECB0817-CWP-550 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1565 | h | 223 | 1
ECB0823-CWP-555 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 7800 | h | 223 | 1
ECB0823-CWP-555 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 7800 | h | 223 | 1
ECB0823-CWP-556 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1950 | h | 223 | 1
ECB0823-CWP-556 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1950 | h | 223 | 1
ECB0824-CWP-558 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 7800 | h | 223 | 1
ECB0824-CWP-558 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 7800 | h | 223 | 1
ECB0824-CWP-559 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 1950 | h | 223 | 1
ECB0824-CWP-559 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 1950 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-19 | 502 | h | 223 | 1
MSD0824-CWP-588 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-19 | 502 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-05-26 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-05-26 | 1 | m | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-26 | 7 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-26 | 7 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-26 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-26 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-05-26 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-05-26 | 6 | t | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-26 | 363 | m | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-26 | 363 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-26 | 404 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-26 | 404 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-26 | 545 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-26 | 545 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-26 | 84 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-26 | 84 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-05-26 | 51 | m | 223 | 1
TTU1340-CWP-507 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-05-26 | 51 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 488 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 488 | m | 223 | 1
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 585 | m | 223 | 1
ECB0822-CWP-130 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 585 | m | 223 | 1
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 731 | m | 223 | 1
ECB0822-CWP-208 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 731 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 731 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 731 | m | 223 | 1
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 1140 | m | 223 | 1
ECB0600-CWP-408 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 1140 | m | 223 | 1
ECB1214-CWP-534 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 527 | m | 223 | 1
ECB1214-CWP-534 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 527 | m | 223 | 1
ECB1214-CWP-535 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 527 | m | 223 | 1
ECB1214-CWP-535 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 527 | m | 223 | 1
ECB1214-CWP-536 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 527 | m | 223 | 1
ECB1214-CWP-536 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 527 | m | 223 | 1
ECB1214-CWP-537 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 527 | m | 223 | 1
ECB1214-CWP-537 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 527 | m | 223 | 1
ECB1048-CWP-567 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 100 | m | 223 | 1
ECB1048-CWP-567 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 100 | m | 223 | 1
ECB1048-CWP-568 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 100 | m | 223 | 1
ECB1048-CWP-568 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 100 | m | 223 | 1
ECB1048-CWP-569 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 100 | m | 223 | 1
ECB1048-CWP-569 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 100 | m | 223 | 1
ECB1062-CWP-573 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 324 | m | 223 | 1
ECB1062-CWP-573 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 324 | m | 223 | 1
ECB1062-CWP-574 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 1295 | m | 223 | 1
ECB1062-CWP-574 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 1295 | m | 223 | 1
ECB1062-CWP-575 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 1295 | m | 223 | 1
ECB1062-CWP-575 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 1295 | m | 223 | 1
ECB1214-CWP-576 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 88 | m | 223 | 1
ECB1214-CWP-576 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 88 | m | 223 | 1
ECB1214-CWP-577 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-05-26 | 88 | m | 223 | 1
ECB1214-CWP-577 | CABLAGEM - WIRING | Material | At Completion Units | 2024-05-26 | 88 | m | 223 | 1
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 0 | un | 223 | 1
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 0 | un | 223 | 1
JIL0800-CWP-058 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 34 | un | 223 | 1
JIL0800-CWP-058 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 34 | un | 223 | 1
JIL0820-CWP-418 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 6 | un | 223 | 1
JIL0820-CWP-418 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 6 | un | 223 | 1
EEE0822-CWP-158 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 1 | un | 223 | 1
EEE0822-CWP-158 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 1 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 5 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 5 | un | 223 | 1
JIL0822-CWP-166 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 244 | un | 223 | 1
JIL0822-CWP-166 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 244 | un | 223 | 1
JIL0822-CWP-213 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 1 | un | 223 | 1
JIL0822-CWP-213 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 1 | un | 223 | 1
JIL0822-CWP-228 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 4 | un | 223 | 1
JIL0822-CWP-228 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 4 | un | 223 | 1
JIL0822-CWP-233 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 8 | un | 223 | 1
JIL0822-CWP-233 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 8 | un | 223 | 1
JIL0827-CWP-363 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 5 | un | 223 | 1
JIL0827-CWP-363 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 5 | un | 223 | 1
EEE1062-CWP-460 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 1 | un | 223 | 1
EEE1062-CWP-460 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 1 | un | 223 | 1
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-05-26 | 10 | un | 223 | 1
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-05-26 | 10 | un | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-26 | 2 | m | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-26 | 2 | m | 223 | 1
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-26 | 14 | m | 223 | 1
EBD1214-CWP-401 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-26 | 14 | m | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-26 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-26 | 0 | un | 223 | 1
ELU0600-CWP-007 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-05-26 | 10 | un | 223 | 1
ELU0600-CWP-007 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-05-26 | 10 | un | 223 | 1
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 40 | un | 223 | 1
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 40 | un | 223 | 1
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 39 | un | 223 | 1
ERE0822-CWP-136 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 39 | un | 223 | 1
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 40 | un | 223 | 1
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 40 | un | 223 | 1
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 40 | un | 223 | 1
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 40 | un | 223 | 1
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 40 | un | 223 | 1
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 40 | un | 223 | 1
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 40 | un | 223 | 1
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 40 | un | 223 | 1
EEE0820-CWP-141 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 33 | un | 223 | 1
EEE0820-CWP-141 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 33 | un | 223 | 1
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 39 | un | 223 | 1
ERE0822-CWP-133 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 39 | un | 223 | 1
EEE1062-CWP-386 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 1 | un | 223 | 1
EEE1062-CWP-386 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 1 | un | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-26 |  |  | 223 | 1
MCD0821-CWP-423 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-26 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-26 |  |  | 223 | 1
MCD0824-CWP-091 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-26 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-26 |  |  | 223 | 1
MCD0821-CWP-066 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-26 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-26 |  |  | 223 | 1
MCD0823-CWP-438 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-26 |  |  | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-05-26 |  |  | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | At Completion Units | 2024-05-26 |  |  | 223 | 1
MEM0821-CWP-083 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 18 | t | 223 | 1
MEM0821-CWP-083 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 18 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 0 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 0 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 2 | t | 223 | 1
MEM0823-CWP-439 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 0 | t | 223 | 1
MEM0823-CWP-439 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 0 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 1 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 1 | t | 223 | 1
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 0 | t | 223 | 1
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 0 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 2 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 2 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 0 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 0 | t | 223 | 1
MEM0622-CWP-003 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-05-26 | 8 | t | 223 | 1
MEM0622-CWP-003 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-05-26 | 8 | t | 223 | 1
MEM1214-CWP-524 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-05-26 | 1 | un | 223 | 1
MEM1214-CWP-524 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-05-26 | 1 | un | 223 | 1
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-05-26 | 36 | t | 223 | 1
MCD0826-CWP-281 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-05-26 | 36 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-05-26 | 1 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-05-26 | 1 | t | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-26 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-26 | 65 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-26 | 3 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-26 | 3 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-26 | 18 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-26 | 18 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-26 | 3 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-26 | 3 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-05-26 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-05-26 | 5 | tons | 223 | 1
MMR0817-CWP-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 23280 | h | 223 | 1
MMR0817-CWP-036 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 23280 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 93051 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 93051 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 5706 | h | 223 | 1
JIL0800-CWP-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 158296 | h | 223 | 1
JIL0800-CWP-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 158296 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 94571 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 94571 | h | 223 | 1
JIL0820-CWP-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 27936 | h | 223 | 1
JIL0820-CWP-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 27936 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 307 | h | 223 | 1
MCD0821-CWP-423 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 307 | h | 223 | 1
MEM0821-CWP-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 329136 | h | 223 | 1
MEM0821-CWP-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 329136 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 27498 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 8586 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 8586 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 96678 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 96678 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 161 | h | 223 | 1
MCD0824-CWP-091 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 161 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 80 | h | 223 | 1
MCD0821-CWP-066 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 80 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 55812 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 55812 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 96678 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 96678 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 2589 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 3156 | h | 223 | 1
SES0821-CWP-501 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 3156 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 44696 | h | 223 | 1
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 178781 | h | 223 | 1
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 178781 | h | 223 | 1
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 178781 | h | 223 | 1
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 178781 | h | 223 | 1
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 178781 | h | 223 | 1
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 178781 | h | 223 | 1
EEE0820-CWP-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 147494 | h | 223 | 1
EEE0820-CWP-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 147494 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 3371 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 7915 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 7915 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 7962 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 69051 | h | 223 | 1
MEM0822-PWPp-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 69051 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 102697 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 38760 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 38760 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 43086 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 43086 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 109 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 129 | h | 223 | 1
EEE0820-PWPl-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 129 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 129 | h | 223 | 1
EEE0820-PWPl-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 129 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 129 | h | 223 | 1
EEE0820-PWPl-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 129 | h | 223 | 1
EEE0822-CWP-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 4656 | h | 223 | 1
EEE0822-CWP-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 4656 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 22347 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 22347 | h | 223 | 1
JIL0822-CWP-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 1601592 | h | 223 | 1
JIL0822-CWP-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 1601592 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 251317 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 27498 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 18604 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 44696 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 11428 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 11428 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 58140 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 58140 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 4770 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 21767 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 21767 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 45943 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 1649 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 1649 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 808823 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 808823 | h | 223 | 1
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 60876 | h | 223 | 1
ECB0822-CWP-208 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 60876 | h | 223 | 1
JIL0822-CWP-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 5578 | h | 223 | 1
JIL0822-CWP-213 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 5578 | h | 223 | 1
JIL0822-CWP-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 17848 | h | 223 | 1
JIL0822-CWP-228 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 17848 | h | 223 | 1
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 8243 | h | 223 | 1
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 8243 | h | 223 | 1
JIL0822-CWP-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 35694 | h | 223 | 1
JIL0822-CWP-233 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 35694 | h | 223 | 1
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 16490 | h | 223 | 1
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 16490 | h | 223 | 1
JIL0822-CWP-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 2231 | h | 223 | 1
JIL0822-CWP-237 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 2231 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 10809 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 10809 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 1275 | h | 223 | 1
MCD0823-CWP-438 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 1275 | h | 223 | 1
MEM0823-CWP-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 221 | h | 223 | 1
MEM0823-CWP-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 221 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 9861 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 9861 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 71499 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 71499 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 20905 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 20905 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 22638 | h | 223 | 1
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 114122 | h | 223 | 1
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 114122 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 27498 | h | 223 | 1
MEM0824-CWP-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 483 | h | 223 | 1
MEM0824-CWP-280 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 483 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 27498 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 166755 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 166755 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 6936 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 6936 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 23279 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 776 | h | 223 | 1
JIL0827-CWP-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 27936 | h | 223 | 1
JIL0827-CWP-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 27936 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 27498 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 17700 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 581 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 581 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 4817 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 3386 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 3386 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 1364 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 23698 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 21394 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 21394 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 3720 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 3720 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 21930 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 21930 | h | 223 | 1
EEE1062-CWP-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 2468 | h | 223 | 1
EEE1062-CWP-386 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 2468 | h | 223 | 1
EEE1062-CWP-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 6798 | h | 223 | 1
EEE1062-CWP-460 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 6798 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 8979 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 8979 | h | 223 | 1
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 45005 | h | 223 | 1
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 45005 | h | 223 | 1
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 7921 | h | 223 | 1
EBD1214-CWP-401 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 7921 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 5472 | h | 223 | 1
TTU1340-CWP-507 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 5472 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 11224 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 11855 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 11855 | h | 223 | 1
ELU0600-CWP-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 48419 | h | 223 | 1
ELU0600-CWP-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 48419 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 20434 | h | 223 | 1
MEM0622-CWP-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 158004 | h | 223 | 1
MEM0622-CWP-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 158004 | h | 223 | 1
MEM1214-CWP-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 17170 | h | 223 | 1
MEM1214-CWP-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 17170 | h | 223 | 1
ECB1214-CWP-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 108538 | h | 223 | 1
ECB1214-CWP-534 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 108538 | h | 223 | 1
ECB1214-CWP-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 108538 | h | 223 | 1
ECB1214-CWP-535 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 108538 | h | 223 | 1
ECB1214-CWP-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 108538 | h | 223 | 1
ECB1214-CWP-536 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 108538 | h | 223 | 1
ECB1214-CWP-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 108538 | h | 223 | 1
ECB1214-CWP-537 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 108538 | h | 223 | 1
ECB1062-CWP-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 62789 | h | 223 | 1
ECB1062-CWP-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 62789 | h | 223 | 1
ECB1062-CWP-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 251155 | h | 223 | 1
ECB1062-CWP-574 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 251155 | h | 223 | 1
ECB1062-CWP-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 251155 | h | 223 | 1
ECB1062-CWP-575 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 251155 | h | 223 | 1
ECB1214-CWP-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 18090 | h | 223 | 1
ECB1214-CWP-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 18090 | h | 223 | 1
ECB1214-CWP-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-05-26 | 36746 | h | 223 | 1
ECB1214-CWP-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-05-26 | 36746 | h | 223 | 1
RIN0800-CWP-021 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 186 | h | 223 | 1
RIN0800-CWP-021 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 186 | h | 223 | 1
MMR0817-CWP-036 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 960 | h | 223 | 1
MMR0817-CWP-036 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 960 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 3837 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 3837 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 600 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 600 | h | 223 | 1
JIL0800-CWP-058 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 6528 | h | 223 | 1
JIL0800-CWP-058 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 6528 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 3900 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 3900 | h | 223 | 1
JIL0820-CWP-418 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 1152 | h | 223 | 1
JIL0820-CWP-418 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 1152 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 13 | h | 223 | 1
MCD0821-CWP-423 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 13 | h | 223 | 1
MEM0821-CWP-083 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 14543 | h | 223 | 1
MEM0821-CWP-083 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 14543 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 2 | h | 223 | 1
ERE0822-CWP-134 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 22464 | h | 223 | 1
ERE0822-CWP-134 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 22464 | h | 223 | 1
ERE0822-CWP-137 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 22464 | h | 223 | 1
ERE0822-CWP-137 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 22464 | h | 223 | 1
EEE1042-CWP-138 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 20407 | h | 223 | 1
EEE1042-CWP-138 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 20407 | h | 223 | 1
EEE1042-CWP-139 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 20407 | h | 223 | 1
EEE1042-CWP-139 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 20407 | h | 223 | 1
EEE1042-CWP-140 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 20407 | h | 223 | 1
EEE1042-CWP-140 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 20407 | h | 223 | 1
EEE0820-CWP-141 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 18432 | h | 223 | 1
EEE0820-CWP-141 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 18432 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 326 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 326 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 4059 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 1598 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 1598 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 1777 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 1777 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 4 | h | 223 | 1
EEE0822-CWP-158 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 192 | h | 223 | 1
EEE0822-CWP-158 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 192 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 922 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 922 | h | 223 | 1
JIL0822-CWP-166 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 46848 | h | 223 | 1
JIL0822-CWP-166 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 46848 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 10364 | h | 223 | 1
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 4680 | h | 223 | 1
ECB0822-CWP-130 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 4680 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 2398 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 2398 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 714 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 714 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 1697 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 68 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 68 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 44792 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 44792 | h | 223 | 1
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 5850 | h | 223 | 1
ECB0822-CWP-208 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 5850 | h | 223 | 1
JIL0822-CWP-213 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 230 | h | 223 | 1
JIL0822-CWP-213 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 230 | h | 223 | 1
JIL0822-CWP-228 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 736 | h | 223 | 1
JIL0822-CWP-228 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 736 | h | 223 | 1
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 340 | h | 223 | 1
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 340 | h | 223 | 1
JIL0822-CWP-233 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 1472 | h | 223 | 1
JIL0822-CWP-233 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 1472 | h | 223 | 1
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 680 | h | 223 | 1
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 680 | h | 223 | 1
JIL0822-CWP-237 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 92 | h | 223 | 1
JIL0822-CWP-237 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 92 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 446 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 446 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 53 | h | 223 | 1
MCD0823-CWP-438 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 53 | h | 223 | 1
MEM0823-CWP-439 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 9 | h | 223 | 1
MEM0823-CWP-439 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 9 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 407 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 407 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 2949 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 2949 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 872 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 872 | h | 223 | 1
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 204 | h | 223 | 1
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 204 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 286 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 286 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 976 | h | 223 | 1
JIL0827-CWP-363 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 864 | h | 223 | 1
JIL0827-CWP-363 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 864 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 1512 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 1512 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 24 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 24 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 48 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 48 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 411 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 411 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 170 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 170 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 5850 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 5850 | h | 223 | 1
EEE1062-CWP-386 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 98 | h | 223 | 1
EEE1062-CWP-386 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 98 | h | 223 | 1
EEE1062-CWP-460 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 276 | h | 223 | 1
EEE1062-CWP-460 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 276 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 370 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 370 | h | 223 | 1
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 1856 | h | 223 | 1
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 1856 | h | 223 | 1
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 327 | h | 223 | 1
EBD1214-CWP-401 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 327 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 226 | h | 223 | 1
TTU1340-CWP-507 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 226 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 489 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 489 | h | 223 | 1
RIN1110-CWP-387 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 2790 | h | 223 | 1
RIN1110-CWP-387 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 2790 | h | 223 | 1
ELU0600-CWP-007 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 4992 | h | 223 | 1
ELU0600-CWP-007 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 4992 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 2179 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 2179 | h | 223 | 1
MEM0622-CWP-003 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 6516 | h | 223 | 1
MEM0622-CWP-003 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 6516 | h | 223 | 1
MEM1214-CWP-524 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 138 | h | 223 | 1
MEM1214-CWP-524 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 138 | h | 223 | 1
ECB1214-CWP-534 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 4216 | h | 223 | 1
ECB1214-CWP-534 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 4216 | h | 223 | 1
ECB1214-CWP-535 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 4216 | h | 223 | 1
ECB1214-CWP-535 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 4216 | h | 223 | 1
ECB1214-CWP-536 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 4216 | h | 223 | 1
ECB1214-CWP-536 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 4216 | h | 223 | 1
ECB1214-CWP-537 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 4216 | h | 223 | 1
ECB1214-CWP-537 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 4216 | h | 223 | 1
ECB1048-CWP-567 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 800 | h | 223 | 1
ECB1048-CWP-567 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 800 | h | 223 | 1
ECB1048-CWP-568 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 800 | h | 223 | 1
ECB1048-CWP-568 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 800 | h | 223 | 1
ECB1048-CWP-569 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 800 | h | 223 | 1
ECB1048-CWP-569 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 800 | h | 223 | 1
ECB1062-CWP-573 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 2590 | h | 223 | 1
ECB1062-CWP-573 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 2590 | h | 223 | 1
ECB1062-CWP-574 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 10360 | h | 223 | 1
ECB1062-CWP-574 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 10360 | h | 223 | 1
ECB1062-CWP-575 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 10360 | h | 223 | 1
ECB1062-CWP-575 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 10360 | h | 223 | 1
ECB1214-CWP-576 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 703 | h | 223 | 1
ECB1214-CWP-576 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 703 | h | 223 | 1
ECB1214-CWP-577 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-05-26 | 703 | h | 223 | 1
ECB1214-CWP-577 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-05-26 | 703 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-06-02 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-06-02 | 1 | m | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-02 | 7 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-02 | 7 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-02 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-02 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-02 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-02 | 6 | t | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-02 | 45 | m | 223 | 1
TTU0822-CWP-112 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-02 | 45 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-02 | 404 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-02 | 404 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-02 | 545 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-02 | 545 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-02 | 84 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-02 | 84 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-02 | 488 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-02 | 488 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-02 | 2775 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-02 | 2775 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-02 | 731 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-02 | 731 | m | 223 | 1
ECB1214-CWP-538 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-02 | 527 | m | 223 | 1
ECB1214-CWP-538 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-02 | 527 | m | 223 | 1
ECB1062-CWP-573 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-02 | 971 | m | 223 | 1
ECB1062-CWP-573 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-02 | 971 | m | 223 | 1
ECB1214-CWP-576 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-02 | 439 | m | 223 | 1
ECB1214-CWP-576 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-02 | 439 | m | 223 | 1
ECB1214-CWP-577 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-02 | 439 | m | 223 | 1
ECB1214-CWP-577 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-02 | 439 | m | 223 | 1
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-02 | 0 | un | 223 | 1
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-02 | 0 | un | 223 | 1
JIL0800-CWP-058 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-02 | 27 | un | 223 | 1
JIL0800-CWP-058 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-02 | 27 | un | 223 | 1
JIL0820-CWP-418 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-02 | 3 | un | 223 | 1
JIL0820-CWP-418 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-02 | 3 | un | 223 | 1
EEE0822-CWP-158 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-02 | 1 | un | 223 | 1
EEE0822-CWP-158 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-02 | 1 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-02 | 1 | un | 223 | 1
EEE0822-CWP-161 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-02 | 1 | un | 223 | 1
JIL0822-CWP-166 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-02 | 140 | un | 223 | 1
JIL0822-CWP-166 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-02 | 140 | un | 223 | 1
JIL0827-CWP-363 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-02 | 3 | un | 223 | 1
JIL0827-CWP-363 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-02 | 3 | un | 223 | 1
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-02 | 10 | un | 223 | 1
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-02 | 10 | un | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-06-02 | 2 | m | 223 | 1
EBD0827-CWP-344 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-06-02 | 2 | m | 223 | 1
EBD0600-CWP-589 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-06-02 | 492 | m | 223 | 1
EBD0600-CWP-589 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-06-02 | 492 | m | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-06-02 | 0 | un | 223 | 1
EEE0826-CWP-449 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-06-02 | 0 | un | 223 | 1
ELU0600-CWP-007 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-06-02 | 16 | un | 223 | 1
ELU0600-CWP-007 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-06-02 | 16 | un | 223 | 1
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 40 | un | 223 | 1
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 40 | un | 223 | 1
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 40 | un | 223 | 1
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 40 | un | 223 | 1
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 7 | un | 223 | 1
EEE1042-CWP-138 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 7 | un | 223 | 1
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 7 | un | 223 | 1
EEE1042-CWP-139 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 7 | un | 223 | 1
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 7 | un | 223 | 1
EEE1042-CWP-140 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 7 | un | 223 | 1
EEE0820-CWP-141 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 40 | un | 223 | 1
EEE0820-CWP-141 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 40 | un | 223 | 1
EEE0820-CWP-143 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 25 | un | 223 | 1
EEE0820-CWP-143 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 25 | un | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-06-02 |  |  | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | At Completion Units | 2024-06-02 |  |  | 223 | 1
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 2 | t | 223 | 1
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 2 | t | 223 | 1
MEM0821-CWP-083 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 0 | t | 223 | 1
MEM0821-CWP-083 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 0 | t | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 20 | t | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 20 | t | 223 | 1
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 35 | t | 223 | 1
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 35 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 0 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 0 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 2 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 0 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 0 | t | 223 | 1
MEM0823-CWP-439 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 1 | t | 223 | 1
MEM0823-CWP-439 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 1 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 0 | t | 223 | 1
MEM0823-CWP-255 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 0 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 3 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 3 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 0 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 0 | t | 223 | 1
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 0 | t | 223 | 1
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 0 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 2 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 2 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 0 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 0 | t | 223 | 1
MEM0622-CWP-003 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-02 | 5 | t | 223 | 1
MEM0622-CWP-003 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-02 | 5 | t | 223 | 1
MEM1214-CWP-524 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-02 | 0 | un | 223 | 1
MEM1214-CWP-524 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-02 | 0 | un | 223 | 1
MEM1214-CWP-525 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-02 | 1 | un | 223 | 1
MEM1214-CWP-525 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-02 | 1 | un | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-06-02 | 1 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-06-02 | 1 | t | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-02 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-02 | 65 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-02 | 2 | tons | 223 | 1
MMR0823-CWP-435 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-02 | 2 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-02 | 12 | tons | 223 | 1
MMR0823-CWP-257 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-02 | 12 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-02 | 3 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-02 | 3 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-02 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-02 | 5 | tons | 223 | 1
SES0817-CWP-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 46560 | h | 223 | 1
SES0817-CWP-037 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 46560 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 93051 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 93051 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 5706 | h | 223 | 1
JIL0800-CWP-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 126637 | h | 223 | 1
JIL0800-CWP-058 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 126637 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 94571 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 94571 | h | 223 | 1
JIL0820-CWP-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 16063 | h | 223 | 1
JIL0820-CWP-418 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 16063 | h | 223 | 1
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 39478 | h | 223 | 1
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 39478 | h | 223 | 1
MEM0821-CWP-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 35656 | h | 223 | 1
MEM0821-CWP-083 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 35656 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 27498 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 8586 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 8586 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 13811 | h | 223 | 1
MEM0821-PWPl-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 13811 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 55812 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 55812 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 405587 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 405587 | h | 223 | 1
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 698511 | h | 223 | 1
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 698511 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 13811 | h | 223 | 1
MEM0821-PWPl-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 13811 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 44696 | h | 223 | 1
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 49165 | h | 223 | 1
EEE1042-CWP-138 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 49165 | h | 223 | 1
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 49165 | h | 223 | 1
EEE1042-CWP-139 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 49165 | h | 223 | 1
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 49165 | h | 223 | 1
EEE1042-CWP-140 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 49165 | h | 223 | 1
EEE0820-CWP-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 178781 | h | 223 | 1
EEE0820-CWP-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 178781 | h | 223 | 1
EEE0820-CWP-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 111738 | h | 223 | 1
EEE0820-CWP-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 111738 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 3371 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 3371 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 7915 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 7915 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 7962 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 102697 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 4845 | h | 223 | 1
TTU0822-CWP-112 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 4845 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 43086 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 43086 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 109 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 106363 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 106363 | h | 223 | 1
EEE0822-CWP-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 4540 | h | 223 | 1
EEE0822-CWP-158 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 4540 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 3911 | h | 223 | 1
EEE0822-CWP-161 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 3911 | h | 223 | 1
JIL0822-CWP-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 920915 | h | 223 | 1
JIL0822-CWP-166 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 920915 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 251317 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 27498 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 18604 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 44696 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 11224 | h | 223 | 1
JIL0822-PWPl-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 11224 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 58140 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 58140 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 4770 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 3469 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 3469 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 16870 | h | 223 | 1
JIL0822-PWPp-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 16870 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 45943 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 1649 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 1649 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 808823 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 808823 | h | 223 | 1
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 8243 | h | 223 | 1
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 8243 | h | 223 | 1
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 16490 | h | 223 | 1
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 16490 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 6755 | h | 223 | 1
MMR0823-CWP-435 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 6755 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 330 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 330 | h | 223 | 1
MEM0823-CWP-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 1020 | h | 223 | 1
MEM0823-CWP-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 1020 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 4273 | h | 223 | 1
MEM0823-CWP-255 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 4273 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 44687 | h | 223 | 1
MMR0823-CWP-257 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 44687 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 2557 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 2557 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 223 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 223 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 20905 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 20905 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 22638 | h | 223 | 1
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 114122 | h | 223 | 1
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 114122 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 1189 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 1189 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 27498 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 145910 | h | 223 | 1
MEM0826-EWPc-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 145910 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 5375 | h | 223 | 1
MCD0826-CWP-281 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 5375 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 10912 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 10912 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 400 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 400 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 23279 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 776 | h | 223 | 1
EEE0826-CWP-449 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 776 | h | 223 | 1
JIL0827-CWP-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 2095 | h | 223 | 1
JIL0827-CWP-363 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 2095 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 27498 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 17700 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 581 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 581 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 4817 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 2286 | h | 223 | 1
EEE0827-CWP-457 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 2286 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 1364 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 23698 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 21394 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 21394 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 3720 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 3720 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 21930 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 21930 | h | 223 | 1
SWP-030-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 41336 | h | 223 | 1
SWP-030-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 41336 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 8979 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 8979 | h | 223 | 1
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 45005 | h | 223 | 1
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 45005 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 11224 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 11855 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 11855 | h | 223 | 1
ELU0600-CWP-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 72629 | h | 223 | 1
ELU0600-CWP-007 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 72629 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 20434 | h | 223 | 1
MEM0622-CWP-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 96119 | h | 223 | 1
MEM0622-CWP-003 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 96119 | h | 223 | 1
SWP-041-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 17861 | h | 223 | 1
SWP-041-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 17861 | h | 223 | 1
MEM1214-CWP-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 6719 | h | 223 | 1
MEM1214-CWP-524 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 6719 | h | 223 | 1
MEM1214-CWP-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 16796 | h | 223 | 1
MEM1214-CWP-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 16796 | h | 223 | 1
ECB1214-CWP-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 108538 | h | 223 | 1
ECB1214-CWP-538 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 108538 | h | 223 | 1
ECB1062-CWP-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 188366 | h | 223 | 1
ECB1062-CWP-573 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 188366 | h | 223 | 1
ECB1214-CWP-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 90448 | h | 223 | 1
ECB1214-CWP-576 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 90448 | h | 223 | 1
ECB1214-CWP-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 183730 | h | 223 | 1
ECB1214-CWP-577 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 183730 | h | 223 | 1
EBD0600-CWP-589 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-02 | 2 | h | 223 | 1
EBD0600-CWP-589 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-02 | 2 | h | 223 | 1
SES0817-CWP-037 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 1920 | h | 223 | 1
SES0817-CWP-037 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 1920 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 3837 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 3837 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 600 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 600 | h | 223 | 1
JIL0800-CWP-058 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 5222 | h | 223 | 1
JIL0800-CWP-058 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 5222 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 3900 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 3900 | h | 223 | 1
JIL0820-CWP-418 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 662 | h | 223 | 1
JIL0820-CWP-418 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 662 | h | 223 | 1
MEM0821-CWP-422 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 2171 | h | 223 | 1
MEM0821-CWP-422 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 2171 | h | 223 | 1
MEM0821-CWP-083 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 121 | h | 223 | 1
MEM0821-CWP-083 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 121 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 2 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 16619 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 16619 | h | 223 | 1
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 28806 | h | 223 | 1
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 28806 | h | 223 | 1
EEE0820-CWP-143 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 14400 | h | 223 | 1
EEE0820-CWP-143 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 14400 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 326 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 326 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 4059 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 200 | h | 223 | 1
TTU0822-CWP-112 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 200 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 1777 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 1777 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 4 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 22200 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 22200 | h | 223 | 1
EEE0822-CWP-158 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 187 | h | 223 | 1
EEE0822-CWP-158 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 187 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 161 | h | 223 | 1
EEE0822-CWP-161 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 161 | h | 223 | 1
JIL0822-CWP-166 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 26938 | h | 223 | 1
JIL0822-CWP-166 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 26938 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 10364 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 2398 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 2398 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 714 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 714 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 1697 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 68 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 68 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 44792 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 44792 | h | 223 | 1
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 340 | h | 223 | 1
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 340 | h | 223 | 1
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 680 | h | 223 | 1
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 680 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 279 | h | 223 | 1
MMR0823-CWP-435 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 279 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 14 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 14 | h | 223 | 1
MEM0823-CWP-439 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 42 | h | 223 | 1
MEM0823-CWP-439 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 42 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 176 | h | 223 | 1
MEM0823-CWP-255 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 176 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 1843 | h | 223 | 1
MMR0823-CWP-257 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 1843 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 105 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 105 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 9 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 9 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 872 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 872 | h | 223 | 1
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 204 | h | 223 | 1
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 204 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 222 | h | 223 | 1
MCD0826-CWP-281 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 222 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 450 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 450 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 16 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 16 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 976 | h | 223 | 1
JIL0827-CWP-363 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 497 | h | 223 | 1
JIL0827-CWP-363 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 497 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 1512 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 1512 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 24 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 24 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 48 | h | 223 | 1
EBD0827-CWP-344 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 48 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 411 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 411 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 170 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 170 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 5850 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 5850 | h | 223 | 1
SWP-030-1062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 8185 | h | 223 | 1
SWP-030-1062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 8185 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 370 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 370 | h | 223 | 1
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 1856 | h | 223 | 1
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 1856 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 489 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 489 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 2179 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 2179 | h | 223 | 1
MEM0622-CWP-003 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 3964 | h | 223 | 1
MEM0622-CWP-003 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 3964 | h | 223 | 1
SWP-041-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 3950 | h | 223 | 1
SWP-041-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 3950 | h | 223 | 1
MEM1214-CWP-524 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 54 | h | 223 | 1
MEM1214-CWP-524 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 54 | h | 223 | 1
MEM1214-CWP-525 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 135 | h | 223 | 1
MEM1214-CWP-525 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 135 | h | 223 | 1
ECB1214-CWP-538 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 4216 | h | 223 | 1
ECB1214-CWP-538 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 4216 | h | 223 | 1
ECB1062-CWP-573 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 7770 | h | 223 | 1
ECB1062-CWP-573 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 7770 | h | 223 | 1
ECB1214-CWP-576 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 3513 | h | 223 | 1
ECB1214-CWP-576 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 3513 | h | 223 | 1
ECB1214-CWP-577 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-02 | 3513 | h | 223 | 1
ECB1214-CWP-577 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-02 | 3513 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-06-09 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-06-09 | 1 | m | 223 | 1
CPI0827-CWP-314 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-06-09 | 2 | m | 223 | 1
CPI0827-CWP-314 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-06-09 | 2 | m | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-09 | 7 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-09 | 7 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-09 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-09 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-09 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-09 | 6 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-09 | 5 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-09 | 5 | t | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-09 | 404 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-09 | 404 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-09 | 154 | m | 223 | 1
TTU0822-CWP-156 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-09 | 154 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-09 | 52 | m | 223 | 1
TTU1214-CWP-392 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-09 | 52 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-09 | 488 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-09 | 488 | m | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-09 | 609 | m | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-09 | 609 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-09 | 6529 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-09 | 6529 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-09 | 731 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-09 | 731 | m | 223 | 1
ECB1214-CWP-539 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-09 | 527 | m | 223 | 1
ECB1214-CWP-539 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-09 | 527 | m | 223 | 1
ECB0821-CWP-554 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-09 | 975 | m | 223 | 1
ECB0821-CWP-554 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-09 | 975 | m | 223 | 1
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-09 | 0 | un | 223 | 1
RIN0800-CWP-021 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-09 | 0 | un | 223 | 1
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-09 | 4 | un | 223 | 1
JIL1214-CWP-396 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-09 | 4 | un | 223 | 1
EBD0600-CWP-589 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-06-09 | 738 | m | 223 | 1
EBD0600-CWP-589 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-06-09 | 738 | m | 223 | 1
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 39 | un | 223 | 1
ERE0822-CWP-134 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 39 | un | 223 | 1
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 39 | un | 223 | 1
ERE0822-CWP-137 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 39 | un | 223 | 1
EEE0820-CWP-141 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 23 | un | 223 | 1
EEE0820-CWP-141 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 23 | un | 223 | 1
EEE0820-CWP-142 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 17 | un | 223 | 1
EEE0820-CWP-142 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 17 | un | 223 | 1
EEE0820-CWP-143 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 40 | un | 223 | 1
EEE0820-CWP-143 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 40 | un | 223 | 1
EEE1049-CWP-378 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 0 | un | 223 | 1
EEE1049-CWP-378 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 0 | un | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | Budgeted Units | 2024-06-09 |  |  | 223 | 1
TTU0827-CWP-343 | CALDEIRARIA (t) | Material | At Completion Units | 2024-06-09 |  |  | 223 | 1
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 2 | t | 223 | 1
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 2 | t | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 21 | t | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 21 | t | 223 | 1
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 36 | t | 223 | 1
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 36 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 0 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 0 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 2 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 0 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 0 | t | 223 | 1
MEM0823-CWP-439 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 0 | t | 223 | 1
MEM0823-CWP-439 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 0 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 17 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 17 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 0 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 0 | t | 223 | 1
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 0 | t | 223 | 1
MEM0824-CWP-280 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 0 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 2 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 2 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-09 | 0 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-09 | 0 | t | 223 | 1
MEM1214-CWP-512 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-09 | 1 | un | 223 | 1
MEM1214-CWP-512 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-09 | 1 | un | 223 | 1
MEM1214-CWP-525 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-09 | 0 | un | 223 | 1
MEM1214-CWP-525 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-09 | 0 | un | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | Budgeted Units | 2024-06-09 | 0 | t | 223 | 1
MSD0823-CWP-254 | DESMONTAGEM ELETROMECANICA - ELECTROMECHANICAL DISASSEMBLY | Material | At Completion Units | 2024-06-09 | 0 | t | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-09 | 65 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-09 | 65 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-09 | 5 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-09 | 5 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-09 | 3 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-09 | 3 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-09 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-09 | 5 | tons | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 93051 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 93051 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 5706 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 94571 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 94571 | h | 223 | 1
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 39478 | h | 223 | 1
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 39478 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 27498 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 27498 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 8586 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 8586 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 55812 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 55812 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 408996 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 408996 | h | 223 | 1
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 704381 | h | 223 | 1
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 704381 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 44696 | h | 223 | 1
EEE0820-CWP-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 120677 | h | 223 | 1
EEE0820-CWP-141 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 120677 | h | 223 | 1
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 75982 | h | 223 | 1
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 75982 | h | 223 | 1
EEE0820-CWP-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 178781 | h | 223 | 1
EEE0820-CWP-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 178781 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 421 | h | 223 | 1
KMT0822-PWPl-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 421 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 7915 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 7915 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 7962 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 44308 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 44308 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 102697 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 43086 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 43086 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 109 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 11628 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 11628 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 85961 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 85961 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 250266 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 251317 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 251317 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 18697 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 18697 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 27498 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 18604 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 44696 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 16473 | h | 223 | 1
TTU0822-CWP-156 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 16473 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 4770 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 11428 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 11428 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 45943 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 1649 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 1649 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 808823 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 808823 | h | 223 | 1
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 3091 | h | 223 | 1
MCD0822-CWP-231 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 3091 | h | 223 | 1
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 6184 | h | 223 | 1
MCD0822-CWP-235 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 6184 | h | 223 | 1
JIL0822-CWP-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 3880 | h | 223 | 1
JIL0822-CWP-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 3880 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 1649 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 1649 | h | 223 | 1
MEM0823-CWP-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 119 | h | 223 | 1
MEM0823-CWP-439 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 119 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 12787 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 12787 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 1116 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 1116 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 10453 | h | 223 | 1
MSD0823-CWP-254 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 10453 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 22638 | h | 223 | 1
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 8559 | h | 223 | 1
CDC0824-CWP-275 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 8559 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 47553 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 47553 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 27498 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 48497 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 48497 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 1779 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 1779 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 23279 | h | 223 | 1
CPI0827-CWP-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 10864 | h | 223 | 1
CPI0827-CWP-314 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 10864 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 27498 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 17700 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 165 | h | 223 | 1
TTU0827-CWP-343 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 165 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 4817 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 1364 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 23698 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 21394 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 21394 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 3720 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 3720 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 12140 | h | 223 | 1
EEE1049-PWPl-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 12140 | h | 223 | 1
EEE1049-CWP-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 114047 | h | 223 | 1
EEE1049-CWP-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 114047 | h | 223 | 1
SWP-030-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 55114 | h | 223 | 1
SWP-030-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 55114 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 5537 | h | 223 | 1
TTU1214-CWP-392 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 5537 | h | 223 | 1
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 19877 | h | 223 | 1
JIL1214-CWP-396 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 19877 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 11224 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 11855 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 11855 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 20434 | h | 223 | 1
MEM1214-CWP-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 11946 | h | 223 | 1
MEM1214-CWP-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 11946 | h | 223 | 1
MEM1214-CWP-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 7092 | h | 223 | 1
MEM1214-CWP-525 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 7092 | h | 223 | 1
ECB1214-CWP-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 108538 | h | 223 | 1
ECB1214-CWP-539 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 108538 | h | 223 | 1
EBD0600-CWP-589 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-09 | 3 | h | 223 | 1
EBD0600-CWP-589 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-09 | 3 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 3837 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 3837 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 600 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 600 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 3900 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 3900 | h | 223 | 1
MEM0821-CWP-422 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 2171 | h | 223 | 1
MEM0821-CWP-422 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 2171 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 2 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 16758 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 16758 | h | 223 | 1
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 29048 | h | 223 | 1
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 29048 | h | 223 | 1
EEE0820-CWP-142 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 10805 | h | 223 | 1
EEE0820-CWP-142 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 10805 | h | 223 | 1
EEE0820-CWP-143 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 4032 | h | 223 | 1
EEE0820-CWP-143 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 4032 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 326 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 326 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 4059 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 1777 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 1777 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 4 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 4875 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 4875 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 3427 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 3427 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 52235 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 52235 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 10364 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 10364 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 745 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 745 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 679 | h | 223 | 1
TTU0822-CWP-156 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 679 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 268 | h | 223 | 1
EBD0822-CWP-157 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 268 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 1697 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 68 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 68 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 44792 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 44792 | h | 223 | 1
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 128 | h | 223 | 1
MCD0822-CWP-231 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 128 | h | 223 | 1
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 255 | h | 223 | 1
MCD0822-CWP-235 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 255 | h | 223 | 1
JIL0822-CWP-240 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 160 | h | 223 | 1
JIL0822-CWP-240 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 160 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 68 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 68 | h | 223 | 1
MEM0823-CWP-439 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 5 | h | 223 | 1
MEM0823-CWP-439 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 5 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 527 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 527 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 46 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 46 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 349 | h | 223 | 1
MSD0823-CWP-254 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 349 | h | 223 | 1
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 204 | h | 223 | 1
MEM0824-CWP-280 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 204 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 2000 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 2000 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 73 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 73 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 976 | h | 223 | 1
CPI0827-CWP-314 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 448 | h | 223 | 1
CPI0827-CWP-314 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 448 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 1512 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 1512 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 7 | h | 223 | 1
TTU0827-CWP-343 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 7 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 411 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 411 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 170 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 170 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 5850 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 5850 | h | 223 | 1
EEE1049-CWP-378 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 68 | h | 223 | 1
EEE1049-CWP-378 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 68 | h | 223 | 1
SWP-030-1062 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 5639 | h | 223 | 1
SWP-030-1062 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 5639 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 228 | h | 223 | 1
TTU1214-CWP-392 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 228 | h | 223 | 1
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 820 | h | 223 | 1
JIL1214-CWP-396 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 820 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 489 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 489 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 2179 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 2179 | h | 223 | 1
MEM1214-CWP-512 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 96 | h | 223 | 1
MEM1214-CWP-512 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 96 | h | 223 | 1
MEM1214-CWP-525 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 57 | h | 223 | 1
MEM1214-CWP-525 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 57 | h | 223 | 1
ECB1214-CWP-539 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 4216 | h | 223 | 1
ECB1214-CWP-539 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 4216 | h | 223 | 1
ECB0821-CWP-554 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-09 | 7803 | h | 223 | 1
ECB0821-CWP-554 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-09 | 7803 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-06-16 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-06-16 | 1 | m | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-16 | 7 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-16 | 7 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-16 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-16 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-16 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-16 | 6 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-16 | 10 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-16 | 10 | t | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-16 | 404 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-16 | 404 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-16 | 293 | m | 223 | 1
ECB0800-CWP-059 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-16 | 293 | m | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-16 | 975 | m | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-16 | 975 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-16 | 6529 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-16 | 6529 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-16 | 128 | m | 223 | 1
ECB0827-CWP-369 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-16 | 128 | m | 223 | 1
ECB1214-CWP-526 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-16 | 527 | m | 223 | 1
ECB1214-CWP-526 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-16 | 527 | m | 223 | 1
ECB0821-CWP-553 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-16 | 1463 | m | 223 | 1
ECB0821-CWP-553 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-16 | 1463 | m | 223 | 1
ECB0821-CWP-554 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-16 | 488 | m | 223 | 1
ECB0821-CWP-554 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-16 | 488 | m | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-16 | 0 | un | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-16 | 0 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-16 | 0 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-16 | 0 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-16 | 0 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-16 | 0 | un | 223 | 1
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-16 | 0 | un | 223 | 1
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-16 | 0 | un | 223 | 1
EEE0820-CWP-142 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 40 | un | 223 | 1
EEE0820-CWP-142 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 40 | un | 223 | 1
EEE0820-CWP-143 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 31 | un | 223 | 1
EEE0820-CWP-143 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 31 | un | 223 | 1
EEE1049-CWP-378 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 1 | un | 223 | 1
EEE1049-CWP-378 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 1 | un | 223 | 1
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 2 | t | 223 | 1
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 2 | t | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 21 | t | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 21 | t | 223 | 1
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 36 | t | 223 | 1
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 36 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 0 | t | 223 | 1
MEM0822-CWP-110 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 0 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 2 | t | 223 | 1
TTU0822-CWP-210 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 0 | t | 223 | 1
TTU0822-CWP-210 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 0 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 0 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 0 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 17 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 17 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 0 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 0 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 2 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 2 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-16 | 0 | t | 223 | 1
MEM0827-CWP-308 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-16 | 0 | t | 223 | 1
MEM1214-CWP-512 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-16 | 1 | un | 223 | 1
MEM1214-CWP-512 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-16 | 1 | un | 223 | 1
MEM1214-CWP-513 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-16 | 1 | un | 223 | 1
MEM1214-CWP-513 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-16 | 1 | un | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-06-16 | 1 | t | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-06-16 | 1 | t | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-16 | 63 | tons | 223 | 1
MMR0822-CWP-145 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-16 | 63 | tons | 223 | 1
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-16 | 2 | tons | 223 | 1
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-16 | 2 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-16 | 9 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-16 | 9 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-16 | 3 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-16 | 3 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-16 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-16 | 5 | tons | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 93051 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 93051 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 5706 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 56742 | h | 223 | 1
ECB0800-CWP-059 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 56742 | h | 223 | 1
SWP-005-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 28578 | h | 223 | 1
SWP-005-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 28578 | h | 223 | 1
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 39478 | h | 223 | 1
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 39478 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 1319 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 1319 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 15222 | h | 223 | 1
JPA0821-PWPl-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 15222 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 8586 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 8586 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 1237 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 1237 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 55812 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 55812 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 408996 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 408996 | h | 223 | 1
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 704381 | h | 223 | 1
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 704381 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 5371 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 5371 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 44696 | h | 223 | 1
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 178781 | h | 223 | 1
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 178781 | h | 223 | 1
EEE0820-CWP-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 156433 | h | 223 | 1
EEE0820-CWP-143 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 156433 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 2441 | h | 223 | 1
MEM0822-CWP-110 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 2441 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 7962 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 77539 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 77539 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 102697 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 43086 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 43086 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 109 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 18604 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 158698 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 158698 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 250266 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 245034 | h | 223 | 1
MMR0822-CWP-145 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 245034 | h | 223 | 1
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 8136 | h | 223 | 1
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 8136 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 34517 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 34517 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 27498 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 18604 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 44696 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 4770 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 11428 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 11428 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 45943 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 1649 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 1649 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 808823 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 808823 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 2949 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 2949 | h | 223 | 1
JIL0822-CWP-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 3880 | h | 223 | 1
JIL0822-CWP-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 3880 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 1649 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 1649 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 12787 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 12787 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 1116 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 1116 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 22638 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 22638 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 47553 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 47553 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 22638 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 22638 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 27498 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 48497 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 48497 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 1779 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 1779 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 23279 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 1397 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 1397 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 27498 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 17700 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 4817 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 1364 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 23698 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 3744 | h | 223 | 1
ECB0827-CWP-369 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 3744 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 3720 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 3720 | h | 223 | 1
EEE1049-CWP-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 268347 | h | 223 | 1
EEE1049-CWP-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 268347 | h | 223 | 1
SWP-030-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 13779 | h | 223 | 1
SWP-030-1062 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 13779 | h | 223 | 1
SWP-042-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 41336 | h | 223 | 1
SWP-042-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 41336 | h | 223 | 1
SWP-033-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 41336 | h | 223 | 1
SWP-033-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 41336 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 11224 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 11855 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 11855 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 214 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 214 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 20434 | h | 223 | 1
MEM1214-CWP-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 11946 | h | 223 | 1
MEM1214-CWP-512 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 11946 | h | 223 | 1
MEM1214-CWP-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 16799 | h | 223 | 1
MEM1214-CWP-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 16799 | h | 223 | 1
ECB1214-CWP-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-16 | 36179 | h | 223 | 1
ECB1214-CWP-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-16 | 36179 | h | 223 | 1
MEM0817-CWP-038 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 576 | h | 223 | 1
MEM0817-CWP-038 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 576 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 3837 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 3837 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 600 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 600 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 2340 | h | 223 | 1
ECB0800-CWP-059 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 2340 | h | 223 | 1
SWP-005-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 6144 | h | 223 | 1
SWP-005-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 6144 | h | 223 | 1
MEM0821-CWP-422 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 2171 | h | 223 | 1
MEM0821-CWP-422 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 2171 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 54 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 54 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 2 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 51 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 51 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 16758 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 16758 | h | 223 | 1
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 29048 | h | 223 | 1
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 29048 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 536 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 536 | h | 223 | 1
EEE0820-CWP-142 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 7627 | h | 223 | 1
EEE0820-CWP-142 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 7627 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 101 | h | 223 | 1
MEM0822-CWP-110 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 101 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 4059 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 1777 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 1777 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 4 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 7800 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 7800 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 6326 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 6326 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 52235 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 52235 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 10105 | h | 223 | 1
MMR0822-CWP-145 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 10105 | h | 223 | 1
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 336 | h | 223 | 1
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 336 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 1376 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 1376 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 1697 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 68 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 68 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 44792 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 44792 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 122 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 122 | h | 223 | 1
JIL0822-CWP-240 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 160 | h | 223 | 1
JIL0822-CWP-240 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 160 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 68 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 68 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 527 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 527 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 46 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 46 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 2000 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 2000 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 73 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 73 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 976 | h | 223 | 1
EEE0826-CWP-448 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 192 | h | 223 | 1
EEE0826-CWP-448 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 192 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 1512 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 1512 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 411 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 411 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 98 | h | 223 | 1
MEM0827-CWP-308 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 98 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 1024 | h | 223 | 1
ECB0827-CWP-369 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 1024 | h | 223 | 1
EEE1049-CWP-378 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 160 | h | 223 | 1
EEE1049-CWP-378 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 160 | h | 223 | 1
SWP-042-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 8887 | h | 223 | 1
SWP-042-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 8887 | h | 223 | 1
SWP-033-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 8887 | h | 223 | 1
SWP-033-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 8887 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 489 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 489 | h | 223 | 1
KMT0622-CWP-006 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 122 | h | 223 | 1
KMT0622-CWP-006 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 122 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 2179 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 2179 | h | 223 | 1
MEM1214-CWP-512 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 96 | h | 223 | 1
MEM1214-CWP-512 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 96 | h | 223 | 1
MEM1214-CWP-513 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 135 | h | 223 | 1
MEM1214-CWP-513 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 135 | h | 223 | 1
ECB1214-CWP-526 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 4216 | h | 223 | 1
ECB1214-CWP-526 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 4216 | h | 223 | 1
ECB0821-CWP-553 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 11704 | h | 223 | 1
ECB0821-CWP-553 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 11704 | h | 223 | 1
ECB0821-CWP-554 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-16 | 3901 | h | 223 | 1
ECB0821-CWP-554 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-16 | 3901 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-06-23 | 1 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-06-23 | 1 | m | 223 | 1
MEM0827-CWP-315 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-06-23 | 1 | m | 223 | 1
MEM0827-CWP-315 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-06-23 | 1 | m | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-23 | 7 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-23 | 7 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-23 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-23 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-23 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-23 | 6 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-23 | 10 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-23 | 10 | t | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-23 | 404 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-23 | 404 | m | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-23 | 975 | m | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-23 | 975 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-23 | 6529 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-23 | 6529 | m | 223 | 1
ECB1214-CWP-527 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-23 | 527 | m | 223 | 1
ECB1214-CWP-527 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-23 | 527 | m | 223 | 1
ECB1049-CWP-570 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-23 | 13 | m | 223 | 1
ECB1049-CWP-570 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-23 | 13 | m | 223 | 1
ECB1049-CWP-571 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-23 | 100 | m | 223 | 1
ECB1049-CWP-571 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-23 | 100 | m | 223 | 1
ECB1049-CWP-572 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-23 | 100 | m | 223 | 1
ECB1049-CWP-572 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-23 | 100 | m | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-23 | 1 | un | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-23 | 1 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-23 | 1 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-23 | 1 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-23 | 1 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-23 | 1 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-23 | 18 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-23 | 18 | un | 223 | 1
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-23 | 1 | un | 223 | 1
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-23 | 1 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-23 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-23 | 0 | un | 223 | 1
JIL0622-CWP-004 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-23 | 0 | un | 223 | 1
JIL0622-CWP-004 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-23 | 0 | un | 223 | 1
EEE0820-CWP-142 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 39 | un | 223 | 1
EEE0820-CWP-142 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 39 | un | 223 | 1
EEE1049-CWP-378 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 0 | un | 223 | 1
EEE1049-CWP-378 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 0 | un | 223 | 1
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 2 | t | 223 | 1
MEM0821-CWP-422 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 2 | t | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 21 | t | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 21 | t | 223 | 1
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 0 | t | 223 | 1
MEM0821-CWP-092 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 0 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 2 | t | 223 | 1
TTU0822-CWP-210 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 1 | t | 223 | 1
TTU0822-CWP-210 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 1 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 0 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 0 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 17 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 17 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 0 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 0 | t | 223 | 1
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 2 | t | 223 | 1
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 2 | t | 223 | 1
MEM0824-CWP-273 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 1 | t | 223 | 1
MEM0824-CWP-273 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 1 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-23 | 2 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-23 | 2 | t | 223 | 1
MEM1214-CWP-513 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-23 | 0 | un | 223 | 1
MEM1214-CWP-513 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-23 | 0 | un | 223 | 1
MEM1214-CWP-514 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-23 | 0 | un | 223 | 1
MEM1214-CWP-514 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-23 | 0 | un | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-06-23 | 1 | t | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-06-23 | 1 | t | 223 | 1
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-23 | 84 | tons | 223 | 1
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-23 | 84 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-23 | 9 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-23 | 9 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-23 | 3 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-23 | 3 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-23 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-23 | 5 | tons | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 93051 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 93051 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 5706 | h | 223 | 1
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 39478 | h | 223 | 1
MEM0821-CWP-422 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 39478 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 3104 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 3104 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 8586 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 8586 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 2910 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 2910 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 55812 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 55812 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 408996 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 408996 | h | 223 | 1
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 5870 | h | 223 | 1
MEM0821-CWP-092 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 5870 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 7766 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 7766 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 44696 | h | 223 | 1
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 178781 | h | 223 | 1
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 178781 | h | 223 | 1
SWP-019-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 32150 | h | 223 | 1
SWP-019-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 32150 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 7962 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 77539 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 77539 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 102697 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 43086 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 43086 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 109 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 109 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 18604 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 158698 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 158698 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 250266 | h | 223 | 1
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 325430 | h | 223 | 1
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 325430 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 34517 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 34517 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 27498 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 27498 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 18604 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 44696 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 4770 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 11428 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 11428 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 45943 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 1649 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 1649 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 808823 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 808823 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 7372 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 7372 | h | 223 | 1
JIL0822-CWP-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 1552 | h | 223 | 1
JIL0822-CWP-240 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 1552 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 1649 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 1649 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 12787 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 12787 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 1116 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 1116 | h | 223 | 1
MEM0824-CWP-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 36953 | h | 223 | 1
MEM0824-CWP-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 36953 | h | 223 | 1
MEM0824-CWP-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 14979 | h | 223 | 1
MEM0824-CWP-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 14979 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 18550 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 5862 | h | 223 | 1
MEM0824-PWPl-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 5862 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 47553 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 47553 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 18550 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 5862 | h | 223 | 1
MEM0824-PWPl-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 5862 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 27498 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 27498 | h | 223 | 1
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 23278 | h | 223 | 1
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 23278 | h | 223 | 1
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 23278 | h | 223 | 1
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 23278 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 48497 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 48497 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 1779 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 1779 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 23279 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 23279 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 2328 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 2328 | h | 223 | 1
MEM0827-CWP-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 5432 | h | 223 | 1
MEM0827-CWP-315 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 5432 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 27498 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 27498 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 17700 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 4817 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 83804 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 83804 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 1364 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 23698 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 3720 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 3720 | h | 223 | 1
EEE1049-CWP-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 154299 | h | 223 | 1
EEE1049-CWP-378 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 154299 | h | 223 | 1
SWP-042-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 22964 | h | 223 | 1
SWP-042-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 22964 | h | 223 | 1
SWP-033-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 22964 | h | 223 | 1
SWP-033-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 22964 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 11224 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 9188 | h | 223 | 1
TTU0623-CWP-412 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 9188 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 652 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 652 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 20434 | h | 223 | 1
JIL0622-CWP-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 1630 | h | 223 | 1
JIL0622-CWP-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 1630 | h | 223 | 1
SWP-035-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 31257 | h | 223 | 1
SWP-035-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 31257 | h | 223 | 1
MEM1214-CWP-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 7093 | h | 223 | 1
MEM1214-CWP-513 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 7093 | h | 223 | 1
MEM1214-CWP-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 9333 | h | 223 | 1
MEM1214-CWP-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 9333 | h | 223 | 1
ECB1214-CWP-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 72359 | h | 223 | 1
ECB1214-CWP-526 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 72359 | h | 223 | 1
ECB1214-CWP-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-23 | 108538 | h | 223 | 1
ECB1214-CWP-527 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-23 | 108538 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 3837 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 3837 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 585 | h | 223 | 1
EBD0800-CWP-056 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 585 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 128 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 128 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 2 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 120 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 120 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 16758 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 16758 | h | 223 | 1
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 242 | h | 223 | 1
MEM0821-CWP-092 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 242 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 775 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 775 | h | 223 | 1
SWP-019-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 6912 | h | 223 | 1
SWP-019-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 6912 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 4059 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 1777 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 1777 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 4 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 4 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 7800 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 7800 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 6326 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 6326 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 52235 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 52235 | h | 223 | 1
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 13420 | h | 223 | 1
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 13420 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 1376 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 1376 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 1697 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 68 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 68 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 44792 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 44792 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 304 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 304 | h | 223 | 1
JIL0822-CWP-240 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 64 | h | 223 | 1
JIL0822-CWP-240 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 64 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 68 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 68 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 527 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 527 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 46 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 46 | h | 223 | 1
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 1439 | h | 223 | 1
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 1439 | h | 223 | 1
MEM0824-CWP-273 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 541 | h | 223 | 1
MEM0824-CWP-273 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 541 | h | 223 | 1
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 1011 | h | 223 | 1
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 1011 | h | 223 | 1
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 960 | h | 223 | 1
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 960 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 2000 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 2000 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 73 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 73 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 976 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 976 | h | 223 | 1
EEE0826-CWP-448 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 192 | h | 223 | 1
EEE0826-CWP-448 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 192 | h | 223 | 1
MEM0827-CWP-315 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 224 | h | 223 | 1
MEM0827-CWP-315 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 224 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 1512 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 1512 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 411 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 411 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 3456 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 3456 | h | 223 | 1
EEE1049-CWP-378 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 92 | h | 223 | 1
EEE1049-CWP-378 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 92 | h | 223 | 1
SWP-042-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 4937 | h | 223 | 1
SWP-042-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 4937 | h | 223 | 1
SWP-033-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 4937 | h | 223 | 1
SWP-033-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 4937 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 379 | h | 223 | 1
TTU0623-CWP-412 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 379 | h | 223 | 1
KMT0622-CWP-006 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 175 | h | 223 | 1
KMT0622-CWP-006 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 175 | h | 223 | 1
JIL0622-CWP-409 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 26 | h | 223 | 1
JIL0622-CWP-409 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 26 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 654 | h | 223 | 1
MMR0622-CWP-008 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 654 | h | 223 | 1
JIL0622-CWP-004 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 67 | h | 223 | 1
JIL0622-CWP-004 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 67 | h | 223 | 1
SWP-035-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 6720 | h | 223 | 1
SWP-035-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 6720 | h | 223 | 1
MEM1214-CWP-513 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 57 | h | 223 | 1
MEM1214-CWP-513 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 57 | h | 223 | 1
MEM1214-CWP-514 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 75 | h | 223 | 1
MEM1214-CWP-514 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 75 | h | 223 | 1
ECB1214-CWP-527 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 4216 | h | 223 | 1
ECB1214-CWP-527 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 4216 | h | 223 | 1
ECB1049-CWP-570 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 100 | h | 223 | 1
ECB1049-CWP-570 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 100 | h | 223 | 1
ECB1049-CWP-571 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 800 | h | 223 | 1
ECB1049-CWP-571 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 800 | h | 223 | 1
ECB1049-CWP-572 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-23 | 800 | h | 223 | 1
ECB1049-CWP-572 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-23 | 800 | h | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | Budgeted Units | 2024-06-30 | 0 | m | 223 | 1
CEC0822-CWP-114 | CONCRETO ALL IN - CONCRETE ALL IN | Material | At Completion Units | 2024-06-30 | 0 | m | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-30 | 7 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-30 | 7 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-30 | 6 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-30 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-30 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-30 | 6 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-06-30 | 10 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-06-30 | 10 | t | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | Budgeted Units | 2024-06-30 | 249 | m | 223 | 1
TTU0822-CWP-113 | TUBULACAO EM METROS - PIPING IN METERS | Material | At Completion Units | 2024-06-30 | 249 | m | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-30 | 975 | m | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-30 | 975 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-30 | 6529 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-30 | 6529 | m | 223 | 1
ECB1214-CWP-528 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-30 | 527 | m | 223 | 1
ECB1214-CWP-528 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-30 | 527 | m | 223 | 1
ECB1049-CWP-570 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-06-30 | 88 | m | 223 | 1
ECB1049-CWP-570 | CABLAGEM - WIRING | Material | At Completion Units | 2024-06-30 | 88 | m | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 1 | un | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 1 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 1 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 1 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 1 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 1 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 2 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 2 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 0 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 0 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 0 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 0 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 1 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 1 | un | 223 | 1
JPA0827-CWP-451 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 1 | un | 223 | 1
JPA0827-CWP-451 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 1 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 80 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 80 | un | 223 | 1
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 1 | un | 223 | 1
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 1 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 0 | un | 223 | 1
JIL0622-CWP-004 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-06-30 | 1 | un | 223 | 1
JIL0622-CWP-004 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-06-30 | 1 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-06-30 | 0 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-06-30 | 0 | un | 223 | 1
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 6 | un | 223 | 1
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 6 | un | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 6 | t | 223 | 1
MEM0821-CWP-067 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 6 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 2 | t | 223 | 1
TTU0822-CWP-210 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 0 | t | 223 | 1
TTU0822-CWP-210 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 0 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 0 | t | 223 | 1
MEM0823-CWP-436 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 0 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 17 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 17 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 0 | t | 223 | 1
TTU0823-CWP-440 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 0 | t | 223 | 1
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 2 | t | 223 | 1
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 2 | t | 223 | 1
MEM0824-CWP-273 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 0 | t | 223 | 1
MEM0824-CWP-273 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 0 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-06-30 | 1 | t | 223 | 1
MEM0827-CWP-370 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-06-30 | 1 | t | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-30 | 108 | un | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-30 | 108 | un | 223 | 1
MEM1214-CWP-514 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-30 | 1 | un | 223 | 1
MEM1214-CWP-514 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-30 | 1 | un | 223 | 1
MEM1214-CWP-515 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-06-30 | 1 | un | 223 | 1
MEM1214-CWP-515 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-06-30 | 1 | un | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-06-30 | 1 | t | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-06-30 | 1 | t | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-06-30 | 0 | unid | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-06-30 | 0 | unid | 223 | 1
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-30 | 84 | tons | 223 | 1
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-30 | 84 | tons | 223 | 1
MMR0822-CWP-147 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-30 | 11 | tons | 223 | 1
MMR0822-CWP-147 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-30 | 11 | tons | 223 | 1
MMR0822-CWP-148 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-30 | 11 | tons | 223 | 1
MMR0822-CWP-148 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-30 | 11 | tons | 223 | 1
MMR0822-CWP-149 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-30 | 11 | tons | 223 | 1
MMR0822-CWP-149 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-30 | 11 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-30 | 9 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-30 | 9 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-30 | 2 | tons | 223 | 1
MMR0827-CWP-456 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-30 | 2 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-06-30 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-06-30 | 5 | tons | 223 | 1
SWP-007-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 21910 | h | 223 | 1
SWP-007-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 21910 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 93051 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 93051 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 5706 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 3104 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 3104 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 8586 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 8586 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 2910 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 2910 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 55812 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 55812 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 408996 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 408996 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 5063 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 5063 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 7766 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 7766 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 44696 | h | 223 | 1
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 13409 | h | 223 | 1
EEE0820-CWP-142 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 13409 | h | 223 | 1
SWP-019-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 32150 | h | 223 | 1
SWP-019-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 32150 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 7962 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 77539 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 77539 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 88351 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 88351 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 102697 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 26569 | h | 223 | 1
TTU0822-CWP-113 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 26569 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 11 | h | 223 | 1
CEC0822-CWP-114 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 11 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 18604 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 158698 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 158698 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 250266 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 7915 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 7915 | h | 223 | 1
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 325430 | h | 223 | 1
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 325430 | h | 223 | 1
MMR0822-CWP-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 41815 | h | 223 | 1
MMR0822-CWP-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 41815 | h | 223 | 1
MMR0822-CWP-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 41815 | h | 223 | 1
MMR0822-CWP-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 41815 | h | 223 | 1
MMR0822-CWP-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 41815 | h | 223 | 1
MMR0822-CWP-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 41815 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 34517 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 34517 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 15222 | h | 223 | 1
JPA0822-PWPl-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 15222 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 18604 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 44696 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 4770 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 11224 | h | 223 | 1
JIL0822-PWPl-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 11224 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 45943 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 1649 | h | 223 | 1
TTU0822-CWP-201 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 1649 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 808823 | h | 223 | 1
TTU0822-CWP-202 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 808823 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 7372 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 7372 | h | 223 | 1
TTU0822-CWP-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 7112 | h | 223 | 1
TTU0822-CWP-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 7112 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 1319 | h | 223 | 1
MEM0823-CWP-436 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 1319 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 11566 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 11566 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 12787 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 12787 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 893 | h | 223 | 1
TTU0823-CWP-440 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 893 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 43384 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 43384 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 847 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 847 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 122 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 122 | h | 223 | 1
MEM0824-CWP-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 41833 | h | 223 | 1
MEM0824-CWP-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 41833 | h | 223 | 1
MEM0824-CWP-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 4805 | h | 223 | 1
MEM0824-CWP-273 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 4805 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 18550 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 47553 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 47553 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 18550 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 15222 | h | 223 | 1
JPA0824-PWPl-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 15222 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 660 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 660 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 27498 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 27498 | h | 223 | 1
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 23278 | h | 223 | 1
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 23278 | h | 223 | 1
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 23278 | h | 223 | 1
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 23278 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 48497 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 48497 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 1779 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 1779 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 22697 | h | 223 | 1
EBD0826-CWP-286 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 22697 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 2328 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 2328 | h | 223 | 1
EEL0827-CWP-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 46075 | h | 223 | 1
EEL0827-CWP-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 46075 | h | 223 | 1
JPA0827-CWP-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 2968 | h | 223 | 1
JPA0827-CWP-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 2968 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 15222 | h | 223 | 1
JPA0827-PWPl-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 15222 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 17700 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 4817 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 372462 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 372462 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 1364 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 23698 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 267208 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 267208 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 1063 | h | 223 | 1
EEE1049-PWPl-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 1063 | h | 223 | 1
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 114135 | h | 223 | 1
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 114135 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 931 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 931 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 20434 | h | 223 | 1
JIL0622-CWP-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 2328 | h | 223 | 1
JIL0622-CWP-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 2328 | h | 223 | 1
SWP-035-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 40187 | h | 223 | 1
SWP-035-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 40187 | h | 223 | 1
MEM1214-CWP-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 14559 | h | 223 | 1
MEM1214-CWP-514 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 14559 | h | 223 | 1
MEM1214-CWP-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 23892 | h | 223 | 1
MEM1214-CWP-515 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 23892 | h | 223 | 1
ECB1214-CWP-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-06-30 | 108538 | h | 223 | 1
ECB1214-CWP-528 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-06-30 | 108538 | h | 223 | 1
SWP-007-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 4710 | h | 223 | 1
SWP-007-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 4710 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 3837 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 3837 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 128 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 128 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 2 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 120 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 120 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 4609 | h | 223 | 1
MEM0821-CWP-067 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 4609 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 209 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 209 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 775 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 775 | h | 223 | 1
SWP-019-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 6912 | h | 223 | 1
SWP-019-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 6912 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 3615 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 3615 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 4059 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1096 | h | 223 | 1
TTU0822-CWP-113 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1096 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1 | h | 223 | 1
CEC0822-CWP-114 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 7800 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 7800 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 6326 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 6326 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 52235 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 52235 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 326 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 326 | h | 223 | 1
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 13420 | h | 223 | 1
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 13420 | h | 223 | 1
MMR0822-CWP-147 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1724 | h | 223 | 1
MMR0822-CWP-147 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1724 | h | 223 | 1
MMR0822-CWP-148 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1724 | h | 223 | 1
MMR0822-CWP-148 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1724 | h | 223 | 1
MMR0822-CWP-149 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1724 | h | 223 | 1
MMR0822-CWP-149 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1724 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1376 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1376 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1697 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 68 | h | 223 | 1
TTU0822-CWP-201 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 68 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 44792 | h | 223 | 1
TTU0822-CWP-202 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 44792 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 304 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 304 | h | 223 | 1
TTU0822-CWP-211 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 293 | h | 223 | 1
TTU0822-CWP-211 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 293 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 54 | h | 223 | 1
MEM0823-CWP-436 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 54 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 477 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 477 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 527 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 527 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 37 | h | 223 | 1
TTU0823-CWP-440 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 37 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 26 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 26 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 35 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 35 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 37 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 37 | h | 223 | 1
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1629 | h | 223 | 1
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1629 | h | 223 | 1
MEM0824-CWP-273 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 275 | h | 223 | 1
MEM0824-CWP-273 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 275 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 27 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 27 | h | 223 | 1
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1011 | h | 223 | 1
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1011 | h | 223 | 1
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 960 | h | 223 | 1
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 960 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 2000 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 2000 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 73 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 73 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 757 | h | 223 | 1
EBD0826-CWP-286 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 757 | h | 223 | 1
EEL0827-CWP-338 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1900 | h | 223 | 1
EEL0827-CWP-338 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1900 | h | 223 | 1
JPA0827-CWP-451 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 122 | h | 223 | 1
JPA0827-CWP-451 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 122 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1172 | h | 223 | 1
MEM0827-CWP-370 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1172 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 319 | h | 223 | 1
MMR0827-CWP-456 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 319 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 15360 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 15360 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 3168 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 3168 | h | 223 | 1
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 1075 | h | 223 | 1
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 1075 | h | 223 | 1
KMT0622-CWP-006 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 87 | h | 223 | 1
KMT0622-CWP-006 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 87 | h | 223 | 1
JIL0622-CWP-409 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 38 | h | 223 | 1
JIL0622-CWP-409 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 38 | h | 223 | 1
JIL0622-CWP-004 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 96 | h | 223 | 1
JIL0622-CWP-004 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 96 | h | 223 | 1
SWP-035-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 8640 | h | 223 | 1
SWP-035-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 8640 | h | 223 | 1
MEM1214-CWP-514 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 117 | h | 223 | 1
MEM1214-CWP-514 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 117 | h | 223 | 1
MEM1214-CWP-515 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 192 | h | 223 | 1
MEM1214-CWP-515 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 192 | h | 223 | 1
ECB1214-CWP-528 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 4216 | h | 223 | 1
ECB1214-CWP-528 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 4216 | h | 223 | 1
ECB1049-CWP-570 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-06-30 | 700 | h | 223 | 1
ECB1049-CWP-570 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-06-30 | 700 | h | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-07 | 7 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-07 | 7 | t | 223 | 1
MCD0822-CWP-103 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-07 | 15 | t | 223 | 1
MCD0822-CWP-103 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-07 | 15 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-07 | 1 | t | 223 | 1
SES0822-CWP-104 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-07 | 1 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-07 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-07 | 6 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-07 | 10 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-07 | 10 | t | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-07 | 366 | m | 223 | 1
ECB0822-CWP-249 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-07 | 366 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-07 | 6529 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-07 | 6529 | m | 223 | 1
EEE0826-CWP-300 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-07 | 43 | m | 223 | 1
EEE0826-CWP-300 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-07 | 43 | m | 223 | 1
ECB1214-CWP-529 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-07 | 527 | m | 223 | 1
ECB1214-CWP-529 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-07 | 527 | m | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 1 | un | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 1 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 1 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 1 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 2 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 2 | un | 223 | 1
JIL0822-CWP-165 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 20 | un | 223 | 1
JIL0822-CWP-165 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 20 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 4 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 4 | un | 223 | 1
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 1 | un | 223 | 1
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 1 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 1 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 1 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 0 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 0 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 1 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 1 | un | 223 | 1
JPA0827-CWP-451 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 2 | un | 223 | 1
JPA0827-CWP-451 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 2 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 80 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 80 | un | 223 | 1
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 0 | un | 223 | 1
KMT0622-CWP-006 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 0 | un | 223 | 1
JIL0622-CWP-004 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-07 | 0 | un | 223 | 1
JIL0622-CWP-004 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-07 | 0 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-07-07 | 1 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-07-07 | 1 | un | 223 | 1
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-07-07 | 6 | un | 223 | 1
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-07-07 | 6 | un | 223 | 1
MEM0817-CWP-045 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-07 | 1 | t | 223 | 1
MEM0817-CWP-045 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-07 | 1 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-07 | 2 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-07 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-07 | 2 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-07 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-07 | 2 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-07 | 2 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-07 | 17 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-07 | 17 | t | 223 | 1
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-07 | 2 | t | 223 | 1
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-07 | 2 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-07 | 0 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-07 | 0 | t | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-07 | 289 | un | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-07 | 289 | un | 223 | 1
MEM1214-CWP-516 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-07 | 1 | un | 223 | 1
MEM1214-CWP-516 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-07 | 1 | un | 223 | 1
MEM1214-CWP-517 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-07 | 0 | un | 223 | 1
MEM1214-CWP-517 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-07 | 0 | un | 223 | 1
MEM0817-CWP-498 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-07-07 | 0 | t | 223 | 1
MEM0817-CWP-498 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-07-07 | 0 | t | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-07-07 | 5 | t | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-07-07 | 5 | t | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-07-07 | 1 | t | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-07-07 | 1 | t | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-07-07 | 1 | unid | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-07-07 | 1 | unid | 223 | 1
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-07 | 54 | tons | 223 | 1
MMR0822-CWP-146 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-07 | 54 | tons | 223 | 1
MMR0822-CWP-147 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-07 | 12 | tons | 223 | 1
MMR0822-CWP-147 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-07 | 12 | tons | 223 | 1
MMR0822-CWP-148 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-07 | 12 | tons | 223 | 1
MMR0822-CWP-148 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-07 | 12 | tons | 223 | 1
MMR0822-CWP-149 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-07 | 12 | tons | 223 | 1
MMR0822-CWP-149 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-07 | 12 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-07 | 9 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-07 | 9 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-07 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-07 | 5 | tons | 223 | 1
SSD0817-CWP-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 23280 | h | 223 | 1
SSD0817-CWP-027 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 23280 | h | 223 | 1
SES0817-CWP-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 7760 | h | 223 | 1
SES0817-CWP-029 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 7760 | h | 223 | 1
MEM0817-CWP-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 2328 | h | 223 | 1
MEM0817-CWP-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 2328 | h | 223 | 1
MEM0817-CWP-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 39576 | h | 223 | 1
MEM0817-CWP-039 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 39576 | h | 223 | 1
MCD0817-CWP-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 59360 | h | 223 | 1
MCD0817-CWP-044 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 59360 | h | 223 | 1
SWP-007-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 6668 | h | 223 | 1
SWP-007-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 6668 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 93051 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 93051 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 5706 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 3104 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 3104 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 4365 | h | 223 | 1
EBD0821-CWP-081 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 4365 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 2910 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 2910 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 55812 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 55812 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 71574 | h | 223 | 1
MEM0821-CWP-067 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 71574 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 6984 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 6984 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 42245 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 42245 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 7766 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 7766 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 44696 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 7962 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 55385 | h | 223 | 1
MEM0822-PWPl-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 55385 | h | 223 | 1
MCD0822-CWP-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 248941 | h | 223 | 1
MCD0822-CWP-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 248941 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 6626 | h | 223 | 1
SES0822-CWP-104 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 6626 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 102697 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 102697 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 18604 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 158698 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 158698 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 250266 | h | 223 | 1
JIL0822-CWP-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 93115 | h | 223 | 1
JIL0822-CWP-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 93115 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 18624 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 18624 | h | 223 | 1
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 208818 | h | 223 | 1
MMR0822-CWP-146 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 208818 | h | 223 | 1
MMR0822-CWP-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 47788 | h | 223 | 1
MMR0822-CWP-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 47788 | h | 223 | 1
MMR0822-CWP-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 47788 | h | 223 | 1
MMR0822-CWP-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 47788 | h | 223 | 1
MMR0822-CWP-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 47788 | h | 223 | 1
MMR0822-CWP-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 47788 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 34517 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 34517 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 244 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 244 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 44696 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 4770 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 45265 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 45265 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 41142 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 41142 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 45943 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 45943 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 7372 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 7372 | h | 223 | 1
TTU0822-CWP-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 8890 | h | 223 | 1
TTU0822-CWP-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 8890 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 30844 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 30844 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 12787 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 12787 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 216918 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 216918 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 4233 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 4233 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 611 | h | 223 | 1
MEM0824-CWP-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 39742 | h | 223 | 1
MEM0824-CWP-271 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 39742 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 18550 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 47553 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 47553 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 18550 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 1552 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 1552 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 7365 | h | 223 | 1
JPA0826-PWPl-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 7365 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 621 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 621 | h | 223 | 1
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 23278 | h | 223 | 1
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 23278 | h | 223 | 1
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 23278 | h | 223 | 1
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 23278 | h | 223 | 1
EEE0826-CWP-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 8407 | h | 223 | 1
EEE0826-CWP-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 8407 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 48497 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 48497 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 1779 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 1779 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 2328 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 2328 | h | 223 | 1
EEL0827-CWP-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 12125 | h | 223 | 1
EEL0827-CWP-338 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 12125 | h | 223 | 1
MSD0827-CWP-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 23280 | h | 223 | 1
MSD0827-CWP-317 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 23280 | h | 223 | 1
SES0827-CWP-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 7760 | h | 223 | 1
SES0827-CWP-319 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 7760 | h | 223 | 1
STP0827-CWP-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 11640 | h | 223 | 1
STP0827-CWP-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 11640 | h | 223 | 1
MCD0827-CWP-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 59360 | h | 223 | 1
MCD0827-CWP-334 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 59360 | h | 223 | 1
JPA0827-CWP-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 6984 | h | 223 | 1
JPA0827-CWP-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 6984 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 17700 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 4817 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 372462 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 372462 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 1364 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 23698 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 23698 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 323888 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 323888 | h | 223 | 1
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 130440 | h | 223 | 1
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 130440 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 931 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 931 | h | 223 | 1
SWP-001-0622 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 41336 | h | 223 | 1
SWP-001-0622 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 41336 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 20434 | h | 223 | 1
JIL0622-CWP-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 698 | h | 223 | 1
JIL0622-CWP-004 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 698 | h | 223 | 1
SWP-037-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 28578 | h | 223 | 1
SWP-037-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 28578 | h | 223 | 1
MEM1214-CWP-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 23892 | h | 223 | 1
MEM1214-CWP-516 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 23892 | h | 223 | 1
MEM1214-CWP-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 373 | h | 223 | 1
MEM1214-CWP-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 373 | h | 223 | 1
ECB1214-CWP-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-07 | 108538 | h | 223 | 1
ECB1214-CWP-529 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-07 | 108538 | h | 223 | 1
SSD0817-CWP-027 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 960 | h | 223 | 1
SSD0817-CWP-027 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 960 | h | 223 | 1
SSD0817-CWP-028 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 160 | h | 223 | 1
SSD0817-CWP-028 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 160 | h | 223 | 1
SES0817-CWP-029 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 320 | h | 223 | 1
SES0817-CWP-029 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 320 | h | 223 | 1
MEM0817-CWP-498 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 58 | h | 223 | 1
MEM0817-CWP-498 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 58 | h | 223 | 1
MEM0817-CWP-045 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 102 | h | 223 | 1
MEM0817-CWP-045 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 102 | h | 223 | 1
MEM0817-CWP-039 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1632 | h | 223 | 1
MEM0817-CWP-039 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1632 | h | 223 | 1
MCD0817-CWP-044 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 2448 | h | 223 | 1
MCD0817-CWP-044 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 2448 | h | 223 | 1
SWP-007-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1434 | h | 223 | 1
SWP-007-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1434 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 3837 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 3837 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 128 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 128 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 2 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 120 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 120 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 288 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 288 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 4217 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 4217 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 775 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 775 | h | 223 | 1
MCD0822-CWP-103 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 9777 | h | 223 | 1
MCD0822-CWP-103 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 9777 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 633 | h | 223 | 1
SES0822-CWP-104 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 633 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 4059 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 2925 | h | 223 | 1
ECB0822-CWP-249 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 2925 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 6326 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 6326 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 52235 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 52235 | h | 223 | 1
JIL0822-CWP-165 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 3840 | h | 223 | 1
JIL0822-CWP-165 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 3840 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 768 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 768 | h | 223 | 1
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 8611 | h | 223 | 1
MMR0822-CWP-146 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 8611 | h | 223 | 1
MMR0822-CWP-147 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1971 | h | 223 | 1
MMR0822-CWP-147 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1971 | h | 223 | 1
MMR0822-CWP-148 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1971 | h | 223 | 1
MMR0822-CWP-148 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1971 | h | 223 | 1
MMR0822-CWP-149 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1971 | h | 223 | 1
MMR0822-CWP-149 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1971 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1376 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1376 | h | 223 | 1
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 102 | h | 223 | 1
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 102 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1697 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1697 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1697 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1697 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 304 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 304 | h | 223 | 1
TTU0822-CWP-211 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 367 | h | 223 | 1
TTU0822-CWP-211 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 367 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1272 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1272 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 527 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 527 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 131 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 131 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 175 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 175 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 183 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 183 | h | 223 | 1
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1629 | h | 223 | 1
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1629 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 64 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 64 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 26 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 26 | h | 223 | 1
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1011 | h | 223 | 1
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1011 | h | 223 | 1
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 960 | h | 223 | 1
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 960 | h | 223 | 1
EEE0826-CWP-300 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 347 | h | 223 | 1
EEE0826-CWP-300 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 347 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 2000 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 2000 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 73 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 73 | h | 223 | 1
EEL0827-CWP-338 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 500 | h | 223 | 1
EEL0827-CWP-338 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 500 | h | 223 | 1
MSD0827-CWP-317 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 960 | h | 223 | 1
MSD0827-CWP-317 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 960 | h | 223 | 1
SES0827-CWP-318 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 160 | h | 223 | 1
SES0827-CWP-318 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 160 | h | 223 | 1
SES0827-CWP-319 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 320 | h | 223 | 1
SES0827-CWP-319 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 320 | h | 223 | 1
STP0827-CWP-327 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 960 | h | 223 | 1
STP0827-CWP-327 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 960 | h | 223 | 1
MCD0827-CWP-334 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 2448 | h | 223 | 1
MCD0827-CWP-334 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 2448 | h | 223 | 1
JPA0827-CWP-451 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 288 | h | 223 | 1
JPA0827-CWP-451 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 288 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 15360 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 15360 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 3840 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 3840 | h | 223 | 1
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 1229 | h | 223 | 1
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 1229 | h | 223 | 1
JIL0622-CWP-409 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 11 | h | 223 | 1
JIL0622-CWP-409 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 11 | h | 223 | 1
SWP-001-0622 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 8887 | h | 223 | 1
SWP-001-0622 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 8887 | h | 223 | 1
JIL0622-CWP-004 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 29 | h | 223 | 1
JIL0622-CWP-004 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 29 | h | 223 | 1
SWP-037-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 6144 | h | 223 | 1
SWP-037-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 6144 | h | 223 | 1
MEM1214-CWP-516 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 192 | h | 223 | 1
MEM1214-CWP-516 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 192 | h | 223 | 1
MEM1214-CWP-517 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 3 | h | 223 | 1
MEM1214-CWP-517 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 3 | h | 223 | 1
ECB1214-CWP-529 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-07 | 4216 | h | 223 | 1
ECB1214-CWP-529 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-07 | 4216 | h | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-14 | 4 | t | 223 | 1
SES0820-CWP-063 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-14 | 4 | t | 223 | 1
MCD0822-CWP-103 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-14 | 17 | t | 223 | 1
MCD0822-CWP-103 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-14 | 17 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-14 | 6 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-14 | 6 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-14 | 5 | t | 223 | 1
SES0822-CWP-115 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-14 | 5 | t | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-14 | 6529 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-14 | 6529 | m | 223 | 1
EEE0826-CWP-300 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-14 | 50 | m | 223 | 1
EEE0826-CWP-300 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-14 | 50 | m | 223 | 1
ECB1214-CWP-530 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-14 | 527 | m | 223 | 1
ECB1214-CWP-530 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-14 | 527 | m | 223 | 1
ECB1214-CWP-531 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-14 | 527 | m | 223 | 1
ECB1214-CWP-531 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-14 | 527 | m | 223 | 1
ECB0826-CWP-563 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-14 | 274 | m | 223 | 1
ECB0826-CWP-563 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-14 | 274 | m | 223 | 1
ECB0827-CWP-564 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-14 | 488 | m | 223 | 1
ECB0827-CWP-564 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-14 | 488 | m | 223 | 1
ECB0827-CWP-565 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-14 | 975 | m | 223 | 1
ECB0827-CWP-565 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-14 | 975 | m | 223 | 1
ECB0827-CWP-566 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-14 | 975 | m | 223 | 1
ECB0827-CWP-566 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-14 | 975 | m | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 1 | un | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 1 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 0 | un | 223 | 1
JPA0821-CWP-424 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 0 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 2 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 2 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 59 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 59 | un | 223 | 1
JIL0822-CWP-165 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 20 | un | 223 | 1
JIL0822-CWP-165 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 20 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 4 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 4 | un | 223 | 1
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 3 | un | 223 | 1
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 3 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 1 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 1 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 0 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 0 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 0 | un | 223 | 1
EEE0826-CWP-448 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 0 | un | 223 | 1
JPA0827-CWP-451 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 1 | un | 223 | 1
JPA0827-CWP-451 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 1 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 80 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 80 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-14 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-14 | 0 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-07-14 | 1 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-07-14 | 1 | un | 223 | 1
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-07-14 | 6 | un | 223 | 1
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-07-14 | 6 | un | 223 | 1
MEM0817-CWP-045 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-14 | 0 | t | 223 | 1
MEM0817-CWP-045 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-14 | 0 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-14 | 1 | t | 223 | 1
MEM0822-CWP-185 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-14 | 1 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-14 | 1 | t | 223 | 1
MEM0822-CWP-187 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-14 | 1 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-14 | 1 | t | 223 | 1
MEM0822-CWP-189 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-14 | 1 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-14 | 17 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-14 | 17 | t | 223 | 1
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-14 | 0 | t | 223 | 1
MEM0824-CWP-271 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-14 | 0 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-14 | 0 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-14 | 0 | t | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-14 | 289 | un | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-14 | 289 | un | 223 | 1
MEM0827-CWP-335 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-14 | 1 | un | 223 | 1
MEM0827-CWP-335 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-14 | 1 | un | 223 | 1
MEM1214-CWP-517 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-14 | 1 | un | 223 | 1
MEM1214-CWP-517 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-14 | 1 | un | 223 | 1
MEM1214-CWP-518 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-14 | 1 | un | 223 | 1
MEM1214-CWP-518 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-14 | 1 | un | 223 | 1
MEM0817-CWP-498 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-07-14 | 2 | t | 223 | 1
MEM0817-CWP-498 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-07-14 | 2 | t | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-07-14 | 14 | t | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-07-14 | 14 | t | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-07-14 | 0 | t | 223 | 1
MEM0822-CWP-499 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-07-14 | 0 | t | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-07-14 | 1 | unid | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-07-14 | 1 | unid | 223 | 1
MMR0817-CWP-046 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-14 | 6 | tons | 223 | 1
MMR0817-CWP-046 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-14 | 6 | tons | 223 | 1
MMR0822-CWP-147 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-14 | 10 | tons | 223 | 1
MMR0822-CWP-147 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-14 | 10 | tons | 223 | 1
MMR0822-CWP-148 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-14 | 10 | tons | 223 | 1
MMR0822-CWP-148 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-14 | 10 | tons | 223 | 1
MMR0822-CWP-149 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-14 | 10 | tons | 223 | 1
MMR0822-CWP-149 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-14 | 10 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-14 | 4 | tons | 223 | 1
MMR0822-CWP-427 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-14 | 4 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-14 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-14 | 5 | tons | 223 | 1
MEM0817-CWP-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 2328 | h | 223 | 1
MEM0817-CWP-045 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 2328 | h | 223 | 1
MMR0817-CWP-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 23280 | h | 223 | 1
MMR0817-CWP-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 23280 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 55831 | h | 223 | 1
SES0820-CWP-063 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 55831 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 5706 | h | 223 | 1
SWP-003-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 20540 | h | 223 | 1
SWP-003-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 20540 | h | 223 | 1
SWP-006-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 21910 | h | 223 | 1
SWP-006-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 21910 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 3104 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 3104 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 1673 | h | 223 | 1
JPA0821-CWP-424 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 1673 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 55812 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 55812 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 6984 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 6984 | h | 223 | 1
SWP-008-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 29471 | h | 223 | 1
SWP-008-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 29471 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 112654 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 112654 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 7766 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 7766 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 44696 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 7962 | h | 223 | 1
MCD0822-CWP-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 281820 | h | 223 | 1
MCD0822-CWP-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 281820 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 69321 | h | 223 | 1
SES0822-CWP-106 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 69321 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 274982 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 274982 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 18604 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 46287 | h | 223 | 1
SES0822-CWP-115 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 46287 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 250266 | h | 223 | 1
JIL0822-CWP-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 93115 | h | 223 | 1
JIL0822-CWP-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 93115 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 18624 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 18624 | h | 223 | 1
MMR0822-CWP-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 37832 | h | 223 | 1
MMR0822-CWP-147 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 37832 | h | 223 | 1
MMR0822-CWP-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 37832 | h | 223 | 1
MMR0822-CWP-148 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 37832 | h | 223 | 1
MMR0822-CWP-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 37832 | h | 223 | 1
MMR0822-CWP-149 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 37832 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 10067 | h | 223 | 1
MMR0822-CWP-427 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 10067 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 1221 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 44696 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 4770 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 27159 | h | 223 | 1
MEM0822-CWP-185 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 27159 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 24685 | h | 223 | 1
MEM0822-CWP-187 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 24685 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 27566 | h | 223 | 1
MEM0822-CWP-189 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 27566 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 4423 | h | 223 | 1
TTU0822-CWP-210 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 4423 | h | 223 | 1
TTU0822-CWP-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 5334 | h | 223 | 1
TTU0822-CWP-211 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 5334 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 30844 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 30844 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 12787 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 12787 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 216918 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 216918 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 4233 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 4233 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 611 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 18550 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 18550 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 16224 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 16224 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 18550 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 46365 | h | 223 | 1
CFU0824-CWP-276 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 46365 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 18550 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 1552 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 1552 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 776 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 776 | h | 223 | 1
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 23278 | h | 223 | 1
JIL0826-CWP-297 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 23278 | h | 223 | 1
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 23278 | h | 223 | 1
JIL0826-CWP-298 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 23278 | h | 223 | 1
EEE0826-CWP-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 9700 | h | 223 | 1
EEE0826-CWP-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 9700 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 37585 | h | 223 | 1
EBD0826-CWP-282 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 37585 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 1378 | h | 223 | 1
TTU0826-CWP-283 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 1378 | h | 223 | 1
JPA0826-CWP-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 1995 | h | 223 | 1
JPA0826-CWP-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 1995 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 931 | h | 223 | 1
EEE0826-CWP-448 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 931 | h | 223 | 1
STP0827-CWP-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 13968 | h | 223 | 1
STP0827-CWP-322 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 13968 | h | 223 | 1
STP0827-CWP-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 34920 | h | 223 | 1
STP0827-CWP-327 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 34920 | h | 223 | 1
SES0827-CWP-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 7760 | h | 223 | 1
SES0827-CWP-331 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 7760 | h | 223 | 1
SES0827-CWP-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 37248 | h | 223 | 1
SES0827-CWP-332 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 37248 | h | 223 | 1
MEM0827-CWP-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 19400 | h | 223 | 1
MEM0827-CWP-335 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 19400 | h | 223 | 1
JPA0827-CWP-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 4016 | h | 223 | 1
JPA0827-CWP-451 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 4016 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 17700 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 4817 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 372462 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 372462 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 1364 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 6813 | h | 223 | 1
MEM0827-CWP-310 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 6813 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 323888 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 323888 | h | 223 | 1
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 130440 | h | 223 | 1
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 130440 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 931 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 931 | h | 223 | 1
SWP-001-0622 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 22964 | h | 223 | 1
SWP-001-0622 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 22964 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 20434 | h | 223 | 1
MEM1214-CWP-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 23519 | h | 223 | 1
MEM1214-CWP-517 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 23519 | h | 223 | 1
MEM1214-CWP-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 21279 | h | 223 | 1
MEM1214-CWP-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 21279 | h | 223 | 1
ECB1214-CWP-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 108538 | h | 223 | 1
ECB1214-CWP-530 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 108538 | h | 223 | 1
ECB1214-CWP-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 72359 | h | 223 | 1
ECB1214-CWP-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 72359 | h | 223 | 1
ECB0826-CWP-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 115121 | h | 223 | 1
ECB0826-CWP-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 115121 | h | 223 | 1
ECB0827-CWP-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 970504 | h | 223 | 1
ECB0827-CWP-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 970504 | h | 223 | 1
ECB0827-CWP-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 1941008 | h | 223 | 1
ECB0827-CWP-565 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 1941008 | h | 223 | 1
ECB0827-CWP-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-14 | 2138495 | h | 223 | 1
ECB0827-CWP-566 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-14 | 2138495 | h | 223 | 1
MEM0817-CWP-498 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1574 | h | 223 | 1
MEM0817-CWP-498 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1574 | h | 223 | 1
MEM0817-CWP-045 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 90 | h | 223 | 1
MEM0817-CWP-045 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 90 | h | 223 | 1
MMR0817-CWP-046 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1002 | h | 223 | 1
MMR0817-CWP-046 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1002 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 2302 | h | 223 | 1
SES0820-CWP-063 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 2302 | h | 223 | 1
SWP-003-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 4416 | h | 223 | 1
SWP-003-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 4416 | h | 223 | 1
SWP-006-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 4710 | h | 223 | 1
SWP-006-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 4710 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 128 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 128 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 2 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 69 | h | 223 | 1
JPA0821-CWP-424 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 69 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 288 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 288 | h | 223 | 1
SWP-008-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 6336 | h | 223 | 1
SWP-008-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 6336 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 11246 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 11246 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 394 | h | 223 | 1
MEM0822-CWP-499 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 394 | h | 223 | 1
MCD0822-CWP-103 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 11069 | h | 223 | 1
MCD0822-CWP-103 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 11069 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 4059 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 4059 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 11340 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 11340 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 2900 | h | 223 | 1
SES0822-CWP-115 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 2900 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 52235 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 52235 | h | 223 | 1
JIL0822-CWP-165 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 3840 | h | 223 | 1
JIL0822-CWP-165 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 3840 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 768 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 768 | h | 223 | 1
MMR0822-CWP-147 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1560 | h | 223 | 1
MMR0822-CWP-147 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1560 | h | 223 | 1
MMR0822-CWP-148 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1560 | h | 223 | 1
MMR0822-CWP-148 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1560 | h | 223 | 1
MMR0822-CWP-149 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1560 | h | 223 | 1
MMR0822-CWP-149 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1560 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 631 | h | 223 | 1
MMR0822-CWP-427 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 631 | h | 223 | 1
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 512 | h | 223 | 1
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 512 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1018 | h | 223 | 1
MEM0822-CWP-185 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1018 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1018 | h | 223 | 1
MEM0822-CWP-187 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1018 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1018 | h | 223 | 1
MEM0822-CWP-189 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1018 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 182 | h | 223 | 1
TTU0822-CWP-210 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 182 | h | 223 | 1
TTU0822-CWP-211 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 220 | h | 223 | 1
TTU0822-CWP-211 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 220 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1272 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1272 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 527 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 527 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 131 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 131 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 175 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 175 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 183 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 183 | h | 223 | 1
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 190 | h | 223 | 1
MEM0824-CWP-271 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 190 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 64 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 64 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 32 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 32 | h | 223 | 1
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 808 | h | 223 | 1
JIL0826-CWP-297 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 808 | h | 223 | 1
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 960 | h | 223 | 1
JIL0826-CWP-298 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 960 | h | 223 | 1
EEE0826-CWP-300 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 400 | h | 223 | 1
EEE0826-CWP-300 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 400 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1550 | h | 223 | 1
EBD0826-CWP-282 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1550 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 57 | h | 223 | 1
TTU0826-CWP-283 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 57 | h | 223 | 1
JPA0826-CWP-450 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 82 | h | 223 | 1
JPA0826-CWP-450 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 82 | h | 223 | 1
STP0827-CWP-322 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 576 | h | 223 | 1
STP0827-CWP-322 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 576 | h | 223 | 1
STP0827-CWP-327 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 960 | h | 223 | 1
STP0827-CWP-327 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 960 | h | 223 | 1
SES0827-CWP-330 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 320 | h | 223 | 1
SES0827-CWP-330 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 320 | h | 223 | 1
SES0827-CWP-331 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 320 | h | 223 | 1
SES0827-CWP-331 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 320 | h | 223 | 1
SES0827-CWP-332 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1536 | h | 223 | 1
SES0827-CWP-332 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1536 | h | 223 | 1
MEM0827-CWP-335 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 800 | h | 223 | 1
MEM0827-CWP-335 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 800 | h | 223 | 1
JPA0827-CWP-451 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 166 | h | 223 | 1
JPA0827-CWP-451 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 166 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 15360 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 15360 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 3840 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 3840 | h | 223 | 1
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 1229 | h | 223 | 1
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 1229 | h | 223 | 1
SWP-001-0622 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 4937 | h | 223 | 1
SWP-001-0622 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 4937 | h | 223 | 1
MEM1214-CWP-517 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 189 | h | 223 | 1
MEM1214-CWP-517 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 189 | h | 223 | 1
MEM1214-CWP-518 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 171 | h | 223 | 1
MEM1214-CWP-518 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 171 | h | 223 | 1
ECB1214-CWP-530 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 4216 | h | 223 | 1
ECB1214-CWP-530 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 4216 | h | 223 | 1
ECB1214-CWP-531 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 4216 | h | 223 | 1
ECB1214-CWP-531 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 4216 | h | 223 | 1
ECB0826-CWP-563 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 2194 | h | 223 | 1
ECB0826-CWP-563 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 2194 | h | 223 | 1
ECB0827-CWP-564 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 3900 | h | 223 | 1
ECB0827-CWP-564 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 3900 | h | 223 | 1
ECB0827-CWP-565 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 7800 | h | 223 | 1
ECB0827-CWP-565 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 7800 | h | 223 | 1
ECB0827-CWP-566 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-14 | 7800 | h | 223 | 1
ECB0827-CWP-566 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-14 | 7800 | h | 223 | 1
MCD0822-CWP-103 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-21 | 16 | t | 223 | 1
MCD0822-CWP-103 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-21 | 16 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-21 | 1 | t | 223 | 1
SES0822-CWP-106 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-21 | 1 | t | 223 | 1
MCD0824-CWP-279 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-21 | 1 | t | 223 | 1
MCD0824-CWP-279 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-21 | 1 | t | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-21 | 6529 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-21 | 6529 | m | 223 | 1
EEE0826-CWP-300 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-21 | 7 | m | 223 | 1
EEE0826-CWP-300 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-21 | 7 | m | 223 | 1
ECB1214-CWP-532 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-21 | 527 | m | 223 | 1
ECB1214-CWP-532 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-21 | 527 | m | 223 | 1
ECB1214-CWP-533 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-21 | 527 | m | 223 | 1
ECB1214-CWP-533 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-21 | 527 | m | 223 | 1
ECB0826-CWP-562 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-21 | 518 | m | 223 | 1
ECB0826-CWP-562 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-21 | 518 | m | 223 | 1
ECB0826-CWP-563 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-21 | 701 | m | 223 | 1
ECB0826-CWP-563 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-21 | 701 | m | 223 | 1
ECB0827-CWP-564 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-21 | 488 | m | 223 | 1
ECB0827-CWP-564 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-21 | 488 | m | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 1 | un | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 1 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 2 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 2 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 68 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 68 | un | 223 | 1
JIL0822-CWP-165 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 20 | un | 223 | 1
JIL0822-CWP-165 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 20 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 4 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 4 | un | 223 | 1
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 3 | un | 223 | 1
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 3 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 1 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 1 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 0 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 0 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 62 | un | 223 | 1
JIL0827-CWP-306 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 62 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-21 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-21 | 0 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-07-21 | 1 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-07-21 | 1 | un | 223 | 1
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | Budgeted Units | 2024-07-21 | 3 | un | 223 | 1
EEE1049-CWP-373 | EQUIPAMENTO ELETRICO - ELECTRICAL EQUIPMENT | Material | At Completion Units | 2024-07-21 | 3 | un | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-21 | 17 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-21 | 17 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-21 | 2 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-21 | 2 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-21 | 0 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-21 | 0 | t | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-21 | 289 | un | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-21 | 289 | un | 223 | 1
MEM1214-CWP-518 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-21 | 0 | un | 223 | 1
MEM1214-CWP-518 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-21 | 0 | un | 223 | 1
MEM1214-CWP-519 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-21 | 1 | un | 223 | 1
MEM1214-CWP-519 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-21 | 1 | un | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-07-21 | 14 | t | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-07-21 | 14 | t | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-07-21 | 1 | unid | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-07-21 | 1 | unid | 223 | 1
MMR0817-CWP-046 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-21 | 3 | tons | 223 | 1
MMR0817-CWP-046 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-21 | 3 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-21 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-21 | 5 | tons | 223 | 1
MMR0817-CWP-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 11640 | h | 223 | 1
MMR0817-CWP-046 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 11640 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 5706 | h | 223 | 1
SWP-003-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 50904 | h | 223 | 1
SWP-003-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 50904 | h | 223 | 1
SWP-006-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 6668 | h | 223 | 1
SWP-006-0820 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 6668 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 3104 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 3104 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 9767 | h | 223 | 1
ECB0821-CWP-082 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 9767 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 6984 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 6984 | h | 223 | 1
SWP-008-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 53583 | h | 223 | 1
SWP-008-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 53583 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 112654 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 112654 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 7766 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 7766 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 44696 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 21230 | h | 223 | 1
ERE0822-CWP-135 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 21230 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 44696 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 7962 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 7962 | h | 223 | 1
MCD0822-CWP-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 220759 | h | 223 | 1
MCD0822-CWP-103 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 220759 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 314265 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 314265 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 250266 | h | 223 | 1
JIL0822-CWP-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 93115 | h | 223 | 1
JIL0822-CWP-165 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 93115 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 18624 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 18624 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 1221 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 21230 | h | 223 | 1
ERE0822-CWP-132 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 21230 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 44696 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 4770 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 30844 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 30844 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 12787 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 12787 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 216918 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 216918 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 4233 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 4233 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 611 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 7619 | h | 223 | 1
MEM0824-PWPl-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 7619 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 6518 | h | 223 | 1
MEM0824-PWPl-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 6518 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 18550 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 1552 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 1552 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 8596 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 8596 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 30655 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 30655 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 776 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 776 | h | 223 | 1
EEE0826-CWP-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 1293 | h | 223 | 1
EEE0826-CWP-300 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 1293 | h | 223 | 1
JPA0826-CWP-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 2661 | h | 223 | 1
JPA0826-CWP-450 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 2661 | h | 223 | 1
SES0827-CWP-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 12224 | h | 223 | 1
SES0827-CWP-339 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 12224 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 17700 | h | 223 | 1
SWP-025-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 21910 | h | 223 | 1
SWP-025-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 21910 | h | 223 | 1
SWP-026-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 21127 | h | 223 | 1
SWP-026-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 21127 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 4817 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 288658 | h | 223 | 1
JIL0827-CWP-306 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 288658 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 1364 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 323888 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 323888 | h | 223 | 1
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 59785 | h | 223 | 1
EEE1049-CWP-373 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 59785 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 931 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 931 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 20434 | h | 223 | 1
MEM1214-CWP-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 2613 | h | 223 | 1
MEM1214-CWP-518 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 2613 | h | 223 | 1
MEM1214-CWP-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 23892 | h | 223 | 1
MEM1214-CWP-519 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 23892 | h | 223 | 1
ECB1214-CWP-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 36179 | h | 223 | 1
ECB1214-CWP-531 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 36179 | h | 223 | 1
ECB1214-CWP-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 108538 | h | 223 | 1
ECB1214-CWP-532 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 108538 | h | 223 | 1
ECB1214-CWP-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 36179 | h | 223 | 1
ECB1214-CWP-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 36179 | h | 223 | 1
ECB0826-CWP-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 217450 | h | 223 | 1
ECB0826-CWP-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 217450 | h | 223 | 1
ECB0826-CWP-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 294197 | h | 223 | 1
ECB0826-CWP-563 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 294197 | h | 223 | 1
ECB0827-CWP-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-21 | 970504 | h | 223 | 1
ECB0827-CWP-564 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-21 | 970504 | h | 223 | 1
MMR0817-CWP-046 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 438 | h | 223 | 1
MMR0817-CWP-046 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 438 | h | 223 | 1
SWP-003-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 10944 | h | 223 | 1
SWP-003-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 10944 | h | 223 | 1
SWP-006-0820 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 1434 | h | 223 | 1
SWP-006-0820 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 1434 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 128 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 128 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 2 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 288 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 288 | h | 223 | 1
SWP-008-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 11520 | h | 223 | 1
SWP-008-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 11520 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 11246 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 11246 | h | 223 | 1
MCD0822-CWP-103 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 10146 | h | 223 | 1
MCD0822-CWP-103 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 10146 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 710 | h | 223 | 1
SES0822-CWP-106 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 710 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 12960 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 12960 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 52235 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 52235 | h | 223 | 1
JIL0822-CWP-165 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 3840 | h | 223 | 1
JIL0822-CWP-165 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 3840 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 768 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 768 | h | 223 | 1
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 512 | h | 223 | 1
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 512 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 1272 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 1272 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 527 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 527 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 131 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 131 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 175 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 175 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 183 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 183 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 64 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 64 | h | 223 | 1
MCD0824-CWP-279 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 679 | h | 223 | 1
MCD0824-CWP-279 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 679 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 1264 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 1264 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 32 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 32 | h | 223 | 1
EEE0826-CWP-300 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 53 | h | 223 | 1
EEE0826-CWP-300 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 53 | h | 223 | 1
JPA0826-CWP-450 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 110 | h | 223 | 1
JPA0826-CWP-450 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 110 | h | 223 | 1
MEM0827-CWP-328 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 576 | h | 223 | 1
MEM0827-CWP-328 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 576 | h | 223 | 1
SES0827-CWP-339 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 504 | h | 223 | 1
SES0827-CWP-339 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 504 | h | 223 | 1
SWP-025-0827 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 4710 | h | 223 | 1
SWP-025-0827 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 4710 | h | 223 | 1
SWP-026-0827 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 4542 | h | 223 | 1
SWP-026-0827 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 4542 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 11904 | h | 223 | 1
JIL0827-CWP-306 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 11904 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 3840 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 3840 | h | 223 | 1
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 563 | h | 223 | 1
EEE1049-CWP-373 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 563 | h | 223 | 1
MEM1214-CWP-518 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 21 | h | 223 | 1
MEM1214-CWP-518 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 21 | h | 223 | 1
MEM1214-CWP-519 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 192 | h | 223 | 1
MEM1214-CWP-519 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 192 | h | 223 | 1
ECB1214-CWP-532 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 4216 | h | 223 | 1
ECB1214-CWP-532 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 4216 | h | 223 | 1
ECB1214-CWP-533 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 4216 | h | 223 | 1
ECB1214-CWP-533 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 4216 | h | 223 | 1
ECB0826-CWP-562 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 4144 | h | 223 | 1
ECB0826-CWP-562 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 4144 | h | 223 | 1
ECB0826-CWP-563 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 5606 | h | 223 | 1
ECB0826-CWP-563 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 5606 | h | 223 | 1
ECB0827-CWP-564 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-21 | 3900 | h | 223 | 1
ECB0827-CWP-564 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-21 | 3900 | h | 223 | 1
MCD0824-CWP-279 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-07-28 | 2 | t | 223 | 1
MCD0824-CWP-279 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-07-28 | 2 | t | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-28 | 3754 | m | 223 | 1
JCI0822-CWP-433 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-28 | 3754 | m | 223 | 1
ECB0817-CWP-552 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-28 | 65 | m | 223 | 1
ECB0817-CWP-552 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-28 | 65 | m | 223 | 1
ECB0826-CWP-561 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-28 | 762 | m | 223 | 1
ECB0826-CWP-561 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-28 | 762 | m | 223 | 1
ECB0826-CWP-562 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-07-28 | 457 | m | 223 | 1
ECB0826-CWP-562 | CABLAGEM - WIRING | Material | At Completion Units | 2024-07-28 | 457 | m | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-28 | 0 | un | 223 | 1
EEE0821-CWP-425 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-28 | 0 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-28 | 0 | un | 223 | 1
KMT0821-CWP-072 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-28 | 0 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-28 | 68 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-28 | 68 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-28 | 2 | un | 223 | 1
JPA0822-CWP-434 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-28 | 2 | un | 223 | 1
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-28 | 2 | un | 223 | 1
KMT0822-CWP-131 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-28 | 2 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-28 | 1 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-28 | 1 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-28 | 0 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-28 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-28 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-28 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-07-28 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-07-28 | 0 | un | 223 | 1
EEE0822-CWP-162 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-07-28 | 9 | un | 223 | 1
EEE0822-CWP-162 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-07-28 | 9 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-07-28 | 1 | un | 223 | 1
EEE0823-CWP-443 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-07-28 | 1 | un | 223 | 1
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-28 | 2 | t | 223 | 1
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-28 | 2 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-28 | 17 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-28 | 17 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-28 | 2 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-28 | 2 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-07-28 | 0 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-07-28 | 0 | t | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-07-28 | 289 | un | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-07-28 | 289 | un | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-07-28 | 14 | t | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-07-28 | 14 | t | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-07-28 | 1 | unid | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-07-28 | 1 | unid | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-07-28 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-07-28 | 5 | tons | 223 | 1
STP0817-CWP-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 13968 | h | 223 | 1
STP0817-CWP-032 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 13968 | h | 223 | 1
SES0817-CWP-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 3880 | h | 223 | 1
SES0817-CWP-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 3880 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 5706 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 1785 | h | 223 | 1
EEE0821-CWP-425 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 1785 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 1921 | h | 223 | 1
KMT0821-CWP-072 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 1921 | h | 223 | 1
SWP-008-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 41974 | h | 223 | 1
SWP-008-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 41974 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 22558 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 22558 | h | 223 | 1
SWP-010-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 28578 | h | 223 | 1
SWP-010-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 28578 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 112654 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 112654 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 7766 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 7766 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 44696 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 5545 | h | 223 | 1
SES0822-PWPl-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 5545 | h | 223 | 1
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 48271 | h | 223 | 1
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 48271 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 314265 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 314265 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 250266 | h | 223 | 1
EEE0822-CWP-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 41553 | h | 223 | 1
EEE0822-CWP-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 41553 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 10709 | h | 223 | 1
JPA0822-CWP-434 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 10709 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 1221 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 44696 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 44696 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 4770 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 30844 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 30844 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 12787 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 12787 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 216918 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 216918 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 4233 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 4233 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 611 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 18550 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 18550 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 18550 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 1552 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 1552 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 11994 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 11994 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 42775 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 42775 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 776 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 776 | h | 223 | 1
ELU0827-CWP-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 2328 | h | 223 | 1
ELU0827-CWP-340 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 2328 | h | 223 | 1
MEM0827-CWP-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 59360 | h | 223 | 1
MEM0827-CWP-329 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 59360 | h | 223 | 1
MEM0827-CWP-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 3880 | h | 223 | 1
MEM0827-CWP-337 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 3880 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 17700 | h | 223 | 1
SWP-025-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 6668 | h | 223 | 1
SWP-025-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 6668 | h | 223 | 1
SWP-026-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 43173 | h | 223 | 1
SWP-026-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 43173 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 4817 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 1364 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 323888 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 323888 | h | 223 | 1
SWP-031-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 37955 | h | 223 | 1
SWP-031-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 37955 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 931 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 931 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 20434 | h | 223 | 1
ECB1214-CWP-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 72359 | h | 223 | 1
ECB1214-CWP-533 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 72359 | h | 223 | 1
ECB0826-CWP-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 319779 | h | 223 | 1
ECB0826-CWP-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 319779 | h | 223 | 1
ECB0826-CWP-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-07-28 | 191868 | h | 223 | 1
ECB0826-CWP-562 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-07-28 | 191868 | h | 223 | 1
STP0817-CWP-032 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 576 | h | 223 | 1
STP0817-CWP-032 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 576 | h | 223 | 1
SES0817-CWP-040 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 320 | h | 223 | 1
SES0817-CWP-040 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 320 | h | 223 | 1
SES0817-CWP-041 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 320 | h | 223 | 1
SES0817-CWP-041 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 320 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 74 | h | 223 | 1
EEE0821-CWP-425 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 74 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 2 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 79 | h | 223 | 1
KMT0821-CWP-072 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 79 | h | 223 | 1
SWP-008-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 9024 | h | 223 | 1
SWP-008-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 9024 | h | 223 | 1
SWP-009-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 8352 | h | 223 | 1
SWP-009-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 8352 | h | 223 | 1
SWP-010-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 6144 | h | 223 | 1
SWP-010-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 6144 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 11246 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 11246 | h | 223 | 1
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 1896 | h | 223 | 1
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 1896 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 12960 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 12960 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 30035 | h | 223 | 1
JCI0822-CWP-433 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 30035 | h | 223 | 1
EEE0822-CWP-162 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 1714 | h | 223 | 1
EEE0822-CWP-162 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 1714 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 442 | h | 223 | 1
JPA0822-CWP-434 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 442 | h | 223 | 1
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 410 | h | 223 | 1
KMT0822-CWP-131 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 410 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 1272 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 1272 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 527 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 527 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 131 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 131 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 175 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 175 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 183 | h | 223 | 1
EEE0823-CWP-443 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 183 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 64 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 64 | h | 223 | 1
MCD0824-CWP-279 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 948 | h | 223 | 1
MCD0824-CWP-279 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 948 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 1764 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 1764 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 32 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 32 | h | 223 | 1
ELU0827-CWP-340 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 96 | h | 223 | 1
ELU0827-CWP-340 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 96 | h | 223 | 1
MEM0827-CWP-329 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 2448 | h | 223 | 1
MEM0827-CWP-329 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 2448 | h | 223 | 1
MEM0827-CWP-337 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 160 | h | 223 | 1
MEM0827-CWP-337 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 160 | h | 223 | 1
SWP-025-0827 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 1434 | h | 223 | 1
SWP-025-0827 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 1434 | h | 223 | 1
SWP-026-0827 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 9282 | h | 223 | 1
SWP-026-0827 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 9282 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 3840 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 3840 | h | 223 | 1
SWP-031-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 8160 | h | 223 | 1
SWP-031-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 8160 | h | 223 | 1
ECB0817-CWP-552 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 522 | h | 223 | 1
ECB0817-CWP-552 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 522 | h | 223 | 1
ECB0826-CWP-561 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 6094 | h | 223 | 1
ECB0826-CWP-561 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 6094 | h | 223 | 1
ECB0826-CWP-562 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-07-28 | 3656 | h | 223 | 1
ECB0826-CWP-562 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-07-28 | 3656 | h | 223 | 1
MCD0824-CWP-278 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-08-04 | 1 | t | 223 | 1
MCD0824-CWP-278 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-08-04 | 1 | t | 223 | 1
MCD0824-CWP-279 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-08-04 | 0 | t | 223 | 1
MCD0824-CWP-279 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-08-04 | 0 | t | 223 | 1
ECB0817-CWP-552 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-08-04 | 261 | m | 223 | 1
ECB0817-CWP-552 | CABLAGEM - WIRING | Material | At Completion Units | 2024-08-04 | 261 | m | 223 | 1
ECB0826-CWP-561 | CABLAGEM - WIRING | Material | Budgeted Units | 2024-08-04 | 213 | m | 223 | 1
ECB0826-CWP-561 | CABLAGEM - WIRING | Material | At Completion Units | 2024-08-04 | 213 | m | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-04 | 68 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-04 | 68 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-04 | 0 | un | 223 | 1
EEE0823-CWP-442 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-04 | 0 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-04 | 0 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-04 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-04 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-04 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-04 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-04 | 0 | un | 223 | 1
EEE0822-CWP-162 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-08-04 | 21 | un | 223 | 1
EEE0822-CWP-162 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-08-04 | 21 | un | 223 | 1
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-04 | 6 | t | 223 | 1
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-04 | 6 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-04 | 17 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-04 | 17 | t | 223 | 1
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-04 | 2 | t | 223 | 1
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-04 | 2 | t | 223 | 1
MEM0824-CWP-272 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-04 | 1 | t | 223 | 1
MEM0824-CWP-272 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-04 | 1 | t | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-04 | 3 | t | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-04 | 3 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-04 | 2 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-04 | 2 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-04 | 0 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-04 | 0 | t | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-08-04 | 289 | un | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-08-04 | 289 | un | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | Budgeted Units | 2024-08-04 | 11 | t | 223 | 1
MEM0822-CWP-111 | CALDEIRARIA - PLATEWORK | Material | At Completion Units | 2024-08-04 | 11 | t | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | Budgeted Units | 2024-08-04 | 0 | unid | 223 | 1
JPA0823-CWP-444 | DESMONTAGEM ELETRICA | Material | At Completion Units | 2024-08-04 | 0 | unid | 223 | 1
MMR0827-CWP-336 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-08-04 | 9 | tons | 223 | 1
MMR0827-CWP-336 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-08-04 | 9 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-08-04 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-08-04 | 5 | tons | 223 | 1
SES0817-CWP-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 3880 | h | 223 | 1
SES0817-CWP-041 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 3880 | h | 223 | 1
SES0817-CWP-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 37248 | h | 223 | 1
SES0817-CWP-042 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 37248 | h | 223 | 1
EEL0817-CWP-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 145496 | h | 223 | 1
EEL0817-CWP-048 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 145496 | h | 223 | 1
SES0817-CWP-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 8149 | h | 223 | 1
SES0817-CWP-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 8149 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 5706 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 31114 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 31114 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 112654 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 112654 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 7766 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 7766 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 44696 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 21230 | h | 223 | 1
ERE0822-CWP-136 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 21230 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 44696 | h | 223 | 1
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 125925 | h | 223 | 1
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 125925 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 314265 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 314265 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 250266 | h | 223 | 1
EEE0822-CWP-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 97772 | h | 223 | 1
EEE0822-CWP-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 97772 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 1221 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 21230 | h | 223 | 1
ERE0822-CWP-133 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 21230 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 4770 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 30844 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 30844 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 12787 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 12787 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 43384 | h | 223 | 1
JPA0823-CWP-444 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 43384 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 847 | h | 223 | 1
EEE0823-CWP-442 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 847 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 611 | h | 223 | 1
MEM0824-CWP-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 36953 | h | 223 | 1
MEM0824-CWP-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 36953 | h | 223 | 1
MEM0824-CWP-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 14979 | h | 223 | 1
MEM0824-CWP-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 14979 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 4969 | h | 223 | 1
MEM0824-PWPl-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 4969 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 4969 | h | 223 | 1
MEM0824-PWPl-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 4969 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 56669 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 56669 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 1552 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 1552 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 10994 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 10994 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 11994 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 11994 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 42775 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 42775 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 776 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 776 | h | 223 | 1
SWP-023-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 48225 | h | 223 | 1
SWP-023-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 48225 | h | 223 | 1
MMR0827-CWP-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 23280 | h | 223 | 1
MMR0827-CWP-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 23280 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 17700 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 4817 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 1364 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 323888 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 323888 | h | 223 | 1
SWP-031-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 53583 | h | 223 | 1
SWP-031-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 53583 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 931 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 931 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 20434 | h | 223 | 1
ECB0826-CWP-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-04 | 89538 | h | 223 | 1
ECB0826-CWP-561 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-04 | 89538 | h | 223 | 1
SES0817-CWP-042 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 1536 | h | 223 | 1
SES0817-CWP-042 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 1536 | h | 223 | 1
EEL0817-CWP-048 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 6000 | h | 223 | 1
EEL0817-CWP-048 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 6000 | h | 223 | 1
SES0817-CWP-049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 336 | h | 223 | 1
SES0817-CWP-049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 336 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 2 | h | 223 | 1
SWP-009-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 11520 | h | 223 | 1
SWP-009-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 11520 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 9278 | h | 223 | 1
MEM0822-CWP-111 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 9278 | h | 223 | 1
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 4946 | h | 223 | 1
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 4946 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 12960 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 12960 | h | 223 | 1
EEE0822-CWP-162 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 4032 | h | 223 | 1
EEE0822-CWP-162 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 4032 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 1272 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 1272 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 527 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 527 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 26 | h | 223 | 1
JPA0823-CWP-444 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 26 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 35 | h | 223 | 1
EEE0823-CWP-442 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 35 | h | 223 | 1
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 1439 | h | 223 | 1
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 1439 | h | 223 | 1
MEM0824-CWP-272 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 541 | h | 223 | 1
MEM0824-CWP-272 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 541 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 2240 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 2240 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 64 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 64 | h | 223 | 1
MCD0824-CWP-278 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 869 | h | 223 | 1
MCD0824-CWP-278 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 869 | h | 223 | 1
MCD0824-CWP-279 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 269 | h | 223 | 1
MCD0824-CWP-279 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 269 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 1764 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 1764 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 32 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 32 | h | 223 | 1
SWP-023-0826 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 10368 | h | 223 | 1
SWP-023-0826 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 10368 | h | 223 | 1
MMR0827-CWP-336 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 960 | h | 223 | 1
MMR0827-CWP-336 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 960 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 3840 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 3840 | h | 223 | 1
SWP-031-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 11520 | h | 223 | 1
SWP-031-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 11520 | h | 223 | 1
ECB0817-CWP-552 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 2086 | h | 223 | 1
ECB0817-CWP-552 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 2086 | h | 223 | 1
ECB0826-CWP-561 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-04 | 1706 | h | 223 | 1
ECB0826-CWP-561 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-04 | 1706 | h | 223 | 1
MCD0824-CWP-278 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-08-11 | 2 | t | 223 | 1
MCD0824-CWP-278 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-08-11 | 2 | t | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-11 | 68 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-11 | 68 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-11 | 0 | un | 223 | 1
JPA0824-CWP-474 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-11 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-11 | 0 | un | 223 | 1
JPA0826-CWP-450 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-11 | 0 | un | 223 | 1
JIL0827-CWP-341 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-11 | 10 | un | 223 | 1
JIL0827-CWP-341 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-11 | 10 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-11 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-11 | 0 | un | 223 | 1
EEE0822-CWP-162 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | Budgeted Units | 2024-08-11 | 12 | un | 223 | 1
EEE0822-CWP-162 | MATERIAIS ELÉTRICOS DIVERSOS - RANDOM ELECTRICAL MATERIALS | Material | At Completion Units | 2024-08-11 | 12 | un | 223 | 1
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-11 | 6 | t | 223 | 1
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-11 | 6 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-11 | 14 | t | 223 | 1
MEM0823-CWP-258 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-11 | 14 | t | 223 | 1
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-11 | 2 | t | 223 | 1
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-11 | 2 | t | 223 | 1
MEM0824-CWP-272 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-11 | 0 | t | 223 | 1
MEM0824-CWP-272 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-11 | 0 | t | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-11 | 5 | t | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-11 | 5 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-11 | 2 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-11 | 2 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-11 | 0 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-11 | 0 | t | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | Budgeted Units | 2024-08-11 | 181 | un | 223 | 1
TTU0823-CWP-437 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT (un) | Material | At Completion Units | 2024-08-11 | 181 | un | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-08-11 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-08-11 | 5 | tons | 223 | 1
ELU0817-CWP-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 191856 | h | 223 | 1
ELU0817-CWP-050 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 191856 | h | 223 | 1
SES0817-CWP-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 4075 | h | 223 | 1
SES0817-CWP-049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 4075 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 5706 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 31114 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 31114 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 112654 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 112654 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 7766 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 7766 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 44696 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 44696 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 44696 | h | 223 | 1
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 125925 | h | 223 | 1
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 125925 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 314265 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 314265 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 18604 | h | 223 | 1
SWP-015-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 21586 | h | 223 | 1
SWP-015-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 21586 | h | 223 | 1
SWP-016-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 39039 | h | 223 | 1
SWP-016-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 39039 | h | 223 | 1
SWP-017-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 39039 | h | 223 | 1
SWP-017-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 39039 | h | 223 | 1
SWP-018-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 39039 | h | 223 | 1
SWP-018-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 39039 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 250266 | h | 223 | 1
EEE0822-CWP-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 56219 | h | 223 | 1
EEE0822-CWP-162 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 56219 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 4770 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 19278 | h | 223 | 1
TTU0823-CWP-437 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 19278 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 10230 | h | 223 | 1
MEM0823-CWP-258 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 10230 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 611 | h | 223 | 1
MEM0824-CWP-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 41833 | h | 223 | 1
MEM0824-CWP-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 41833 | h | 223 | 1
MEM0824-CWP-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 4805 | h | 223 | 1
MEM0824-CWP-272 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 4805 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 103035 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 103035 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 892 | h | 223 | 1
JPA0824-CWP-474 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 892 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 19989 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 19989 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 11994 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 11994 | h | 223 | 1
SWP-021-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 29471 | h | 223 | 1
SWP-021-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 29471 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 42775 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 42775 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 776 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 776 | h | 223 | 1
SWP-023-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 16075 | h | 223 | 1
SWP-023-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 16075 | h | 223 | 1
JIL0827-CWP-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 36375 | h | 223 | 1
JIL0827-CWP-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 36375 | h | 223 | 1
MMR0827-CWP-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 11640 | h | 223 | 1
MMR0827-CWP-336 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 11640 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 17700 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 4817 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 1364 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 323888 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 323888 | h | 223 | 1
SWP-031-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 33490 | h | 223 | 1
SWP-031-1214 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 33490 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 33027 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 33027 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 931 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 931 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 20434 | h | 223 | 1
SWP-040-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-11 | 17861 | h | 223 | 1
SWP-040-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-11 | 17861 | h | 223 | 1
ELU0817-CWP-050 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 96 | h | 223 | 1
ELU0817-CWP-050 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 96 | h | 223 | 1
SES0817-CWP-049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 168 | h | 223 | 1
SES0817-CWP-049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 168 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 2 | h | 223 | 1
SWP-009-0821 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 7008 | h | 223 | 1
SWP-009-0821 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 7008 | h | 223 | 1
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 4946 | h | 223 | 1
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 4946 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 12960 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 12960 | h | 223 | 1
SWP-015-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 4641 | h | 223 | 1
SWP-015-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 4641 | h | 223 | 1
SWP-016-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 8393 | h | 223 | 1
SWP-016-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 8393 | h | 223 | 1
SWP-017-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 8393 | h | 223 | 1
SWP-017-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 8393 | h | 223 | 1
SWP-018-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 8393 | h | 223 | 1
SWP-018-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 8393 | h | 223 | 1
EEE0822-CWP-162 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 2318 | h | 223 | 1
EEE0822-CWP-162 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 2318 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 795 | h | 223 | 1
TTU0823-CWP-437 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 795 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 422 | h | 223 | 1
MEM0823-CWP-258 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 422 | h | 223 | 1
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 1629 | h | 223 | 1
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 1629 | h | 223 | 1
MEM0824-CWP-272 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 275 | h | 223 | 1
MEM0824-CWP-272 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 275 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 4072 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 4072 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 37 | h | 223 | 1
JPA0824-CWP-474 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 37 | h | 223 | 1
MCD0824-CWP-278 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 1580 | h | 223 | 1
MCD0824-CWP-278 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 1580 | h | 223 | 1
SWP-021-0824 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 6758 | h | 223 | 1
SWP-021-0824 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 6758 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 1764 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 1764 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 32 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 32 | h | 223 | 1
SWP-023-0826 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 3456 | h | 223 | 1
SWP-023-0826 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 3456 | h | 223 | 1
JIL0827-CWP-341 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 1200 | h | 223 | 1
JIL0827-CWP-341 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 1200 | h | 223 | 1
MMR0827-CWP-336 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 480 | h | 223 | 1
MMR0827-CWP-336 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 480 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 3840 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 3840 | h | 223 | 1
SWP-031-1214 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 7200 | h | 223 | 1
SWP-031-1214 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 7200 | h | 223 | 1
SWP-040-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-11 | 3950 | h | 223 | 1
SWP-040-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-11 | 3950 | h | 223 | 1
MCD0824-CWP-278 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | Budgeted Units | 2024-08-18 | 1 | t | 223 | 1
MCD0824-CWP-278 | ESTRUTURA METALICA - STEEL STRUCTURE | Material | At Completion Units | 2024-08-18 | 1 | t | 223 | 1
JIL0817-CWP-051 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-18 | 10 | un | 223 | 1
JIL0817-CWP-051 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-18 | 10 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-18 | 31 | un | 223 | 1
JIL0822-CWP-107 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-18 | 31 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-18 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-18 | 0 | un | 223 | 1
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-18 | 3 | t | 223 | 1
SES0822-CWP-102 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-18 | 3 | t | 223 | 1
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-18 | 2 | t | 223 | 1
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-18 | 2 | t | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-18 | 5 | t | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-18 | 5 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-18 | 2 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-18 | 2 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-18 | 0 | t | 223 | 1
MEM0826-CWP-293 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-18 | 0 | t | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-08-18 | 5 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-08-18 | 5 | tons | 223 | 1
JIL0817-CWP-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 46560 | h | 223 | 1
JIL0817-CWP-051 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 46560 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 5706 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 31114 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 31114 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 112654 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 112654 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 7766 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 7766 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 2589 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 21230 | h | 223 | 1
ERE0822-CWP-134 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 21230 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 21230 | h | 223 | 1
ERE0822-CWP-137 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 21230 | h | 223 | 1
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 12056 | h | 223 | 1
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 12056 | h | 223 | 1
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 35679 | h | 223 | 1
SES0822-CWP-102 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 35679 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 144038 | h | 223 | 1
JIL0822-CWP-107 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 144038 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 18604 | h | 223 | 1
SWP-011-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 29024 | h | 223 | 1
SWP-011-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 29024 | h | 223 | 1
SWP-015-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 42713 | h | 223 | 1
SWP-015-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 42713 | h | 223 | 1
SWP-016-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 25261 | h | 223 | 1
SWP-016-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 25261 | h | 223 | 1
SWP-017-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 25261 | h | 223 | 1
SWP-017-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 25261 | h | 223 | 1
SWP-018-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 25261 | h | 223 | 1
SWP-018-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 25261 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 611 | h | 223 | 1
MEM0824-CWP-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 39742 | h | 223 | 1
MEM0824-CWP-270 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 39742 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 103035 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 103035 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 19989 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 19989 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 1399 | h | 223 | 1
MCD0824-CWP-279 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 1399 | h | 223 | 1
SWP-021-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 13396 | h | 223 | 1
SWP-021-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 13396 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 42775 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 42775 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 155 | h | 223 | 1
MEM0826-CWP-293 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 155 | h | 223 | 1
SWP-024-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 48225 | h | 223 | 1
SWP-024-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 48225 | h | 223 | 1
JIL0827-CWP-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 10185 | h | 223 | 1
JIL0827-CWP-341 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 10185 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 17700 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 17700 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 4817 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 4817 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 1364 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 1364 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 323888 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 323888 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 6605 | h | 223 | 1
SUWP-OU-PF-0601 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 6605 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 931 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 931 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-18 | 20434 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-18 | 20434 | h | 223 | 1
JIL0817-CWP-051 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 1920 | h | 223 | 1
JIL0817-CWP-051 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 1920 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 2 | h | 223 | 1
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 2666 | h | 223 | 1
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 2666 | h | 223 | 1
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 2061 | h | 223 | 1
SES0822-CWP-102 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 2061 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 5940 | h | 223 | 1
JIL0822-CWP-107 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 5940 | h | 223 | 1
SWP-011-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 6240 | h | 223 | 1
SWP-011-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 6240 | h | 223 | 1
SWP-015-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 9183 | h | 223 | 1
SWP-015-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 9183 | h | 223 | 1
SWP-016-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 5431 | h | 223 | 1
SWP-016-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 5431 | h | 223 | 1
SWP-017-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 5431 | h | 223 | 1
SWP-017-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 5431 | h | 223 | 1
SWP-018-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 5431 | h | 223 | 1
SWP-018-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 5431 | h | 223 | 1
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 1629 | h | 223 | 1
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 1629 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 4072 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 4072 | h | 223 | 1
MCD0824-CWP-278 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 711 | h | 223 | 1
MCD0824-CWP-278 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 711 | h | 223 | 1
SWP-021-0824 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 3072 | h | 223 | 1
SWP-021-0824 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 3072 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 1764 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 1764 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 6 | h | 223 | 1
MEM0826-CWP-293 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 6 | h | 223 | 1
SWP-024-0826 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 10368 | h | 223 | 1
SWP-024-0826 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 10368 | h | 223 | 1
JIL0827-CWP-341 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 720 | h | 223 | 1
JIL0827-CWP-341 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 720 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-18 | 3840 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-18 | 3840 | h | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-08-25 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-08-25 | 0 | un | 223 | 1
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-25 | 0 | t | 223 | 1
MEM0824-CWP-270 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-25 | 0 | t | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-25 | 5 | t | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-25 | 5 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-08-25 | 2 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-08-25 | 2 | t | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | Budgeted Units | 2024-08-25 | 3 | tons | 223 | 1
MMR0622-CWP-008 | REFRATARIOS - REFRACTORY | Material | At Completion Units | 2024-08-25 | 3 | tons | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 5706 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 9127 | h | 223 | 1
SWP-009-0821 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 9127 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 112654 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 112654 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 3689 | h | 223 | 1
MEM0822-CWP-499 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 3689 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 2589 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 2589 | h | 223 | 1
SWP-012-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 20540 | h | 223 | 1
SWP-012-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 20540 | h | 223 | 1
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 53583 | h | 223 | 1
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 53583 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 18604 | h | 223 | 1
SWP-011-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 53583 | h | 223 | 1
SWP-011-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 53583 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 611 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 103035 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 103035 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 19989 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 19989 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 42775 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 42775 | h | 223 | 1
SWP-024-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 16075 | h | 223 | 1
SWP-024-0826 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 16075 | h | 223 | 1
SWP-027-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 125028 | h | 223 | 1
SWP-027-0827 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 125028 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 4867 | h | 223 | 1
MEM0827-CWP-370 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 4867 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 153 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 1325 | h | 223 | 1
MMR0827-CWP-456 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 1325 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 375 | h | 223 | 1
MEM0827-CWP-308 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 375 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 251013 | h | 223 | 1
SWP-028-1049 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 251013 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 931 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 931 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-08-25 | 10217 | h | 223 | 1
MMR0622-CWP-008 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-08-25 | 10217 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 2 | h | 223 | 1
SWP-012-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 4542 | h | 223 | 1
SWP-012-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 4542 | h | 223 | 1
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 11849 | h | 223 | 1
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 11849 | h | 223 | 1
SWP-011-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 11520 | h | 223 | 1
SWP-011-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 11520 | h | 223 | 1
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 190 | h | 223 | 1
MEM0824-CWP-270 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 190 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 4072 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 4072 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 1764 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 1764 | h | 223 | 1
SWP-024-0826 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 3456 | h | 223 | 1
SWP-024-0826 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 3456 | h | 223 | 1
SWP-027-0827 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 1955 | h | 223 | 1
SWP-027-0827 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 1955 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 2976 | h | 223 | 1
SWP-028-1049 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 2976 | h | 223 | 1
SWP-0xx-0817 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-08-25 | 1955 | h | 223 | 1
SWP-0xx-0817 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-08-25 | 1955 | h | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | Budgeted Units | 2024-09-01 | 0 | un | 223 | 1
JIL0622-CWP-409 | INSTRUMENTACAO E AUTOMACAO - INSTRUMENTATION & AUTOMATION | Material | At Completion Units | 2024-09-01 | 0 | un | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-09-01 | 2 | t | 223 | 1
MEM0824-CWP-265 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-09-01 | 2 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | Budgeted Units | 2024-09-01 | 1 | t | 223 | 1
MEM0824-CWP-269 | EQUIPAMENTO MECANICO - MECHANICAL EQUIPMENT | Material | At Completion Units | 2024-09-01 | 1 | t | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 5706 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 112654 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 112654 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 1294 | h | 223 | 1
MCD0822-CWP-500 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 1294 | h | 223 | 1
SWP-012-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 50904 | h | 223 | 1
SWP-012-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 50904 | h | 223 | 1
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 53583 | h | 223 | 1
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 53583 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 18604 | h | 223 | 1
SWP-011-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 6698 | h | 223 | 1
SWP-011-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 6698 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 4770 | h | 223 | 1
SWP-020-0823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 30313 | h | 223 | 1
SWP-020-0823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 30313 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 611 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 29193 | h | 223 | 1
MEM0824-CWP-265 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 29193 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 5664 | h | 223 | 1
MCD0824-CWP-278 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 5664 | h | 223 | 1
SWP-022-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 30313 | h | 223 | 1
SWP-022-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 30313 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 12119 | h | 223 | 1
MEM0824-CWP-269 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 12119 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 153 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 305 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-01 | 279 | h | 223 | 1
JIL0622-CWP-409 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-01 | 279 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 2 | h | 223 | 1
SWP-012-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 11257 | h | 223 | 1
SWP-012-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 11257 | h | 223 | 1
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 11849 | h | 223 | 1
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 11849 | h | 223 | 1
SWP-011-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 1440 | h | 223 | 1
SWP-011-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 1440 | h | 223 | 1
SWP-020-0823 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 6517 | h | 223 | 1
SWP-020-0823 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 6517 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 1832 | h | 223 | 1
MEM0824-CWP-265 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 1832 | h | 223 | 1
SWP-022-0824 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 6517 | h | 223 | 1
SWP-022-0824 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 6517 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 500 | h | 223 | 1
MEM0824-CWP-269 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 500 | h | 223 | 1
SWP-027-0827 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 1117 | h | 223 | 1
SWP-027-0827 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 1117 | h | 223 | 1
SWP-0xx-0817 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-01 | 1117 | h | 223 | 1
SWP-0xx-0817 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-01 | 1117 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 5706 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 112654 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 112654 | h | 223 | 1
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 5805 | h | 223 | 1
SWP-013-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 5805 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 18604 | h | 223 | 1
SWP-014-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 35722 | h | 223 | 1
SWP-014-0822 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 35722 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 4770 | h | 223 | 1
SWP-020-0823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 33987 | h | 223 | 1
SWP-020-0823 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 33987 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 611 | h | 223 | 1
SWP-022-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 33987 | h | 223 | 1
SWP-022-0824 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 33987 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 153 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 11224 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-08 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-08 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-08 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-08 | 2 | h | 223 | 1
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-08 | 1284 | h | 223 | 1
SWP-013-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-08 | 1284 | h | 223 | 1
SWP-014-0822 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-08 | 19200 | h | 223 | 1
SWP-014-0822 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-08 | 19200 | h | 223 | 1
SWP-020-0823 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-08 | 7307 | h | 223 | 1
SWP-020-0823 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-08 | 7307 | h | 223 | 1
SWP-022-0824 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-08 | 7307 | h | 223 | 1
SWP-022-0824 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-08 | 7307 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 5706 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 89185 | h | 223 | 1
MEM0822-CWP-111 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 89185 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 153 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 11224 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 11224 | h | 223 | 1
B39093 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 372288 | h | 223 | 1
B39093 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 372288 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-15 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-15 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-15 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-15 | 2 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 5706 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 153 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 8979 | h | 223 | 1
A303040 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 8979 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-22 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-22 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-22 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-22 | 2 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-29 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-29 | 5706 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-29 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-29 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-29 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-29 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-29 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-29 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-29 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-29 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-29 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-29 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-29 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-29 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-29 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-29 | 153 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-09-29 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-09-29 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-09-29 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-09-29 | 2 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-06 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-06 | 5706 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-06 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-06 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-06 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-06 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-06 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-06 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-06 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-06 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-06 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-06 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-06 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-06 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-06 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-06 | 153 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-06 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-06 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-10-06 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-10-06 | 2 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-13 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-13 | 5706 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-13 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-13 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-13 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-13 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-13 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-13 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-13 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-13 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-13 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-13 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-13 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-13 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-13 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-13 | 153 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-13 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-13 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-10-13 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-10-13 | 2 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-20 | 5706 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-20 | 5706 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-20 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-20 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-20 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-20 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-20 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-20 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-20 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-20 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-20 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-20 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-20 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-20 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-20 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-20 | 153 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-20 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-20 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-10-20 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-10-20 | 2 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-27 | 2710 | h | 223 | 1
EBD0800-CWP-056 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-27 | 2710 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-27 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-27 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-27 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-27 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-27 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-27 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-27 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-27 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-27 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-27 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-27 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-27 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-27 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-27 | 153 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-10-27 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-10-27 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-10-27 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-10-27 | 2 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-03 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-03 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-03 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-03 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-03 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-03 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-03 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-03 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-03 | 4770 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-03 | 4770 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-03 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-03 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-03 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-03 | 153 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-03 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-03 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-11-03 | 2 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-11-03 | 2 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-10 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-10 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-10 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-10 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-10 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-10 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-10 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-10 | 1221 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-10 | 2266 | h | 223 | 1
EBD0822-CWP-157 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-10 | 2266 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-10 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-10 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-10 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-10 | 153 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-10 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-10 | 305 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | Budgeted Units | 2024-11-10 | 0 | h | 223 | 1
MCD0824-CWP-091 | MAO DE OBRA - WORKFORCE | Labor | At Completion Units | 2024-11-10 | 0 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-17 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-17 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-17 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-17 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-17 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-17 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-17 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-17 | 1221 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-17 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-17 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-17 | 153 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-17 | 153 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-17 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-17 | 305 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-24 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-24 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-24 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-24 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-24 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-24 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-24 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-24 | 1221 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-24 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-24 | 611 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-24 | 76 | h | 223 | 1
EBD0827-CWP-344 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-24 | 76 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-11-24 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-11-24 | 305 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-01 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-01 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-01 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-01 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-01 | 18604 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-01 | 18604 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-01 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-01 | 1221 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-01 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-01 | 611 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-01 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-01 | 305 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-08 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-08 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-08 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-08 | 250266 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-08 | 1860 | h | 223 | 1
ECB0822-CWP-130 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-08 | 1860 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-08 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-08 | 1221 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-08 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-08 | 611 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-08 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-08 | 305 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-15 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-15 | 18604 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-15 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-15 | 611 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-15 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-15 | 305 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-22 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-22 | 18604 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-22 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-22 | 611 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-22 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-22 | 305 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-29 | 18604 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-29 | 18604 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-29 | 100106 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-29 | 100106 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-29 | 488 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-29 | 488 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-29 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-29 | 611 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2024-12-29 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2024-12-29 | 305 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-05 | 16279 | h | 223 | 1
ECB0822-CWP-249 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-05 | 16279 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-05 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-05 | 250266 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-05 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-05 | 1221 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-05 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-05 | 611 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-05 | 305 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-05 | 305 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-12 | 250266 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-12 | 250266 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-12 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-12 | 1221 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-12 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-12 | 611 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-12 | 244 | h | 223 | 1
KMT0622-CWP-006 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-12 | 244 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-19 | 168930 | h | 223 | 1
JCI0822-CWP-433 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-19 | 168930 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-19 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-19 | 1221 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-19 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-19 | 611 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-26 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-26 | 1221 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-01-26 | 611 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-01-26 | 611 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-02-02 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-02-02 | 1221 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-02-02 | 183 | h | 223 | 1
EEE0823-CWP-443 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-02-02 | 183 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-02-09 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-02-09 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-02-16 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-02-16 | 1221 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | Budgeted Units | 2025-02-23 | 1099 | h | 223 | 1
KMT0822-CWP-131 | PROFIS - PHYSICAL PROGRESS | Nonlabor | At Completion Units | 2025-02-23 | 1099 | h | 223 | 1